## Sheet1
Highways Agency Confirmation of Task Order
Redactions made under FOIA 2000 exemptions sec 40: personal info and sec 43: commercial Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | AECOM
Project Title: | Network Coding 2
Contract Ref. | 114/2/1391/1 | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | Modelling | Sub Pin: | 4 |  | PIN No.: | Redacted
HA Reference: | EE 57 15/16AECOM | HA Ordering Officer: |  |  | Redacted
Consultant Ref: | MX010.005 | Consultant Contact: |  |  | Redacted
Start & End Date: | 15/07/2015 - 07/09/2015 | CTO Authorisation No.
Task Overview
To update the network based on the changes identified during the ‘Area of Influence test’, and during the update of the zoning system. To analyse the data collected in the previous task: traffic count data and journey time data.
Task Objectives and Milestones
The network will be updated based on the changes identified during the ‘Area of Influence test’, and during the update of the zoning system. This update will prepare the base year network for the introduction of the RIS schemes on the futures scenarios.
Task Outcomes
The following will be key deliverables from this task: • Updated network • Traffic counts and journey times analysis to be included on the calibration / validation process.
Project Risk and Management
The risks on this task will be managed in accordance with the contract. There are several risks to this task identified at this stage: • Definition of the User class. • Complexity of the coding. • Availability of existing traffic count/ journey time/ delay information and late information from 3rd parties (surveys, traffic counts, journey times, etc) • Availability of planning data.
Project Title: | Network Coding 2 |  |  |  | HA Reference: | EE 57 15/16AECOM
HA Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Target Cost
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HA Sponsor
EE 57 15/16AECOM | 18854.16 | 0 |  |  | 18854.16 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 18854.16
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 18854.16
Total Project Fee Estimate |  |  |  |  | 18854.16
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted | Redacted | Redacted | @ | 70.65 | 635.85
Redacted | Redacted | Redacted | @ | 79.64 | 2070.64
Redacted | Redacted | Redacted | @ | 50.46 | 1816.56
Redacted | Redacted | Redacted | @ | 38.59 | 2006.68
Redacted | Redacted | Redacted | @ | 31.57 | 3409.56
Redacted | Redacted | Redacted | @ | 27.28 | 8729.6
Redacted | Redacted | Redacted | @ | 41.17 | 185.265
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2015-07-21 |  | Works Total |  | 18854.155
Confidential and commercially sensitive information which shall not be disclosed to third parties
|  |  | Sub Total |  | 18854.155
|  |  | Expenses |  | 0
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 18854.155