SCHEDULE 14

GOVERNANCE

VERSION CONTROL

| VERSION | DATE | COMMENT |
| --- | --- | --- |
| 1.0 | October 2019 | Execution version |

DEFINITIONS

In this Schedule, the following definitions shall apply:

| "Board Member" | the initial persons appointed by the Authority and Supplier to the Boards as set out in Annex 1 and any replacements from time to time agreed by the Parties in accordance with Paragraph 3.3; |
| --- | --- |
| "Boards" | the Contract Mobilisation Board, Contract Management Board, Strategic Partnership Board, Use of Force Board, and Welfare Board and "Board" shall mean any of them; |
| "Contract Management Board" | the body described under that that title in the second table of Annex 1; |
| "Contract Managers" | the individuals appointed as such by the Authority and the Supplier in accordance with Paragraph 2; and |
| "Contract Mobilisation Board" | the body described under that title in the first table of Annex 1; |
| "Strategic Partnership Board" | the body described in under that title in the third table of Annex 1; |
| "Use of Force Board" | the body described in under that title in the third table of Annex 1; and |
| "Welfare Board" | the body described in under that title in the third table of Annex 1. |

MANAGEMENT OF THE SERVICES

The Supplier and the Authority shall each appoint a Contract Manager for the purposes of this Agreement through whom the Services shall be managed at a day-to-day.

Both Parties shall ensure that appropriate resource is made available on a regular basis such that the aims, objectives and specific provisions of this Agreement can be fully realised.

BOARDS

Establishment and structure of the Boards

The Boards shall be established by the Authority for the purposes of this Agreement on which both the Supplier and the Authority shall be represented.

In relation to each Board, the:

Authority Board Members;

Supplier Board Members;

frequency that the Board shall meet (unless otherwise agreed between the Parties);

location of the Board's meetings; and

planned start date by which the Board shall be established,

shall be as set out in Annex 1.

In the event that either Party wishes to replace any of its appointed Board Members, that Party shall notify the other in writing of the proposed change for agreement by the other Party (such agreement not to be unreasonably withheld or delayed).  Notwithstanding the foregoing it is intended that each Authority Board Member has at all times a counterpart Supplier Board Member of equivalent seniority and expertise.

Purpose of the Boards

Each Board shall fulfil the purpose set out in Annex 1.

Board meetings

Each Party shall ensure that its Board Members shall make all reasonable efforts to attend Board meetings at which that Board Member's attendance is required.  If any Board Member is not able to attend a Board meeting, that person shall use all reasonable endeavours to ensure that:

a delegate attends the relevant Board meeting in his/her place who (wherever possible) is properly briefed and prepared; and

that he/she is debriefed by such delegate after the Board meeting.

A chairperson shall be appointed by the Authority for each Board as identified in Annex 1.  The chairperson shall be responsible for:

scheduling Board meetings;

setting the agenda for Board meetings and circulating to all attendees in advance of such meeting;

chairing the Board meetings;

monitoring the progress of any follow up tasks and activities agreed to be carried out following Board meetings;

ensuring that minutes for Board meetings are recorded and disseminated electronically to the appropriate persons and to all Board meeting participants within seven (7) Working Days after the Board meeting; and

facilitating the process or procedure by which any decision agreed at any Board meeting is given effect in the appropriate manner.

Board meetings shall be quorate as long as at least two representatives from each Party are present.

The Parties shall ensure, as far as reasonably practicable, that all Boards shall as soon as reasonably practicable resolve the issues and achieve the objectives placed before them.  Each Party shall endeavour to ensure that Board Members are empowered to make relevant decisions or have access to empowered individuals for decisions to be made to achieve this.

CONTRACT MANAGEMENT MECHANISMS

Both Parties shall pro-actively manage risks attributed to them under the terms of this Agreement.

The Supplier shall develop, operate, maintain and amend, as agreed with the Authority, processes for:

the identification and management of risks;

the identification and management of issues; and

monitoring and controlling project plans.

The Risk Register shall be updated by the Supplier and submitted for review by the Strategic Partnership Board.

ANNUAL SERVICE DELIVERY PLAN

The Annual Service Delivery Plan to be provided and updated by the Supplier in accordance with Clause 9 (Annual Service Delivery Plan) will be discussed at the closest Strategic Partnership Board meeting to each anniversary of the Effective Date.

As part of the review of the Annual Service Delivery Plan, the Parties shall include any agreed changes to the performance mechanism in Schedule 5 (Performance and Monitoring Mechanism) and associated CDIs in accordance with Clause 7.7 (Changes to Contract Delivery Indicators and Service Credits).

ANNEX 1

CONTRACT MOBILISATION BOARD REPRESENTATION AND STRUCTURE

| Purpose | Review progress on mobilisation planning, sign off and approve any contract requirements which must be produced during mobilisation, commission new services and assess change proposals for acceptance, review contract risk register |
| --- | --- |
| Authority Members of Contract Mobilisation Board | PECS GEN4 Programme Dep Director (Chairperson), Ops Advisor, others from team as necessary. Head of PECS, Senior CDM, PMU, Police, YCS and HMCTS, MOJ Finance and Commercial, potentially policy leads |
| Supplier Members of Contract Mobilisation Board | Contract Operations Director, Mobilisation Director, workstream leads as necessary. |
| Start Date for Contract Mobilisation Board meetings | Effective Date |
| End Date for Contract Mobilisation Board meetings | Operational Services Commencement Date |
| Frequency of Contract Mobilisation Board meetings | Monthly |

CONTRACT MANAGEMENT BOARD REPRESENTATION AND STRUCTURE

| Purpose | Oversee service delivery for respective contract lots in previous month; agree performance points/credits etc; resolve operational tensions and issues; change management; dispute resolution; matter escalation to Strategic Partnership Board |
| --- | --- |
| Authority Members of Contract Management Board | Senior CDM (Chairperson), Regional CDMs, YCS, MOJ Commercial. |
| Supplier Members of Contract Management Board | Contract Operations Director, Senior Finance Business Partner, Director of MI and Performance, Contracts Manager (Legal and Commercial), Assistant Director Operations (East and Southeast), Assistant Director Operations (Central and West), Assistant Director Operations (London), Assistant Director of Standards and Security. |
| Start Date for Contract Management Board meetings | Effective Date (or later if required by the Authority) |
| Frequency of Contract Management Board meetings | Monthly |

STRATEGIC PARTNERSHIP BOARD REPRESENTATION AND STRUCTURE

| Purpose | Quarterly performance review; resolve issues escalated from CMB; budget monitoring; strategic alignment on future direction/policy change; level of Operational Staff; review performance in relation to young people and safeguarding; commission new services and assess change proposals for acceptance, review contract risk register. Ensure the Parties' strategies are aligned (including but not limited to business planning, resource management, prioritisation, ethos, partnering and culture); provide directional context and decision making in relation to delivery and achieving agreed aims; promote development of new opportunities to meet Authority objectives. |
| --- | --- |
| Authority members of Strategic Partnership Board | Head of PECS (Chairperson), Senior CDMs, PMU, Police, YCS and HMCTS, MOJ Finance and Commercial. |
| Supplier members of Strategic Partnership Board | Contract Operations Director, Business Operations Director, Managing Director. |
| Start date for Strategic Partnership Board meetings | Three (3) months after Effective Date |
| Frequency of Strategic Partnership Board meetings | Quarterly (or at an alternative frequency to be determined by the Authority) |

USE OF FORCE BOARD REPRESENTATION AND STRUCTURE

| Purpose | Focused meeting on use of force on children and young people; review of incidents where injury and warning sign reports have been raised; review of practice; training and lessons learnt exercise; review of safeguarding concerns. |
| --- | --- |
| Authority members of Use of Force Board | Head of PECS (Chairperson), Senior CDM, Regional CDMs, YCS, MOJ Commercial and HMCTS. |
| Supplier members of Use of Force Board | Assistant Director of Standards and Security, Head of Children and Young People Services. |
| Start date for Use of Force Board meetings | Six (6) months after Operational Services Commencement Date |
| Frequency of Use of Force Board meetings | Every six (6) months (or at an alternative frequency to be determined by the Authority) |

WELFARE BOARD REPRESENTATION AND STRUCTURE

| Purpose | Focused meeting to ensure all care and welfare issues are addressed. |
| --- | --- |
| Authority members of Welfare Board | Head of PECS (Chairperson), Senior CDMs, Police, YCS and HMCTS, MOJ Finance and Commercial. Lay Observer representative (for non-commercial in confidence elements only) |
| Supplier members of Welfare Board | Assistant Director of Standards and Security, Assistant Director Operations (East and Southeast) Safeguard Lead. |
| Start date for Welfare Board meetings | Three (3) months after Operational Services Commencement Date |
| Frequency of Welfare Board meetings | Quarterly stand alone meeting (or at an alternative frequency to be determined by the Authority). For information only, this is likely to be on the same day as the Strategic Partnership Board. |

O