## Comrcl
Schedule 13 – Issues Matrix to Contract 700008662
POC | Date Raised | Source Document | Location in Document | RFS Comment in Compliance Matrix | MOD Query | To Who | Response Required Date | RFS Response to MOD Query | MOD Response | MOD Response | Status
1 | 2020-07-31 | DEFFORM 47ST | A9 - Definitions | The MoD confirmed an SRD does not apply to this requirement | The Authority confirm an SRD does not apply to this requirement but this is a mandatory definition within all MOD contracts and therefore cannot be removed. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
2 | 2020-07-31 | DEFFORM 47ST | A20 - Contract Conditions | Robertson Fuel Systems' (RFS) proposal is subject to the caveats, exceptions and comments in this compliance matrix and any attachments hereto. The comments, caveats and/or exceptions are based on RFS's standard business methodology described herein and are consistent with prior dealings with the UK Ministry of Defence (MoD). | The Authority take into account RFS proposals with the caveats, exceptions and comments in the compliance matrix. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
3 | 2020-07-31 | DEFFORM 47ST | C2 - Construction of Tenders | This proposal is in USD. For the total value on the Offer form (DEFFORM 47ST Annex A), we used RFS’s quoted prices and the MoD’s estimated quantities from Schedule 2 Tables 1 and 2, respectively. | The Authority confirm they are content with RFS proposal being submitted in USD. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
4 | 2020-07-31 | DEFFORM 47ST | C3 - Construction of Tenders | See Clause D below | In line with POC 7, the Authority require RFS priced offer to be broken down in line with the criteria shown at Section D - Details of Price Breakdown and Mandatory Criteria. | Ryan Albertsen | 2020-08-07 | See comments at POC 7. | POC to be closed , please refer to POC 7. |  | CLOSED
5 | 2020-07-31 | DEFFORM 47ST | C5 - Variant Bids | RFS's response is within the scope of the requirement except as otherwise noted herein. | The Authority are content with RFS comment in the compliance matrix. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
6 | 2020-07-31 | DEFFORM 47ST | C6 - C12 - Defence Reform Act 2014 - Part 2, Single Source Contract | Not applicable. This proposal will not result in a Qualifying Defense Contract as it will be less than £5M. See also comments to DEFFORM 47ST Section D. | The Authority can confirm that this contract will not result in a Qualifying Defence Contract. However this term is a mandatory requirement within all MOD Contract Terms and Conditions and only provides an understanding of the implications in the event that it does result in a QDC. | Ryan Albertsen | 2020-08-07 | As RFS is unable to comply with QDC requirements, The Authority must agree that in the event anything about the contract changes, resulting in a QDC, the Authority's only recourse is to terminate the contract for convenience. These comments apply to any other QDC sections throughout, e.g., POC 10. | As the worst case scenario cost has been calculated and totals less than £5mil. I am content the contract will not become a QDC and therefore happy with RFS response. Wording will remain in contract as this is a mandatory condition but the Authority will terminate the contract for conveniance if such situation arises. POC to be CLOSED |  | CLOSED
7 | 2020-07-31 | DEFFORM 47ST | D - Details of Price Breakdown and Mandatory Criteria | RFS bases its prices on the value of its proprietary products to the customer. Its business model does not require it to maintain cost data by product or program and as a result it is unable to provide cost data and will not be submitting Details of Price Breakdown or DEFFORM 815. This business model, maintained for over 40 years, results in RFS assuming the risk of cost overruns, providing the customer a risk free price and accelerating product availability. In lieu of Section D or DEFFORM 815, see supporting price information attached to Schedule 2 Table 1 as Appendix A. | The Authority require RFS priced offer to be broken down in line with the criteria shown at Section D - Details of Price Breakdown and Mandatory Criteria. | Ryan Albertsen | 2020-08-07 | Such breakdown is not available. RFS does not track costs in the manner requested. For example, no employee tracks time by project, and employees are cross-trained to enable moving quickly from one project to another, as needed. Parts are sometimes purchased in bulk at risk, and sometimes not. So other than serialized items, there's no way to know which cost applies to a particular part used in an end product. Also, we have only two accounting personnel. Tracking costs in the manner described would require significantly more accounting and other personnel that would have no value add to the end product. Instead, RFS elects to operate lean where possible, allowing more value added resources for engineering, design, development, production, quality control, etc. The supporting price information in RFS's proposal is what is available. Please let us know if you have any questions regarding that info. | The Authority confirm they are content with RFS comment. POC to be CLOSED. |  | CLOSED
8 | 2020-07-31 | DEFFORM 47ST | F8 - Government Furnished Assets | RFS maintains accountability for Government Furnished Assets in accordance with its customer property management system, which has been approved as compliant to the requirements of Federal Acquisition Regulation 52.245-1 "Government Property" by the United States Government (USG) and must be deemed to satisfy DEF STAN 05-99. A copy of the USG's letter approving RFS's customer property management system is attached. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
9 | 2020-07-31 | DEFFORM 47ST | F14 - Sensitive Information | Acceptable subject to any third party recipient being subject to appropriate confidentiality obligations. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
10 | 2020-07-31 | DEFFORM 47ST | F15 - Remedies for actional contraventions under the Defence Reform Act 2014 | Not applicable; please delete for avoidance of doubt. See comments to DEFFORM 47ST Sections C6-C12 and D. | This term is a mandatory requirement within all MOD Contract Terms and Conditions and therefore cannot be removed. | Ryan Albertsen | 2020-08-07 | This relates to QDC. Comments at POC 7 apply. | As the worst case scenario cost has been calculated and totals less than £5mi. I am content the contract will not become a QDC and therefore happy with RFS response. Wording will remain in contract as this is a mandatory clause. POC to be CLOSED |  | CLOSED
11 | 2020-07-31 | Appendix 1 to DEFFORM 47ST. | 3-6 - IPR Restrictions | RFS self funds the design and development of its products and retains the proprietary rights thereto, including the subject products. Customers are granted Limited Rights within the meaning of the U.S. Federal Acquisition Regulation 52.227-14(a). RFS is unaware of any other restrictions on use or obligations to make payments on any intellectual property included in the items. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
12 | 2020-07-31 | Appendix 1 to DEFFORM 47ST. | 7-12 - Notification of Foreign Export Control Restrictions | The items are subject to U.S. Export Administration Regulations and U.S. International Traffic in Arms Regulations, and a non-UK export license will be required. RFS would classify the RCEFS B-Kit under ECCN 9A610.x, and the IAFS (ComboPak) under USML Cat. II(j)(11), if shipped as PN HM025-610-11 (i.e., with the ammunition storage magazine (ASM)), or ECCN 9A610.x, if shipped as PN HM025-410-21 (without the ASM). DEFFORM 528 is attached. If the Authority has any existing licenses that can be used, please let us know. If the items will ship to the Authority's freight forwarder in Dulles, Virginia (per SC2 Contract Conditions Clause 46.8), RFS assumes that the Authority and its freight forwarder will be responsible for obtaining any necessary export license. In the event RFS becomes the exporter of record, it will apply for any necessary export license(s) and/or determine the applicability of any license exception(s) or exemption(s); the price for which is in Schedule 10 attached. In that event, the Authority may need to provide an end use/end user statement and/or import certificate to support the license application(s). There may be restrictions on re-export or re-transfer; some such restrictions may be unknown until a license application is approved. Any such provisos will be disclosed to the Authority once known. Any import/export compliance into the UK or out of the UK is the responsibility of the Authority. The Authority will send any Government Furnished Assets to RFS's facility under DDP delivery terms and be responsible for all expenses related to transportation, import, duties, and taxes. | The Authority are still reviewing this POC and will provide a formal response shortly. | Ryan Albertsen | 2020-08-07 | Awaiting The Authority's comments. | The Authority are currently finding out whether we have any existing licenses. If the Authority do not have any existing licenses can you confirm what's the time and cost implications of RFS providing the necessary licenses. | The Authority confirm that they have all neccesary licences in place and in the event new items are purchased from RFS, the Authority will purchase the export licecnes detailed at Schedule 10. POC to be CLOSED | CLOSED
13 | 2020-07-31 | Appendix 1 to DEFFORM 47ST. | 13-15 - Import Duty | RFS is unfamiliar with the processes involved with EU customs compliance and understands that the Authority will be responsible for import and related obligations under EXWORKS delivery terms. RFS is able to include additional references on its shipping paperwork as required and advised by the Authority for the subject deliverables (EORI number, Notifying Party information, etc.). In any event, RFS's prices are EXWORKS, Tempe, Arizona, and do not include any VAT, import taxes, fees or duties, which are the Authority's responsibility. | The Authority confirm they are content with RFS comments, this contract will be drafted using EXWORKS delivery terms. | Ryan Albertsen | 2020-08-07 | Acknowledged. EXWORKS, Tempe, Arizona | POC to be CLOSED |  | CLOSED
14 | 2020-07-31 | Appendix 1 to DEFFORM 47ST. | 16 - Sub-contracts form 1686 (aka Appendix 5) | RFS will comply with this requirement so long as furnished reportable information has been conspicuously marked "OFFICIAL" or "OFFICIAL- SENSITIVE" as deemed necessary by the disclosing party. No such information is contemplated. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
15 | 2020-07-31 | Appendix 1 to DEFFORM 47ST. | 26 - Change of Circumstances | A current Statement of Good Standing is attached. | The Authority confirm they are content with RFS comments and attached Statement of Good Standing. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
16 | 2020-07-31 | Appendix 1 to DEFFORM 47ST Annex A | 27 - Asbestos, Hazardous Materials and Depletion of the Ozon Layer | To the best of RFS's knowledge, no hazardous materials, substances or ozone depleting substances are being supplied. Please delete this paragraph as inapplicable and for avoidance of doubt. | Point 27 is a mandatory requirement within all Authority tenders. We are content that there is a Nil Return but keeping this within the contract shows that it has still been considered. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
17 | 2020-07-31 | Appendix 1 to DEFFORM 47ST Annex A | 28 - Military Aviation Authority (MAA) | MAA Regulatory Articles consist of hundreds of documents with which RFS is not familiar and does not have the resources to become so. RFS's MAA compliance is limited to the RAs listed at Schedule 2 Annex 2, subject to any comments provided at such Annex 2. | The Authority confirm they are content with RFS comment that compliance is limited to the RAs listed in Schedule 2 Annex 2. | Ryan Albertsen | 2020-08-07 | Acknowledged, subject to RFS's comments in Schedule 2 Annex 2. | POC to be CLOSED |  | CLOSED
18 | 2020-07-31 | Appendix 1 to DEFFORM 47ST Annex A | 29 - Bank or Parent Company Guarantee | This proposal does not include a bank guarantee. The parties have been doing business for years and a guarantee has never been required. Please delete the requirement as inapplicable. | The Authority confirm they are content with RFS comment, a Bank or Parent Company Guarantee is not required. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
19 | 2020-07-31 | Appendix 1 to DEFFORM 47ST Annex A | 30-33 - The Armed Forces Covenant | RFS's hiring practices include provisions for service men and women, reservists and veterans. Approximately 30% of RFS's current employee base consists of veterans of the US Armed Forces. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
20 | 2020-07-31 | Standardise Contracting Terms (SC2) | 4 - Governing Law | RFS proposes New York law and The Hague for venue. This is negotiable, but we prefer some neutrality in choice of law and venue. Please delete subparagraph g. | The Authority's policy requires all contract terms and conditions must be subject to English or Scots Law. The previous contract with RFS HELSS/0002 was also subject to English Law. | Ryan Albertsen | 2020-08-07 | RFS will consent to English law, with London as a place of venue and binding arbitration in accordance with Clause 40 (Dispute Resolution) in lieu of English Courts as the only method for any dispute resolution. For paragraph 4.g., RFS does not have appointed solicitor(s) in England and any notices must be provided to Ryan Albertsen at RFS in Tempe, Arizona. | The Authority confirm they are content with RFS comment and has been added into Schedule 3 - Contract Data Sheet Condition 4. POC to be CLOSED |  | CLOSED
21 | 2020-07-31 | Standardise Contracting Terms (SC2) | 13 - Transparency | See attached Schedule 5. | The Authority confirm they are content with Schedule 5 - Commercially Sensitive Information. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
22 | 2020-07-31 | Standardise Contracting Terms (SC2) | 18 - Contractor's Records | Contractor's records relating to production of the deliverables are available for review at RFS's facility. Financial information is not available for review to any customer. Any records needed from a subcontractor will be acquired by RFS, if available and within these parameters, as the Authority does not have privity of contract with any subcontractor. | This clause it not specifically written around financial records and covers for all records specified in and connected with the Contract. With regard to the records made available to the Authority under Clause 18 of this Condition, and subject to the provisions of Clause 14, Disclosure of Information, the Contractor shall permit records to be examined and if necessary copied, by the Authority, or Representative of the Authority, as the Authority may require. | Ryan Albertsen | 2020-08-07 | Due to the proprietary nature of RFS's products, records relating to the product, such as manufacturing drawings, production work orders, testing, inspection, etc., are available for review only at RFS's facility. If The Authority desires a copy of a particular document, the parties will discuss at that time whether the document may be copied. This RFS policy applies for customers. The Authority will receive a Certificate of Conformance with each shipment indicating that items are in accordance with the requirements of the contract. | The Authority can confirm they are content with this comment. POC CLOSED. |  | CLOSED
23 | 2020-07-31 | Standardise Contracting Terms (SC2) | 21 - Supply of Contractor Deliverables and Quality Assurance | RFS’s Quality System is third party certified as compliant with AS9100D and ISO 9001:2015 (see attached certificate), which must be deemed acceptable to meet necessary conditions of the contract. Any topic not covered in AS9100D or ISO 9001:2015 is deemed inapplicable. A separate quality plan will not be written. Upon request, the Authority may be granted temporary access to RFS's Oasis account to review its quality system third party audit results. | The Authority confirm they are content with RFS comment. Authority do require a Quality Plan to be submitted as part of RFS proposal response. This is referenced at Schedule 3 Point 21 - Quality Assurance. | Ryan Albertsen | 2020-08-07 | RFS's Quality System is an internal document. Please let us know if you would like temporary access to RFS's Oasis account to review its third party audit results. | The Authority request access to RFS's OASIS account to review its third party audit results. Please send to DES Apache-EngQA (Barry.Paton100@mod.gov.uk) | The Authority can confirm that RFS OASIS account has been reviewed and DES Apache-EngQA is content that from a QA perspective that they are fully compliant. POC to be CLOSED | CLOSED
24 | 2020-07-31 | Standardise Contracting Terms (SC2) | 22 - Marking Contractor Deliverables | Items will be marked in accordance with MIL-STD-130, which is consistent with RFS's drawings and long standing practice. All prior deliveries to the Authority have been marked in accordance with this standard. | The Authority confirm they are content with RFS comment and RFS are compliant. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
25 | 2020-07-31 | Standardise Contracting Terms (SC2) | 23 - Packaging and Labelling (excluding Contractor Deliverables containing Munitions) | Consistent with RFS's prior contracts with the Authority, this proposal is priced subject to items being packaged and labelled in accordance with ASTM D3591 standard commercial practices. If any UK Military, NATO, or other special Packaging is required, additional charges will apply and can be quoted separately upon request (such requirements are outsourced and the cost is passed on to the customer). RFS will include DEFFORM 129J with each shipment. Please provide an electronic fillable 129J form. | The Authority confirm they are content with RFS comment and RFS are compliant. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
26 | 2020-07-31 | Standardise Contracting Terms (SC2) | 24 - Supply of Hazardous Materials or Substances in Contractor Deliverables | To the best of RFS's knowledge, no hazardous materials, substances or ozone depleting substances are being supplied. Please delete this paragraph as inapplicable and for avoidance of doubt. A signed Schedule 6 is attached. | Clause 24 is a mandatory requirement within all Authority tenders. We are content that there is a Nil Return but keeping this within the contract shows that it has still be considered. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
27 | 2020-07-31 | Standardise Contracting Terms (SC2) | 25 - Timber and Wood-Derived Products | None of the products include timber or wood-derived products. RFS reads the reporting requirement under this clause to apply only in the event wood is in the product and thus does not intend to submit any statistical report under this clause. Accordingly, Schedule 7 is not included in this proposal. In the event timber or wood-derived materials are used in packaging (e.g., crate), RFS will comply with paragraph 25.L. | The Authority requires RFS to complete Schedule 7 providing a Nil Return e.g. NOT APPLICABLE to show this has been considered. | Ryan Albertsen | 2020-08-07 | See attached Schedule 7 marked NOT APPLICABLE. | POC to be CLOSED |  | CLOSED
28 | 2020-07-31 | Standardise Contracting Terms (SC2) | 28 - Delivery / Collection | Delivery terms are EXWORKS, Tempe, Arizona, and all costs and expenses of delivery are the responsibility of the Authority. Items may be collected by the Authority or its representative; or, if desired, RFS can pre-pay and add delivery expenses to its invoice. Title and risk of loss pass when items are loaded for shipment at RFS's facility in Tempe, Arizona. | The Authority have reviewed the comment, can you confirm which part of 28 - Delivery and Collection RFS are not compliant with? This clause is mandatory and we are not permitted to caveat any of these conditions without MoD Commercial Policy approval which would delay Contract Award substantially. The Authority would be content to add RFS additional wording at Schedule 3, Contract Data Sheet, to confirm the exact location. | Ryan Albertsen | 2020-08-07 | For 28.b.(4), RFS is not responsible for the costs of delivery, but will prepay and add freight to its invoice in the event 28.b. applies; EXWORKS Tempe AZ still applies. For 28.d, RFS requests clarity that title and risk of loss pass when items are loaded for shipment at RFS's facility in Tempe, Arizona, regardless of whether 28.b or 28.c apply. | The Authority confirm that RFS are not responsible for cost of Delivery. The Authority confirm that title and risk of loss will pass when items are loaded for shipment at RFS facility. This information has been added into Schedule 3 - Condition 28.b - Delivery by the Contractor for clarity. POC to be CLOSED |  | CLOSED
29 | 2020-07-31 | Standardise Contracting Terms (SC2) | 30 - Rejection | RFS requests the following or similar language be added to the beginning of the last sentence of 30a: "After a reasonable opportunity for Contractor to cure any such nonconformance, ". | 30 - Rejection is a mandatory clause within all MOD contracts and cannot be edited, the Authority confirm that RFS will be given reasonable opportunity for Contractor to cure any such nonconformance. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
30 | 2020-07-31 | Standardise Contracting Terms (SC2) | 32 - Self to Self Delivery | In the event of a self-to-self delivery exceeding 60 days, there will be a fixed storage fee equal to one-half of one percent (0.5%) per calendar month (or portion of a calendar month) of the value of the inventory stored and managed by RFS. This fee will be calculated monthly on the basis of the value of the inventory (based on its purchase price) as of the last day of each month and invoiced quarterly. | The Authority have confirmed within Schedule 3 - Contract Data Sheet that Self to Self delivery is not required, therefore no storage or fees will be required by RFS. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
31 | 2020-07-31 | Standardise Contracting Terms (SC2) | 33 - Import and Export Licences | The Authority is responsible for any UK import license and related fees or activities that may be required. The Authority is also responsible for applying for any needed re-export authorizations, as contemplated under U.S. regulations. RFS will provide supporting information upon request. See also Clauses 7-12 and 13-15 to DEFFORM 47ST Annex A Appendix 1. With regard to risks and dependencies, all delivery is contingent on the timely receipt of needed export approvals and support documentation. RFS is not aware of any instances of license applications for RFS products to the UK being denied and does not anticipate issues with receiving approvals in advance of item availability. The Authority will send any Government Furnished Assets to RFS's facility under DDP delivery terms and be responsible for all expenses related to transportation, import, duties, and taxes. | The Authority confirm they are content with RFS comment and it is the Authority's responsibility to obtain any UK Import licenses. | Ryan Albertsen | 2020-08-07 | Acknowledged. Please also confirm The Authority will send any GFA to RFS under DDP delivery terms and The Authority will be responsible for all expenses related to such transportation, export/import, duties and taxes. | The Authority can confirm that we will send any GFA to RFS under DDP and are still reviewing the licences with UKDPO and will provide a formal response shortly. | The Authority confirm that they have all neccesary licences in place and in the event new items are purchased from RFS, the Authority will purchase the export licecnes detailed at Schedule 10. POC to be CLOSED | CLOSED
32 | 2020-07-31 | Standardise Contracting Terms (SC2) | 35 - Contract Price | The prices quoted are firm fixed prices (but see notes at Schedule 2 Statement of Requirement Item 3b). They do not including the cost of freight, any VAT or any customs related or excise or other duty. Any such costs or expenses are the responsibility of the Authority in all respects. | The Authority confirm they are content with RFS comment and that RFS firmed price proposal excludes the cost of freight, any VAT or any customs related or excise or other duty. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
33 | 2020-07-31 | Standardise Contracting Terms (SC2) | 36 - Payment and Recovery of Sums Due | For paragraph 36.d, please add the following at the end of the sentence: ", which shall not exceed 30 days from the date the Authority receives the Deliverables, or 60 days after the Authority's freight forwarder receives the Deliverables, whichever first occurs." | This clause is mandatory within all MOD Contracts and cannot be edited. The Authority are content to add RFS comment into the special clause 46.4 - Payment Terms. | Ryan Albertsen | 2020-08-07 | Acknowledged | This info added to clause 46.4 - Payment Terms. POC to be CLOSED. |  | CLOSED
34 | 2020-07-31 | Standardise Contracting Terms (SC2) | 37 - Value Added Tax | See comments above at SC2 Clause 35. RFS is not registered for UK VAT and has not previously been required to register or be involved in any determination of VAT liability. | The Authority confirm that Value Added Tax is MOD responsibility. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
35 | 2020-07-31 | Standardise Contracting Terms (SC2) | 40 - Dispute Resolution. | RFS requests the International Chamber of Commerce Rules of Arbitration in lieu of the Arbitration Act of 1996. | Under Point 39 of RFS Compliance Matrix added a comment stating "RFS requests the International Chamber of Commerce Rules of Arbitration in leu of the Arbitration Act of 1996". Can RFS confirm what they require for this comment? | Ryan Albertsen | 2020-08-07 | The Arbitration Act of 1996 is acceptable, subject to the comments at POC 20. | The Authority are content with this comment. POC to be CLOSED. |  | CLOSED
36 | 2020-07-31 | Standardise Contracting Terms (SC2) | 42 - Termination for Convenience | Based on RFS's business model, the costs and expenses associated with a termination for convenience are not subject to exact calculation. Therefore, in the event of T4C, the following termination liability schedule applies (as a percentage of the purchase price terminated, based on days terminated prior to delivery): 0-30 days = 50%, 31-180 days = 35%, 181+ days = 10%. | The Authority are still reviewing this POC and will provide a formal response shortly. | Ryan Albertsen | 2020-08-07 | Awaiting The Authority's comments. | This clause is included in the highly unlikely event that The Authority no longer have a requirement. The Authority have provided Robertsons an indemnity at Clause 42.d and details at 42.e that the total liability shall be limited to the total price of the Contractor Deliverables payable under the contract. This indemnity provides Robertsons with the potential to redeem 100% of the price of the Contractor Deliverables and are substantially better terms than those proposed in the Termination Liability Schedule in the original response to this POC. | The Authority confirm they are content to accept RFS Termination for convencience clause. This has now been added to 46. Special Conditions that apply to this Contract. POC to be CLOSED. | CLOSED
37 | 2020-07-31 | Standardise Contracting Terms (SC2) | 43 - Material Breach | For Clause 43b, such damages will be limited to the value of the items so terminated. | The Authority will not limit damages to the value of the items terminated. The Authority requires the right to claim such damages as may have been sustained as a result of the Contractor's material breach of the Contract. For this requirement it could include but not limited to, any shipping/delivery the Authority puts in place under the EXWORKs terms. | Ryan Albertsen | 2020-08-07 | It is acceptable to have an uncapped liability in the event of RFS's wilful misconduct or refusal to perform. Absent that, RFS cannot expose itself to unlimited liability, particularly if that included R&D associated with a reprocurement. RFS will agree to limited damages up to 110% of the value of the items terminated, which should cover such additional reasonable expenses as shipping/delivery, etc., | The Authority are unable to define material breach as a definitive meaning has not been agreed by the English courts. In this circumstance The Authority would be unable obtain the Contractor Deliverable in substitution from another supplier and therefore this liability does not exist. The Authority are reviewing the potential damages and will respond as soon as possible. | The Authority have reviewed the potential damages and confirm that they are content to agree to limit the damages to 110% of the value of the items terminated. POC to be CLOSED. | CLOSED
38 | 2020-07-31 | 45. Project Specific DEFCONs and DEFCON SC Variants that apply to this contract | DEFCON 532B - Protection of Personal Data | No personal data is anticipated to be processed as part of this contract. This DEFCON and DEFFORM 532 or 532B are deemed inapplicable. | DEFCON 532B and DEFFORM 532B is a mandatory requirement within all MOD Contracts. If no personal data is anticipated, then RFS must complete DEFFORM 532B stating "Not Applicable". | Ryan Albertsen | 2020-08-07 | See attached DEFFORM 532 marked NOT APPLICABLE. | POC to be CLOSED |  | CLOSED
39 | 2020-07-31 | 45. Project Specific DEFCONs and DEFCON SC Variants that apply to this contract | DEFCON 611 (SC2) - Issued Property | See notes at DEFFORM 47ST, section F8. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
40 | 2020-07-31 | 45. Project Specific DEFCONs and DEFCON SC Variants that apply to this contract | DEFCON 658 - Cyber | RFS meets or exceeds the requirements in the low risk classification stated in the contract. RFS’s Cyber Security Plan meets NIST 800-171, which must be deemed acceptable to meet necessary conditions of the contract. | The Authority are still reviewing this POC and will provide a formal response shortly. | Ryan Albertsen | 2020-08-07 | Awaiting The Authority's comments. | The Authority deem NISR 800-171 as an acceptable means of complicance but the Authority will still require the completion of a Supplier Assurance questionaire online. I have confirmed that this is a different questionaire to the one completed to gain an Exostar account. Supplier Assurance Questionaire can be found at: https://supplier-cyber-protection.service.gov.uk/. POC is CLOSED |  | CLOSED
41 | 2020-07-31 | 45. Project Specific DEFCONs and DEFCON SC Variants that apply to this contract | DEFCON 694 - Accounting for Property of the Authority | See notes at DEFFORM 47ST, section F8. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
42 | 2020-07-31 | 45. Project Specific DEFCONs and DEFCON SC Variants that apply to this contract | DEFCON 812 - Single Source Open Book | See notes at DEFFORM 47ST, section D. Also, no individual subcontractor meets the definition of "Material Single Source Sub-Contract (Non-Qualifying)". | The MoD would like to understand the reasoning for RFS rejection of this DEFCON. The Authority will not agree to removal of DEFCON 812. It is MoD Policy to include this clause. The reason for this is set out below: DEFCON 812 (Edn 04/15) Single Source Open Book - this has been included within the contract and is being applied as the contract: is not the result of a competitive process (as defined in the Single Source Contract Regulations 2014 (SSCR)); the contract is not a Qualifying Defence Contract; and the contract is valued at £1m GBP or above. In summary the ‘open book’ provisions of the SSCR require contractors and sub-contractors which are subject to the SSCR to maintain relevant accounting and other records and provides rights for the MOD (or representative) to have access to those records for the purpose of verifying costs and monitoring performance. The purpose of this DEFCON is to secure equivalent open book rights for the MOD in single-source contracts and sub-contracts which are not subject to the SSCR and which are valued at or above £1M. | Ryan Albertsen | 2020-08-07 | See RFS's comments at POCs 6 and 7. | The Authority will remove this DEFCON. POC to be CLOSED. |  | CLOSED
43 | 2020-07-31 | 45. Project Specific DEFCONs and DEFCON SC Variants that apply to this contract | DEFCON 814 - Single Source Confidentiality of Open Book and Reporting Info | See notes at DEFFORM 47ST, section D and F15. See also Schedule 5. | The MoD would like to understand the reasoning for RFS rejection of this DEFCON. The Authority will not agree to the removal of DEFCON 814. It is MoD Policy to include this clause. The reason for this is set out below: DEFCON 814 (Edn 02/19) or SC2 (Edn 11/17) Single Source Confidentiality of Open Book and Reporting Information - this has been included as the contract is not the result of a competitive process (as defined in the Single Source Contract Regulations 2014 (SSCR)); the contract is not a Qualifying Defence Contract (QDC); and the contract includes either DEFCON 812 and DEFCON 813. In summary as this contract has not been identified as a QDC the clause requires the provision to the MOD of reports and notifications equivalent to those required under the SSCR, some of which will contain confidential information. The Authority may wish to aggregate this information with other information obtained under other single-source contracts, including those subject to the SSCR. This DEFCON 814 allows the MOD to do that, while providing contractual protection to the contractor in respect of that confidential information. | Ryan Albertsen | 2020-08-07 | See RFS's comments at POCs 6 and 7. | The Authority will remove this DEFCON. POC to be CLOSED. |  | CLOSED
44 | 2020-07-31 | 45. Project Specific DEFCONs and DEFCON SC Variants that apply to this contract | DEFCON 815 - Contract Pricing Statement - Single Source Non-Qualifying Contracts | See notes at DEFFORM 47ST, section D. | The MoD would like to understand the reasoning for RFS rejection of this DEFCON. The Authority will not agree to the removal of DEFCON 815. It is MoD Policy to include this clause. The reason for this is set out below: DEFCON 815 (Edn 04/15) Contract Pricing Statement - Single Source Non-qualifying contracts - has been included as the contract is not the result of a competitive process (as defined in the Single Source Contract Regulations 2014 (SSCR)); the contract is not a Qualifying Defence Contract; and the contract is valued at £1M or above. In summary this DEFCON requires you as the Contractor to produce a Contract Pricing Statement setting out the key facts, assumptions and calculations used to arrive at the Contract Price. If you as the Contractor fail to do that, or if those facts, assumptions and calculations are subsequently shown to have been unreasonable or unsuitable given the information available to you as the Contractor at the time of pricing, then the Authority should be able to claim against you the Contractor for any loss it may have suffered as a result. Similar protections are made available to you as the Contractor, in relation to information provided by the MOD at the time of pricing, which were material to the contract price agreed. In order to maintain the MOD’s post-costing rights, and our ability to detect problems with the original contract pricing, DEFCON 812 (Single Source Open Book) has been included under this Contract in addition to DEFCON 815. | Ryan Albertsen | 2020-08-07 | See RFS's comments at POCs 6 and 7. | The Authority will remove this DEFCON. POC to be CLOSED. |  | CLOSED
45 | 2020-07-31 | 45. Project Specific DEFCONs and DEFCON SC Variants that apply to this contract | DEFFORM 129J - Shipping Form Design | See notes at SC2, section 23. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
46 | 2020-07-31 | 45. Project Specific DEFCONs and DEFCON SC Variants that apply to this contract | DEFFORM 532 - Personal Data Particulars | See comment at DEFCON 532B above. | DEFCON 532B and DEFFORM 532B is a mandatory requirement within all MOD Contracts. If no personal data is anticipated, then RFS must complete DEFFORM 532B stating "Not Applicable". | Ryan Albertsen | 2020-08-07 | Acknowledged. See POC 38. | POC to be CLOSED |  | CLOSED
47 | 2020-07-31 | 46. Special Conditions that apply to this Contract | 46.4 - Payment Terms | For items completed at Contractor's facility, Contractor will input an invoice in CP&F upon shipment of the item(s) (i.e., when items are loaded with a carrier in Arizona). For Ad Hoc Work authorized at locations other than Contractor's facility, the invoice will be input upon completion of the requirement to the satisfaction of the Authority's Project Manager. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
48 | 2020-07-31 | 46. Special Conditions that apply to this Contract | 46.5 - Cybersecurity | RFS meets or exceeds the requirements in the low risk classification stated in the contract. RFS’s Cyber Security Plan meets NIST 800-171, which must be deemed acceptable to meet necessary conditions of the contract. | The Authority are still reviewing this POC and will provide a formal response shortly. | Ryan Albertsen | 2020-08-07 | Awaiting The Authority's comments. | The Authority deem NISR 800-171 as an acceptable means of complicance but the Authority will still require the completion of a Supplier Assurance questionaire online. I have confirmed that this is a different questionaire to the one completed to gain an Exostar account. Supplier Assurance Questionaire can be found at: https://supplier-cyber-protection.service.gov.uk/. POC to be CLOSED. |  | CLOSED
49 | 2020-07-31 | 46. Special Conditions that apply to this Contract | 46.6 - Military Aviation Authority (MA) Regulatory Publication | See notes at DEFFORM 47ST Annex 1 Appendix 1 Section 28. See also Schedule 2 Annex 2. | The Authority confirm they are content with RFS comment. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
50 | 2020-07-31 | 46. Special Conditions that apply to this Contract | 46.7 - Obsolescence | RFS maintains an obsolescence management strategy consistent with this section. In the event an obsolescence issue is identified during the term of the contract, the Authority will be notified and provided a resolution strategy(ies). A separate Obsolescence Management Plan will not be written for this proposal. | The Authority are still reviewing this POC and will provide a formal response shortly. | Ryan Albertsen | 2020-08-07 | Awaiting The Authority's comments. | The Authority can confirm that a Obsolencence Management Plan is not required. POC to be CLOSED. |  | CLOSED
51 | 2020-07-31 | Schedules | Schedule 2 - Table 1 - Pricing | Attached. Also provided in Excel format for convenience; the PDF version controls. RFS made assumptions for PNs on items 3a and 3b (see notes on Schedule 2 SOR). See also notes at SC2 Section 35. RFS's prices are based on calendar years and the headings in Schedules 2, 10 and 12 have been adjusted accordingly. | The Authority request RFS to submit their proposal prices in Financial Years, e.g. 01/04/2021 - 31/03/2022 as detailed in the original ITT. | Ryan Albertsen | 2020-08-07 | If The Authority's financial year does not coincide with the calendar year, then each financial year will have two prices. RFS's prices are based on calendar years. The applicable price is based on the date of the order, or the date an asset is received for overhaul, whichever is later. | RFS have confirmed that pricing will be provided in line with Authority's financial years. POC to be CLOSED. |  | CLOSED
52 | 2020-07-31 | Schedules | Schedule 2 - Table 1 - Appendix A - Contractors Price Support for Table 1 Items | Attached. See notes at DEFFORM 47ST, Section D. | The Authority require RFS priced offer to be broken down in line with the criteria shown at Section D - Details of Price Breakdown and Mandatory Criteria. | Ryan Albertsen | 2020-08-07 | See comments at POC 7. | The Authority confirm they are content with RFS comment. POC to be CLOSED. |  | CLOSED
53 | 2020-07-31 | Schedules | Schedule 2 - SOR Table - Contractors Compliance response | Attached. | The Authority are reviewing RFS SOR Compliance response and will provide a formal response shortly. | Ryan Albertsen | 2020-08-07 | Awaiting The Authority's comments. | The Authority confirm they are content with RFS Compliance response. POC to be CLOSED. |  | CLOSED
54 | 2020-07-31 | Schedules | Schedule 2 Annex 1 - Work Scope for Item 1 (OH IAFS) and Item 2 (OH RCEFS) - to be completed by Contractor in Tender | Attached. See also Schedule 12 for Over & Above pricing. | The Authority are reviewing the Work Scope and will provide a formal response shortly. | Ryan Albertsen | 2020-08-07 | Awaiting The Authority's comments. | The Authority confirm they are content with RFS Work Scope. POC to be CLOSED. |  | CLOSED
55 | 2020-07-31 | Schedules | Schedule 2 Annex 2 - RAs | RA compliance matrix attached. See also notes at DEFFORM 47ST Annex A Appendix 1 Section 28. | The Authority confirm they are content with RFS comment that compliance is limited to the RAs listed in Schedule 2 Annex 2. | Ryan Albertsen | 2020-08-07 | Acknowledged, subject to RFS's comments in Schedule 2 Annex 2. | The Authority confirm they are content with RFS comment. POC to be CLOSED. |  | CLOSED
56 | 2020-07-31 | Schedules | Schedule 3 - Contract Data Sheet | Condition 4: See notes at SC2 Section 4. Condition 21: See notes at SC2 Section 21. Condition 22: See notes at SC2 Section 22. Condition 24: Completed Schedule 6 attached. See also notes at SC2 section 24. Condition 25: See notes at SC2 Section 25. Conditions 28b and 28c: See notes at SC2 Section 28. Condition 30: See notes at SC2 Section 30. Condition 32: See notes at SC2 Section 32. Condition 35: See notes at SC2 Section 35. Also, all of the prices quoted are firm prices. Condition 42: See notes at SC2 Section 42. | Please refer to relevant POCs in relation to the SC2 Clause. | Ryan Albertsen | 2020-08-07 | See relevant POCs. | POC to be closed, please refer to SC2 Clause POC for Authority's comments. |  | CLOSED
57 | 2020-07-31 | Schedules | Schedule 5 - Contractors Commercial Sensitive Information | Attached | The Authority are content with the submitted Schedule 5. | Ryan Albertsen | 2020-08-07 | Acknowledged | The Authority are content to redact pricing information detailed at Schedule 2 and Schedule 10 from advertsing but will advertise a total price of the contract. POC to be CLOSED |  | CLOSED
58 | 2020-07-31 | Schedules | Schedule 6 - Hazardous Contractor Deliverables, Materials or Substances Supplied under the Contract | Attached | The Authority are content with the submitted Schedule 6. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
59 | 2020-07-31 | Schedules | Schedule 7 - Timber and Wood Derived Products Supplied under the Contract. | See notes at SC2 Section 25. | Please refer to POC 27 | Ryan Albertsen | 2020-08-07 | See comments at POC 27. | POC to be CLOSED |  | CLOSED
60 | 2020-07-31 | Schedules | Schedule 8 - Acceptance Procedure | Please clarify the repeated statement "equipment must be . . . to the same specification as the agreed Master Spares List." Only SOR Item 4 is on the Master Spares List. Items 1 and 2 will be refurbished IAW Schedule 2 Annex 1 Work Scope. Items 3 and 4 will be new, except as otherwise stated in Schedule 2 Table 1 and SOR. Also, we've added Over & Above items to Schedule 12 (not just ad hoc services). So Item 5 will need to be adjusted too. The Certificates of Conformity will be consistent with SC2 Section 26, not EASA Form 1 or FAA 8130. Robertson recommends deleting Schedule 8 and leaving condition SC2 condition 29. | The Authority are still reviewing this POC and will provide a formal response shortly. | Ryan Albertsen | 2020-08-07 | Awaiting The Authority's comments. | Schedule 8 - Acceptance Procedure is a mandatory Schedule within all MOD contracts. The Authority will align this document to the requirement. POC to be CLOSED. |  | CLOSED
61 | 2020-07-31 | Schedules | Schedules 10 - Masters Spares List - RCEFS & IAFS Agreed Firm Prices | Attached. See also notes at Schedule 2 Table 1, and SC2 Section 35. | The Authority are content with the submitted Schedule 10. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
62 | 2020-07-31 | Schedules | Schedule 11 - Government Furnished Assets | For IAFS, we recommend listing PN HM025-600-11 (tank with ammunition storage magazine attached) and/or PN HM025-410-21 (tank w/o ASM attached). If the ASM is in good condition, the Authority may wish to ship the tank w/o ASM to save freight costs (the ASM is very heavy). We do not recommend listing HM025-600-21, which is the HM025-600-11 plus 3 connecting drop hoses that are replaceable, not repairable. If the MoD prefers to retain HM025-600-21 and have RFS replenish the drop hoses as part of the refurbishment, that can be done at over and above prices for the spares on Schedule 10. | The Authority are still reviewing this POC and will provide a formal response shortly. | Ryan Albertsen | 2020-08-07 | Awaiting The Authority's comments. | The Authority are content with this comment. POC to be CLOSED. |  | CLOSED
63 | 2020-07-31 | Schedules | Schedule 12 - Firm Rates for Item 5 of Schedule 2. | Attached. See also notes at Schedule 2 Table 1, Schedule 2 Annex 1, and SC2 Section 35. This Schedule 12 includes Over and Above (O&A) pricing for efforts that are not included in the Schedule 2 Annex 2 Work Scope for Schedule 2 Table 1 items 1 and 2. We presume the Authority prefers to handle the O&A as Ad Hoc Tasking under Item 5. | Can RFS also submit Travel and Subsistence rates and include these at Schedule 12 - Firm Rates for Item 5 of Schedule 2 in line with the contract. | Ryan Albertsen | 2020-08-07 | Travel and subsistence rates will be calculated at the time of travel (if any) in accordance with the footnote in Schedule 12. | The Authority are content with this comment. POC to be CLOSED. |  | CLOSED
64 | 2020-07-31 | Quality Assurance Conditions | AQAP 2310 - NATO Quality Assurance Requirements for Aviation, Space, Defence Suppliers | Same comments, caveats, exceptions as Schedule 3-Condition 21 and SC2 Section 21. | Please refer to POC 23 | Ryan Albertsen | 2020-08-07 | See comments at POC 23. | The Authority request access to RFS's OASIS account to review its third party audit results. Please send to DES Apache-EngQA (Barry.Paton100@mod.gov.uk) | The Authority can confirm that RFS OASIS account has been reviewed and DES Apache-EngQA is content that from a QA perspective that they are fully compliant. POC to be CLOSED | CLOSED
65 | 2020-07-31 | Quality Assurance Conditions | DEFSTAN 05-061 Pt 9 (Issue 5) - Quality Assurance Procedural Requirements - Independent Inspection Requirements for Safety | No safety critical items are contemplated. Please delete as inapplicable. | The Authority are content to delete DEFSTAN 05 -061 Pt 9 (Issue 5). | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
66 | 2020-07-31 | Deliverables | Supplier Contractual Obligations | Subject to comments herein. | The Authority are content with RFS comment in the compliance matrix. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED
67 | 2020-07-31 | Good Standing | Statement Relating to Good Standing (to be signed and submitted with Tender) | Attached. | The Authority are content with the submitted Statement Relating to Good Standing. | Ryan Albertsen | 2020-08-07 | Acknowledged | POC to be CLOSED |  | CLOSED

## Technical
POC | Date Raised | Source Document | MOD Query | To Who | Response Required Date | RFS Response | MOD Response | Status
1 | 2020-08-07 | ITT 700008662 RCEFS and IAFS - Robertson's Proposal | Can the following items be added to the spares lists and pricing be supplied? Support Assembly HM029-253-12 Closure Support HM029-252-2 Closure Support HM029-252-1 Support Assembly HM029-253-11 Strap Assembly HM029-218-41 These have been requested recently as common faulty items. | This text/paragraph/page has been redacted under exemptions set out by the Freedom of Information act | 2020-08-14 | This text/paragraph/page has been redacted under exemptions set out by the Freedom of Information act | The Authority have reviewed and are content with response. POC to be CLOSED | CLOSED
2 | 2020-08-07 | ITT 700008662 RCEFS and IAFS - Robertson's Proposal | Can repair schemes be created to replace the above items at front line Unit; therefore not requiring return of AMATTS to industry for minor repairs. | This text/paragraph/page has been redacted under exemptions set out by the Freedom of Information act | 2020-08-14 | This text/paragraph/page has been redacted under exemptions set out by the Freedom of Information act | The authority have reviewed and are content with response. The DT have minimal issues other than the aforementioned Support Assemblies. POC to be CLOSED. | CLOSED
3 | 2020-08-07 | ITT 700008662 RCEFS and IAFS - Robertson's Proposal | How many version 1.0 RCEFS tank shells would be able to be repaired, before being forced to replace wth 2.0 shells? | This text/paragraph/page has been redacted under exemptions set out by the Freedom of Information act | 2020-08-14 | Depending on the level of damage, the MoD's existing 1.0 shells may be repairable. If they instead need replaced, 1.0 shells can only be manufactured if the MoD has any usable legacy ESSS shells. RFS currently has no legacy ESSS shells available. | The Authority are content with this comment. POC to be CLOSED | CLOSED
4 | 2020-08-07 | ITT 700008662 RCEFS and IAFS - Robertson's Proposal | Pt 20 - How do RFS comply with RA 4800 to repair components, are RFS compliant with US Federal Regs for repair & maintenance.? | This text/paragraph/page has been redacted under exemptions set out by the Freedom of Information act | 2020-08-14 | RFS did not see RA 4800 as a requirement. Please identify where it is located in the ITT. | The Authority can confirm that RA 4800 is not required. POC to be CLOSED | CLOSED
5 | 2020-08-07 | ITT 700008662 RCEFS and IAFS - Robertson's Proposal | Can RFS define GFP as shown within Schedule 2 - Schedule of Requirements Annex 1 - Work Scope. | This text/paragraph/page has been redacted under exemptions set out by the Freedom of Information act | 2020-08-14 | See p.3 of Work Scope. | The Authority are content with this comment. POC to be CLOSED | CLOSED
6 | 2020-08-07 | ITT 700008662 RCEFS and IAFS - Robertson's Proposal | The Authority confirm that we require IAFS HM025-600-11 | This text/paragraph/page has been redacted under exemptions set out by the Freedom of Information act | 2020-08-14 | Acknowledged. | The Authority are content with this comment. POC to be CLOSED. | CLOSED
7 | 2020-08-07 | ITT 700008662 RCEFS and IAFS - Robertson's Proposal | Do RFS repair Ammo magazines as part of refurbishment? | This text/paragraph/page has been redacted under exemptions set out by the Freedom of Information act | 2020-08-14 | Yes, as an Over & Above effort priced in Schedule 12. Such work is performed by the ammo mag OEM. See also Schedule 2, Annex 1 - Work Scope. | The Authority are content with this comment. POC to be CLOSED. | CLOSED