Resilient Heritage Programme Evaluation

Organisation	Heritage Lottery Fund

Department	Strategy & Business Development

Title of procurement	Resilient Heritage

Brief description of supply	Evaluation Service

Estimated value of tender	Up to £40,000 including expenses and VAT

Estimated duration	December 2017 to March 2019

Name of HLF Contact	                    Hilary Leavy

Evaluation Manager

020 7591 6188

hilary.leavy@hlf.org.uk

Timetable	Response deadline:
11.00 am on 14 November 2017	

Clarification questions deadline:
31 October 2017

Clarification meetings:
Week commencing 20 November 2017

Confirmation of contract:
Week commencing 27 November 2017

Completion of research:
January 2022

# 1.	Overview

  - The Heritage Lottery Fund (HLF) was set up in 1994 under the National Lottery Act and distributes money raised by the National Lottery to support projects involving the national, regional and local heritage of the United Kingdom. We operate under the auspices of the National Heritage Memorial Fund (NHMF). Since April 2013 we have been operating under our current Strategic Framework: ‘A lasting difference for heritage and people’. See the HLF website for more details.

  - HLF invests in the full breadth of the UK’s heritage and, through our funding, we aim to make a lasting difference for heritage and people. This is reflected in the outcomes for heritage, people and communities which underpin our grant-making.

  - Resilient Heritage is a grants programme of between £3,000 and £250,000 to help strengthen organisations, build staff and volunteer capacity and better manage heritage in the long term.

  - Funding is intended to increase organisational resilience by helping adapt to changing and challenging circumstances, withstand threats and respond to opportunities.  We want to support organisations and groups to build their capacity through adopting new ways of working, testing out ideas, increasing skills of staff, volunteers and trustees and becoming more financially sustainable.

  - The programme aims to support organisations to increase their capacity and capability or to undertake a significant programme of organisational change in order to become more resilient. This may include taking on new responsibility for heritage, reviewing current business models and implementing change, exploring alternative funding streams (including social investment) or reviewing and setting up new governance arrangements. It will also be possible to apply for some short term revenue support whilst activity is undertaken.

  - Resilient Heritage grants are expected to deliver the following outcomes:

Outcomes for heritage:

- With our support, heritage will be better managed

Outcomes for people:

- With our support, people will have developed skills

Outcomes for communities

- With our support: your organisation will be more resilient

  - Building on three previous programmes Transition Funding, Start-up grants and Catalyst: small grants, we have developed Resilient Heritage (guidance documents for these programmes are available on request). This is a programme that is flexible, allowing applicants to bid for all the activities covered by the previous programmes but also allows for a broader capacity building focus to meet the applicant’s needs. Projects will usually take no longer than 18 months to complete.

  - We have strongly encouraged established organisations to include a diagnostic stage as part of their project planning, using the online Resilient Heritage Strength Checker.  This helps organisations analyse how they currently work and highlights areas of strengths and weakness, to help identify what they need to address as part of their project.

  - We are looking to commission an evaluation which captures learning about Resilient Heritage.  We would also like the evaluation to look at the overall initiative and the additional support provided by our online Resilient Heritage Strength Checker and mentor and other consultancy support.

  - Applicants are encouraged to consider commissioning support from a professional when carrying out their Resilient Heritage project. They can include budget to either find someone through their own networks or to appoint an HLF-approved mentor. If an applicant chooses to use an HLF-mentor local development staff will provide a list of those who would be suitable to undertake the work and advise how much budget to allocate for the mentors time.

  - We are interested in examining how differences in the findings across grantees relate to the characteristics of the grantees (i.e. organisation location, size, financial health and the type of heritage organisation).  For instance have those organisations who trialled new approaches to fundraising or identified other new sources of income become more financially sustainable and resilient.

  - The evaluation should be delivered in a collaborative relationship with Heritage Lottery Fund, as well as with grantees.

Key audiences for the evaluation include:
 - HLF staff
 - The grantees
 - Other funders, heritage stakeholders and other interested parties

The evaluation will also be used to inform future policy development.

# Purpose of the Evaluation

  - The aim of the evaluation is to assess the impact of Resilient Heritage funding on increasing grantees capacity, capability and overall resilience.

  - We want the evaluation to address the following questions:

1. How did overall management capacities (governance, leadership, management, fundraising, financial management, communications etc.) improve as a result of capacity building engagement?
2. In what ways have the quality of grantees activities improved?
3. In what ways have grantees capacity increased (scale, reach or extent of impact)?
4. For those looking to take on the management of heritage, to what extent has the Resilient Heritage grant prepared them for this?

5. Is there evidence that the change Resilient Heritage enables grantees to achieve leads to long term sustainability?
6. How effective was the mentor support element?
7. How effective was the Resilient Heritage Strength Checker in identifying needs and priorities for project planning and improving organisational strength?

  - The evaluation should seek to understand if grantees have increased organisational resilience, increased capacity or achieved significant strategic change, and the extent to which the programme outcomes have been achieved.

  - The evaluation should identify examples of best practice and effective ways of sharing learning.

# Outputs

  - The following outputs will be required:

- an interim report

- a second interim report

- a final report in word;

- any other reports as set out here or agreed between HLF and the contractor; and

- a set of research data, to be stored in a readily accessible electronic format such as Excel

# A project plan with specific deliverables* and timetable will be agreed with the successful consultant/ies. However, HLF expects the following deliverables in accordance with the following timetable as a minimum:

| Deliverable/Key Milestones* | Due date |
| --- | --- |
| Inception Meeting to agree plans, including reporting structures, learning events and a communication and dissemination strategy | TBC |
| Make arrangements to contact all grantees. | Within 10 working days of contract start date |
| An interim report detailing learning to date and any recommendations to ensure outcomes are achieved | March 2018 |
| An interim report detailing learning to date and grantee progress | January 2019 |
| A final report, of 50 pages maximum, with structure agreed with HLF | December 2019 |

# The above represents our minimum requirements.

# * HLF reserves the right to amend this timetable where required.

  - All reports must adhere to HLF’s accessibility and formatting guidance (appended).

  - The initial findings will be confidential to HLF. HLF may prepare or commission summary reports and other materials for subsequent wider distribution, based on the results.

  - All reports to include appendices as agreed between HLF and the contractor. The contents and structure of the report to be agreed in advance of writing. All reports to be supplied in electronic format and hard copy if requested.

  - All bidders are required to adhere to all appropriate regulations and guidelines on the collection, storage, transmission and destruction of personal data (MRS/SRA, Data Protection Act 1998: Guidelines for Social Research, April 2013).

# Contract management

  - We expect the research/evaluation to begin in January 2018 and be completed by January 2020. The final report shall be submitted to HLF in December 2019.

  - The anticipated budget is £40,000 to include all expenses and VAT. The contract will be let by the National Heritage Memorial Fund.

  - The payment schedule will be three payments and will be made in three instalments.  The first payment will be made upon signing of the contract and inception meeting.  The second one upon receipt of the second interim report in January 2019, and the final payment upon HLF’s receipt of an approved final copy of the report in January 2020.

  - The contract will be based on the HLF standard terms and conditions.

  - The research will be managed on a day to day basis for HLF by Hilary Leavy.

# Award Criteria

  - A proposal for undertaking the work should be a maximum of 10 pages and include:

- a detailed method for undertaking the study;

- details of staff allocated to the project, together with experience of the contractor and staff members in carrying out similar projects. The project manager / lead contact should be identified;

- the allocation of days between members of the team;

- the daily charging rate of individual staff involved;

- a timescale for carrying out the project;

- an overall cost for the work.

  - Your Bid will be scored out of 100%.

70% of the marks will be allocated to your response to the Quality Questions below. Each question will be scored using the methodology in the table below.

Tender responses submitted will be assessed by HLF against the following Quality Questions:-

| - Demonstrated a clear understanding of the aims, objectives and main concerns of the evaluation. | Weighing 25% |
| --- | --- |
| - Demonstrated an awareness of the different policy contexts, evaluation and issues relating to capacity building and organisational resilience. | Weighting 25% |
| - Demonstrated a record of producing high quality evaluation reports to support policy and practice development, and to do so concisely | Weighting 15% |
| - Demonstrated the bidder has the capacity and resources to carry out the evaluation within the timescale, or if working in partnership, each organisation has the capacity to fulfil its role and roles of each partner is clear. | Weighting 10% |
| - Demonstrated a clear and realistic project plan, showing phases of the evaluation, tasks for each phase and roles and responsibilities for each member of the team. | Weighting 10% |
| - Demonstrated well considered plans for dissemination of evaluation findings. | Weighting 15% |

## Quality Questions scoring methodology

| Score | Word descriptor | Description |
| --- | --- | --- |
| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the HLF confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the HLF confidence in the ability of the Bidder to deliver the contract. Meets the HLF’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the HLF a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the HLF a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in most respects. |

30% of marks will be awarded for Price.

Price: The evaluation of price will be carried out on the Schedule of charges you provide in response to Table A

## Price Criterion at 30%

- 30 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in your schedule of charges table will be used to score this question.

- For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 30% (full marks) for price and the second placed bidder gets 27.6% and so on. (8/100 x 30 = 2.4 marks; 30-2.4 = 27.6 marks)

- The scores for quality and price will be added together to obtain the overall score for each Bidder.

## Table A - Schedule of Charges

Please show in your tender submission, the number of staff and the amount of time that will be scheduled to work on the contract with the daily charging rate.

Please complete the table below providing a detailed breakdown of costs against each capitalised description, detailing a total and full ‘Firm Fixed Cost’ for each element of the service provision for the total contract period. Bidders may extend the tables to detail additional elements/costs if required.

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this contract.

As part of our wider approach to corporate social responsibility the National Heritage Memorial Fund/Heritage Lottery Fund prefers our business partners to have similar values to our own. We pay all of our staff the living wage (in London and the rest of the UK) and we would like our suppliers and contractors to do likewise. Please highlight in you proposal/tender/bid whether you do pay your staff the living wage.

Bidders shall complete the schedule below, estimating the number of days, travel and subsistence costs associated with their tender submission.

TABLE A: (firm and fixed costs)

| Cost | Post 1 @cost per day (No of days) e.g. Project Manager/ Director @ £500 | Post 2 @cost per day (No of days) e.g. Senior Consultant/manager/researcher @£300 | Post 3 @cost per day (No of days) Junior Consultant/equivalent e.g. £200 | Total days | Total fees |
| --- | --- | --- | --- | --- | --- |
| Inception meeting to agree plans and finalise requirements with the Fund | e.g. 0.5 | 1 | 1.5 | 3 | 850 |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |

| Cost Type | Value (£) |
| --- | --- |
| Sub - Total |  |
| VAT |  |
| Total* |  |

* (This must include all expenses as well as work costs; this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements set out in the ITT)

Notes: 	HLF reserves the right to reject abnormally low tenders. HLF reserves the right to amend the timetable of work where required.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

# Procurement Process

  - HLF reserves the right to reject abnormally low tenders. HLF reserves the right not to appoint and to achieve the outcomes of the research/evaluation through other methods.

  - The procurement timetable will be:

Deadline for clarification questions*: 31 October 2017

Tender return deadline: completed proposal to be returned to HLF by 11.00 am on 14 November 2017.

Clarification meetings** may be held with shortlisted consultants and would take place on week commencing 20 November 2017

HLF will notify bidders of our procurement decision week commencing: 27 November 2017.

*HLF will upload responses to clarification on our website, here.  Please note that we will make the anonymised questions, and our responses to them, available to everyone on the HLF website.

**We reserve the right to carry out clarifications if necessary; these may be carried out via email or by inviting bidders to attend a clarification meeting.  In order to ensure that both HLF’s and Bidder’s resources are used appropriately, we will only invite up to three (the ultimate number will depend on the closeness of the scores) highest scoring bidders to attend a clarification meeting.  Scores will be moderated based on any clarifications provided during this meeting.  You are responsible for all your expenses when attending such meetings.

  - Your tender proposals must be sent electronically via e-mail before the tender return deadline of 11.00 am on 14 November 2017 to the following contact:

Hilary Leavy

Evaluation Manager

Heritage Lottery Fund

020 7591 6188

hilary.leavy@hlf.org.uk

  - Please visit the HLF website for further information about the organisation.

# Appendix: Accessibility and formatting guidance

HLF is committed to providing a website that is accessible to the widest possible audience. Our website is annually tested by accessibility auditors and we must meet the WCAG 2.0 AA compliance level. Our accessibility testing covers all of our content, including downloadable documents, as well as the design and functionality of the site.

Reports and other documents created for HLF (including the tender submissions) need to be clear, straightforward to use, and ready to circulate internally, externally and online, as well as suitable for use by screen reading software. Tips for creating accessible documents can be found below. However, we strongly recommend referring to the RNIB, Gov.uk and WebAIM for more detailed information.

## Readability

In the final report, and all other documents that may be published online including the tender application consultants should ensure that:

- The size of the font is at least 11pt;

- There is a strong contrast between the background colour and the colour of the text. Black text on a white background provides the best contrast. This also applies to any shading used in tables and/or diagrams;

- Italics are only used when quoting book titles for citations and items on the reference list should be arranged alphabetically by author

- Colour formatting and use of photos should be of a resolution size that is easily printable and does not compromise the printability of the document.

For further guidance on ensuring readability of printed materials, please refer to the RNIB Clear Print guidelines. These can be found on the RNIB website.

## Accessibility

Reports should adhere to the following guidelines:

### Formatting

Headings and content in your document should be clearly identified and consistently formatted, to allow easy navigation for users. Heading Styles should be used to convey both the structure of the document and the relationship between sections and sub-sections of the content.

### Spacing

Screen readers audibly represent spaces, tabs and paragraph breaks within copy, so it is best practice to avoid the repetitive use of manually inserted spaces. Instead, indenting and formatting should be used to create whitespace (e.g., use a page break to start a new page, as opposed to multiple paragraph breaks).

### Alternative text

Alt text is additional information for images and tables. This extra information is essential for both document accessibility (screen reading software reads the Alt text aloud) and for the web. Alt text should be concise and descriptive, and should not begin with ‘Image of’ or ‘Picture of’.

### Images

These should be formatted in-line with text, to support screen readers. Crediting pictures may be necessary, usually in response to a direct request from a third party.

### Tables

These should be for used for presenting data and not for layout or design. They should also be simple, and include a descriptive title.

### Additional documents

Any additional information, separate to the report, for example proformas and transcripts which may be used as standalone documents must be fully referenced to the piece of work being submitting and therefore dated, formatted and numbered appropriately.

### Acknowledgement

All reports should acknowledge HLF. Our logo can be found on the HLF website.

### Further resources

Please refer to the links below for further information:

- 'Microsoft Word: creating accessible documents' - webaim.org

- 'How to create an accessible PDF' - GOV.UK

We also recommend using an accessibility consultant to help you produce your reports. Agencies that HLF have worked with include Shaw Trust and The Accessible Digital Documents Company.

HLF retains the right to amend documents in order to create accessible versions for publishing.