# Annex A

| Title of Project | Ocean Country Partnership Programme: Maldives Shark diving codes of conduct, Fuvahmulah, Maldives |
| --- | --- |
| Date and Time for Return of Bids | Wednesday 15 May 2024 @ 09:00 hours UK GMT |
| Contract Reference Number | C24-0604-1887 |
| Address for Bid Submission | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO JAMIE SMALL, BETH FLAVELL OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below: (00 44 1733 866 988) |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: +441733 866987 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: +441733 866987 |
| Proposed Start Date | 29 May 2024 |
| Proposed End Date | 21 March 2025 |

Ocean Country Partnership Programme: Maldives

Shark diving codes of conduct, Fuvahmulah, Maldives

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Background	3

3.	Project Aims	4

4.	Project Objectives	4

5.	Contractor Requirements	5

6.	Potential Follow-On Work	6

7.	Product Specification	6

8.	Timescale	7

9.	Health and Safety	7

10.	Project Management	8

11.	Instructions for Bid Submission	8

12.	Evaluation Criteria	10

13.	Payment	11

14.	Additional Requirements	11

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation.

Our role is to provide scientific evidence, information, and advice to inform decisions to  protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

JNCC co-leads the Biodiversity loss theme of the Ocean Country Partnership Programme (OCPP), a UK government-led programme under the Blue Planet Programme. For the past 2 years, the OCPP has been working in collaboration with the Government of Maldives  providing technical assistance for Marine Protected Areas (MPAs).

## Project Background

JNCC co-leads the Marine Biodiversity theme of the Ocean Country Partnership Programme (OCPP), a UK government-led programme under the Blue Planet Programme. More information on the OCPP can be found here: https://www.gov.uk/government/publications/blue-planet-fund/ocean-country-partnership-programme-ocpp.

The Marine Biodiversity strand of the OCPP aims to:

- Increase understanding of the value of Marine Protected Areas (MPAs) in supporting sustainable livelihoods, food security, health and well-being;

- Increase understanding of MPA theory and practice, including evidence gathering, identification, selection, monitoring and assessment of MPAs;

- Increase support and compliance for MPAs with stakeholders; and

- Enhance capability and drive within countries to sustainably manage, monitor and assess conservation activities in the future.

Since 2021 the OCPP has been working in collaboration with the Government of Maldives providing technical assistance for MPAs. In 2023/24 the OCPP supported a review of shark diving practices at Fuvahmulah to inform the Maldives Ministry of Climate Change, Environment and Energy (MCCEE) and Fuvahmulah City Council (FCC) of current management measures and best practice options.

Fuvahmulah was declared an UNESCO Biosphere Reserve in 2020 due to its varied biodiversity including diverse coral reef ecosystems and significant populations of sharks. Several protected areas sit within the Biosphere Reserve including Farikede MPA, and Thundi (Thoondu) MPA, designated to protect oceanic species that utilise the area including pelagic thresher sharks (Alopias pelagicus), oceanic manta rays (Mobula birostris) and whale sharks (Rhincodon typus) amongst others. Additionally, an area known as the Tiger Harbour dive site provides divers with almost guaranteed encounters with tiger sharks (Galeocerdo cuvier) that are attracted to the site as a result of provisioning. Consequently, Fuvahmulah has become globally recognised for its variety of shark diving encounters.

To support the sustainable development of Fuvahmulah’s shark ecotourism industry and ensure activities support the values of the Biosphere Reserve and MPA designations, FCC and MCCEE are developing management measures with stakeholders and require the support of a shark expert familiar with Fuvahmulah and its current shark diving practices.

This contract is being delivered on behalf of the Government of Maldives Ministry of Climate Change, Environment and Energy and Fuvahmulah City Council.

## Project Aims

This contract focuses on the development of shark diving codes of conduct tailored to Fuvahmulah, based on best practices highlighted in the ‘Review of shark diving practices at Fuvahmulah, Maldives’ report, and the contractor and local stakeholder expertise and experience. Additionally, the contract seeks to scope requirements for the development of a shark dive guide certification training programme for local dives guides to undertake (noting this contract does not include the delivery of this training at this stage).

## Project Objectives

To meet the overall aims of this project (Section 3), the objectives are:

- Establish shark diving codes of conduct, agreed upon by stakeholders, for non-provisioned and provisioned interactions with sharks around Fuvahmulah.

  - Facilitate the development of tailored codes of conduct for scuba diving and free diving with predatory sharks around Fuvahmulah based on global best practices, the knowledge and expertise of Fuvahmulah dive operators and the contractor’s expert knowledge.

    - Separate codes of conducts will be developed for interactions with tiger sharks at Tiger Harbour dive site and for multiple species including thresher sharks encountered at all dive sites outside of Tiger Harbour.

  - Work closely with Fuvahmulah City Council, the MCCEE, the OCPP and stakeholders to develop suitable timeframes and opportunities for workshops and other methods of engagement to ensure the codes of conduct are developed collaboratively.

  - Work with Fuvahmulah City Council to organise and facilitate virtual and in-person workshop(s) to develop codes of conduct.

  - Develop workshop(s) materials in Dhivehi and English depending on stakeholder needs.

  - Ensure codes of conduct are complimentary to existing national and local regulations and policies.

  - Prepare materials to clearly communicate information about the codes of conduct, for example this could include a report summarising the process and evidence used to develop the codes of conduct and developing infographics in suitable languages to support awareness and understanding.

- Undertake scoping of the requirements, including potential content, for the development of a dive guide certification training programme for shark diving.

  - Collect information on existing training used by dive operators in Fuvahmulah, Maldives and elsewhere to identify gaps and potential programmes to build upon.

  - Work with stakeholders to identify their training needs and the suitability of a certification training programme.

  - Explore how a certification training programme could be recognised and established on Fuvahmulah.

  - Develop a report to detail the information gathered through the review and recommended next steps.

- Build Maldivian expertise and capacity in shark ecotourism management and social science techniques.

  - Provide knowledge exchange opportunities for Maldivian nationals working within the marine environment sector to learn and develop skills related to shark ecotourism management and social science methodologies.

  - Contribute as required to awareness, research and education events linked to shark ecotourism and sustainable marine management in Maldives.

## Contractor Requirements

The successful contractor should:

- Have experience of developing best practice diving codes of conduct for provisioned and non-provisioned interactions with large predatory sharks in collaboration with dive operators and management authorities.

- Have experience of advising the shark ecotourism sector on provisioning methods to attract sharks for tourism purposes.

- Have experience of providing advice on health and safety aspects of shark diving for scuba divers, free divers and snorkellers.

- Have expertise in large predatory shark behaviour.

- Be a confident communicator with experience of developing and delivering virtual and in-person stakeholder engagement and workshops for dive operators and other shark diving industry related stakeholders.

- Have an in-depth understanding of the current management measures and shark diving activities undertaken at Fuvahmulah.

- Have a good understanding of and ideally existing relationships with the Maldives shark diving ecotourism sector and stakeholders.

- Have no conflicting interests with existing dive operations that take place at Fuvahmulah.

- Be available and willing to visit Fuvahmulah to run workshops with stakeholders. Please note that the contractor will not dive, snorkel or free-dive as part of this OCPP project and contract.

- Be responsible for independently arranging travel to Fuvahmulah including organisation and costs of the travel itinerary, based on the travel rates included within section 11. JNCC are happy to work with the successful contractor to review travel plans and costs where required.

- Be responsible for arranging stakeholder engagement activities, e.g., arranging stakeholder workshops or other engagement required to meet the needs of the project outputs including associated travel and subsistence costs. Facility hire for stakeholder workshops does not need to be included within your bid, but nominal costs for refreshments should be included.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2025/26.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible.  This includes those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.   All reports and other documentation which are to be made publicly available must be produced using an OCPP template (to be provided), unless otherwise stated. All reports (draft and final) should be provided electronically via email both as a Microsoft Word document and an Adobe PDF. Copies of documentation associated with case studies should be provided in electronic format with an associated reference catalogue.

The contractor will not publish any information, by any means of publication, resulting from this contract without written consent from JNCC, the Government of Maldives, Ministry of Climate Change, Environment and Energy, and Fuvahmulah City Council.

Collection of personal data to meet the outputs of this contract should be handled in line with JNCC’s OCPP Privacy Notice.

## Timescale

Provisional timings for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (online) | 29th May 2024 |
| Proposed workplan provided by contractor | 17th June 2024 |
| Preparation and planning, online stakeholder engagement, and initial drafting of materials | 17th – 2nd September |
| Delivery of stakeholder workshop(s) to develop codes of conduct (includes workshop reports). | 2nd September – 18th November 2024 |
| First draft of codes of conduct | 29th November 2024 |
| First draft of scoping report for shark dive guide certification programme. | 31st December 2025 |
| Finalised codes of conduct | 31st January 2025 |
| Development of codes of conduct supporting materials e.g., codes of conduct infographics | 1st February – 1st March 2025 |
| Delivery of final products – codes of conduct and supporting materials and final scoping shark dive guide certification programme report. | 14th March 2025 |

## Health and Safety

The successful bidder is expected to follow appropriate Health & Safety procedures including adhering to JNCC’s policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC. (NB under no circumstances should any work or service commence prior to the receipt of written approval of the risk assessment by the JNCC H&S Advisor).

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful Contractor shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Jamie Small

Email: Jamie.small@jncc.gov.uk

Telephone: +44 (0) 1733 259687

Name: Beth Flavell

Email:  beth.flavell@jncc.gov.uk

Telephone: +44 (0)1733 866952

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 12);

A detailed project plan (including a Gannt chart) and an estimate of time required to achieve each objective;

Details of the Project Team including their roles and experience, an estimate of their time input into each task and CVs of all personnel who will be involved in the contract/project; please ensure all CVs MUST be attached as a separate PDF documentation from the proposal, so that we can meet our JNCC GDPR retention policy requirements.

Overall quote for the contract (in GBP or USD) should include:

  - Attending virtual start-up, interim and final meetings with JNCC project team, Ministry of Environment, Fuvahmulah City Council and Fuvahmulah Biosphere Reserve staff.

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project including all costs associated with overseas travel and subsistence to undertake stakeholder workshops (excl. workshop facility hire) on Fuvahmulah, Maldives. Note flights should be economy or premium economy class only, with suitable justification for the use of premium economy.

  - JNCC adhere to UK civil service travel and subsistence rates however, rates are not listed for Maldives and the nearest city, Colombo, Sri Lanka does not adequately reflect travel and subsistence costs for Maldives. Therefore, when estimating costs for subsistence and accommodation please use the following maximum rates that have been advised by the British High Commission in Malé and based on costs experienced by JNCC when undertaking Maldives trips:

    - Malé accommodation per night $170

    - Malé daily subsistence rate $40

    - Outside of Malé accommodation per night $100

    - Outside of Malé daily subsistence rate $30

The following documentation:

  - If your company includes more than 5 employees, please provide copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

In addition, note that the bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in Section 12.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation shall be undertaken by JNCC staff. However, for transparency, JNCC will quality check with the Government of Maldives for their final review before award of contract.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid |  |  |  |
| 1 | Clarity of proposal particularly work programme and deliverables | 10 |  |
| 2 | Understanding of the requirements and adequacy of outputs | 10 |  |
| 3 | Soundness and logicality of methods | 5 |  |
| 4 | Identification and proposed solutions to potential risks/issues which threaten success | 5 |  |
|  | Sub Total | 30 |  |
| 2. Details of Contractor |  |  |  |
| 6 | Relevant experience working in Maldives | 10 |  |
| 7 | Relevant expertise and experience advising the shark diving industry on sustainable practices including provisioning and best practice management. | 15 |  |
| 8 | Relevant expertise and experience of collaborating with the shark diving industry to develop codes of conduct | 20 |  |
| 9 | Relevant experience of undertaking stakeholder engagement in Maldives | 10 |  |
|  | Sub Total | 55 |  |
| 3. Cost |  |  |  |
| 10 | Transparency and correctness of presentation | 10 |  |
| 11 | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Sub Total | 15 |  |
| Total Score |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£) or US Dollars ($).

Payment will be made on completion of milestones following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Publication of Contract Notice | 1 May 2024 |
| Last date for receipt of clarification questions | 8 May 2024 |
| Final submission date for bids | 15 May 2024 |