Medicines Manufacturing Innovation Centre: Project Timescales

| Activity | Timing |
| --- | --- |
| Completion of MMIC design to RIBA Stage 3 | May/June 2019 |
| Procurement and Contracting of Design & Build Contractor | Jun - Aug 2019 |
| Commencement of D&B Activity | Sept 2019 |
| D&B Practical Completion | March 2021 |
| CPI Installation & Commissioning of Laboratory Equipment and Commencement of First Projects | Apr-Jun 2021 |
| MMIC Fully Operational | From Jul 2021 Onwards |