Medicines Manufacturing Innovation Centre, Advanced Manufacturing Innovation District Scotland, Renfrewshire

CONTRACT: NEC4 Engineering and Construction Contract

PROJECT MANAGER: SCHEDULE OF PROFESSIONAL SERVICES

|  | Pre-construction services - to be provided or initiated principally before the award of the D&B Contract but also at other times as required: | Man Days |
| --- | --- | --- |
|  | Review the works information as to the proposed development and CPI’s objectives and constraints, including financial constraints. |  |
|  | Review the site information, visit the site and understand interactions with CPI’s existing National Biologics Manufacturing Centre. |  |
|  | Assist in the preparation of an overall programme for the planning, design, construction, commissioning, FFE and process equipment installation and start-up phases of the development. Review and develop the project programme from time to time for our approval. |  |
|  | Conduct a review of the proposed concept design and explore potential options with the design team and CPI to consider possible alternatives and to confirm the design. |  |
|  | Advise on the procurement strategy for the construction contractor and on the content of the invitation to tender documents. |  |
|  | Establish and maintain project management procedures and lines of communication for the exchange of information as between the respective consultants, contractors and sub-contractors and others concerned in the development. Propose the processes and procedures for document and data management throughout the development. |  |
|  | Monitor and expedite the activities of CPI’s other consultants with a view to maintaining progress in accordance with the programme. |  |
|  | Advise as to the early purchase of any materials or products which may be subject to long delivery periods. |  |
|  | Co-ordinate the provision of information relating to the site and the works required for inclusion in the Construction Phase Plan. |  |
|  | Advise upon appropriate contractual and insurance arrangements in connection with the Design and Build Contract and any specialist sub-contracts to be awarded for the construction of the Works. |  |
|  | Analyse and report upon tenders received (assume 5Nr). Assist in the evaluation of the short-listed D&B tenders (assume 3 Nr) and in the final selection of the contractor. |  |
|  | Assist and advise where required in finalising the details of terms with contractors, sub-contractors and suppliers. If required, amend tender documents to incorporate savings or other changes within the final, agreed works information. |  |
|  | Once CPI is ready to enter into the D&B Contract, confirm in writing that so far as concerns matters within your responsibility or knowledge, a state of readiness has been achieved for construction to commence and to proceed in accordance with the proposed D&B Contract, cost plan and construction programme, or notify CPI of any respects in which that is not the case. |  |

|  | Construction period services - to be provided principally but not exclusively following the appointment of the D&B contractor. | Man Days |
| --- | --- | --- |
|  | Support the design and build contractor’s delivery of an excellent safety performance. |  |
|  | Manage technical and other queries from the design and build contractor |  |
|  | Convene, attend, chair and minute project or progress meetings and design review meetings whenever reasonably necessary. |  |
|  | Closely monitor the design and construction of the Works with respect to compliance with the contract, works information, cost plan and programme, reporting to CPI any actual or potential delays, cost increases or variations from the works information and advise as to measures to avoid or reduce them. |  |
|  | Manage the D&B Contractor to maintain progress according to the project schedule, to control the project scope and cost, optimise value for money and to resolve issues. |  |
|  | Establish and maintain a costed risk register and actively manage and mitigate risks to achieve risk reduction and elimination throughout the course of the development. |  |
|  | Manage the design review process to align with the needs of the project programme. |  |
|  | Manage the review of selected detailed designs, drawings, specifications, calculations and other technical documentation from the design and build contractor to achieve compliance with the works information and adherence to the project programme. |  |
|  | Monitor the submission and approval of design and specification information to be provided by the Contractor or sub-contractors or suppliers. |  |
|  | Take steps to see that the design intent as set out in the works information is not compromised by subsequent design changes, substitutions or detailing. |  |
|  | With CPI’s other consultants advise as to the implications of any changes to the scheme design on the cost of the project and on the overall programme. |  |
|  | Review the selection of specialist sub-contractors and advise CPI accordingly. |  |
|  | Manage change orders and their impact on the project schedule and cost; approve these as agreed with CPI. |  |
|  | Manage the contractor’s commissioning team in the commissioning of the facility systems and utilities and in the compilation of commissioning records. |  |
|  | Monitor and record the activities of the Contractor and of sub-contractors, including labour levels, productivity, plant deployment and usage, effects of inclement weather and other disruptive factors and similar matters. |  |
|  | Report to CPI on project progress, adhering to an agreed frequency (assume monthly), format and content. |  |
|  | Act as the Contract Administrator under the D&B Contract with regard to sign-off/certification of valuations and payments including the final account, completion certificate, defect certificate and final certificate. Review the quantity surveyors’ periodic valuations and liaise with CPI’s staff with regard to payments to contractors and other consultants. |  |
|  | Keep under continuous review the performance of the other consultants and instruct and co-ordinate their activities as necessary with a view to achieving the satisfactory completion of the Development according to programme. |  |
|  | Manage the identification and early correction of reservations throughout the construction period; manage completion of the final reservation list. |  |
|  | At practical completion, co-ordinate handover and see that all appropriate inspections and tests are made and all supporting documentation is available.. |  |
|  | Check that any required BREEAM reports, energy performance certificate(s) and recommendation report(s) are provided and registered in respect of the Development. |  |

|  | Post construction services - to be performed generally after the completion of construction, but at other times as required: | Man Days |
| --- | --- | --- |
|  | Monitor the progress of remedial works during the rectification period and the making good of defects. |  |
|  | Supervise the compilation of as-built or record drawings and maintenance manuals. |  |

|  | General services - to be provided throughout the period of the Appointment, as necessary: | Man Days |
| --- | --- | --- |
|  | Provide any assistance reasonably required to confirm that the required insurances are in place. |  |
|  | Assist in procuring the completion of collateral warranties, manufacturers’ guarantees, maintenance manuals and similar matters. |  |
|  | Advise CPI as to requirements from the local authority and BREEAM for the management of Site Waste and work with CPI and the D&B contractor to achieve compliance with these requirements. |  |
|  | Subject to our instructions, act generally as our representative with regard to the Development and perform all other project management services, whether incidental to the foregoing or not, as reasonably required by CPI in connection with the development. |  |
|  | Total Number of Man Days |  |
|  | Daily Rate 1 |  |
|  | Daily Rate 2 |  |
|  | Total Fee for Scheduled Services |  |

|  | Additional Services Proposed (Please indicate daily rates for additional services even if nothing has been identified at this point) | Man Days |
| --- | --- | --- |
|  | Total Number of Man Days |  |
|  | Daily Rate 1 |  |
|  | Daily Rate 2 |  |
|  | Total Fee for Scheduled Services |  |