Order Schedule 20 (Order Specification)

- As stated in the Tender Documentation (section 2 Specification)

Introduction:

The Artificial Intelligence Safety Institute (AISI) is a department within the Department of Science and Innovation Technology (DSIT) whose mission is to minimise the surprise of rapid and unexpected advances in AI (Artificial Intelligence) to the UK and humanity. In pursuit of this objective, AISI aims to offer vital insights into the advanced capabilities of frontier AI by conducting evaluations of frontier models and carrying out AI safety research.

To achieve this aim, AISI have several workstreams dedicated to this, including the Cyber Misuse workstream, from which this requirement has been proposed. AISI’s Cyber Misuse workstream focuses on the uplift that advanced AI systems provide to a range of threat actors, and their ability to more effectively conduct existing and novel offensive cyber-attacks.

In order to achieve the above Cyber Misuse workstream focus, it is vital to record, measure and evaluate the capability uplift that frontier AI models provide to actors of varying expertise. With this knowledge, HMG (His Majesty’s Government) will be able to better determine the potential for harm caused by frontier AI models in cyber misuse, thereby better-informing policy decisions.

Background: Human Uplift Studies.

Human uplift studies (HUS) are the most robust method currently available for assessing offensive cyber capability uplift. Uplift studies use the randomised controlled trial format to assess interaction with AI systems as a treatment variable, comparing participants’ performance on a cyber task as the outcome variable. A randomised controlled trial (RCT) is a study design where participants are randomly assigned to either an experimental or control group and the performance difference between the experimental and control group is tested.

The Cyber Misuse workstream requires a supplier’s expertise and capacity, to design and conduct a series of human uplift studies. This will allow the team to generate robust experimental data on the capability uplift given to actors (of varying capabilities) in relation to those AISI has prioritised the cyber specific threat scenarios highlighted below:

Technical non-experts and non-technical insider attacks to Critical National Infrastructure

Uplifting cybersecurity experts to conduct attacks on hardened critical systems.

Scaling profitable Cyber Crime through ransomware attacks and social engineering, by niche experts (e.g. cybercrime groups).

Aims & Objectives

AISI’s mission is to equip governments with an empirical understanding of the safety of advanced AI systems. The design and conduction of Human Uplift Studies will provide HMG with insight into the capability uplift that various threat actors receive when using frontier AI models in relation to offensive cyber-attacks.

Potential threat actors.

- Non-technical - A person not versed at all in cybersecurity and engineering who decides to perform an attack nonetheless, e.g. a disgruntled worker.

- Technical non-expert - A novice with limited or no knowledge in the realm of cybersecurity, but with some technical expertise, e.g. a data analyst or engineer.

- Niche expert - A technical expert who specializes in some specific domain of the field, e.g. Ransomware developers, or SOC analysts.

This contract will aim to provide:

The design, conduction and an analysis of a series of Human Uplift Studies and accompanying final reports.

Requirements

Definitions:

| Acronym | Definition |
| --- | --- |
| CTF | Capture-the-flag - These are cyber security challenges where, in this case, a model will be challenged to find and exploit vulnerabilities in a system to capture a “flag”, usually a random string that the model will need to access and return to succeed at the challenge. |
| LLM agent | Large Language Model Agent – This is an AI system that received text as input and outputs text. By adding tools to these models, they can act as agents using their tools to interact with an environment. |
| Frontier models | Frontier models in this context refer to the most current and advanced models, alongside those upcoming models that indicate they could meet and even exceed the capabilities of current advanced models. |
| AI | Artificial Intelligence (AI) is the field of study and development of computer systems capable of performing tasks that typically require human intelligence, such as learning, problem-solving, decision-making, and natural language processing. |
| API | Application Programming Interface – these are a set of rules, protocols, and tools that define how different software components should interact with each other. APIs specify the kinds of requests that can be made, how to make them, the data formats that should be used, and the conventions to follow. |
| AI assurance | AI assurance has been included in this glossary to avoid confusion. AI assurance is the testing of the accuracy, robustness and effectiveness of AI and their systems. This is not what our requirement refers to. This requirement looks towards the use of AI systems, and the capability uplift they provide to threat actors. The focus of the research is on the misuse of frontier AI, specifically by malicious actors in conducting cyber-attacks. Additionally, cyber-attacks on frontier AI models are out of scope. |
| Evaluations | Evaluations refer to the measuring of the performance of a Frontier Model at executing a key cyber capability. See the paper: Model Evaluation for Extreme Risks by GDM for examples. |
| Inspect | AISI’s technical infrastructure. https://ukgovernmentbeis.github.io/inspect_ai/ |

The supplier must generate a series of human uplift studies (3 would be the preferred minimum, depending on the level of associated cost, with the supplier making a comprehensive plan at the start of the engagement that we will review and agree before implementation starts. This plan should be costed appropriately).

Target areas to evaluate are as follows (these will be further discussed in conjunction with the supplier), in order of priority:

- Vulnerability discovery and exploitation (including a reverse engineering element)

- Network operations

- Operating System (OS) exploitation

- Industrial Control System (ICS) exploitation

For the conduction of Human Uplift Studies, the supplier must consider the following in their proposals:

- LLM boundaries – the supplier must consider whether the LLM’s that the treatment group receive include guardrails free/jailbroken versions.

- Model – the supplier must consider the use of different models in this engagement.

- Controls – the supplier must consider what aid both the control and treatment groups have access to during this study (e.g. Google-based internet research)

- Expertise levels – the supplier must consider the expertise level of the group being studied e.g. expertise levels that range from a university student/graduate to cyber-security expert.

- Tasks – most of the experimental tasks for participants to undertake must be designed by the supplier however, AISI will require that some tasks in the study will be from AISI’s Capture the Flag (CTF) evaluation suite. The supplier must adapt these for humans to take. AISI will also require that both new tasks and AISI’s tasks (see D3) are baselined in the following format: “Challenge Z takes a person of X level experience, Y minutes/hours to complete the task”. We would prefer that the tasks developed by the supplier be tested on non-logging models (although this is a soft requirement). Any tasks that are used from AISI’s evaluation suite must be used with non-logging models. Please indicate in your methodology how you plan to develop robust baselines. The supplier could draw on academic/grey literature for this.

- Any AI-based tasks/challenges designed for participants must be compatible with Inspect, a framework for large language model evaluations created by AISI.

- Number of participants: We expect large study sizes where possible (32-128). Proposed numbers of participants must be included the plan at the start of the engagement and should be indicated in the supplier’s proposals. The participants must be fully informed when consenting to attending the study (and it should be made evident in the consent form the outcomes of this paper will likely be published).  The supplier must encourage putting in means that allow a wide and diverse participant group to take part (for example, offering participation on different days of the week at multiple times). If it is possible that participants don’t need to be supervised at all in the methodology, the participation could be self-directed and done at a time convenient for participants. The results should be returned to AISI pseudo-anonymised. This might include demographic data such as age, gender etc.

- All tasks designed by the supplier must be provided with solutions.

- The supplier may incentivise participants that would not normally take part in this study.

- Any other considerations and/or additions should be added to the supplier’s methodology.

The supplier must deliver the following deliverables:

Deliverables

D1: A series of human uplift studies with individuals of varying levels of cyber expertise (tasks should be mostly created by the supplier but will also incorporate some tasks from the Buyer’s evaluation suite).

D2: A report including the methodology of the Human Uplift study and a summary and analysis of the results.

Proposed Methodology

| Deliverable | Proposed Methodology | Proposed Acceptance Criteria |
| --- | --- | --- |
| D1: A series of human uplift studies with individuals of varying levels of cyber expertise (tasks should be mostly created by the supplier but will also incorporate some tasks from the Buyer’s evaluation suite). | All work regarding this deliverable will be completed iteratively with AISI over the duration of the contract. We expect to discuss progress in weekly meetings with feedback from AISI on the structure and format of the final output. The Supplier must address specific questions from AISI and provide justification for key priority areas and tasks identified. | Full study conduction and completed analysis for Human Uplift Studies that address all identified priority threat scenarios (as defined between the supplier and AISI), that meet the requirements as specified in section 2. |
| D2: A report including the methodology of the Human Uplift study and a summary and analysis of the results. | We expect a draft report to be provided to AISI before the final deliverable is produced. | A fully prepared report to a scientifically publishable standard. |

Project/Programme timescales

The project duration is for 9 months, with the potential for an extension for a further 3 months by mutual agreement.  High-level milestones with their expected completion are included below. These will be further developed and confirmed with the supplier in the mobilisation period.

| Milestones | Completed at the latest by |
| --- | --- |
| M1: Mobilisation period | Month 1 from contract award date |
| M2: Full study design proposal ready for AISI’s review. | Month 2 from contract award date |
| M3: Required infrastructure implemented and participants recruited. | Month 3 from contract award date |
| M4: Live experiment(s) successfully completed | Month 7-9 from contract award date |
| M5: Analysis completed, and draft report shared with AISI, with AISI baselines complete. | Month 9 from contract award date |
| M6: Final report | Month 9 from contract award date |

Governance and Working Arrangements

The Supplier must confirm a named point of contact through whom all enquiries can be filtered.  Details of Key Supplier Staff must be included in the tender submission (Order Schedule 7)

A project manager from the Buyer will be assigned to the project and will be the central point of contact for the Supplier. The project manager will be available to answer queries and support development regularly, at least at a frequency of once every two weeks. This can be assessed with the Supplier if greater frequency is required, for example towards the end of the project. Project management meetings will be held by either video conference or telephone.

The project manager, the Analytical lead, and the SRO of the Buyer’s team from which this funding comes, will be responsible for signing off the final outputs of the research project.

The Supplier must review DPS Order Schedule 8 (Business Continuity & Disaster Recover) and develop a high level but proportional plan satisfying this Schedule’s requirements in the first 30 days of the Contract. The Buyer will be required to review this plan, but emphasis is given that the plan must be proportional to the Schedule’s requirements

The Supplier must review DPS Order Schedule 10 (Exit Management) and develop a high level but proportional plan satisfying this Schedule’s requirements in the first 30 days of the Contract. The Buyer will be required to review this plan, but emphasis is given that the plan must be proportional to the Schedule’s requirements

Mobilisation Period

During the mobilisation period the Buyer and the Supplier will, based on the Specification and the bid proposal plan, agree the following:

- Buyer and Supplier will agree the number of participants and the number of Human Uplifts Studies that can delivered during the lifetime of the contract

- Confirm and agree timelines and completion dates in order to achieve the defined milestones

- Create of a Risk Register with input from both parties /frequency of reviews/meetings

- Confirm Governance and the relevant boards/ frequency of meetings (Call Off schedule 15)

- Management Information, agree types of reports and frequency

- Set Service level agreements as stated in the specification (Call Off schedule 14)

- Buyer to provide the supplier information regarding the change process

Service Levels and Performance

DSIT will measure the quality of the Supplier’s delivery by:

- The quality of the Supplier’s delivery against achievements of key milestones. Milestones dates are indicative and will be agreed between DSIT and the Supplier during project initiation.

- These key milestones are material to the Contract and on-time delivery is of the essence.

- Service level agreements can change throughout the lifetime of the contract, any changes will be agreed by both parties during the performance management meetings

Risks

The Supplier is required to identify and assess the risks associated with undertaking the research and propose how these may be managed and overcome. The Supplier must develop and manage a full risk register.

These should be reported in weekly updates and reviewed at bi-weekly meetings with DSIT.

It is important to note a key risk that we are aware of is the short delivery timelines. We are keen that Suppliers can establish an effective approach to timely delivery.

Ownership and Publication

The Buyer will own the intellectual property of all deliverables. The Supplier should prepare the deliverables for the outputs in both publishable (redacted) and not-to-be-published (unredacted) formats. The Supplier will agree the approach to redactions in reviewing near-final drafts and consider this as part of the sign-off process for the final outputs. The Buyer reserves the right to make the final decision about whether and how to publish the outputs, in line with internal protocols on publication approvals, publication template, branding, accessibility, publication location, and communications handling advice. All published deliverables should be in English and in a clear and accessible language.

Quality Management

The Supplier should have measures in place to ensure that the deliverables produced are of a high quality and free from error. Quality assurance measures should be factored into workplan timelines. The quality assurance plan must consider and include as minimum standards. Guidance related to the standards can be found in the Government Social Research Code, https://www.gov.uk/government/publications/the-goverment-social-research-code/government-social-research-code The Green Book https://www.gov.uk/government/publications/the-green-book-appraisal-and-evaluation-in-central-government/the-green-book-2020      and The Magenta Book

https://www.gov.uk/government/publications/the-magenta-book  where appropriate.

The Supplier will be required to undertake appropriate, independent quality assurance of all deliverables and guarantee the accuracy of all outputs to the Buyer. This could for example be carried out by an external academic.

The Supplier will be required to provide details of the quality assurance procedures they have in place in their bid. During the project, it will also be required to detail what quality assurance processes they have undertaken during the research.

Social Value

In addition to the aims, objectives and outcomes of the project, all UK Government contracts are required to contribute to wider social value as an additional benefit of the contract. Social value is a broad term used to describe the wider social, environmental and economic effects of an organisation’s actions, and how they contribute to the long-term wellbeing of individuals, communities and societies. More detail can be found here.

Social value is not just a policy requirement. Social value directly supports the mission of DSIT. We require the selected Supplier to deliver social value in the delivery of this contract. Although the whole of the specification of this project could be considered as contributing to social value, this element is specifically focussed on how the evaluation contract is delivered by the Supplier and is not about the technical delivery methodology per se. Commitments on the inclusivity and benefits of the methodology should be included in the wider technical proposal.

Social value is not a specific costed activity but is an added co-benefit of delivery and an approach to delivery that is expected of all DSIT Suppliers.

Sub-contractors

The Supplier must have measures in place to manage any sub-contractors and ensure that their selection is conducted in an open and transparent manner.

Budget

The Buyer has maximum budget for this contract. The budget is up to £900,000 inclusive of VAT and non-UK taxes. Payment will be based on a Time and Materials basis unless agreed in writing by both parties for specific deliverables/milestones. This budget is for information only, there is no guaranteed volume of work and as such there is no obligation for the Buyer to spend any or all of this amount.

Payment

Tenderers will provide an invoice schedule as part of their Commercial Proposal which should take into consideration the estimated budgets and timelines. The Buyer would anticipate two invoices during the project delivery, but alternatives may be proposed by the Supplier.

Price will be fixed based on the commercial offers made. Payments, in GBP, will be linked to delivery of deliverables. The indicative milestones and phasing of payments is to be as detailed in the Pricing Annex.

The Buyer will only pay for deliverables that have met the agreed standards. The Buyer will not pay for any reworkings or redrafting of documents. To be discussed and agreed upon during the mobilisation process.

Any payment conditions applicable to the prime Supplier must also be replicated with sub-contractors.

The Buyer aims to pay all correctly submitted invoices within 10 days from the date of receipt of a compliant invoice and within 30 days at the latest in line with standard terms and conditions of Contract.

The Buyer reserves the right to amend the Contract to increase the scope of activities required of the Supplier, so long as any additional activities meet the objectives of the Contract and in accordance with Public Procurement Regs 2015.

Contract amendments would be managed by a formal variation process and will be made with mutual agreement with the Supplier. This is only permitted if the proposals are compliant within the remit of Public Contracts Regulations 2015.

Performance/Contract Management

The Buyer will manage the Contract and have regular performance discussions with the Supplier, at least every two weeks. Where the quality of deliverables are failing to meet the Buyer’s expectations identified in both these requirements and the Tenderer’s tender submission, the Buyer will work with the Supplier to identify measures to remedy these performance issues.  As per schedule 14 (Service Level Agreement).

The Supplier is required to appoint a lead Project Manager, responsible for the Supplier’s delivery of the contract. The Project Manager must have sufficient experience, seniority and time allocated to manage the project effectively. There will be one project lead from DSIT to liaise closely with the Supplier’s Project Manager.

It is expected that following the project initiation meeting, regular contact will take place between the Supplier and DSIT by video-conference, telephone, email and face to face meetings. The frequency of contact will be agreed at the project inception meeting, however weekly project update meetings are required especially during the initial stages of the project and then a minimum requirement of every 2 weeks.

The Supplier is required on a weekly basis to provide a written update to DSIT on the research’s progress, flag any emerging issues and risks and updates regarding the research itself and quality assurance (as and when applicable).

Continuous Improvement

The Supplier will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

The Supplier should present new ways of working to the Buyer during monthly/quarterly Contract review meetings.

Changes to the way in which the Services are to be delivered must be brought to the Buyer’s attention and agreed prior to any changes being implemented these changes will be fully costed and a change process procedure will be completed and agreed by both Project Management

The Supplier is also required to provide feedback of emerging findings and key lessons during the course of the research at the weekly project meetings/calls. The format of how this will be presented will be agreed upon contract commencement.

If a consortium bid is submitted, the Supplier is required to explain any relevant lines of responsibility among consortium members, and proposed arrangements for management and liaison with the DSIT project manager.

Joint/Order Contract Schedules/ Special Terms

Please ensure you are fully familiar with the attached Joint/ Order contract schedule and please review the special Terms clauses stated in the partially completed Order Form

Any queries regarding these contract documents can be raised during the Clarification period.

The Order form states what activity is required for each contract schedule

Data Security

The Supplier is required to implement appropriate arrangements for data security at all times. Such procedures must meet the standards outlined in the framework terms and conditions, General Data Protection Regulation and the Data Protection Act.

The Supplier must confirm that such procedures will be implemented and outline the technical measures to be put in place to meet such requirements.

Ethical Conduct

The Supplier must have a clear approach for ensuring that the work is compliant with relevant ethical codes of conduct, as the Supplier is responsible for the ethical conduct of the research. The Supplier is required to set out any potential ethical issues presented by the research along with details of the arrangements for ethical scrutiny to ensure the day-to-day management of these risks. The Supplier will need to clearly explain how the information they provide will be stored, reported and protected and inform DSIT if this changes.

The Supplier must obtain consent if any participants are involved and make it clear to participants that their data will be shared and used for research purposes.

The commissioning and management of the research should be carried out in accordance with Government Social Research ethics guidance2 and the Data Protection Act 2018.

Location

The location of the Services will be carried out at the supplier’s address.