Order Schedule 4 (Order Tender)

As stated in the tender submission

Question 6: Expertise and Resource Management (5 pages)

We are a not-for-profit research institute with a mission to help improve policy and decision making through objective research and analysis. We have a 75-year history of conducting impactful research across all areas of policy, including at the forefront of artificial intelligence (AI) and cybersecurity research. We seek to combine the impartiality and independence of a not-for-profit, the academic rigour of a university and the agile, client-oriented delivery and robust project management of a professional consultancy.

Our organisational experience and expertise include:

A deep understanding of AI: With a history of studying AI and its implications dating back to the 1950s, our organisation has been at the forefront of AI research with influential contributions in fields such as symbolic processing, heuristic search, knowledge representation, planning, learning, theorem proving, and cognitive modelling. This foundational knowledge has evolved to include the examination of defence and security implications of AI for an extensive range of clients including the UK MOD (including the Defence AI Unit, the Defence Science and Technology Laboratory, and the joint Anglo-Swedish Development, Concepts and Doctrine Centre), the Foreign, Commonwealth and Development Office, the Australian and US DoDs, and the EDA and NATO. Consequently, we have an extensive portfolio of successful projects engaging with cutting-edge AI research, which uniquely positions us to design and implement tasks and infrastructure for evaluating human uplift of AI models in offensive cyber capabilities. For example, this includes work on:

- The weaponisation of AI by authoritarian states as part of their hostile influence and information operations, with projects on the application of machine learning to detect and understand online misinformation, Chinese astroturfing using generative AI, and using human-machine teaming to identify false information.

- The systemic risk of General-Purpose Artificial Intelligence (GPAI) Models and avenues of policy response.

- The impact of AI on strategic stability, with various studies examining the strategic implications of AI on crisis and strategic stability, and the impact on deterrence.

- AI and Military decision making, considering both operational assessment and military command and control, as well as the risk of biases and errors in artificial intelligence.

Our AI expertise also extends beyond that of defence and security. We are at the forefront of developing new training models and considering avenues for international AI collaboration. Our portfolio covers science and technology governance models, non-proliferation, and building trust in AI systems. Recently we have engaged in work on AI labelling and codes of conduct, Red Teaming, and building organisational capacity to absorb AI-related impacts, particularly those affecting workforces.

Cybersecurity: Our cybersecurity expertise is deeply rooted in extensive research and practical applications dating to the early development of concepts underpinning the Internet and computing such as packet switching. Since the 1980s, we have provided cutting-edge research and analysis of the evolution of computer science, network security and cybersecurity, conducting studies for US, UK and European governments. We have a broad portfolio covering all aspects of cybersecurity from research on technical and operational aspects to the strategic and geopolitical implications of the cyber domain. Recent publications cover broad topics like cybersecurity and protection of critical infrastructure (e.g. risks of hostile cyberattacks to the U.S. financial system, and other critical infrastructure including energy, transportation, communications, health care, water, and municipal services) to work considering the feasibility of adversarial cyberattacks against applied AI models themselves and vulnerability disclosure practices. Recently, our organisation also secured $38M of funding – in collaboration with a partner organisation – from a pool of donors, supported by the Audacious Project, to perform AI capability evaluations in biology and cyber. This is supporting ongoing work to build large-scale, rigorous, and unprecedented infrastructure for evaluation of AI capabilities in these domains.

Large Participant Group Studies: Our organisation has significant experience in managing and executing complex, large-scale research studies that involve extensive stakeholder engagement and large participant groups. We have a substantive track record in conducting randomised control trials for the UK government, making us well-equipped to recruit and handle the required participants for the human uplift studies. Specific to this requirement, we also have experience in conducting human uplift studies to test the capability uplift of AI models. We regularly identify and engage with technical experts, including in cybersecurity and AI, which means that we have solid existing networks that can be leveraged to identify and recruit participants for the human uplift studies.

Team experience and expertise

Our proposed study team brings a wealth of experience across several domains, ensuring a comprehensive approach to AISI’s requirement. Our UK based team will lead the delivery of the project and provide day-to-day liaison and management to AISI; technical expertise and delivery support will be delivered by our American colleagues from our research centre dedicated to reducing risks from biological threats and emerging technologies. This centre combines in-depth policy research with state-of-the-art technical research to provide policymakers with the information and expertise needed to prevent, prepare for, and mitigate large-scale catastrophes, including AI-related risks.

Our project team’s expertise includes:

- Extensive work on AI (including frontier models): We have team members who specialise in cutting-edge AI models, ensuring that our evaluations leverage the latest advancements in AI technology. Multiple staff on our project team have worked at Google, Amazon, and Meta in recent years, developing machine learning infrastructure and applications. Further, we have the capability to

- having led, managed, and designed studies for a range of US, EU and UK clients on AI application and governance. Multiple supporting staff have valuable experience in niche avenues which inform this project, including published literature on frontier AI capabilities and risks, AI security, and hardware-enabled AI governance mechanisms.

- Deep technical cybersecurity knowledge: Our team members have extensive backgrounds in cybersecurity and cyberspace operations, ensuring that our approach to evaluating AI models is grounded in current cybersecurity practices and challenges. Senior team members have decades of cybersecurity experience, including in reverse engineering, vulnerability discovery, network operations, and OS exploitation. This includes one of our software engineers who has 11 years of experience in vulnerability discovery and exploitation and has won $300K finding zero-days as a white hat, including an RCE + jailbreak on the Amazon Kindle. Our work has spanned the cyber domain and its application, including evaluation of cybersecurity capabilities, requirements development, systems architecture reviews, and workforce training and education in the military and civil sectors. For example, we have supported US government and NATO sponsors with evaluating cyber test infrastructure, capabilities and workforce requirements to develop standards for testing, explore promising methods for improving cyber tests, and to anticipate future infrastructure and architecture needs.

- Intersection of Cybersecurity and AI: Our team also has extensive expertise at the intersection of cybersecurity and AI, demonstrated through several high-impact projects and advisory roles. Project members have published one of the first in-depth analyses on securing frontier models against capable actors, titled "Securing AI Model Weights," which required and further developed our expertise in both AI and cybersecurity. Additionally, we have been awarded a $1.4M grant from the US State Department to provide guidance on AI security to leading AI labs in multiple countries, with a senior project member serving as co-PI on the project. A senior member of the team has also advised various US government entities, including the White House, Department of Commerce, State Department, and Department of Energy, on multiple topics at the intersection of AI and cybersecurity. This advisory experience underscores our team's deep understanding and capability in navigating and addressing the complex challenges that arise in securing AI systems, feeding into the design of our methodology.

- Design and Execution of Human Uplift Studies: Our team has a proven track record in designing and executing human uplift studies, red-teaming exercises and randomised control trials. This includes creating study protocols, recruiting and managing participants, and analysing data to generate actionable insights. A senior member of our team served as a co-PI on our organisation’s pioneering study titled "The Operational Risks of AI in Large-Scale Biological Attacks." This study, one of the first to focus on the misuse of frontier models, was methodologically designed from scratch by accommodating 45 participants randomised across tasks. This senior member additionally leads AI threat

- our Technology and Security Policy (TASP) programme, further reinforcing her expertise in AI and human uplift studies. She has also previously advised the UK government on the design of human uplift studies.

Project Management and Quality Assurance: Alongside our subject matter expertise, this project will also benefit from skilled project managers and quality assurance staff. Our team has extensive experience in coordinating complex, multi-disciplinary projects, ensuring that all aspects are seamlessly integrated and executed on time and within budget. The proposed project leader has over a decade’s experience of leading multidisciplinary research studies for UK and international clients, including on cybersecurity and AI topics. Quality assurance is integral to our project management approach, and we implement rigorous quality control measures at every stage of the project, including peer reviews, audits, and validation checks. Our commitment to quality ensures that deliverables meet the highest standards and client expectations. As an ISO 9001 certified organisation, we adhere to international consensus on good quality management practices, particularly suited for knowledge-intensive organisations. This certification confirms our commitment to quality, not only in its research and project activities but also in its interactions with clients and other stakeholders.

Resource Management:

Effective project, risk and quality management are integral to our work and longstanding reputation for excellence in this field. We will apply robust project management practices to support the delivery of this study. These will include regular client and project team communication, quality assurance procedures, adherence to research ethics principles and practices, appropriate data security protocols, and continuous risk management.

With almost 2,000 research staff globally and experts working across nearly all policy areas, we offer access to a multidisciplinary team of different staff with deep experience in the methods, subject matters and different sectors. The proposed core team comprises:

- Experienced project leader and project manager to ensure that the project is delivered to budget, schedule and quality.

- Deep technical and subject matter experts including AI and cybersecurity researchers and software engineers to lead the technical design and delivery of the study, including researchers from our Technology and Security Policy fellowship.

- Competent junior researchers to support project administration and delivery.

In addition, two experienced Quality Assurance reviewers with domain and methodological expertise independent from the core team will review and critique our project approach and deliverables to ensure all project outputs meet our stringent internal quality standards.

We allocate senior and junior resources appropriately to maximise efficiency and expertise. Senior experts will provide strategic direction and oversight, research

design and delivery of key project activities, while junior staff will support project delivery (e.g. data collection, participant coordination, day-to-day project admin). This approach ensures that our most experienced personnel dedicate sufficient time to the contract while leveraging the support of junior staff to maintain operational efficiency. A detailed overview of allocation of resources can be found in our response to Question 8.

Project resourcing will be supported by our in-house dedicated Programme Support Office (PSO). The PSO team will provide support throughout the duration of the framework, dealing with invoicing and payment and helping ensuring continuity of service. The PSO also provides support to each dedicated project management team for any individual tasking, as well as provides key project management data. In addition, we will draw on our Finance, Legal, IT, Data Protection, Security and HR functions as required.

In relation to the management of external participants, we propose to amend AISI’s suggested participant categories (to be discussed and agreed with AISI). At this stage, we offer the following categories and associated expertise levels for the three proposed tests:

Vulnerability discovery (including a reverse engineering element) Technical non-experts (software engineers), and/or

Niche experts (junior reverse engineers and/or vulnerability researchers, under 3 years’ experience)

Network operations Technical non-experts (software engineers), and/or

Niche experts (penetration testers)

Operating System (OS) exploitation Technical non-experts (software engineers), and/or

Niche experts (junior exploitation developers, under 3 years’ experience)

Our initial assessment is that a non-technical participant category would not provide informative outcomes in terms of human uplift and would not offer AISI value for money, though we are open to reconsidering in coordination with AISI. An amended participant categorisation could also enable us to more easily identify and recruit appropriate participants and to increase the number of participants per group/test.

# Question 7: Methodology

The delivery of the Human Uplift Studies will be done through six stages:

Step 1: Full study design and coordination with AISI. Senior members of the team will work closely with AISI to ensure the remaining implementation details are developed. We believe in being proactive yet deferential – iteratively providing AISI with detailed plans and proposals while adjusting and adapting quickly to feedback. All study stages will adhere to our internal and other relevant data security, ethics and legal requirements (see also Question 2).

Step 2: Implementation of infrastructure and human uplift tasks. We will develop a scalable platform for human uplift trials alongside the three human uplift tasks to be delivered as part of this contract. The platform will be built upon and be compatible with AISI’s INSPECT framework and:

- Support presenting identical tasks for humans and AI models to tackle.

- Support both locally run models and the use of APIs (and be run on leading open-source and proprietary models).

- Utilise guardrail-free models whenever possible (e.g. open-source models and collaboration with labs) and provide jailbreaking resources to participants when not (e.g. use of standard APIs).

- Utilise non-logging model access where possible. Tasks from AISI’s evaluation suite will only be used via non-logging access. If permissible, we will record interactions between participants and models locally to drive further insights.

- Provide both the treatment and control groups with easy access to common cyber tools and allow the use of other software and tools, internet access (including search) with the exception of barring the control group from using foundational or cyber-specific generative AI tools and (when necessary) barring both groups from accessing specific and narrowly scoped information that might undermine the realism of the exercise.

- Support automated evaluation of task answers.

The human uplift tasks will be developed through an iterative testing process using a sample of convenience and from scratch or significantly modified and adapted from existing challenges. We propose to include three tasks (to be agreed with AISI and may be replaced by existing tasks from AISI’s CTF evaluation suite or other tasks.):

  - Vulnerability discovery (including a reverse engineering element): Participants are provided a compiled binary with an intentionally inserted vulnerability not accessible to AI training data. They must identify the vulnerability in the binary and answer an automatically verifiable question indicating the discovery of the vulnerability. Participants will be given at most 8 hours for the task (binaries will be sized appropriately).

  - Network operations: Participants are provided a recorded network packet capture file. They must provide a topology map of the observable network and identify a (known) vulnerability that is exploitable with the network access available to the recording device. Participants will be given at most 5 hours for the task (capture files will be sized appropriately).

  - Operating System (OS) exploitation: Participants are provided the source code of software (assumed to be installed in the machine) with an intentionally inserted vulnerability not accessible to AI training data, alongside a goal (such as escalating to admin/superuser privileges). They must provide a shell command that achieves this goal. Participants will be given at most 8 hours for the task (source code will be sized appropriately).

- For all tasks designed, both tasks and the solutions will be shared with AISI.

Step 3: Recruitment of study participants. At least 100 participants will be recruited for each task, with more recruited depending on feasibility. All participants will sign consent forms indicating they are aware of the study details, including its intended publication. Participants will be recruited in an equitable manner, providing both flexibility and some level of compensation for their time, depending on their expertise level. The participant groups will be: non-technical, technical non-experts, and niche experts. For the proposed participant groups and their associated expertise by test, see reply to Question 6 (to be agreed with AISI).  After recruitment, participants will be randomly allocated between the treatment and control groups. Qualifying and willing participants may take part in more than one task.

Step 4: Experiment execution. Participants will receive the task, engage with the LLM, submit their responses, and be timed through the platform. A project point of contact will be available to address any questions or technical difficulties. We will use a structured follow-up protocol to ask further questions about their participation after the experiment ends. To ensure that a reliable baseline that is fully comparable to the treatment group is used, all our baselines will be based on our own control group – performing the exact same task, under the same conditions, and drawn randomly from the same participant group. These results will be sanity-checked against literature, when available.

Step 5: Analysis of study results. The team will perform both quantitative and qualitative analysis on the result. The quantitative analysis will include extraction of key statistics for success rate and completion time for the treatment and control groups and sub-groups stratified by key traits (e.g. age, experience) and an analysis of the differences between treatment and control, including statistical significance. The qualitative analysis will include a discussion of results and hypotheses consistent with the data, key insights from participants’ interactions with the LLMs (if permissible), key insights from the post-experiment surveys of participants, and recommendations for future research.

Step 6: Delivery of study results. The direct results of the study, of the form “Challenge W took person X of Y level expertise, Z minutes/hours to complete the task using the available tools”, will be provided in anonymised form, removing personal data and adhering to all other human subjects’ research constraints. This will allow the extraction of all distribution statistics (e.g. average, variance), as well as the independent replication of all analysis. We will further provide the results of our analysis described in step 5 after internal quality assurance and professional copy editing in a format agreed with AISI (e.g. Word/PDF or other relevant format).

Question 8: Project Management

| This section shows our proposed allocation of resources and time management in delivering the project, a draft risk register, and a draft project plan (all to be revised and finalised in consultation with AISI during mobilisation). Role | Responsibility | Total days |
| --- | --- | --- |
| 1x Project Leader | Responsible for overseeing and project from inception to completion. | 36 |
| 2x Project manager (lead and support) | Ensuring smooth cross collaboration, managing budget and expenses, updating teams with progress, risks, activity log, and assisting with progress reports. Flagging any scope creep and potential risks. | 17 |
| 3x AI and Information Security Researcher | AI and information security experts who will lead on technical platform design and build, test design and execution. | 225 |
| 3x Tech and Security Policy Fellow | Technology fellows who will support quantitative and qualitative analysis. | 90 |
| 2x Research Assistant | Will assist in infrastructure development and participant recruitment, as well as provide quantitative and qualitative analysis support. | 72 |
| 1x Senior Research Analyst | Will provide quantitative and qualitative analysis support, and support to report writing. | 32 |
| 2x Software Engineer | Senior AI Security experts to support project methodology development and evaluation. | 20 |
| 1x Policy Researcher | Threat evaluations lead to provide oversight and input toward research design to ensure study outcomes. | 10 |
| 1x Sr. Information Scientist | Senior expert and leader responsible for oversight of outcomes of broader cyber evaluations work. | 5 |
| 2x QA reviewer | Responsible for quality assurance of all study outputs. | 6 |

Question 9: Understanding of the Sector

Rapid change in offensive and defensive capabilities, alongside the persistence of vulnerabilities, are obstacles to ensuring security and safety in cyberspace. The advancement of AI model capabilities may enable their potential use for cyberattacks at a much greater scale and scope. AI models could help malicious actors make more automated, faster, frequent, and efficient attacks, allowing them to target specific individuals, groups, or institutions more effectively. AI models also present the potential to provide less sophisticated cyber actors, such as criminal organisations, terrorist groups and even individual actors, with greater capability. The development and increasing use of these models present challenges for identifying and assessing risks. The pace of development tends to outstrip the ability of regulators to respond and much of the expertise needed to assess AI threats is found within the companies that develop these systems, complicating transparency in assessing whether these technologies are used for good or harmful purposes.

The public understanding of how AI models can increase capabilities for conducting cyber attacks is also clouded by sensationalist claims such as “LLMs can autonomously hack websites.” These claims create the impression of models that are far more capable and autonomous than they are, while simultaneously obscuring how the models can augment human skills and support greater speed and capacity in executing cyber attacks, such as massive phishing campaigns.

Our previous research has identified two key reasons why addressing these issues is crucial. First, as AI technologies become more capable and widely available, it is essential to develop methods to ensure they are safe and secure, especially to prevent their malicious use in the cyber domain. Second, accurate risk assessment methods are vital for maintaining public trust and developing effective regulations.

Recent proposals for AI regulation recommend rigorous testing processes conducted by third-party evaluators. Human uplift studies currently represent one of the most rigorous evaluation methods to better identify and mitigate dangerous capabilities early, as they provide the most realistic simulation of real-world use and provide proper controls. They provide a means to benchmark model capabilities against a set of tasks that can be compared across models and with different user populations. As models develop in the future, benchmarking must evolve with model capabilities.

Existing work in evaluating offensive cyber capabilities of AI systems takes place in several governments (most notably the UK via its open-sourced INSPECT framework), at leading AI labs including Anthropic and Meta, various startups and service providers such as Pattern Labs, and of course at our own organisation.

Our previous research on methods to identify new and emerging risks from AI foundation models, as well as our wider work on red-teaming and randomised control trials, illustrate key principles for conducting robust human uplift studies:

- Clear and well-defined research objectives, to be agreed with AISI

- Adequate sample size and retention with robust research processes, such as randomisation and strict blinding

- Rigorous quantitative and qualitative analysis guided by ethical conduct at all times

Question 10: Social Value

This section outlines our approach to maximising Social Value throughout the contract. It provides an overview of our organisation’s actions and plans to create new business, jobs, and skills through education and training, followed by a project plan to ensure these commitments are implemented.

We aim to create social value through all our research activities, with a view to creating lasting positive impact on individuals and communities and consequently offers a range of existing support for Theme 2 and MAC 2.3 education and training. We are particularly proud of the Learning and Development programme that our organisation offers to junior and developing researchers and support staff. This is a rolling programme of competency-based training (focusing on research methods and project management) and personal improvement (structured thinking, etc.). Initiatives include beginner AI training sessions on AI and Large Language Models (LLMs) and quantitative training for those with little prior experience. Additionally, all staff are paired with mentors to discuss training needs, set yearly objectives, and receive ongoing support for personal development. We also consider skills growth in local communities, carrying out a wide range of research and analysis aimed at improving quality of life and services in the local Cambridgeshire area, such as our project assessing skills shortages in the Cambridge region, and potential avenues to address these gaps. Recognising that structural inequalities might lead to biases within the job market even before entering our recruitment process, we take proactive steps to ensure equitable job creation. We offer paid internship placements, run an EU trainee programme, support the UK’s apprentice schemes, and promote recruitment opportunities across a wide range of universities.

Method Statement

To ensure our commitment to MAC 2.3, we propose the following actions to be completed during the project life cycle.

- To enhance AI skills among diverse practitioners at our organisation, we will conduct a comprehensive Key Skills Survey to identify current proficiency levels, interest areas, and learning preferences. This survey will inform the development of targeted training programs, including online courses, workshops, and mentorship opportunities, tailored to address identified skill gaps. We will: Periodically update the Key Skills Survey to reflect evolving AI technologies and organisational needs.

- Continuously assess the effectiveness of learning programs and adjust based on feedback and new insights.

- In this project, we include two junior research assistants on the project team. At no cost to the project, these researchers will be undertaking learning and development activities linked to the methods and approaches deployed in the evaluation, focusing particularly on areas of need identified through the key skills survey. This on-the-job learning is essential for the advancement of our junior staff.

- While the confidential nature of the project means that sharing information more widely is difficult, we will work with AISI to determine, what if anything, could be shared to enhance public learning through public Impact Driving activities.

Addendum

| WP0 | Project management and quality assurance |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Task 0.1: Project management and meetings |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 0.2: QA |  |  |  |  |  |  |  |  |  |  |  |  |
| WP1 | Mobilisation period | M1 |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 1.1: Kick-off meetings and mobilisation |  |  |  |  |  |  |  |  |  |  |  |  |
| WP2 | Full study design |  | M2 |  |  |  |  |  |  |  |  |  |  |
|  | Task 2.1: Full study proposal |  |  |  |  |  |  |  |  |  |  |  |  |
| WP3 | Implementation of infrastructure and recruitment of participants |  |  | M3 |  |  |  | M4 |  |  |  |  |  |
|  | Task 3.1: Developing and designing infrastructure |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 3.2: Study protocol and admin |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 3.3: Recruitment of study participants |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 3.4: Baselining |  |  |  |  |  |  |  |  |  |  |  |  |
| WP4 | Running experiments |  |  |  |  |  |  |  |  | M4 |  |  |  |
|  | Task 4.1: Vulnerability discovery and exploitation |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 4.2: Network operations |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 4.3: Operating system (OS) exploitation |  |  |  |  |  |  |  |  |  |  |  |  |
| WP5 | Analysis |  |  |  |  |  |  |  |  | M5 |  |  |  |
|  | Task 5.1: Analysis |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Task 5.2: Draft report preparation |  |  |  |  |  |  |  |  |  |  |  |  |
| WP6 | Final report |  |  |  |  |  |  |  |  | M6 |  |  |  |
|  | Task 6.1: Final report |  |  |  |  |  |  |  |  |  |  |  |  |

| Milestones | Completed at the latest by | Cost |
| --- | --- | --- |
| M1: Mobilisation period | Month 1 from contract award date | £92,009.28 |
| M2: Full study design proposal ready for AISI’s review. | Month 2 from contract award date | £13,964.25 |
| M3: Initial phase of required infrastructure implementation and participants recruitment. | Month 3 from contract award date | £190,581.65 |
| M4: Completion of infrastructure implementation and participant recruitment | Month 7-9 from contract award date | £213,025.62 |
| Live experiment(s) successfully completed |  |  |
| M5: Analysis completed, and draft report shared with AISI, with AISI baselines complete. | Month 9 from contract award date | £141,537.28 |
| M6: Final report | Month 9 from contract award date | £39,847.05 |