## Sheet1
Highways England Confirmation of Task Order |  |  |  |  | Redacted under Sections 40 and 43 of the FOI Act (2000)
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | Atkins
Project Title: | M20 Lorry Area Brock (Interim) Project – Task Order No.5
Contract Ref. | 2589 | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | M20 Op Stack Interim Solution | Sub Pin: | 6 |  | PIN No.: | Redacted
HE Reference: | SE 10 18/19ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5163040 | Consultant Contact: |  |  | Redacted
Start & End Date: | 17/07/2018 - 31/03/2019 | CTO Authorisation No.
Task Overview
Comms Support Commission Further to HE’s review of the Atkins CVs (Redacted and Redacted), we seek to commission Project BROCK Comms Support from Atkins. The main HE reporting line is to Redacted (HE Comms Lead) with Redacted being the second point of contact for comms (HE Senior PM). The works brief includes but is not restricted to: Communications and stakeholder engagement with the following objectives:- • Develop/update the stakeholder list (currently approx. 70% complete) • Finalise an overarching strategy (the comm’s plan – which will form the PCF comm’s product), that includes stakeholder analysis, communication aims and key messages (this is currently approx. 60% developed) • Produce an action plan – what and how we’ll communicate, to who and by when (by end May) • Assist in delivering the plan (this will need to be flexible as it will be based on the action pan to be prepared) • Scan the media horizon and analyse media content affecting Brock/ Brexit etc. and report to Redacted • Advise on and assist with engagement with the wider public, ensuring that they are aware what is a temporary measure, and that through links to the Permanent Project they are aware of when/where they can influence the longer term solutions. • Advise to ensure that all stakeholder perceptions and expectations are managed, to maximise understanding and, where possible, generate support for interim project measures. • Help deliver positive messaging to wider audiences showing progress of delivery in line with the 2019 delivery date. • Support delivery of Project BROCK information during the permanent scheme consultation (May/June2018). Note: all advice/ line to take issued to permanent programme should go through Redacted, not direct from Atkins. • Support the HE cross Kent co-ordination of projects (this may ramp up rapidly ie M20J3-5 Smart + M20J10a + us + KCC schemes + AOne+ schemes). • liaise with MMS comm’s & engagement to ensure both are suitably co-ordinated with each other. • Compliance strategy engagement with Channel Ports if required • Information to support the HE website management animation/fly though of Brock (once known and we need to go public) via Redacted (engagement with HE/Atkins/BB colleagues to obtain latest info) • Information to support correspondence management via HE • Note: All engagement with key stakeholders (eg RHA/FTA, Ports/Police, SEBs, MP’s local government etc) will be done by HE staff. Site Supervisor Commission (Temporary Arrangement) Further to HE’s review of the Atkins CV (Redacted), we seek to commission Atkins for site supervision and assurance for Project BROCK. The main HE points of contact are Redacted (HE PM), Redacted (HE SPM) and the NEC PM (TBC). Note the Site Supervisor commission is to be approved under Spatial Planning Framework as a temporary measure only. This commission will be transferred to the Collaborative Delivery Framework once a new agreement is in place, no later than the 31st August 2018. The works brief includes but is not restricted to:- • Provide Supervisor role under ECC • Supervise Contractor’s repairs and upgrades and compliance with the WI • Check workmanship and quality • Check material delivery conformance with specification • Ensure testing requirements are met, and capture testing outcome/paperwork • Collaboration with Contractor during all event, managing change accordingly working with NEC PM
Task Objectives and Milestones
Comms Support Commission • Tasks, responsibilities and milestones to be defined at a kick-off meeting with HE (Redacted) and Atkins. • Finalise Comms Strategy & PCF product • Baseline milestones and input to HE Master Schedule. Site Supervisor Commission • Undertake NEC ECC Supervisor role to monitor construction works from 3rd May 2018 until 31st August 2018. This role will be commissioned under CDF framework from 1st September 2018 until end of the contract as agreed with HE PM. CEMAR TQ Coordinator Commission • Coordinate and arrange responses to contractual TQs raised via CEMAR by PC and HE. Principal Designer Commission • Fulfill the requirements of the Principal Designer described in the Construction (Design and Management) Regulations 2015 (CDM 2015) in respect of the Construction Phase (the permanent works) only. The Operations Phase (i.e. the temporary works associated with implementation of the operational traffic management scheme for freight management) is excluded from this commission. CDM Advisor and H&S Support Commission • Ensure and monitor that Principal Designer and Principal Contractor are discharging responsibilities under CDM 2015 • To provide CDM Advisor support for the duration of the Temporary Solution (excluding the operational phase) • To report to Highways England Senior Health and Safety Manager on a weekly basis • Carry out Welfare facilities inspections • Monitor contractor’s Safe Systems of Work • Carry out site inspections and safety engagement tours • Ensure all incidents are recorded on AIRSWEB • Facilitate any incident investigation • Communicate safety alerts, lessons learned and good practice both inwardly and outwardly • Attend contractor safety committee meetings Project Timescales: May 2018 – March 2019 (ECC Supervisor to be commissioned under CDF framework from 1st September 2018)
Task Outcomes
Outcomes • A safe network and informed users. Demonstrate safety first culture and approach to delivering projects. • Highways England delivers on its customer and business goals and excels on customer service delivery. • Maintains good relationship with stakeholders, the public, and the customer. • Managing risks and delivering value for money projects. • Demonstrate performance through competence.
Project Risk and Management
Atkins Management • Framework Contract management – Redacted • Framework Task management – Redacted • Project Manager – Redacted • Project Director – Redacted • Principal Designer representative – Redacted Assumed that reimbursement for a Highway Vehicle, if required, will be treated as an expense.
Project Title: | M20 Lorry Area Brock (Interim) Project – Task Order No.5 |  |  |  | HE Reference: | SE 10 18/19ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 10 18/19ATK | Redacted | 0 |  |  | Redacted | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 213879.94
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 213879.94
Total Project Fee Estimate |  |  |  |  | 213879.94
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted | Senior Planner/Engineer | 712 | @ | Redacted | Redacted
Redacted | Director | 248 | @ | Redacted | Redacted
Redacted | Director | 981 | @ | Redacted | Redacted
Redacted | Director | 664 | @ | Redacted | Redacted
Redacted | Director | 172 | @ | Redacted | Redacted
Redacted | Associate Director | 8 | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2018-07-16 |  | Works Total |  | Redacted
Confidential and commercially sensitive information which shall not be disclosed to third parties |  |  | Surveys |  | Redacted
|  |  | Sub Total |  | Redacted
|  |  | Expenses |  | Redacted
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 248879.94