Consultancy to Support Project Management for Sustainable and Resilient Coastal Cities (SARCC) EU project.

# Specification

  - Introduction

Southend-on-Sea Borough Council (SBC) would like to appoint a Consultant to provide support to the Council’s Project Manager through (i) the project initiation phase,

(ii) financial reporting phase; and (iii) project closure phase of the Sustainable and Resilient Coastal Cities (SARCC) programme, which runs from January 2019 through to October 2022. It is the second Interreg project where Southend Borough Council have taken the role of Lead Partner and this procurement exercise is to provide consultancy support for the overall project management.

  - Background

In January 2019, Southend on Sea Borough Council (the Council) was successful in its application as a Lead Partner under the 6th Call of the Interreg 2 Seas Programme for a project entitled Sustainable and Resilient Coastal Cities (SARCC). An outline of the project can be found on the following website:

www.interreg2seas.eu/en/sarcc

The main outputs expected to be delivered include demonstration pilots for nature based solutions to tackle sea level rise. The, the project will also deliver:

- An Implementation Framework and Monitoring

- A Urban Decision Makers Capacity Building Programme

- Visualisation and Community Engagement

- 8 Nature Based Solution investment pilots

- Communications

- Project Management

  - Contract Period

The project officially commenced on 25 January 2019 and finishes on 25th September 2022, running for a total of 42 months. The Partnership brings together a total of 14 Partners - 9 public authorities, 2 business/charities and 3 academics – who will work together to build and demonstrate a framework for authorities to deliver nature based solutions to sea level rise.

The Public/City Partners: Southend Borough Council, Environment Agency (operating in Penzance UK), Middelkerke, Vlissingen, Blankenberge, Ostende, Flemish Coastal Agency, Belgian Government Coastal Agency, Ville de Gravelines

The Business/Charity Partners:  Maritime Archaeological Trust, EXO Environmental Ltd

The Academic Partners: Vives University, HZ Technology, TU Delft

In addition the project has 9 Observer Partners that will benefit from the project in terms of communication and dissemination activities. There is a good mix of Partners and Observer Partners from each of the four Member States of the 2 Seas programme (UK, France, Belgium and the Netherlands).

  - Service Requirements and Outputs

The purpose of this document is to invite potential consultants to bid for the opportunity to provide compliance support to the Council, as Lead Partner, throughout the duration of SARCC.

The Consultant will report directly to the Project Manager of the SARCC project and will be required to support the following three phases of the project:

Initiation Phase

The initiation phase runs until 25 July 2019 and information about this can be found on the following link: https://www.interreg2seas.eu

It will require the Consultant to deliver support on:

- Advising the Lead Partner on the set up of their administration

- Providing advice to the Partners on their project administration at the Partner Meetings

- Advising Partners on eligibility of estimates and providing an overview regarding the eligibility of the match funding/financial processes.

- Liaising with the Lead Partner and Joint Secretariat with regards to financial and procedural matters of the Interreg 2 Seas programme.

- Prepare an introductory session at the first Partners Meeting in Middelkerke (reserve Southend) on Monday 3 June 2019 to discuss project expectations in terms of reporting and management.

- Advise Lead Partner on the project implementation and project control.

Financial Reporting Phase

The Financial Reporting Phase will run from 25 July 2019 until the final three months of the SARCC programme. It will require the Consultant to:

- Set up and implement project reporting structure for the first financial claim of the project (anticipated to be in October 2019).

- Advise on what is required to form the Lead Partner Financial/Periodic Report.

- Advise on eligibility of expenses for Partners.

- Advise on the process of delivering the payment claims (providing a template for use by the Partners).

- Provide guidelines and formats for the submission of the required financial information by the Partners.

- Liaise with the Lead Partner’s First Level Controller and Partner First Level Controllers on the first claim when required.

- Advise on how the Lead Partner can draw up budget modifications if they are required.

- Advise and prepare ERDF settlements with Partners to the Funding Body.

Closing Phase

The Closing Phase will run for the final three months of the project e.g. from end of November 2021 through to 25th February 2022. The Consultant will be required to:

- Prepare and advise the Lead Partner on the final financial report for the Project.

- Liaise with the First Level Controller of the Lead Partner and Partners when required to ensure all of the relevant information is included.

- Advise on the preparation of the final payment claim with the Lead Partner.

- Advise on the final financial settlements with all Partners.

The Consultant will be expected to attend three Partner Meetings in person throughout the project (a half-day session, estimated to be 3 hours*) and provide Partners with an overview of what is expected of them in terms of the initiation phase, financial reporting phase and closing phase.

These dates will be provided to the Consultant in advance of the Partner Meetings and the Council will cover the reasonable costs of travel, accommodation and subsistence (in line with the Council’s own guidelines on these matters) for each Partner Meeting.

The Consultant will need to prepare and run the half-day session on behalf of the Lead Partner. The Consultant will also be asked to join other Partner Meetings via teleconferencing facilities e.g. Skype (or where agreed in person) to provide Partners with an overview of the current phase of the project and what is expected from them in terms of reporting and financial requirements. In addition to the three Partner Meetings that the Consultant will attend in person there will be an additional five Partner Meetings.

* In addition to of the first Partner Meeting where the Consultant will be expected to attend the half-day session on Monday 3 June 2019 and then provide a day of support on Tuesday 5 June when the detail of the initiation phase will be determined.

  - Project Key Dates

The initiation phase is now running and will continue until 25 July 2019. The first Partner Meeting will take place in Middelkerke between 3 and 4 June 2019 (reserve location Southend). The Consultant is expected to lead the first half-day session on Monday 3 June 2019 (14:00-17:00), providing Partners with details on what is expected from them during the initiation phase, and attend the full day meeting on Tuesday 4 June 2019 when the details of the initiation phase will be determined.  The initial Initiation meeting with the Joint secretariat was complete on 19 March 2019.

Partner Meetings are then expected to run every six months (dates to be agreed at the meeting in June 2019) and the Lead Partner will agree with the Consultant the most appropriate meeting to attend in terms of the financial reporting phase (anticipated to be the second Partner Meeting in early 2020).

The project ends on 25 September 2022 and the closing phase of the project will commence in early 2022. The Lead Partner will agree with the Consultant when the last Partner Meeting will take place (early 2022 anticipated) to provide a session to the Partners on what is expected of them in the closing phase.

  - Budget

In total, the Council has a budget of £40,000 available for the Consultancy to provide Project Management support to the Lead Partner and support the Partner Meetings as outlined above. Please note that VAT can be added to the budget.

The total budget of £40,000 must also cover all additional expenses, such as all expenses necessary to communicate with the Lead Partner and partners, if required, and all costs for preparing, printing, copying and storage of reports, drawings, contract documentation and other documents.

For clarity, Council will cover the reasonable costs of travel, accommodation and subsistence (in line with the Council’s own guidelines on these matters) for each Partner Meeting.

  - Other Details

The Council will cover the expenses associated with the Partner Meetings, including travel, accommodation and subsistence. The Council will book travel arrangements for the Consultant and adhere to the Council’s guidelines in terms of costs for accommodation and subsistence.

# Enquiries and Quotation Submissions

Providers should note that all clarification questions must be made via e-mail only. The Council at their discretion reserves the right to circulate any response to all providers.

All clarification questions must be clearly marked CLARIFICATION with the question and provider details clearly set out. Any clarification questions from the provider to the Council should be sent to stephanieli@southend.gov.uk

To allow information to be circulated in time, the deadline for receiving clarification questions is 05 April 2019.

The quotation return date is 22 April 2019. Quotations must be submitted by email to stephanieli@southend.gov.uk (you are recommended to request confirmation of receipt).

# Payment terms

The Council will release payment in five instalments to the successful Provider as per the following payment schedule:

| Payment | Date | Percentage |
| --- | --- | --- |
| Upon completion of Initiation phase | 25 July 2019 | 40% |
| Upon completion of Financial Reporting Phase – part 1 | August 2020 | 15% |
| Upon completion of Financial Reporting Phase – part 2 | February 2022 | 15% |
| Upon completion of Closing Phase – part 1 | June 2022 | 15% |
| Upon completion of Closing Phase – part 2 | 25 October 2022 | 15% |

# Evaluation of Quotations

All quotations will be subject to a thorough evaluation. The Council will examine quotations for completeness and may seek clarification were necessary a quotation determined to be incomplete or not substantially fulfilling the conditions or requirements in this document will be rejected.

- Commercial (price) evaluations will be conducted, based on the information submitted as part of this quotation submission.

- Quality Evaluation Technical evaluations will be conducted based on the below.

# Award Criteria

The Council does not bind itself to accept the lowest priced quotation, or any quotation for this service. The Council will have no obligation to Providers arising from this quotation unless and until it enters into a formal contract with the successful Provider for the provision of the goods and/or services that are subject to this Quotation document. Any contract awarded will be to the Provider whose proposal is determined to be the most economically advantageous.

(Please note: Bidders must have provided ‘acceptable’ responses to each of the Technical Questions to be considered for the contract).

# 15% Price Allocation

To be detailed within this written quotation submission, by the Provider. The Quotation is accepted on a “Fixed Price” basis and the Provider will not be entitled to claim any additional payments or expenses including but not limited to any increase in the price of the service and / or cost of, or incidental to, the employment of labour. The prices included in the Quotation shall be the maximum payable by the Council for the duration of the contract.

If the Provider considers that there has been a material change in the undertaking of the Services, for which a variation should be issued; the Provider, before proceeding with any service affected by such an event, shall request immediately in writing that the Council issue a variation as specified in the Terms and Conditions.

Pricing Evaluation (15%) – Using the Prices submitted by Providers a percentage will be allocated to the total cost as follows:

Score = (Lowest Price Quotation / Your Price) * 15%

- The Table below gives an example of how the methodology works when applied to contract prices. The prices used here are examples of the pricing methodology and do not reflect any expectation of this contract in relation to any aspect of the pricing.

|  | Bid A | Bid B | Bid C | Bid D |
| --- | --- | --- | --- | --- |
| Price | £500 | £300 | £450 | £600 |
| Points Score | 9% | 15% | 10% | 7.5% |

The scores awarded in the example table to Bid B and Bid D calculated as follows:

- Bid B with the lowest price in relation to the other bids is awarded the score of 15  giving a calculation as follows: (£300 / £300) x 15% = 15.00%

- Bid D with the highest contract price in relation to the other bids is therefore the lowest scoring bid in the pricing section, awarded 7.5%. The applied methodology arrives at this score through a calculation as follows: (£300/ £600) x 15% = 7.5%.

# 85% Quality Allocation

85 % Quality Evaluation Technical evaluations will be conducted based on the below.

To be detailed within this written quotation submission, by the Provider, in Section A (Technical Questionnaire). Your quote in response to this brief should consider and provide the following:

| SECTION | SECTION WEIGHTING |
| --- | --- |
| Please provide an overview of your proposed approach to support the Initiation Phase of this project, including ability to deliver within timetable stated in the specification. | 30% |
| Please demonstrate how your experience will help in delivering the outcomes as detailed in the specification: - Examples of how you have supported similar EU projects - Examples of management of financial and compliance documentation | 25% |
| Please demonstrate how you will support and ensure the effective flow of information between the Southend Borough Council and other partners in the project initiation phase and throughout the duration of the project. | 20% |
| Please identify potential project challenges and propose how you would overcome them. | 10% |

Evaluation of Responses will be carried out on an individual question basis. Each question will be scored out of 5. (Please note: scores of an ‘acceptable’ standard must be achieved on all technical questions in order for your submission to be considered further).

| SCORING MATRIX |  | SCORE |
| --- | --- | --- |
| Unacceptable / not answered | Question not answered – and / or – Response to the question significantly deficient – and / or - raises fundamental concerns regarding the organisation’s ability to successfully deliver the Contract. Answer does not provide satisfactory evidence as to the organisation’s capability to deliver the contract successfully. | 0 |
| Poor | A response that is inadequate or only partially addresses the question. Response provides only limited evidence as to the organisation’s capabilities to deliver the contract successfully. Raises a large number of concerns and/or includes a large number of informational deficiencies. Does not raise any fundamental concerns regarding the organisation’s ability. | 1 |
| Acceptable | An acceptable response submitted in terms of the level of detail, accuracy and relevance. Answer provides an average level of evidence as to the organisation’s capability. The response raises some concerns and/or includes a significant number of informational deficiencies. Does not raise any fundamental concerns regarding the organisation’s ability. | 2 |
| Good | A good response in terms of the level of detail, accuracy and relevance. The information provides good evidence of the ability of the organisation to deliver the Contract successfully; but does raise minor concerns and/or includes deficiencies around some of the information provided in the response. Does not raise any fundamental concerns regarding the organisation’s ability. | 3 |
| Very Good | A very good response in terms of the level of detail, accuracy and relevance. The information submitted provides significant evidence of the ability of the organisation to deliver the Contract successfully. However, the response lacks a level of detail needed for full marks. The response raises no fundamental concerns regarding the organisation’s ability. | 4 |
| Excellent | An excellent response in terms of the level of detail, accuracy and relevance. The level of information provided is comprehensive and evidences strongly an assurance as to the organisation’s capability to deliver the contract successfully. The response raises no concerns and has no information deficiencies. | 5 |

# Section A- Basic Contact Details & Technical Questionnaire

| Contact name for enquiries about this bid: |  |  |
| --- | --- | --- |
| Address: Post Code: |  |  |
| Telephone Number: |  |  |
| Email Address: |  |  |
| Company Registration Number (if this applies): |  |  |
| VAT Registration number: (if this applies): |  |  |
| Have you ever been employed by this Council? (if yes please provide details) |  | Yes No |
| Please state if you have a relative(s) who is employed by the Council at a senior level or who is a Councillor? (if yes please provide details) |  | Yes No |

PROSPECTIVE PROVIDER RESPONSE FORM TECHNICAL QUESTIONNAIRE

Please note that page limits are on the basis of font Arial 11 and also include charts, diagrams, tables etc. Additional appendices are not permitted and will not be evaluated.

- Please provide an overview of your proposed approach to support the Initiation Phase of this project, including ability to deliver within timetable stated in the specification. Page limit is 2 side of A4. Weighting = 30%

- Please demonstrate how your experience will help in delivering the outcomes as detailed in the specification: - Examples of how you have supported similar EU projects - Examples of management of financial and compliance documentation Page limit is 2 side of A4. Weighting = 25%

- Please demonstrate how you will support and ensure the effective flow of information between the Southend Borough Council and other partners in the project initiation phase and throughout the duration of the project. Page limit is 1 side of A4. Weighting = 20%

- Please identify potential project challenges and propose how you would overcome them. Page limit is 2 side of A4. Weighting = 10%

# PROSPECTIVE PROVIDER RESPONSE FORM B – COMMERCIAL QUESTIONNAIRE

Please provide a quote for the full cost per working day for providing consultancy services detailed in the Specification.

(Weighting = 15%)