## App A - Schedule of Work
Appendix A
MCA - SCHEDULE OF WORKS - TCA 3/7/1158
Site Address: |  | Maritime & Coastguard Agency
Dundee, Forth Port Ltd, Port Office, Stannergale, Road, Dundee, DD1 3LU
Project Type: |  | Refurbishment of existing farm office and staff facility.
Tenderers for the above contract should complete the tables below, indicating what they would charge for each required element. Prices must: • Be stated in Pounds Sterling; • Include all other charges and overheads associated with the element being priced.
|  | General Works, Site Conditions and Prelims: | Tender: £ | Tenderer Comments
Notes
** | All works are to comply with all current legislative regulations and best practice guidance.
** | Asbestos Survey required
** | Drainage inspection required to advise of removal of existing raised flooring.
1 | Health, Safety & Environment
1.01 | Allow for the provision of all pre-construction safety file documentation including risk assessments, method statements, COSHH assessments, safety programs, lifting plans etc.
1.02 | Allow for all new staff and operatives to undertake a site safety induction prior to starting work on the site. This is envisaged to last approximatly 10 minutes and can be conducted with a group of operatives if required.
1.03 | Allow for all safety related equipment including such items as barriers, signage, working at height access equipment and lifting equipment etc. to enable works to be carried out with minimal risk to operatives and building users. Our aim is for a zero accident working environment and we encourage all staff and contractors to work toward this goal.
1.04 | Allow for your own companies Safe Systems of Work to be utilised and provide the necessary Authorised Persons to issue work permits and safety documentation as required.
1.05 | Allow for all approriate waste transportation licences and ensure all arrisings are removed from site and disposed of in an environmentally approved manner. Any spills are to be controlled and cleared immediately they occur, back up remediation plans / resources should be available in the event of a major spill or release of product.
2 | EXTERNAL WORKS
General External works required
2.01 | Installation new roof, soffits and guttering to existing building required. Completed by Landlord.. |  |  | note
2.02 | Replace broken glass windows.
2.03 | Remove louvered glass panels and install one complete glazed panel.
2.04 | Remove existing roller shutter and install one new roller shutter with as shown in drawing MCAd2019D1-2.
2.05 | Make good existing render where large cracks have appeared.
2.06 | De weed around existing building and clear.
2.07 | Remove existing side entrance door and replace for new UPVC entrance door.
2.08 | Remove existing side low level window and replace with new double glazed UPVC unit to match new front door.
2.09 | Remove existing external light fittings and replace with new L.E.D flood lights.
3 | INTERNAL WORKS
Strip out
3 | Demolish existing internal walls to create one large open space, retaining existing perimeter walls.
3.01 | Remove part of raised flooring to open up the garage area (subject to drainage survey).
3.02 | Remove floor coverings from front areas in preparation to receive new screed and new flooring.
3.03 | Remove all kitchen base units including sink and water heater.
3.04 | Remove existing WC areas complete including old water tank.
3.05 | Remove all existing sockets, lighting and heaters.
3.06 | Cap existing plumbing to WC and kitchen area and alter positions to suit new layout
3.07 | Remove damp plaster board wall in rear storage areas and prepare to receive new.
Build Works
3.07 | Retain column and repair prior to decoration.
3.08 | Install new stud walls using as proposed plan MCA-DUN2019D1-02. Using 72mm C-Stud frame with 12.5mm plasterboard to both sides, insulated with 50mm Rockwool. New stud wall between WC/Kitchen to receive 12.5mm soundbloc plasterboard reduce noise cancelling.
3.09 | Tape & Fill all new walls ready to receive decorations.
3.1 | In rear area (new office / kitchen) Patch repair existing perimeter walls using 12.5mm plasterboard, tape & fill.
3.11 | Install 4 new internal door frames within new building.
3.12 | Install four new internal FD30 min fire doors with central vision panel, complete with ironmongery set.
3.13 | Install two new internal FD30 min fire doors with central vison panel to new WC room, complete with WC ironmongery.
3.14 | Overboard and install new ceiling throughout using 12.5mm plasterboard, tape & fill ready to receive decorations.
3.15 | Install new timber skirting & architraves to Kitchen, WC and garage areas.
3.16 | Install the following kitchen units from the Howden Glendevon gloss white range. 1 x 1000 drawer line sink base unit, 1 x 500 x 4 drawer unit, 1 x 1000 wall unit, 28mm bullnosed black laminated worktop with connection bolts, joint compound, included for all end panels, plinths, cornice and brushed steel effect handles
3.17 | Provide space for fridge as per plan
3.18 | Allow to install Metro bevelled tiles to splash back between the worktop and wall cupboards, included for chrome trims. all tiling to be finished to a good quality. Tile colour white. Grout colour grey.
3.19 | Within garage install to windows steel security bars. 1 windows in total.
3.2 | Install new 150mm extract vent holes with vent and cover to kitchen and WC area.
Plumbing Works
3.21 | Cold water feeds to be relocated to suit new layout.
3.22 | To kitchen area install insert sink with pillar lever taps & wastes. Allow for connecting to existing under sink water heater and wastes pipes in toilet
3.23 | To WC install new one new toilet and one new sink basin with taps and waste.
3.24 | Allow for new hot water feeds to both Kitchen area and WC.
3.25 | Ensure all new wastes are altered to suit new layout.
Flooring
3.26 | Supply and install Milliken carpet tiles Ref; light trails colour Titanium to all floor except toilet allow for all door naps and finishing strips between carpet and Altro flooring to kitchen area
3.27 | Supply and fit Altro Reliance 25 safety flooring to area shown on plan by kitchen area mastic sealant all perimeter
3.28 | WC area. Apply levelling screeds / latex as is deemed necessary and supply and fit Altro Reliance 25 Safety flooring with 150mm upstands to perimeters. Colour storm Allow to provide finishing strips sealed with mastic sealant at the tops of all perimeter upstands.
Electrical Works
3.29 | In Kitchen area, install 3 x twin sockets above work surface, 1 x single socket outlet below work surface for fridge connected to a neon fused spur above work surface
3.3 | Provide and install 3 x 1000kw wall mounted heaters with thermostatic controls. (1 in WC and 1 in Kitchen area, 1 in office area)
3.31 | In kitchen area, install 3 x twin socket outlets with USB ports in white trunking as indicated on plan
3.32 | Install new LED lighting in new WC, Kitchen and garage areas
3.33 | Install new emergency lighting to suit new layout
3.34 | In garage area, install 8x twin sockets for charging points.
3.35 | Upgrade existing new fuse board.
Decorations
3.36 | Prepare and decorate all new and previously painted walls and ceilings. Using 1 undercoat and 2 top coat of Dulux Trade matt Emulsion Paint walls magnolia ceilings white
3.37 | Prepare and decorate all new and previously painted timber surfaces with 1 coat undercoat and 2 top coats blue gloss
4 | Completion
4.01 | Allow for the provision of 1 x electronic copy on CD Rom and one printed hard copy of all test sheets, manufacturers information, engineers service and maintenance guides, suppliers contact information, disposal information, together with full layout and schematic drawings of the carpark lighting in DWG. & PDF. formats. This information is to be presented in a post-construction health and safety file format.
4.03 | On completion the Contractor to undertake deep clean of working areas and leave the premises clean and tidy, free from dirt, dust and any builders waste and plant.
5 | Preliminaries & Overheads
5.01 | Prelims
5.02 | Overheads & Profit
| TENDER TOTAL |  | 0
| VAT |  | 0
| TOTAL INCLUSIVE OF VAT |  | 0
The nominated Procurement Manager is:
Procurement & Contracts Team
Bay 3/19 – Spring Place
105 Commercial Road
Southampton
SO15 1EG
Tel: 020 381 72984
Email: Contracts@mcga.gov.uk
Signed:
in the capacity of:
duly authorised to sign tenders for and on behalf of :
Postal Address:
Telephone No:
Email:
Date: