# Annex A

| Title of project: | MONITORING DESIGNATED SITES: SETTING PRIORITIES AND MAKING BEST USE OF NEW TECHNOLOGY |
| --- | --- |
| Date and time for return of tenders: | Friday 8 February @ 16:00 hours |
| Contract Reference No: | C18-0285-1307 |
| Address for tender submission: | 1 electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND TENDERS DIRECTLY TO ANT MADDOCK OR DORA IANTOSCA VIA THEIR PERSONAL EMAIL ADDRESSES, AS THIS WILL INVALIDATE YOUR TENDER Tender responses must be less than 10 MB in size. On receipt of your tender, you will receive an automated e-mail to confirm receipt by JNCC Support Co. If you do not receive this automated email, please contact, in the following order: Sue Wenlock (00 44 1733 866880) Chris Downes (00 44 1733 866877) |
| Contacts for technical information relating to this project specification: | Joint Nature Conservation Committee Email: ant.maddock@jncc.gov.uk Tel: 01733 866936 OR Joint Nature Conservation Committee Email: tony.weighell@jncc.gov.uk |
| Contact for any queries regarding the tendering procedure: | Dora Iantosca Finance Team Joint Nature Conservation Committee Email: Dora.Iantosca@jncc.gov.uk Tel: 01733 866894 |
| Proposed start-date: | Early February 2019 |
| Proposed end-date: | Phase 1: 29 March 2019. Phase 2: 28 June 2019. |

WORKSHOP AND PREPARATION TO REVIEW SETTING PRIORITIES FOR SITE MONITORING AND MAKING BEST USE OF NEW TECHNOLOGIES WITHIN COMMON STANDARDS MONITORING

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation. Its work contributes to maintaining and enriching biological diversity, conserving geological features and sustaining natural systems.

Our role is to provide evidence, information and advice so that decisions are made that protect natural resources and systems. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally:

advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

providing advice and disseminate knowledge on nature conservation issues affecting the UK and internationally;

establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on the JNCC intranet: http://jncc.defra.gov.uk/page-1729.

## Project Aims

Update the current CSM approach to monitoring protected areas by the Statutory Nature Conservation Bodies (SNCBs) within the UK. This update will adapt to the availability of new technologies and ensure effective choices are made in respect of monitoring frequency and techniques applied. This will complement the two-route site selection model and existing Common Standards Monitoring (CSM) Guidance and help the SNCB’s achieve two objectives:

- Continue to report on the condition of designated conservation sites in the UK effectively; and

- maximise the value of the CSM process in supporting effective site management.

Note that this contract is in two Phases. Section 6 of this contract is therefore relevant and should be noted in respect of the second phase of the work.

## Project Background

This project will span the 2018_19 and 2019_20 financial years and have two phases. Phase 1 should be completed by 29 March 2019. If undertaken, Phase 2 should be completed by 28 June 2019.  The contractor must split their bid timings and costs into these two Phases.

An Inter-agency Working Group (IAWG) is updating the CSM Guidelines and is developing updated and transparent approaches to site monitoring that maximise the value of the human and financial resources available. The IAWG (with a representative from each of four countries) want to combine new technologies with the more traditional expertise of the SNCBs, to devise a way which is efficient, effective, reliable, and delivers for biodiversity.

## The need to review CSM monitoring

The original Common Standards Monitoring (CSM) was designed to be a rapid assessment method to be carried out, in most cases, by Conservation Officers or Site Managers.  It aimed at being a low-risk, comprehensive, approach which ensured that all elements of the A/SSSI (Area/Site of Special Scientific Interest) network were covered at least once in every six years and was a good way to report on the condition of sites individually and in aggregate.  However, the method resulted in many ‘no change’ assessments, at considerable cost.  The SNCBs want to develop a strategy for future monitoring of A/SSSIs that allows resources to be used most effectively.

## Risk

Site condition monitoring requires choices to be made in respect of monitoring frequency for individual sites (or categories of sites). The intention is that future monitoring effort will be prioritised for sites most at risk, whilst capturing overall changes in condition to the network of A/SSSIs through ‘targeted use of site monitoring resources’.

The term ‘risk-based approach’ reflects this intention to develop guidelines on how the SNCBs can make consistent and transparent decisions about evaluating site monitoring objectives, determining site management requirements and choosing among different techniques that are available now or may become available.

The SNCBs want to balance the need to keep risks to do with monitoring at acceptable levels, with the need to focus scarce resources on effective action.  They are looking for ways to make the most of new technologies, at the same time allowing CSM methods to be used more flexibly and economically, targeted at sites where data are most needed.  They do not want to sacrifice technical rigour and would like to maintain as many of the strengths of the original method as possible.

The SNCBs wish to take a targeted approach to monitoring, based on risk or on operational/policy drivers, and all of them have started to do so.  There are several aspects to risk in this context:

- Basing monitoring on site risk.  Focus monitoring on sites thought to be at risk of being in poor condition;

- Basing monitoring on targets.  Focus monitoring on sites thought likely to contribute to meeting operational targets;

- Quantifying uncertainty when reporting the results of monitoring, so that risks are clearly understood (most relevant for new technologies);

- Risks to the monitoring organisations.  This includes legal risks (infraction, appeals or other legal challenges); may include risks of failing to meet operational targets; or reputational risk if biodiversity monitoring is perceived inadequate or poor.

Integrating new technologies with existing data sources

JNCC, with the SNCBs, is developing ‘a matrix’ to identify and characterise different potential monitoring methods (e.g. remote sensing, novel DNA techniques, modelling and more conventional methods) as an aid to making decisions on the choice of techniques for future site monitoring, The successful contractor will be briefed on the scope and content of this ‘matrix’ at the project inception meeting.

## Project Objectives

To meet the overall aim of this project the contract will achieve the following objectives separated into two Phases:

Phase 1 (February to March 2019)

- hold one-on-one discussions with the SNCBs to understand each country’s current approach to monitoring A/SSSIs;

- review current approaches to environmental monitoring in the UK at site and landscape scales applied by organisations other than the SNCBs;

- combine results of i. and ii. to report to JNCC and the IAWG on the range of approaches to site and landscape scale monitoring currently in use in the UK and their applicability to the future requirements of the CSM process.

Phase 2 (April to June 2019) – subject to conditions defined in Section 6

- using the background information gathered in Phase 1, and in conjunction with JNCC and the IAWG, plan the scope and details of a workshop to develop an agreed approach to facilitate protected area monitoring by the SNCBs;

- facilitate the workshop with the SNCBs and JNCC; and

- submit a final synthesis project report outlining the approach(es) to future site monitoring agreed and/or recommended by the workshop.

## Project Objectives: Detailed tasks

- Work will begin in February 2019 with Phase 1 to be completed by 29 March 2019.

- Phase 1 (February to March 2019)

- Consultation with the SNCBs

Contractor led, one-on-one discussions with the SNCBs to understand each country’s current approach to monitoring A/SSSIs, in particular with reference to setting priorities for use of resources, use of the different techniques available for site monitoring, frequency of monitoring and the identification of those sites where monitoring is most relevant or urgent to inform management planning to maintain or improve site condition.

These one-on-one discussions will establish and record the processes the SNCBs use to identify sites where monitoring is most relevant or urgent including:

- the frequency of monitoring and the techniques used to determine this frequency;

- how priorities for use of monitoring resources are established; and

- the extent to which the four SNCBs employ different or similar approaches to selecting sites for monitoring.

- Review of approaches outside the SNCBs

- The review will expand the information gathered in i) to examine approaches taken by other environmental bodies in the UK.  This review will be high-level, identifying the most important aspects of, and drivers in, the wider monitoring landscape, rather than an exhaustive or detailed account.  This review should cover techniques used to focus resources (prioritise their use) at site/landscapes/feature scales to maximise the value of monitoring in the context of environmental reporting and management, and the policy drivers for these prioritisation procedures should be identified.

- Phase 1 report on consultation and review

- Consolidate the results of the Consultation and Review into a standalone report for JNCC and the IAWG in a format to be agreed with JNCC and consistent with the objectives of the project.

- The Phase 1 report will provide background information for planning discussions at the workshop to be held as part of the Phase 2 work.

Phase 2 (April to June 2019)

Phase 2 involves the contractor planning, facilitating and reporting on a one-day workshop to be held in May or early June 2019 to develop an agreed, or recommended, approach to future protected area monitoring by the SNCBs.

Note: The work under Phase 2 will be undertaken at JNCC’s discretion (see Section 6). Provisional dates for the preparatory April IAWG meeting and the May workshop will be set at the inception meeting in early February for planning purposes. JNCC anticipates confirming the requirement, or otherwise, for the Phase 2 work no later than end February 2019.

- Workshop planning

- In collaboration with JNCC and the IAWG, the contractor will plan the scope and details of the workshop using the background information gathered in Phase 1 to develop an agreed approach to facilitate protected area monitoring by the SNCBs. This will involve participating in an IAWG meeting in April 2019.

- NOTE: JNCC will identify a workshop location and arrange and pay for venue hire but the contractor will manage all other workshop logistics associated with the workshop including invitations to participants.

The workshop discussion will be based on:

- the results of Phase 1;

- use of the ‘matrix’ of monitoring methods referred to above;

- existing Common Standards Monitoring (CSM) Guidance.

- The format and structure of the workshop, agreed among the contractor, JNCC and the IAWG, is likely to include:

- contractor presentation of a brief summary of existing SNCB approaches for targeted use of site monitoring resources;

- contractor presentation of a brief overview of approaches used in the UK by other bodies for targeting monitoring resources;

- an outline of the ‘matrix of monitoring methods’ currently under development by JNCC and the decision-making procedures that can used to apply the available techniques and the ‘two-route’ site selection model (done by JNCC);

- contractor-led structured discussions about priorities and objectives for site monitoring and the role within CSM of a decision-making procedure for targeting resources; and

- contractor-led agreement of the next steps and statement of the consensus across the SNCBs.

- Facilitate the workshop

- The contractor will facilitate the workshop in conjunction with the SNCBs and JNCC and will provide sufficient facilitators to manage the workshop.

- Synthesis report

- A synthesis report including the workshop outcomes will be produced by the contractor for the IAWG and JNCC. The synthesis report will contain draft proposals and options for integrating guidance on ‘targeted use of site monitoring resources’ within the CSM Guidelines.

- The final report will include a brief account of the workshop, and description and assessment of options for and an optimum common approach, as developed at the workshop.  If the workshop has successfully identified a credible joined-up approach, this should be worded so that it can form the first draft of a joint position to propose to our governance bodies.  If the level of agreement falls short of our hopes, the report should set out and explain the main points of agreement and divergence.  It should include a note of any follow-on actions which have been agreed (delivering these is not part of this contract).

## Potential follow-on work

Tenderers should be aware that there is the potential for the successful contractor to be requested by JNCC to undertake Phase 2 on this contract into the financial year 2019/20.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds, and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given, that you will be asked to undertake the Phase 2 work outlined within this contract. However, tenderers are asked to provide detailed project plans for Phase 2 in this application.

## Outputs

- Review following Phase 1 (by 29 March 2019).  Consolidate the results of the Consultation and Review into a standalone report for JNCC and the IAWG. This should include an explanation of the methodologies and outcomes achieved in objectives i) and ii). The first draft will be a working document, which can be circulated in advance of the workshop.

- Delivery and management of the workshop in Phase 2: and

- Synthesis report (within three weeks of the workshop). The report should include the outcomes from each key step, draft proposals and options for integrating guidance on ‘targeted use of site monitoring resources’ within the CSM Guidelines. It is important that the agreed approach is presented in this report. If no agreed approach is reached, details of what was agreed and where and why divergences occurred, are required; and

- The contractor to discuss with JNCC and the IAWG the possibility of publishing in a suitable scientific paper the work in this contract.

## Dissemination

The report produced under this contract will be a JNCC product and shall not be published or disseminated without the written permission of JNCC. It may at some point be published on the JNCC website and all material supplied as part of this contract shall remain copyright of JNCC. The findings from this contract will also be made available to JNCC, the UK Conservation Agencies (Natural England, DAERA-NI, Scottish Natural Heritage, Natural Resources Wales), Defra and UK Devolved Administrations.

## Timescale

Provisional dates for delivery of the contact outputs are set out below. Exact dates are to be agreed at start-up meeting based on Contractor and JNCC staff availability.

| Milestones | Provisional dates |
| --- | --- |
| Phase 1 |  |
| Start-up meeting (UK) | early February |
| Project meetings | February to March |
| Completion of review (Phase 1) | 29 March 2019 |
| Phase 2 |  |
| Workshop | May / early June 2019 |
| Draft report | Within a week of workshop |
| Final report | Within 3 weeks of the workshop, 2019 depending on comments received from IAWG. |

## Health and safety

The Contractor is expected to follow appropriate Health & Safety procedures and undertake appropriate risk assessments, evidence of which should be supplied to JNCC. Any incidents occurring within the contract should be immediately reported to JNCC.

## Product specification

The final report must adhere to the JNCC report template and house style guidance. The reports should be provided electronically via email as a Microsoft Word document and an Adobe PDF. Copies of documentation associated with the case studies should be provided in electronic format, with an associated reference catalogue.

## Project management

The Contractor shall nominate a project manager, who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact point is:

Email:  ant.maddock@jncc.gov.uk  Tel: +44 (0)1733 866936

## Instructions for tender submission

The tender submission should include the following:

A brief summary of the potential Contractor’s experience in relation to the requirements of this contract;

A proposed approach for achieving the objectives of the contract (and delivering the detailed tasks identified within each objective). This should be sufficiently detailed allow assessment against the evaluation criteria (Section 13);

A detailed project plan (including Gantt chart), including the proposed work programme and an estimate of time required to achieve each objective;

A draft Table of Contents for the final report;

Details of Quality Control procedures to be followed.

Details of the Project Team, including their roles and experience, an estimate of their time input into each task, and CVs of all personnel involved in the contract;

Availability of the Project Team for a start-up meeting in early February 2019;

Overall quote for the contract, to include:

  - Daily rates for all members of the Project Team;

  - Rates for attending start-up, interim and final meetings in Peterborough or Aberdeen (costs for travel and accommodation are attached and should be used. These rates are analogous to the civil service rates);

  - Costs and time allocation should be clearly allocated to specific tasks within this contract; and

  - VAT if applicable. The contractor is to specify whether VAT at the prevailing rate would be applicable to this project and to provide their company’s VAT registration number.

The following documentation:

  - Copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting;

  - Copies of current public and employer liability insurance certificates;

  - Copies of any appropriate risk assessments; and

  - Copies of any environmental policies should you have them.

In addition, note that the tender submission should provide sufficient information to allow assessment against the criteria outlined in Section 14.

## Evaluation Criteria

JNCC are not bound to accept the lowest priced or any tender.  Having the technical expertise and experience to complete the work to a high standard, and being able to complete it within the timescale, are of the essence for this contract.

The tender evaluation will be undertaken by a panel consisting of JNCC staff and staff members from Natural England, Natural Resources Wales, Scottish Natural Heritage and DAERA-NI.  Unless otherwise stated in your tender submission, bids will be forwarded to these agencies for evaluation purposes only.

For information on how we handle personal data please see our Privacy Notice at http://jncc.defra.gov.uk/privacypolicy

Tenders will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Max Score | Score |
| --- | --- | --- | --- |
| 1. Quality of proposal, (60% of the total for the three assessment categories) |  |  |  |
|  | Clarity of proposal, work plan and deliverables | 15 |  |
|  | Identification of key steps, sticking points and problem areas | 10 |  |
|  | Proportional apportionment of time into the main work areas | 10 |  |
|  | Experience in natural resource monitoring and risk assessment | 10 |  |
|  | Experience in arranging and managing workshops | 10 |  |
|  | Knowledge of Common Standards Monitoring (http://jncc.defra.gov.uk/page-2219 & page-2199) | 5 |  |
|  | Sub Totals | 60 |  |
| 2. Details of Contractor (20 % of the three assessment categories) |  |  |  |
|  | Expertise, experience and balance of team | 7 |  |
|  | Risks if important team members drop out | 5 |  |
|  | Adequacy of subcontractors (if any) | 5 |  |
|  | Experience with Common Standards Monitoring | 3 |  |
|  | Sub Totals | 20 |  |
| 3. Cost (20% of the total for the three assessment categories) |  |  |  |
|  | Transparency and correctness of presentation | 5 |  |
|  | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Appropriateness of ratio of senior to junior staff time | 5 |  |
|  | Clarity of each team member’s contribution and value added | 5 |  |
|  | Sub Totals | 20 |  |
| Total score |  | 100 |  |

## Payment

Phase 1: Payment for Phase 1 work will be made at the end of March 2019 and following the submission of an invoice and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

Phase 2: Payment for Phase 2 work will be made on completion of the work, following the submission of an invoice and based on satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Contractor requirements

All tenderers are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key milestones.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates and fees given.

The Contractor is expected to supply all necessary equipment, software, licences etc. to carry out the obligations required under the contract.

The two-route approach uses Earth Observation or modelling to collect whole-landscape data and then uses that in conjunction with more detailed, site-based data to guide the selection of sites for monitoring.