## Sheet1
ODIHAM PARISH COUNCIL - GROUNDS MAINTENANCE CONTRACT 2025-2028
SCHEDULE OF WORKS
|  | M | A | M | J | J | A | S | O | N | D | Anticipated number of visits | Additional cuts allowed. Timing to be specified by Contractor | Total number of cuts per annum to be provided | Year 1 |  | Year 2 |  | Year 3 |  | Total Years 1-3 | Council Comments | Contractor Comments
[15 empty] | Price per visit | Price per annum | Price per visit | Price per annum | Price per visit | Price per annum
1 | Recreation Ground including 2 fenced children's play areas, trim trail and MUGA
| Strim cut or mow all the grassed areas of the site including the area adjacent to the MUGA, the area within the fenced children's play areas, strimming around the seats and litter bins. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Strim cut or mow up to all of the perimeter hedges including the under storey.* | [10 empty] | 4 |  | 4 |  | 0 |  | 0 |  | 0 | 0 | *Allow for management of ecotine areas to create wildlife corridors. | bar: M to A; S; N
| Pick litter from the site including the play areas and place in litter bin. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Remove all debris, green waste and cuttings from the site. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Clear all litter and remove all weeds and foliage in and around the MUGA (including the pathway and bank at the rear of the courts) and sweep the court removing all debris. | [10 empty] | 8 |  | 8 |  | 0 |  | 0 |  | 0 | 0 | bar: M to S; N
| Management of weeds around the base of play equipment, base of fencing, seats and litter bins. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0 | Contractor to advise method. Base of Trim Trail equipment should not be strimmed.
| Cut and prune both sides and the top of the hedge adjoining Recreation Road. | [10 empty] | 3 |  | 3 |  | 0 |  | 0 |  | 0 | 0 | Note scale of works. Note Council's duty to ensure no vegetation overhanging highway. | bar: M; A; O
2 | Bufton Field Play Area
| Mow and strim the grass outside the play area. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Brush the play area. | [10 empty] | 2 |  | 2 |  | 0 |  | 0 |  | 0 | 0 | bar: A; S
| Annual treatment of moss/algae on play area surfaces. | [10 empty] | 1 |  | 1 |  | 0 |  | 0 |  | 0 | 0 | Treatment and timing to be specified by Contractor.
| Pick litter from the site and place in litter bin. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Remove all debris, green waste from the site. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Trim all greenery inside the play area so that it is flush with the fence. | [10 empty] | 3 |  | 3 |  | 0 |  | 0 |  | 0 | 0 | bar: M; M; S
| Management of weeds around the base of play equipment, base of fencing, seats and litter bins. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0 | Contractor to advise method.
| Trim all greenery around the outside of the perminter of the site, keeping all shrubs and hedges level with the fence and cutting back any tree branches overhanging the play area. | [10 empty] | 3 |  | 3 |  | 0 |  | 0 |  | 0 | 0 | Note scale of works. | bar: M; M; S
3 | Chapel Pond Play Area
| Mow and strim all grass within the site. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Management of weeds around the base of play equipment, base of fencing, seats and litter bins. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0 | Contractor to advise method.
| Pick litter from the site and place in litter bin. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Remove all debris, green waste from the site. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Brush the play area surfaces. | [10 empty] | 2 |  | 2 |  | 0 |  | 0 |  | 0 | 0 | bar: A; S
| Trim all trees and vegetation in and overhanging the site. | [10 empty] | 3 |  | 3 |  | 0 |  | 0 |  | 0 | 0 | Note brambles on northern boundary is included. | bar: M; J; N
| Trim brambles on northern boundary from the road side. | [10 empty] | 2 |  | 2 |  | 0 |  | 0 |  | 0 | 0 | Note Council's duty to ensure no vegetation overhanging highway. | bar: A; S
4 | Allotment Site
| Mow and strim all grass within car park area. | [10 empty] | 2 | 2 | 4 |  | 0 |  | 0 |  | 0 | 0 | Contractor to advise timing.
| Cut/strim all greenery between the allotment and perimeter fence. | [10 empty] | 2 |  | 2 |  | 0 |  | 0 |  | 0 | 0 | Contractor to advise timing. Note access constraints.
| Remove all debris, green waste from the site. | [10 empty] | 2 | 2 | 4 |  | 0 |  | 0 |  | 0 | 0 | Contractor to advise timing.
5 | Chamberlain Gardens (Sports Centre Trust land)
| Mow and strim all grass within the site. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Management of weeds around the base of play equipment, base of fencing, seats and litter bins. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0 | Contractor to advise method.
| Strim cut or mow up to all of the perimeter hedges including the under storey.* | [10 empty] | 4 |  | 4 |  | 0 |  | 0 |  | 0 | 0 | *Allow for management of ecotine areas to create wildlife corridors. | bar: M to A; S; N
| Pick litter from the site and place in litter bin. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Cut and prune all the perimeter hedges and all hedges within the site including the tops removing the foliage and also cutting back any tree growth into adjoining properties. | [10 empty] | 4 |  | 4 |  | 0 |  | 0 |  | 0 | 0 | bar: M to A; A; N
| Trim all trees within the site up to shoulder height and notify the council when trees require to be cut back or more extensively pruned. | [10 empty] | 3 |  | 3 |  | 0 |  | 0 |  | 0 | 0 | Note scale of works and opportunity to quote for additional works. | bar: M; J; N
| Remove all debris, green waste and cuttings from the site. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 |  | 12 |  | 0 |  | 0 |  | 0 | 0
6 | Beacon Field (Sports Centre Trust land)
| Strim, cut or mow all the Beacon Field as well as the area around the exterior of the bowling green and the tennis courts (including all pathway between Chamberlain Gardens and the Beacon Field). | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Strim cut or mow up to all of the perimeter hedges including the under storey.* | [10 empty] | 4 |  | 4 |  | 0 |  | 0 |  | 0 | 0 | *Allow for management of ecotine areas to create wildlife corridors. | bar: M to A; S; N
| Remove all debris, green waste and cuttings from the site. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Pick litter from the site and place in litter bin. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Cut and prune both sides and the top of the large Leylandii hedge on the southern side of the tennis courts. | [10 empty] | 1 | 2 | 3 |  | 0 |  | 0 |  | 0 | 0 | bar: O
7 | War Memorial
| Trim the two hedges either side of the Memorial. | [10 empty] | 2 |  | 2 |  | 0 |  | 0 |  | 0 | 0 | As close as possible to Remembrance. | bar: M; S
| Remove all debris, green waste and cuttings from the site. | [10 empty] | 2 |  | 2 |  | 0 |  | 0 |  | 0 | 0 | As close as possible to Remembrance. | bar: M; S
| Pick litter from the site and place in litter bin. | [10 empty] | 2 |  | 2 |  | 0 |  | 0 |  | 0 | 0 | As close as possible to Remembrance. | bar: M; S
8 | Colt Hill land
| Mow of strim the under storey adjacent with the pavement along the eastern perimeter only. | [10 empty] | 2 |  | 2 |  | 0 |  | 0 |  | 0 | 0 | Note Council's duty to ensure no vegetation overhanging highway. | bar: A; S
| Prune back any tree/shrub brances overhanging the pavement along the eastern perimeter only. | [10 empty] | 1 |  | 1 |  | 0 |  | 0 |  | 0 | 0 | Note Council's duty to ensure no vegetation overhanging highway. | bar: S
| Strim pathway through site. | [10 empty] | 4 |  | 4 |  | 0 |  | 0 |  | 0 | 0 | bar: M; M; J; S
9 | Peace Garden
| Strim cut or mow the grassed area. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0 | Note bulb planting on top and sides of bank.
| Cut and prune all shrubs and other foliage in the whole of the site. | [10 empty] | 7 |  | 7 |  | 0 |  | 0 |  | 0 | 0 | Note ornamental planting. | bar: M to A; J to S; N
| Remove all debris, green waste and cuttings from the site. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
| Pick litter from the site and place in litter bin. | 1 | 1 | 2 | 2 | 2 | 2 | 1 |  | 1 |  | 12 | 2 | 14 |  | 0 |  | 0 |  | 0 | 0
10 | Parish Room
| Prune all greenery around the building including the removal of all creepers from the building and wall. | [10 empty] | 3 |  | 3 |  | 0 |  | 0 |  | 0 | 0 | bar: M; J; N
| Clear french drains on the blocked paving outside the building. | [10 empty] | 3 |  | 3 |  | 0 |  | 0 |  | 0 | 0 | Note scale of works. | bar: M; J; N
| Remove all debris, green waste from the site. | [10 empty] | 3 |  | 3 |  | 0 |  | 0 |  | 0 | 0 | bar: M; J; N
| Pick litter from the site and place in litter bin. | [10 empty] | 3 |  | 3 |  | 0 |  | 0 |  | 0 | 0 | bar: M; J; N
11 | Waste Disposal - bin emptying
| Recreation road play area x 2 | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Recreation road in ground on path opp no. 4 x 2 | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Recreation ground at end of Crownfields x 2 | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Chamberlain Gardens behind tennis courts x 2 | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Play area in Chamberlain gardens behind tennis courts x 1 | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Along side of tennis courts x 1 | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Entrance to Buryfields infant school x 1 | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Chapel Pond play area x 1 | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
12 | Routine Playground inspections
| Recreation Ground - 2 play areas, trim trail, MUGA and football goal | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Bufton Field play area | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Chapel Pond play area | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Chamberlain Gardens play area | [10 empty] | 52 |  | 52 |  | 0 |  | 0 |  | 0 | 0
| Total | [14 empty] | 0 |  | 0 |  | 0 | 0
Completed by:
Company
Person
Date