## Sheet1
Asset Type | 1300 - Lighting
Rebaselined SP New Planned Finish | Actual Start | Actual Finish | Area 12 Maintenance Segments | Area 12 TM Reference | TM Needed? | Taper MP (formula) | End MP (formula) | ScAR | Activity Name | Confirm Job Number | Qts Remaining
12/31/2023 |  |  | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB OS | Yes |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036818 | 64
[8 empty] | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036817 | 28
[8 empty] | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52036824 | 94
|  |  | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB OS | Yes |  |  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036719 | 36
|  |  |  | YNE20 Closure 1 WB OS | Yes |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52036726 | 36
|  |  |  | Unsure on location | Unsure on location |  |  | 4.5.1 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 52036717 | 16
|  |  | YNE6: M62 J27-28 | YNE6 Closure 1 EB NS | LBS123 required |  |  | 4.5.8 | BC - Lamps (LED) for Illuminated Signs and Bollards | 52038541 | 2
[5 empty] | No TM required |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038542 | 8
[8 empty] | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038540 | 20
|  |  | YNE76: A628 Tintwistle - Crowden | YNE76 Closure 1 EB NS | No TM required |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038748 | 2
| 2023-04-12 | 2023-05-12 | YNE18: A63 Welton - Melton | YNE18 Closure 1 WB NS | Yes | 191/0 | 187/1 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036818 | 6
[8 empty] | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036817 | 41
| 2023-05-12 | 2023-06-12 | YNE19: A63 Melton - WesternInt | YNE20 Closure 1 WB NS | Yes | 193/5 | 190/0 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036720 | 16
[8 empty] | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52036726 | 21
| 2023-06-12 | 2023-07-12 | YNE18: A63 Welton - Melton | YNE17 Closure 1 EB NS | Yes EB entry slip verge | 183/6 | 188/1 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036818 | 5
| 2023-07-12 | 2023-08-12 | YNE18: A63 Welton - Melton | YNE18 Closure 1 EB NS | Yes | 187/7 | 192/2 | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036817 | 22
[8 empty] | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52036824 | 4
|  |  | YNE19: A63 Melton - WesternInt | YNE18 Closure 1 EB NS | Yes | 187/7 | 192/2 | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036719 | 18
| 2023-08-12 | 2023-09-12 | YNE19: A63 Melton - WesternInt | YNE20 Closure 1 EB NS | Yes | 191/1 | 195/5 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036720 | 19
[8 empty] | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52036726 | 22
|  |  | YNE20: A63 Western Int - Priory Way | YNE20 Closure 1 EB NS | No TM required | 191/1 | 195/5 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52036734 | 5
12/31/2023 Total | [10 empty] | 485
2024-08-01 | 2024-08-01 | 2024-08-01 | YNE82: A61 | YNE82 Closure 1 NB NS | No TM required | 0 | 0 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038758 | 15
|  |  |  | YNE82 Closure 1 SB NS | No TM required | 0 | 0 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038758 | 14
1/8/2024 Total | [10 empty] | 29
1/31/2024 |  |  | YNE109: A1M J37-38 | Unsure on location | Unsure on location |  |  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038833 | 11
|  |  | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 SB OS | Yes |  |  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52037776 | 3
[8 empty] | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52037728 | 5
|  |  |  | TBC | Yes on slips |  |  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52037776 | 8
[5 empty] | Yes on exit slip |  |  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52037776 | 12
|  |  | YNE7: M62 J28-29 | YNE7 Closure 1 EB NS | No TM required |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038533 | 4
[8 empty] | 4.5.8 | BC - Lamps (LED) for Illuminated Signs and Bollards | 52038534 | 1
|  |  |  | YNE7 Closure 1 WB NS | Yes - on WB entry slip |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038533 | 10
|  |  | YNE8: M62 J29-31 | YNE8 Closure 1 EB NS | Yes |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038486 | 38
|  |  |  | YNE8 Closure 1 WB NS | Yes |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038486 | 45
|  |  | YNE98: A180 Stallingborough - Great Coates | YNE98 Closure | TBC |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52037850 | 108
|  |  |  | Unsure on location | Yes |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52037850 | 109
| 1/16/2024 | 1/17/2024 | YNE80: A616 Wortley - Westwood | YNE80 Closure 1 EB NS | Yes | 0 | 0 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038747 | 17
| 1/19/2024 | 1/20/2024 | YNE106: A1M J34-35 | YNE106 Closure 2 NB NS | No TM required | 2023-02-04 | 2023-07-08 | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038882 | 2
| 1/22/2024 | 1/23/2024 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 2 EB NS | Yes | 44/4 | 49/0 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52037832 | 16
| 1/24/2024 | 1/25/2024 | YNE108: A1M J36-37 | YNE108 Closure 1 NB NS | No TM required | 2023-07-14 | 2023-04-20 | 4.5.8 | BC - Lamps (LED) for Illuminated Signs and Bollards | 52038797 | 5
| 1/26/2024 | 1/27/2024 | YNE96: A180 Barnetby - Brocklesby | YNE96 Closure 1 WB NS | Yes | 45/6 | 40/4 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52037832 | 17
| 1/29/2024 | 1/30/2024 | YNE110: A1 Redhouse - Barnsdale | YNE110 Closure 1 NB NS | Yes | 285/8 | 289/4 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52037779 | 44
|  |  |  | YNE110 Closure 1 SB NS | Yes | 290/2 | 285/5 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52037779 | 53
[8 empty] | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52037728 | 3
[5 empty] | No TM required | 290/2 | 285/5 | 4.5.1 | BCC - Switched Lamps (MCF/U TLD, PL-L, PL-S, SOX) | 52037778 | 2
[8 empty] | 4.5.8 | BC - Lamps (LED) for Illuminated Signs and Bollards | 52037777 | 2
1/31/2024 Total | [10 empty] | 515
2/29/2024 |  |  | YNE62: M1 J31-32 | YNE62 Closure 1 SB NS | Yes J31 SB exit slip |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038602 | 3
|  |  | YNE63: M1 J32-33 | YNE63 Closure 1 NB NS | Yes NB exit slip verge |  |  | 4.5.7 | BC - Lamps (LED) for Road Lighting | 52038606 | 3
|  |  | YNE64: M1 J33-34 South | YNE64 Closure | Unsure of actual location |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038586 | 12
[5 empty] | No TM required |  |  | 4.5.8 | BC - Lamps (LED) for Illuminated Signs and Bollards | 52038585 | 1
[8 empty] | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038586 | 2
|  |  |  | YNE64 Closure 1 NB NS | Yes NE entry J33 verge |  |  | 4.5.7 | BC - Lamps (LED) for Road Lighting | 52038598 | 2
|  |  | YNE66: M1 J34 North - 35 | YNE66 Closure | No TM required |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038663 | 4
|  |  | YNE68: M1 J35a-36 | YNE68 Closure | No TM required |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038670 | 5
|  |  | YNE69: M1 J36-37 | YNE69 Closure 1 SB NS | Yes |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038634 | 2
|  |  | YNE70: M1 J37-38 | YNE70 Closure | Yes |  |  | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | No jobs raised | 5
|  |  | YNE71: M1 J38-39 | YNE71 Closure | Calder box bridge Access issues no TM required |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038620 | 3
|  |  | YNE72: M1 J39-40 | YNE72 Closure | Calder box bridge Access issues no TM required |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038671 | 1
|  |  | YNE73: M1 J40-41 | YNE73 Closure | No TM required |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038667 | 9
| 2023-07-12 | 2023-08-12 | YNE69: M1 J36-37 | YNE69 Closure 1 NB NS | Yes | 276/8 | 285/0 - 283/6 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038634 | 3
[8 empty] | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038637 | 2
| 2024-12-01 | 1/13/2024 | YNE61: M1 J30-31 | YNE61 Closure 1 SB NS | Yes J31 SB entry verge | 244/8 | 238/8 | 4.5.3 | BCC - Switched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038686 | 2
2/29/2024 Total | [10 empty] | 59
3/31/2024 |  |  | YNE25: A63 Garrison - Southcoates | YNE25 Closure 1 EB NS | Yes |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52036953 | 35
|  |  |  | YNE25 Closure 1 EB OS | Yes |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52036953 | 70
|  |  |  | YNE25 Closure 1 WB NS | Yes |  |  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036971 | 9
|  |  |  | YNE25 Closure 1 WB OS | Yes |  |  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52036971 | 81
|  |  | YNE26: A1033 Southcoates - Northern Gate | YNE26 Closure 1 WB NS | TBC - on Southcoates rbt |  |  | 4.5.4 | BCC - Unswitched Lamps (CDM-T, CDO, SON/T, CPO, MCF/U, MBF/U) | 52038689 | 11
|  |  | YNE27: A1033 Northern Gate - Marfleet | YNE27 Closure 1 WB NS | No TM required |  |  | 4.5.9 | Electrical Testing - Network cabling and electrical components | 52038619 | 2
3/31/2024 Total | [10 empty] | 208
Grand Total | [10 empty] | 1296