ANNEX B TO

SCHEDULE 3 TO

700002428

Performance Management Regime

1.	Key Performance Indicators (KPIs)

1.1	The Contractor’s performance in providing the requirements of the contract shall be measured on the basis of the following Key Performance Indicators:

1.1.1	delivery of management services (Management KPI);

1.1.2	delivery of Command Post Exercises (CPX’s) in accordance with the agreed plan (Delivery KPI)

1.2	The following areas of the requirement will be measured to indicate the Contractor’s performance in providing the service:

1.2.1 	the provision of initial and updated plans and/or reports in accordance with the SOR;

1.2.2	the provision of a single point of contact service;

1.2.3	the provision of a sufficient and suitably qualified contract management team (CMT);

1.2.4	the provision of SME support to CPX planning;

1.2.5	the provision of Technical writers for CPX planning;

1.2.6	the provision of management support for all CPXs;

1.2.7	the provision of training support (to include exercise design, planning, execution and exploitation) to all CPXs;

1.2.8	the delivery of CPXs in accordance with the agreed plan.

1.2.9    the delivery of agreed planning and management information.

1.2.10  the delivery of the Threat Tactics Course (TTC).

1.3	The following table sets out which Key Performance Indicators will be applied to each of the areas set out at 1.2 above:

| Service | Key Performance Indicators applicable |  |
| --- | --- | --- |
|  | Management KPI | Delivery KPI |
| initial and updated plans and/or reports | X |  |
| Single point of contact service | X |  |
| sufficient and suitably qualified contract management team | X |  |
| SME support to CPX planning | X |  |
| Technical writers for CPX planning | X |  |
| management support for all CPX’s |  | X |
| training support (to include exercise design, planning, execution and exploitation) to all CPX’s |  | X |
| delivery of CPXs |  | X |
| Delivery of planning or management information | X |  |
| the delivery of the Threat Tactics Course (TTC). |  | X |

2.	Monitoring and Reporting

2.1	The Contractor shall with the exception of CPXs, monitor its performance of the Contract requirements and shall report its performance against the Key Performance Indicators within the Monthly Management Status Report process to the Monthly Performance Management Meeting.

2.2	The Monthly Management Status report shall reflect any Authority feedback and any instances of failure to provide the requirements of the contract to the standard required by the KPI’s, which are either identified by the Contractor or by the Designated Officer which relate to each monthly payment period.

2.3	 At each Monthly Performance Management Meeting:

2.3.1	the Authority shall inform the Contractor of any additional feedback received which has not been included in the Monthly Management Status Report which indicates that the content of the report may be inaccurate;

2.3.2	the Authority and the Contractor shall consider and discuss the content of the Report and any additional feedback;

2.3.3 	the Contractor shall update the Report to reflect any additional feedback; and

2.3.4	the Authority and the Contractor shall agree any amendments to be made to the Report.

The Authority shall confirm its approval of the Report by signing it.

2.4	For each CPX the After Action Questionnaires (AAQ) that have been finalised in accordance with paragraph 4.1 below shall be submitted for consideration to the next Monthly Meeting.

2.5	The Authority shall review all Management KPI breaches and all AAQ submissions where Delivery KPI breaches have been identified. The Authority shall have the final decision on where KPI remedies are applied.

2.6	In the event of disagreement the matter shall be dealt with in accordance with the provisions of DEFCON 530 - Dispute Resolution (English Law).

Persistent Breach

2.7	Where the Contractor is in persistent breach of the KPI’s the contract shall be in default and condition 2.26 (Termination on Contractor Default) of the Contract shall apply

3.	Management Key Performance Indicator Failures

3.1	Where the Contractor fails to achieve the Management KPI for any of the areas set out at paragraph 1.2 the remedies set out in this paragraph 3 shall apply.

Plans and Reports

3.2	A breach of the Management KPI will occur in relation to the required Plans and Reports where the contractor has failed to provide a complete and accurate Plan/Report to the Authority by;

3.2.1	the date on which it was due in accordance with the Contract; or

3.2.2	where the Authority has informed the Contractor of a new due date, such due date.

3.3	Where a breach of the KPI occurs pursuant to Paragraph 3.2 the Authority shall notify the Contractor of the new due date for the Plan/Report.

Point of Contact Service

3.4	A breach of the Management KPI will occur in relation to the required Single Point of Contact Service e.g. if Single point of Contact is not available as outlined within the Statement of Requirement (Schedule 1 and Annex to Schedule 1).

Contract Management Team

3.5	A breach of the Management KPI will occur in relation to the Contract Management Team where the contractor has failed to provide;

3.5.1 	A sufficient Contract Management Team in accordance with the Contract Management Plan.

3.5.2	A Contract Management Team where all members are suitably qualified.

SME Support

3.6 	A breach of the Management KPI will occur where the Contractor has failed to provide suitable SME support for CPX planning.

Technical Writers

3.7	A breach of the Management KPI will occur where the Contractor has failed to provide suitable Technical writers for the CPX Design and planning meetings.

Breach of Management KPI Remedy

3.8 	For each breach of the Management KPI within any monthly payment period, the Authority shall be entitled to make a deduction of 1% to the Management Fee.

3.9	The Authority shall in any monthly payment period be entitled in total to a maximum deduction equivalent to 5% of the Management Fee for Management KPI breaches.

4.	Delivery Key Performance Indicators

After Action Questionnaire (AAQ)

4.1	The Contractor performance for each CPX shall be measured by use of the After Action Questionnaire (AAQ) at Annex TBC.

4.2	The AAQ is to be completed by the Authority on completion of each Event. The AAQ shall be reviewed by both the Authority and the Contractor within the Post CPX Review Meeting at which point the Contractor may submit mitigation for any failures identified.

4.3	AAQ’s and any provided mitigation shall be reviewed within the Monthly Meeting which shall determine the amount deductible by the Authority for any breach to the KPI.

4.4	The Authority shall have the final decision on whether a KPI breach has occurred and the remedies applied.

Delivery KPI Breach

4.5	A breach of the Delivery KPI will occur where the Contractor has failed to provide;

4.5.1	The agreed number of SQEP Exercise Control (EXCON), White Cell and Opposing Forces (OPFOR) personnel with the correct security clearance;

4.5.2	Any agreed Contractor supplied transportation;

4.5.3	Any personnel identified as being in a Critical Role (including Senior Mentor);

4.5.4	All CPX serials in accordance with the agreed briefing and plans;

4.5.5	Role players (not actors) that are credible and deliver the agreed outcome;

4.5.6	The agreed number of Competent Simulation staff.

4.5.7 	The agreed level of management support;

4.5.8	All AAQ activities to the standard required

4.5.9 	The training support as detailed within the SOR;

4.5.10	The agreed development (including maintenance of courseware) and delivery of the Threat Tactics Course (TTC).

Breach of Delivery KPI Remedy

4.6	Where the Contractor fails to provide serial 4.5.1 in any CPX, the Authority shall be entitled to make an adjustment to the cost stated on the Demand Order Form of an amount equal to the cost of the number of Critical personnel that did not attend the CPX. Where there is no failure of subsequent serials a KPI breach will not be recorded and no further action taken. Where subsequent serial breaches are identified paragraph 4.8 and 4.9 shall apply.

4.7	Where the Contractor fails to provide serial 4.5.2 in any CPX, the Authority shall be entitled to make an adjustment to the cost stated on the Demand Order Form of an amount equal to the cost of the transportation that was not available. Where there is no failure of subsequent serials a KPI breach will not be recorded and no further action taken. Where subsequent serial breaches are identified paragraph 4.8 and 4.9 shall apply.

4.8	Where the Contractor fails to provide any of the serials 4.5.3 to 4.5.9 in a CPX a KPI breach shall be recorded. The Authority shall be entitled to make an adjustment to the cost stated on the Demand Order Form of an amount equal to the cost of the number of Critical Personnel that did not attend the CPX where the Contractor fails to provide 4.5.3. In addition, the Authority shall be entitled to a payment equal to 7% of the overall price of the CPX as stated on the Demand Order Form.

4.9	In addition, where the serials 4.5.3 to 4.5.9 are not provided in full the Authority shall be entitled to a payment equivalent to 1% of the Management Fee.

4.10	Where multiple CPX’s are completed within a monthly payment period the Authority shall be entitled to the remedies set out at paragraphs 4.8 and 4.9. However, a maximum of 3% of the Management Fee may be deducted for Delivery KPI breaches in any monthly payment period.

4.11	Where:

4.11.1	a sum has been deducted from the Contractor pursuant to Paragraph 4.8 – 4.9; and

4.11.2	no Delivery KPI breaches are recorded within the next monthly payment period where a CPX occurs,

The Contractor shall be entitled to a payment equivalent to the amount of the Management Fee deducted pursuant to Paragraph 4.9.

After Action Questionnaire (AAQ)

1. 	The AAQ below forms part of the receipt of services provided and as such it is an auditable document and must be completed for every demand placed upon the contractor.

| CPX NAME/TTC Number (Incl Demand Reference) |  |
| --- | --- |
| EVENT DATES |  |

| Question | Score Yes/No/N/A | Comments |
| --- | --- | --- |
| Did the EXCON have a thorough understanding of the exercise design and deliver control throughout the CPX? |  |  |
| Was the EXCON documentation delivered in an accurate format in a timely manner in accordance with the CPX battle rhythm? |  |  |
| Did the EXCON run the forces synch in accordance with direction from the MEL/MIL serials properly and consider 2nd, 3rd, 4th order consequences in sufficient detail? |  |  |
| Were CPX serials executed in accordance with agreed briefings and plans? |  |  |
| Did the White Cell and OPFOR remain engaged, flexible and proactive throughout the CPX whilst also enacting the direction as laid out by the exercise director, making suggestions where appropriate to improve the experience for the Training Audience? |  |  |
| Were sufficient team leaders deployed in a recognisable and specific C2 Structure to manage the required effect? |  |  |
| Did the OPFOR ‘fight to win’ and properly represent TTPs when demonstrating tactical procedures? |  |  |
| Was the OSW (Blue and Red) of sufficient quality? |  |  |
| Was the OPFOR of suitable SQEP across the Tactical Functions? |  |  |
| Did the CPX data analysis support assurance and improvement functions? |  |  |
| Did the EXCON deliver variable complexity scalable in accordance with the exercise directors direction? |  |  |
| Was the TTC delivered on time? |  |  |
| Is the TTC courseware up to date? |  |  |
| Did the senior mentor have sufficient experience and knowledge to support the divisional commander and staff? |  |  |
| Any additional comments |  |  |
| What aspects of the contractor’s performance overall (if any) were particularly good? |  |  |
| What aspects of the contractor’s performance overall (if any) were particularly disappointing? (Comment on any areas not covered in the preceding questions or expand on comments.) |  |  |
| How can the contracted service be improved? |  |  |
| Contractor’s comments and or mitigations |  |  |

| Signatures (Authority) |  | Signatures (Contractor) Acknowledgement |  |
| --- | --- | --- | --- |
| Name: Appt: Unit: Contact Tel: Email: |  | Name: Appt: Unit: Contact Tel: Email: |  |