## Sheet1
Start Date | End Date | Area | Shift | Work Area | Work Area (MP) | Activity | Grand Total
2024-04-18 | 2024-04-19 | WEST | Nights | M62 WA11 WB NS | 121/1 - 116/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 54.57
2024-04-19 | 2024-04-20 | WEST | Nights | M62 WA15 EB NS | 132/4 - 136/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2
2024-05-09 | 2024-05-10 | WEST | Nights | M62 WA15 WB OS | 136/5 - 132/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 87
2024-05-22 | 2024-05-23 | WEST | Nights | M1 WA05 NB NS | 270/2 - 277/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4792.2
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3035.32
2024-05-23 | 2024-05-24 | WEST | Nights | M1 WA06 NB NS | 277/3 - 284/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 5728.42
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3800.91
2024-05-28 | 2024-05-29 | WEST | Nights | M1 WA07 NB NS | 284/7 - 290/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3016.32
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 812.25
2024-05-29 | 2024-05-30 | WEST | Nights | M1 WA08 NB NS | 290/0 - 296/8 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 5932.08
2024-05-30 | 2024-05-31 | WEST | Nights | M1 WA09 NB NS | 296/8 - 300/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4507.93
2024-05-31 | 2024-06-01 | WEST | Nights | M1 WA09 SB NS | 300/1 - 296/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 5150.12
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 80.4
2024-06-03 | 2024-06-04 | WEST | Nights | M1 WA08 SB NS | 296/1 - 291/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4109.75
2024-06-04 | 2024-06-05 | WEST | Nights | M1 WA07 SB NS | 291/7 - 284/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 5030.56
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 880.92
2024-06-05 | 2024-06-06 | WEST | Nights | M1 WA06 SB NS | 284/0 - 275/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4814.62
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3134.21
2024-06-06 | 2024-06-07 | WEST | Nights | M1 WA05 SB NS | 275/3 - 267/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 5552.13
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1848.98
2024-06-07 | 2024-06-08 | WEST | Nights | M1 WA07 NB OS | 267/1 - 273/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2713.73
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2664.57
|  |  |  | M1 WA07 SB OS | 273/5 - 267/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2329.61
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2128.72
2024-06-10 | 2024-06-11 | WEST | Nights | M1 WA08 NB OS | 273/5 - 277/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4146
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3828
|  |  |  | M1 WA08 SB OS | 277/3 - 273/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1354.91
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1158.73
2024-06-11 | 2024-06-12 | WEST | Nights | M1 WA09 NB OS | 277/3 - 281/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3962.4
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3690.64
|  |  |  | M1 WA09 SB OS | 281/7 - 277/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4116.16
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3712.48
2024-06-12 | 2024-06-13 | WEST | Nights | M1 WA10 NB OS | 281/7 - 286/8 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4449.54
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3996.94
2024-06-13 | 2024-06-14 | WEST | Nights | M1 WA11 NB OS | 286/8 - 291/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2177.73
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1641.07
|  |  |  | M1 WA11 SB OS | 291/7 - 286/8 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1360.26
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 993.64
2024-06-14 | 2024-06-15 | WEST | Nights | M1 WA12 NB OS | 291/7 - 296/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 496.53
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 240.93
|  |  |  | M1 WA12 SB OS | 296/1 - 291/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 463.08
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 126.33
2024-06-17 | 2024-06-18 | WEST | Nights | M1 WA13 NB OS | 296/1 - 300/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 531.4
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 250.28
|  |  |  | M1 WA13 SB OS | 300/1 - 296/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 483.52
2024-06-18 | 2024-06-19 | WEST | Nights | M1 WA01 NB NS | 239/7 - 246/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4325.89
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 120.05
2024-06-19 | 2024-06-20 | WEST | Nights | M1 WA02 NB NS | 246/9 - 254/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 5015.51
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 364.41
2024-06-20 | 2024-06-21 | WEST | Nights | M1 WA03 NB NS | 254/6 - 263/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 8177.12
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 20.11
2024-06-21 | 2024-06-22 | WEST | Nights | M1 WA04 NB NS | 263/2 - 270/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4417.18
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 174.69
2024-06-24 | 2024-06-25 | WEST | Nights | M1 WA04 SB NS | 267/1 - 258/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 5917.05
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 113.21
2024-06-25 | 2024-06-26 | WEST | Nights | M1 WA03 SB NS | 258/0 - 250/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 6326.65
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 453.41
2024-06-26 | 2024-06-27 | WEST | Nights | M1 WA02 SB NS | 250/3 - 244/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3581.21
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 37
2024-06-27 | 2024-06-28 | EAST | Nights | M18 WA11 NB NS | 283/2 - 286/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3840
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2229
|  |  |  | M18 WA11 SB NS | 285/9 - 283/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2852
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2122
|  | WEST | Nights | M1 WA01 SB NS | 244/3 - 239/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3467.29
2024-06-28 | 2024-06-29 | EAST | Nights | M18 WA12 NB NS | 286/5 - 291/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2584
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 661
|  |  |  | M18 WA13 NB NS | 291/6 - 293/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 727
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 368
|  |  |  | M18 WA15 M62 NW LINK NS | NW/0 - 154/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 194
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 135
2024-07-01 | 2024-07-02 | EAST | Nights | M18 WA12 SB NS | 291/0 - 285/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3287
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 487
|  | WEST | Nights | M1 WA02 NB OS | 246/2 - 250/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 82.62
2024-07-02 | 2024-07-03 | EAST | Nights | M18 WA16 M62 ES LINK NS | ES/1 - 291/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 786
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 681
|  | WEST | Nights | M1 WA03 NB OS | 250/3 - 254/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 709
|  |  |  | M1 WA03 SB OS | 254/1 - 250/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 429.18
2024-07-03 | 2024-07-04 | EAST | Nights | M18 WA14 M62 NE LINK NS | NE/1 - 155/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 948
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 822
|  |  |  | M18 WA15 M62 NW LINK OS | NW/0 - NW/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 701
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 590
|  | WEST | Nights | M1 WA04 NB OS | 254/1 - 258/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 319.33
2024-07-04 | 2024-07-05 | EAST | Nights | M18 WA13 NB OS | 292/2 - 293/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 120
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 120
|  |  |  | M18 WA13 SB OS | 293/0 - 292/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 750
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 702
|  |  |  | M18 WA14 M62 NE LINK OS | 293/0 - 155/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1149
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1041
|  |  |  | M18 WA17 M62 WS LINK OS | WS/0 - WS/10 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 61
|  | WEST | Nights | M1 WA05 NB OS | 258/0 - 262/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2241.59
|  |  |  | M1 WA05 SB OS | 262/6 - 258/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2025.97
2024-07-05 | 2024-07-06 | EAST | Nights | M18 WA12 NB OS | 288/5 - 292/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 533
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 276
|  |  |  | M18 WA12 SB OS | 292/2 - 288/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 357
|  | WEST | Nights | M1 WA06 NB OS | 262/6 - 267/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 134.62
|  |  |  | M1 WA06 SB OS | 267/1 - 262/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 147.38
2024-07-08 | 2024-07-09 | EAST | Nights | M18 WA11 NB OS | 283/4 - 288/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3176
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2689
|  |  |  | M18 WA11 SB OS | 288/5 - 283/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 525
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 437
2024-07-10 | 2024-07-11 | EAST | Nights | M180 WA01 CW NS | Ings Outer Ring | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 523
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 112
|  |  |  | M180 WA02 EB NS | 0/0 - 1/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1584
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 642
|  |  |  | M180 WA02 WB NS | 1/3 - 0/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1636
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 644
2024-07-11 | 2024-07-12 | EAST | Nights | M180 WA01 CW OS | Ings Inner Ring | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 654
|  |  |  | M180 WA02 WB OS | 1/4 - 0/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 128
2024-07-12 | 2024-07-13 | EAST | Nights | M180 WA03 EB NS | 1/4 - 11/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 7039
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 6155
|  |  |  | M180 WA03 EB OS | 1/4 - 11/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 613
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 509
2024-07-15 | 2024-07-16 | EAST | Nights | M180 WA03 WB NS | 11/7 - 1/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 7126
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 6168
|  |  |  | M180 WA03 WB OS | 11/7 - 1/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3847
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3452
2024-07-16 | 2024-07-16 | EAST | Days | M181 WA01 NB OS | 9/9 - 12/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 809
|  |  |  | M181 WA01 SB OS | 12/4 - 9/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1452
| 2024-07-17 | EAST | Nights | M180 WA04 EB NS | 11/7 - 19/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4877
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3603
|  |  |  | M180 WA04 EB OS | 11/7 - 19/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2873
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1998
2024-07-17 | 2024-07-17 | EAST | Days | M181 WA01 NB NS | 9/9 - 12/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1854
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1681
|  |  |  | M181 WA01 SB NS | 12/4 - 9/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1288
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1235
| 2024-07-18 | EAST | Nights | M180 WA04 WB NS | 19/1 - 11/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4258
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3015
|  |  |  | M180 WA04 WB OS | 19/1 - 11/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4016
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3458
2024-07-18 | 2024-07-19 | EAST | Nights | M180 WA05 EB NS | 19/1 - 30/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2550
|  |  |  | M180 WA05 EB OS | 19/1 - 30/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 750
2024-07-19 | 2024-07-20 | EAST | Nights | M180 WA05 WB NS | 30/0 - 19/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2459
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 188
|  |  |  | M180 WA05 WB OS | 30/0 - 19/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1497
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 936
2024-07-22 | 2024-07-23 | EAST | Nights | M180 WA06 EB NS | 30/0 - 41/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3533.81
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1399
|  |  |  | M180 WA06 EB OS | 30/0 - 41/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 5667.68
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2939
2024-07-23 | 2024-07-24 | EAST | Nights | M180 WA06 WB NS | 41/1 - 30/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2973.68
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 396
|  |  |  | M180 WA06 WB OS | 41/1 - 30/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 8580.07
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 5920
2024-07-24 | 2024-07-26 | WEST | Nights | A628 WA02 WB NS | Flouch - Crowden | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2957
2024-07-25 | 2024-07-26 | EAST | Nights | A180 WA01 EB NS | 41/1 - 44/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 532.95
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 532.95
|  |  |  | A180 WA05 WB NS | 58/5 - 54/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 891.22
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 266.34
2024-07-26 | 2024-07-27 | EAST | Nights | A180 WA02 EB NS | 44/7 - 48/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 344.31
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 230.03
|  |  |  | A180 WA06 WB NS | 62/6 - 58/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 887.69
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 319.51
2024-07-29 | 2024-07-30 | EAST | Nights | A180 WA02 WB NS | 48/9 - 44/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2406.53
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 583.44
|  |  |  | A180 WA03 EB NS | 48/9 - 51/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 954.03
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 346.62
|  | WEST | Nights | A61 WA01 CW NS | Tankersley Outer Ring | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 432
|  |  |  | A61 WA02 NB NS | 0/7 - 0/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 185
|  |  |  | A61 WA02 SB NS | 0/0 - 0/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 30
2024-07-30 | 2024-07-31 | EAST | Nights | A180 WA03 WB NS | 51/6 - 48/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1282.28
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 505.99
|  |  |  | A180 WA04 EB NS | 51/7 - 54/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1198.14
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 192.25
|  | WEST | Nights | A61 WA02 NB OS | 0/7 - 0/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 182
|  |  |  | A61 WA02 SB OS | 0/0 - 0/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 506
2024-07-31 | 2024-08-01 | EAST | Nights | A180 WA04 WB NS | 54/4 - 51/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 506.71
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 167.08
|  |  |  | A180 WA05 EB NS | 54/5 - 58/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 733.49
2024-08-01 | 2024-08-02 | EAST | Nights | A180 WA01 WB NS | 44/7 - 41/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1475.56
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 936.83
|  |  |  | A180 WA06 EB NS | 58/5 - 62/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2020.02
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 271.39
|  | WEST | Nights | A616 WA03 EB NS | 10/8 - 6/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 555
|  |  |  | A616 WA03 WB NS | 6/7 - 10/8 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2768
2024-08-02 | 2024-08-03 | EAST | Nights | A180 WA01 EB OS | 41/1 - 45/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1364.17
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1054.22
|  |  |  | A180 WA01 WB OS | 45/4 - 41/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3597.58
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3597.58
2024-08-05 | 2024-08-05 | EAST | Days | A160 WA01 EB NS | 0/0 - 1/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 462
|  |  |  | A160 WA01 WB NS | 1/7 - 0/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 398
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 81
| 2024-08-06 | EAST | Nights | A180 WA02 WB OS | 48/9 - 45/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3640.89
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 679.72
2024-08-06 | 2024-08-06 | EAST | Days | A160 WA02 EB NS | 1/7 - 4/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 157
|  |  |  | A160 WA02 WB NS | 4/3 - 1/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 334
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 45
| 2024-08-07 | EAST | Nights | A180 WA03 EB OS | 48/9 - 53/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 864.46
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 493.12
|  |  |  | A180 WA03 WB OS | 53/0 - 48/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3410.28
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1697.45
|  | WEST | Nights | A616 WA07 EB NS | 2/2 - 0/0 | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 121
|  |  |  | A616 WA07 WB NS | 0/0 - 2/2 | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 528
2024-08-07 | 2024-08-07 | EAST | Days | A160 WA01 EB OS | 0/0 - 1/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 409
|  |  |  | A160 WA01 WB OS | 1/7 - 0/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1400
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 173
| 2024-08-08 | EAST | Nights | A180 WA04 EB OS | 53/0 - 57/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1580.68
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1087.19
|  |  |  | A180 WA04 WB OS | 57/1 - 53/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3427.2
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2753.13
2024-08-08 | 2024-08-08 | EAST | Days | A160 WA02 EB OS | 1/7 - 4/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2098
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 479
|  |  |  | A160 WA02 WB OS | 4/3 - 1/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1762
| 2024-08-09 | EAST | Nights | A180 WA05 EB OS | 57/1 - 59/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 176.8
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 59.97
|  |  |  | A180 WA05 WB OS | 59/9 - 57/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3000.07
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2407
2024-08-09 | 2024-08-10 | EAST | Nights | A180 WA06 EB OS | 59/9 - 62/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2133.27
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1614.52
|  |  |  | A180 WA06 WB OS | 62/6 - 59/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4013.9
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3389.34
2024-08-19 | 2024-08-19 | EAST | Days | A162 WA01 NB NS | Ferrybridge | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 870
2024-08-20 | 2024-08-20 | EAST | Days | A162 WA01 SB NS | Ferrybridge | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 850
2024-08-21 | 2024-08-21 | EAST | Days | A162 WA01 NB OS | Ferrybridge | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 143
|  |  |  | A162 WA01 SB OS | Ferrybridge | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1136
2024-08-27 | 2024-08-28 | EAST | Nights | A1T WA02 NB OS | 289/4 - 292/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1184
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1145
|  |  |  | A1T WA02 SB OS | 292/7 - 289/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2116
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2070
2024-08-28 | 2024-08-29 | EAST | Nights | A1T WA03 NB OS | 292/7 - 295/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2238
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2142
|  |  |  | A1T WA03 SB OS | 295/4 - 292/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1845
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1771
2024-08-29 | 2024-08-30 | EAST | Nights | A1T WA04 NB OS | 295/4 - 297/8 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1318
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1318
|  |  |  | A1T WA04 SB OS | 297/8 - 295/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 396
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 365
|  | WEST | Nights | A1M WA04 NB NS | 12/2 - 15/0 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 161
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 161
2024-08-30 | 2024-08-31 | EAST | Nights | A1T WA04 NB NS | 295/6 - 297/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 355
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 158
|  |  |  | A1T WA04 SB NS | 297/7 - 295/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 191
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 191
|  | WEST | Nights | A1M WA04 SB NS | 15/0 - 11/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 82
2024-09-02 | 2024-09-03 | EAST | Nights | A1T WA03 SB NS | 295/9 - 292/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 674
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 246
|  | WEST | Nights | A1M WA03 NB NS | 8/6 - 12/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 93
2024-09-03 | 2024-09-04 | EAST | Nights | A1T WA03 NB NS | 292/7 - 295/6 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 627
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 92
2024-09-04 | 2024-09-05 | EAST | Nights | A1T WA02 NB NS | 289/4 - 292/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 273
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 106
|  |  |  | A1T WA02 SB NS | 292/2 - 288/8 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 457
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 57
2024-09-05 | 2024-09-06 | WEST | Nights | A1M WA03 NB OS | 8/5 - 12/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 475
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 456
2024-09-09 | 2024-09-10 | EAST | Nights | M62 WA21 EB NS | 153/4 - 157/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 481
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 466
2024-09-17 | 2024-09-18 | WEST | Nights | M18 WA01 NB NS | 250/0 - 253/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1743
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 816
|  |  |  | M18 WA01 SB NS | 253/3 - 250/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4667
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 870
2024-09-18 | 2024-09-19 | WEST | Nights | M18 WA02 NB NS | 253/5 - 256/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1881
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 354
|  |  |  | M18 WA08 SB NS | 277/4 - 273/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3352
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1721
2024-09-19 | 2024-09-20 | WEST | Nights | M18 WA02 SB NS | 257/3 - 253/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2526
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 529
|  |  |  | M18 WA03 NB NS | 256/9 - 260/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2189
2024-09-20 | 2024-09-21 | WEST | Nights | M18 WA03 SB NS | 260/9 - 257/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2183
|  |  |  | M18 WA04 NB NS | 260/5 - 264/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2785
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1607
2024-09-23 | 2024-09-24 | WEST | Nights | M18 WA06 NB NS | 264/7 - 268/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4098
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1633
|  |  |  | M18 WA07 SB NS | 273/3 - 268/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1984
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1305
2024-09-24 | 2024-09-25 | WEST | Nights | M18 WA06 SB NS | 268/9 - 264/3 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 4389
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 3375
|  |  |  | M18 WA07 NB NS | 268/7 - 272/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2199
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1717
2024-09-25 | 2024-09-26 | WEST | Nights | M18 WA08 NB NS | 272/7 - 276/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2071
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1577
|  |  |  | M18 WA09 SB NS | 281/1 - 277/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2507
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1737
2024-09-26 | 2024-09-27 | WEST | Nights | M18 WA09 NB NS | 276/7 - 280/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2625
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1844
|  |  |  | M18 WA10 SB NS | 283/2 - 281/1 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2730
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1546
2024-09-27 | 2024-09-28 | WEST | Nights | M18 WA04 SB NS | 264/3 - 260/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1783
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1214
2024-09-30 | 2024-10-01 | WEST | Nights | M18 WA01 NB OS | 250/1 - 253/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1632
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1571
|  |  |  | M18 WA01 SB OS | 253/5 - 250/2 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3433
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2039
2024-10-01 | 2024-10-02 | WEST | Nights | M18 WA02 NB OS | 253/5 - 256/9 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 439
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 122
|  |  |  | M18 WA02 SB OS | 256/9 - 253/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 1699
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1169
2024-10-03 | 2024-10-04 | WEST | Nights | M18 WA04 NB OS | 260/5 - 264/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3046
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 2269
|  |  |  | M18 WA04 SB OS | 264/5 - 260/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 2130
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1702
2024-10-04 | 2024-10-05 | WEST | Nights | M18 WA06 NB OS | 264/5 - 268/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 771
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 771
|  |  |  | M18 WA06 SB OS | 268/7 - 264/5 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 547
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 264
2024-10-08 | 2024-10-09 | WEST | Nights | M18 WA08 NB OS | 272/7 - 276/8 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 519
|  |  |  | M18 WA08 SB OS | 276/8 - 272/7 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 495
2024-10-10 | 2024-10-11 | WEST | Nights | M18 WA10 NB OS | 280/7 - 283/4 | Lump: 4.2.1 - Check all Road Restraint System VRS/PRS | 3074
[6 empty] | Lump: 4.2.2.1 - VRS - Tensioned Corrugated Beam | 1398
Grand Total | [6 empty] | 520022.5