## Sheet1
Highways England Confirmation of Task Order |  |  |  |  | Redacted under Section 40 and Section 43 of the FOI Act (2000)
Confidential and Commercially Sensitive Information which shall not be disclosed to third parties
Supplier: | Atkins
Project Title: | Arena Essex (Northlake) Development Proposal Feb 2019 Additional Work
Contract Ref. | 2589 | CPA No.: | Redacted |  | BPA No.: | Redacted
PIN Description: | Spatial Planning 18-19 | Sub Pin: | 4 |  | PIN No.: | Redacted
HE Reference: | SE 73 18/19ATK | HE Ordering Officer: |  |  | Redacted
Consultant Ref: | 5165058.508 | Consultant Contact: |  |  | Redacted
Start & End Date: | 06/03/2019 - 31/03/2019 | CTO Authorisation No.
Task Overview
Introduction and History: Atkins were tasked in the summer of 2018 to provide support to the Arena Essex Development Proposal. This was agreed as task SE 27 18_19ATK. Highways England (HE) have instructed Atkins to utilise any remaining budget as part of task SE 27 18_19ATK to undertake a review of a number of documents received from Arup on the 12th February 2019. Documents/Information available: • Transport Assessment • Trip Generation Methodology Note • Local Model Validation Report • Lower Thames Crossing Sensitivity Test Note • Northlake Local Area Modelling Report • VISSIM and SEARM model files The remaining SE 27 18_19ATK budget is sufficient to mobilise the wider project team and progress the initial task of reviewing the reports listed above. This new task order is intended to run continuously to allow all outstanding assessment work to be completed, including review of the VISSIM and SEARM models themselves. Information: Arup contact: Redacted Methodology: Atkins (Redacted) will continue to co-ordinate the task and ensure that any Atkins staff engaged on the task are familiar with the locality, development pressures and highway schemes in the area. Atkins will react to any queries from HE and Arup and provide comments. Atkins will continue and complete a review of the SEARM and VISSIM model files provided by Arup. The review of the above information provided will take into account Highways England guidance (The strategic road network – planning for the future) and DfT guidance (DfT Circular 2/13 The strategic road network and the delivery of sustainable development). Please advise if different guidance should be used in our review. Regular communication and progress calls or emails will be maintained with HE (Redacted) and Arup (Redacted). Assumptions • The proposal assumes that the VISSIM Base model (originally prepared by Atkins) is approved by HE and only minimal review of Base Year parameters will be required. Whilst Atkins prepared the original model, the purpose of this review will be to ensure that the model is appropriate for application in this task. • Redacted will attend a maximum of 2no. joint meetings with HE/Arup. • Allowance made for Redacted and Redacted to attend 1no. technical meeting with HE/Arup to discuss strategic and local modelling issues. Amy ? is also working on the task and should be included here. • Whilst one of the outputs is to provide HE with substantive comments before 7th March, the task will continue beyond that date. This CTO is intended to cover work to the end of the 2018/19 financial year and an additional CTO will be required to capture ongoing work in the next financial year. • Provision has been made for a weekly update call with Redacted (HE) and weekly liaison with Arup (Redacted).
Task Objectives and Milestones
Task Objectives: • To make contact with the development transport consultants (Arup) through contact information listed above as required. • To receive and comment on submissions from Arup and provide a response in the form of a note for HE use. As per the original task, the following will be expected: • To be familiar with the HE Licence and planning guidance in respect of new connections/links to the SRN. • Become familiar with the locality of the proposed Arena Essex proposals and of the general area and other development pressures. • Understand how Lakeside Shopping Centre expansion proposals impact the area. • Understand the demands of other developments on M25 J30. • Understand principles of ITS project (Atkins currently working with HE on this) on the locality. • Understand and track the Thurrock Council MRN (Major Road Network) submission for east facing slips at the dumbbell roundabout on the A13. • Arrange to meet with HE Spatial Planning Manager to discuss proposals as required. • Attend meetings/telcons as necessary with developers and/ or HE. Milestones • Initial comments in the form of an email by week ending 1st March which should provide sufficient detail to enable HE to make a formal response to Thurrock Council before 7th March. This will primarily identify queries and/or shortcomings in the reports provided by Arup, however will not include review comments of the SEARM and VISSIM models themselves due to the insufficient time available to review these in detail by the 1st March. • Detailed TN response week ending 8th March or to a revised timescale to be discussed and agreed with HE Spatial Planning Manager. • Contact with Arup including a potential meeting to discuss progress. • Regular update meetings/phone calls between Atkins/HE – frequency to be agreed.
Task Outcomes
• To receive and comment on submissions from Arup and provide a response in the form of a note for HE use. • To have a good knowledge of the proposals. • To attend meetings/telcons to support HE officers or without HE attendance where the discussion is purely technical. • To react to and provide comment to HE on any phone conversations/meetings/submissions relating to the Arena Essex development proposal. • To monitor progress on the Arena Essex proposals and other development/spatial planning issues in the locality.
Project Risk and Management
Risks • The risks are around HE’s possible failure to engage with the developers appropriately and the consequence of that could be that the developer is not able to meet development timescales or financial risk profiles. • There is a risk to the HE strategic road network if the proposals for a new connection to the network are not assessed correctly. • There is a reputational risk to HE if the local planning authority cannot determine this application in accordance with their agreed PPA with the developer and HE are seen as holding back economic growth in the South Essex corridor. • Additional tasks and/or meetings will require additional budget, could affect programme and will be subject to agreement of an additional CE. Management • Contract management – Redacted • Contract co-ordinator – Redacted • Technical Lead – Redacted • Technical Reviewers – Redacted
Project Title: | Arena Essex (Northlake) Development Proposal Feb 2019 Additional Work |  |  |  | HE Reference: | SE 73 18/19ATK
HE Project Sponsor | Sign: |  | Print Name: |  |  | Date:
Management Approver: | Sign: |  | Print Name: |  |  | Date:
Contractual Approval: |  |  | Print Name: |  |  | Date:
Fee Type: | Time Online
Notification of Non Conflict: | Redacted has signed the notification of non conflict or management of conflict for this task
Task History Record | Fee Estimate for the Task set out in this CTO | Invoiced Amount/Estimate this Financial Year |  | Date CTO Confirmed | Fee Amount Requested | HE Sponsor
SE 73 18/19ATK | 13428.41 | 0 |  |  | 13428.41 | Redacted
Fee Estimate / Fee Requested for the scope on this CTO |  |  |  |  | 13428.41
Carry over Amount from previous financial year |  |  |  |  | 0
Previously Invoiced Amount |  |  |  |  | 0
Cumulative Project Fee Estimate (this financial year) |  |  |  |  | 13428.41
Total Project Fee Estimate |  |  |  |  | 13428.41
Name | Grade | Hours |  | Hourly Rate | (£)
Redacted (Atkins Office) | Director | 4 | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | 8 | @ | Redacted | Redacted
Redacted (Atkins Office) | Senior Planner/Engineer | 68 | @ | Redacted | Redacted
Redacted (Atkins Office) | Assistant Planner/ Engineer | 40 | @ | Redacted | Redacted
Redacted (Atkins Office) | Principal Planner / Engineer | 45 | @ | Redacted | Redacted
Redacted (Atkins Office) | Director | 8 | @ | Redacted | Redacted
Redacted (Atkins Office) | Associate Director | 8 | @ | Redacted | Redacted
Redacted (Atkins Office) | Associate Director | 21 | @ | Redacted | Redacted
Redacted (Atkins Office) | Assistant Planner/ Engineer | 24 | @ | Redacted | Redacted
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
|  |  | @ |  | 0
Date Produced: | 2019-03-05 |  | Works Total |  | 13428.41
Confidential and commercially sensitive information which shall not be disclosed to third parties |  |  |  |  | 0
|  |  | Sub Total |  | 13428.41
|  |  | Expenses |  | 300
COMMERCIAL RESTRICTED / FINANCE FILE ONLY |  |  | Total |  | 13728.41