| CHANGE CONTROL NOTICE (CCN) |  |  |  |
| --- | --- | --- | --- |
| Contract Title: | The Provision of Confidential Psychological Support for the Infected Blood Inquiry (The Contract) |  |  |
| Contract Reference: | CCHR19A66 | Contract Change Number: | CCHR19A66-1 |
| Date CCN issued: | Wednesday 21st October 2020 | Date Change Effective from: | Monday 2nd November 2020 |
| Between: The Infected Bloody Inquiry (The Customer) and British Red Cross Community Services Ltd (The Supplier) - The Contract is varied as follows: - The Infected Blood Inquiry wishes to extend its current Contract with British Red Cross Community Services Ltd for the Provision of Confidential Psychological Support. - The current expiry date of the Contract is Monday 2nd November 2020. The Infected Blood Inquiry wish to activate the option to extend as permitted in section 4.2 of the Contract and extend the current provision for four (4) months. The revised expiry date would therefore be Tuesday 2nd March 2021. - The original Contract value is £107,880.00 ex VAT and shall be uplifted to £145,860.00 ex VAT to accommodate the extension period of this Contract. - This is an increase of £37,980.00 ex VAT and is within 50% of the original Contract value. This is in line with Regulation 72 of Public Contract Regulations 2015 and the Light Touch Regime Threshold. - Telephone Support - Total Cost (based on 4 months of costs for Telephone support) REDACTED TEXT. - Face to Face Support – Total Cost (based off 40 days of hearings) REDACTED TEXT. - Additional Costs (Travel, Accommodation, Subsistence, Materials, Equipment and Documentation, Welfare Provision) Total Cost REDACTED TEXT ex VAT. - This indicates a total charge of £37,980.00 ex VAT. - There are no amendments to the deliverables of this Contract. - Words and expressions in this Change Control Notice shall have the meanings given to them in the Contract. - The Contract, including any previous Contract changes, authorised in writing by both Parties, shall remain effective and unaltered except as amended by this Change Control Notice. |  |  |  |
| Change authorised to proceed by: REDACTED TEXT; REDACTED TEXT; 21/10/20. Signature; Print Name and Job Title; Date. |
| Authorised for and on behalf of the Supplier: REDACTED TEXT; REDACTED TEXT; 22.10.20. Signature; Print Name and Job Title; Date. |
| Authorised for and on behalf of the Customer: REDACTED TEXT; REDACTED TEXT; 22/10/2020. Signature; Print Name and Job Title; Date. |