## 1. Preliminaries
Scott sched | Item | Description | Quantity | Unit | Rate | Price
| 1.0 | PRELIMINARIES
| 1.1 | Property and project information
| 1 | POSTAL ADDRESS: 3A Alverton Street Penzance
| 2 | SITE ACCESS: Access points are located on Alverton Street and Buriton Row.
| 7 | CONTRACTORS' PARKING: On-site parking is extremely limited, therefore contractors will need to park off site.
| 8 | ADJOINING LAND/PROPERTIES: Waste and west - attached and is part of a terrace of properties
| 9 | DRIVING RAIN INDEX: Zone 4 'Very Severe'. Contractor to ensure all materials and workmanship are appropriate for this exposure rating.
| 10 | NATURE OF PROJECT: Proposed refurbishment works which comprise:
a. Repairs to external walls and roof
b. Improvements to existing WC and insulation in roof space
c. Works to roof space
e. Other repairs as instructed by CA
Note this package of work forms part of a wider scope of works to be undertaken at the property. The contractor is to make due allowances only for the work scheduled herein.
| 11 | CONTRACTOR DESIGNED PORTIONS (CDPs): Not applicable.
| 12 | ENABLING WORKS: Not applicable.
| 13 | CONCURRENT WORKS BY OTHERS: TBC
| 14 | CONCURRENT OCCUPATION: The property will remain vacant
| 15 | TENDER & CONTRACT DRAWINGS: As included in tender package, appendix A
| 16 | PLANNING PERMISSION: Please see enclosed
| 18 | BUILDING REGULATIONS APPROVAL: TBC.
| 19 | TIMESCALES: Assumed start on site in Q4 2024. Start date and duration of works to be agreed.
| 1.2 | Project team
| 1 | EMPLOYER (CDM CLIENT):
Justin Duance, Contemporary Jewellery
Trengwainton Pumphouse, Tremethick Cross, Penzance. TR20 8UF
Contact: Justin Duance
T: 01736 367254
E: Justin@justind.co.uk
| 2 | OCCUPIER:
Justin Duance, Contemporary Jewellery
Trengwainton Pumphouse, Tremethick Cross, Penzance. TR20 8UF
Contact: Justin Duance
T: 01736 367254
E: Justin@justind.co.uk
| 3 | CONTRACTOR (CDM PRINCIPAL CONTRACTOR - PC):
To be appointed
| 4 | SURVEYOR:
Hosken Parks Limited
Okehampton Business Centre, Higher Stockley Mead, OKEHAMPTON EX20 1FJ
Contact: Phillip Parks
T: 01837 659911
M: 07528 102931
E: pparks@hoskenparks.co.uk
| 5 | CDM PRINCIPAL DESIGNER (PD) - PRE-CONTRACT:
Cornwall Planning Group
Chi Gallos, Hayle Marine Renewables Business Park, North Quay, Hayle, TR27 4DD
T: 01736 448500
E: office@cornwallplanninggroup.co.uk
| 6 | CONTRACT ADMINISTRATOR AND QUANTITY SURVEYOR:
Hosken Parks - as clause 1.2.4 above
| 1.3 | Tendering information
| 1 | PRE-TENDER SITE VISIT: Before tendering, ascertain the nature of the site, access thereto and all local conditions and restrictions likely to affect the execution of the Works.
| 2 | ACCESS FOR SITE VISITS: By prior arrangement with the occupier - see clause 1.2.2.
| 3 | FULLY INCLUSIVE TENDERS: Tenders must include for all materials and workmanship shown or described in the tender documents or clearly apparent as being necessary for the complete and proper execution of the works.
| 4 | ACCEPTANCE OF TENDERS: The Employer offers no guarantee that any tenders will be accepted and will not be responsible for any costs incurred in preparation of tenders.
| 5 | EXPIRY OF TENDERS: Tenders shall remain open for not less than three calendar months from date of submission.
| 1.4 | Contract information
| 1 | FORM OF CONTRACT: JCT Minor Works Building Contract (MW 2016).
| 2 | CONTRACT PARTICULARS: Refer to appendix B for details of proposed insertions and amendments.
| 1.5 | Health and safety information (CDM 2015)
| 1 | RELEVANCE: The Construction (Design and Management) Regulations 2015 (CDM 2015) will apply.
| 2 | CONTRACTOR'S ROLES: The Contractor shall act as the Principal Contractor (PC).
| 3 | NOTIFICATION STATUS: To be confirmed. PD to submit F10 to HSE on behalf of Employer if notifiable.
| 4 | OBJECTIVES: Zero incidents during construction and zero/minimal residual risks post-construction.
| 5 | PRE-CONSTRUCTION INFORMATION (PCI): Comprises the information herein plus any and all other information provided by Employer and PD.
| 6 | CONSTRUCTION PHASE PLAN: Prior to setting up the site, the PC shall prepare a suitable and sufficient construction phase plan. Thereafter the PC shall keep the plan updated throughout the construction phase.
| 7 | KEY TASKS: The PC shall carry out, inter alia, the following health and safety tasks:
a. Carry out risk assessments for site activities and COSHH assessments for materials to identify foreseeable risks.
b. Apply the General Principles of Prevention/Hierarchy of Control to eliminate (or reduce and control) risks.
c. Prepare method statements for demolitions, work at height and other high risk activities.
d. Provide and maintain suitable and sufficient resources, supervision, inductions, training and specialist support.
e. Provide and maintain suitable and sufficient access, support, protection, tools, plant, equipment and PPE.
f. Provide and maintain suitable and sufficient site security and physical segregation.
g. Provide and maintain suitable and sufficient fire safety and emergency procedures.
h. Comply with latest version of Construction Leadership Council's site operating procedures for Covid-19.
i. Comply with other relevant health and safety legislation, regulations and approved codes of practice.
| 8 | HEALTH AND SAFETY HAZARDS: The hazards listed below are known or presumed, but there could be others:
A. KEY HAZARDS RELATED TO DESIGN:
No significant/unusual hazards anticipated
B. KEY HAZARDS RELATED TO SITE:
Convent to remain occupied during the works
Adjoining church to remain open during the works
Loose render to elevations
Decay and disrepair to external doors and windows
Broken panes to perimeter lightwell in quadrangle
Deficient guardings to retaining walls and bank
Broken glass embedded in tops of garden/retaining walls
Very severe weather - Zone 4 coastal location
Live services
Asbestos-containing materials (ACMs)
Potential lead paint
C. KEY HAZARDS RELATED TO CONSTRUCTION:
Demolitions
Work at height
Fire
Vehicle and plant movements
Lifting operations
Loading and unloading
Manual handling
Plant, equipment and power tools
Construction dusts - silica, cement, wood, etc
Substances hazardous to health - COSHH
Noise
Slips, trips and cuts
Site security
Sunlight/UV radiation
D. KEY POST-CONSTRUCTION/IN-USE HAZARDS:
Proposed works create no additional hazards.
| 9 | ASBESTOS-CONTAINING MATERIALS (ACMs): Do not disturb unidentified materials. omission further surveys, sampling and removals by accredited surveyors and licensed contractors as appropriate. Comply with Control of Asbestos Regulations 2012.
| 10 | SITE WELFARE FACILITIES: The Contractor shall provide suitable and sufficient welfare facilities in a location(s) to be agreed with Employer, and ensure they are kept clean, tidy and well stocked at all times.
| 11 | HEALTH AND SAFETY FILE: The Contractor shall provide a health and safety file to the Employer on completion of the works, to include the below. The file shall provided in electronic (PDF) and hard copy (4-ring binder) formats:
a. Brief description of work carried out.
b. Residual hazards and how they have been dealt with.
c. Key structural principles and safe working loads.
d. Hazardous materials used.
e. Removal/dismantling of installed plant/equipment.
f. H&S for cleaning/maintenance equipment provided.
g. Details and locations of significant services.
h. Operating and maintenance manual.
i. As-built drawings if applicable.
| 1.6 | Carrying out the works
| 1 | MANAGEMENT: The Contractor shall provide suitable and sufficient resources to ensure that the project is planned and managed effectively, including - but not limited to - procuring labour, materials, plant and tools; planning and co-ordinating design and site activities; supervising, snagging and de-snagging the works; ensuring services are tested and commissioned; obtaining completion certificates, guarantees and warranties; liaising with the Employer and project team, neighbours, statutory authorities, utilities, etc.
| 2 | COMPETENT PERSONS: The works shall be carried out by appropriately skilled and experienced contractors and operatives who are approved by the relevant manufacturers, members of relevant trades associations and competent persons schemes and registered with the Construction Skills Certification Scheme.
| 3 | NUISANCE: The Contractor shall take all necessary steps to prevent nuisance from dust, debris, noise, smoke, vermin and other causes, and shall minimise disruption and inconvenience. Smoking will not be permitted on site. Playing of radios/music will not be permitted on site. Bonfires and hot working will not be permitted on site.
| 4 | REMOVAL OF WASTE: Unless stated otherwise, all materials, waste and spoil arising from the works shall become the property of the Contractor, and shall be removed frequently from site and disposed of appropriately. Provide waste transfer and consignment notes.
| 5 | POWER AND WATER: The Contractor may use the Employer's electricity and water, however the Employer offers no warranty as to their suitability.
| 6 | CONTRACTOR'S SIGN BOARD: The Contractor may erect a sign board to aid site identification for contractors and suppliers. Details to be agreed.
| 7 | ALTERNATIVE PRODUCTS: Manufacturers and/or product references stated herein are given to indicate the minimum standard and quality that will be acceptable. Alternatives of equivalent quality may be acceptable but must be separately identified by the Contractor at the time of tender and may only be used with the CA's consent.
| 8 | MATERIALS AND WORKMANSHIP: Comply with all relevant Building Regulations, British and European Standards and Codes of Practice, trade association best practice, manufacturers drawings, specifications, installation instructions, safety data sheets and the like.
| 9 | COMPLETENESS OF MATERIALS AND WORKMANSHIP: Materials, products and workmanship shall include (and the work descriptions herein are deemed to include) all preparatory works and ancillary materials, components, fixings, adhesives, sealants, software and the like necessary for proper and complete installation.
| 10 | CONTRACTOR'S DESIGNED PORTIONS: Provide design services for the CDP packages listed in section 1.1 including providing Contractor's Proposals with tender and Technical Submission of drawings and documentation to the Employer in good time to allow for comments and revisions without causing delays to programme.
| 11 | DEFECTIVE DESIGN, MATERIALS AND WORKMANSHIP: Immediately any design, materials or workmanship is known or appears to be not in accordance with the contract, submit proposals for making good, adjustment of contract sum or removal and re-execution.
| 12 | STRUCTURAL AND CARCASSING TIMBER: Shall be kiln dried, graded, regularised and pressure/vacuum treated to BS8417 as appropriate to end use class.
| 13 | SAMPLES: The Contractor shall provide materials and product samples, colour swatches and pre-fabrication drawings for comment/approval by the Employer, and shall do so in good time to prevent delays.
| 14 | DEFINITIONS:
REMOVE: Means disconnect, dismantle as necessary and remove the stated element, work or component and all associated accessories, fastenings, supports, linings and bedding materials, and dispose of unwanted materials whilst taking all necessary care to avoid damaging elements to be retained. It does not include removing associated pipework, wiring, ductwork or other services.
REPLACE: Means remove the stated existing components, features and finishes. Provide and fit in lieu new components, features or finishes which, unless specified otherwise, must match those which have been removed. Make good as necessary.
REPAIR: Means carry out local remedial work to components, features and finishes as found in the existing building, re-secure or re-fix as necessary and leave in a sound and neat condition.
MAKE GOOD: Means carry out local remedial work to components, features and finishes which have been disturbed by other, previous work and leave in a sound and neat condition to match existing.
EASE: Means make minor adjustments to moving parts of the stated component to achieve good fit in both open and closed positions and ensure free movement in relation to fixed surrounds. Make good as necessary.
TO MATCH EXISTING: Means use products, materials and methods to match closely all visual characteristics and features of the existing work, with joints between existing and new work as inconspicuous as possible, all to approval of appearance.
| 15 | TEMPORARY LIGHTING: Provide and maintain suitable and sufficient lighting as necessary to enable the proper and safe execution of the works.
| 16 | TEMPORARY ACCESS: Provide and maintain suitable and sufficient scaffolding, edge protection and/or other access plant/equipment to enable safe working at height.
| 17 | TEMPORARY PROTECTION: Provide and maintain suitable and sufficient weather, dust, debris, impact and security protection to prevent damage to property and persons.
| 18 | TEMPORARY SUPPORT: Provide and maintain suitable and sufficient temporary structural and earthwork support to enable safe works to structures and excavations.
| 19 | CLIMATIC CONDITIONS: Keep accurate record of climatic conditions and delays due to adverse weather, including description of weather, types of work affected and number of hours lost.
| 20 | EXTENSIONS OF TIME: Give notice in accordance with Contract as soon as delays or likely delays become apparent. Provide further information as required by CA, and for weather-related EOT claims provide Met Office Downtime Reports for duration of contract.
Sub-total

## 2. Dayworks rates
Scott sched | Item | Description | Quantity | Unit | Rate | Price
| 2.0 | RATES FOR DAYWORKS, OVERHEADS AND PROFIT
| 1 | DAYWORKS DEFINITION: Dayworks shall be in accordance with Option 'B' of the 'Definition of the Prime Cost of Dayworks Carried Out under a Building Contract' published by the RICS, current at the date of tender. Plant and equipment costs shall be in accordance with the 'Schedule of Basic Plant Charges' published by the RICS, current at the date of tender.
| 2 | DAYWORKS RATES: Provide all-inclusive (i.e. inclusive of all incidental costs, overheads and profit) hourly rates and percentage additions for the following: |  |  | Rates only
a. Roofer (hourly rate)
b. Leadworker (hourly rate)
c. Carpenter (hourly rate)
d. Mason (hourly rate)
e. Plasterer/renderer/boarder (hourly rate)
f. Electrician (hourly rate)
g. Plumber (hourly rate)
h. Painter and decorator (hourly rate)
i. Labourer/unskilled operative (hourly rate)
j. Materials (% addition)
k. Plant (% addition)
| 3 | MAIN CONTRACTOR'S OVERHEADS AND PROFIT: Provide OH&P percentage addition applicable to sub-contracts.

## 3. Provisional sums
Scott sched | Item | Description | Quantity | Unit | Rate | Price Grant Funded | Price Employer Funded
| 3.0 | PROVISIONAL SUMS
Include the following provisional sums to be expended on receipt of written instructions from the CA or deducted from final account:
| 1 | Allow a provisional sum to undertake ad hoc roof repairs including fascias and soffits |  | PS |  | 5000
| 2 | Supply and install loft ladder |  | PS |  | 750
| 3 | Contingencies. |  | PS |  | TBC
| 4 | Skirtings and architraves - provisional allowance |  | PS |  |  | 1000
| 5 | Kitchenette - supply and installation |  | PS |  |  | 5000
| 6 | Window seat - supply and installation |  | PS |  |  | 750
[5 empty] | Sub-total | 5750 | 6750
Install any needed extra foundation for the stanchion posts if the ground level is lowe for aco drains

## 4. Lot 1
Scott sched | Ref | Trade | Location | Room | Title | Description | Quantity | Unit | Rate | Price
MEASURED WORKS
| 1 | Preliminaries |  |  |  | Contractor to provide a breakdown of their proposed preliminary costs
| 1.2 | Scaffold
| 1.3 | Asbestos surveys and removals: |  |  |  | Survey completed and included in tender package
Sub-total
| 2 | Roof
| 2.01 | Guttering | External | Front elevation | Repair and re-route gutter | Replace the cast iron gutter with cast iron and re route the downpipe removing the hopper on the north wall.
| 2.02 | Allow a provisional sum to undertake ad hoc roof repairs included fascias and soffits | External | General | External repair | General roof repairs, provisional scope unknown. |  |  | PS
Room 7 roof needs replacing. All roof replacements to be dry lay small slates of two or three different sizes to give the same look as the original roof.
Sub-total
| 3 | Demolition and Removals
| 3.01 | Demolition | Toilet block | 15 | Remove corridor wall | Remove external plywood walls and carefully strip the masonry ensuring the tiles don't get broken. Remove the door between the toilet and outshot 2 and any carpentry.
| 3.02 | Demolitions | Ground floor | 15 | Remove sanitaryware
Sub-total
| 4 | External walls and metalwork
| 4.01 | Masonry | External | West gable wall | West gable wall painting | Paint the render as necessary with either a cream masonry paint or if lime rendered paint with a breathable hydrophobic paint
| 4.02 | Masonry | External | West gable wall | Main Chimney stack rebuild | Take down the main chimney and rebuild with the appropriate lead tray and flashing. Make sure the flues are covered with a vented cowl.
| 4.03 | Masonry | External | West gable wall | Reduced brick stack flashing | Clean out the vegetation and inspect the flashing replacing any flashing and pointing as necessary
| 4.04 | Masonry | External | West gable wall | Gable wall render repair | Inspect the rendering on the west gable wall replace if needed. Re-point and render in an appropriate fibre reinforced lime render
| 4.05 | Masonry | External | East gable wall | Repointing | Repoint decayed pointing and replace the flaunching on the chimney
| 4.06 | Masonry | External | East gable wall | Clear out vegetation | Clear vegetation from the flashing and inspect for any damage
| 4.07 | Masonry | External | East gable wall | Chimney stack inspect | Inspect the chimney stack for any moisture ingress and repair and re-point as necessary
| 4.08 | Masonry | External | East gable wall | Barge slates | Refix and replace any missing barge slates
| 4.09 | Masonry | External | Safe room | Repair guttering | Repair and replace missing guttering. Drainage replacement is under Yard category
| 4.10 | Masonry | External | Safe room | Roof coverings | Remove and re cover to match existing. Small slates of differing sizes to match the current. Re flash and re-slate the top of the roof into the neighbours wall.
| 4.11 | Masonry | External | Safe room | Paint external walls | Paint the render on the external walls of the safe room
| 4.12 | Masonry | External | Rear elevation | Guttering inspection | Check the guttering for any leaks. Repair and clean any vegetation
| 4.13 | Carpentry | Kitchen | 7 | Remove and fill the window | Remove the north easterly window and fill. It can look like a blanked off rendered window from the outside.
| 1.14 | Masonry | External | 15 | Corridor stanchions | Brush the loose metal away with a wire brush, prime and repaint with black metal paint.
| 1.15 | Masonry | Toilet block | 15 | Make good corridor boarder | Make good the removed corridor wall adding new tiles
Sub-total
| 5 | Walls and Ceilings
| 5.01 | Carpentry | Toilet block | Toilet | Insulate corridor toilet | Dry line and Insulate the walls with 50mm insulated plasterboard and vapour barrier if needed.
| 5.02 | Carpentry | Toilet block | Toilet | Insulate main building toilet | Dry line and Insulate the walls with 50mm insulated plasterboard and vapour barrier if needed.
| 5.03 | Masonry | Toilet block | 15 | Remove ceiling insulate and replaster ceiling | Remove the old lath and plaster ceilings and beam coverings insulate with pir insulation where possible and plasterboard and re-plaster. On the external ceiling insulate and use moisture resistant plasterboard and plaster with appropriate plaster.
| 5.04 | Masonry | Generally | 15 | Allowance to repair and make good existing ceilings ready for decoration
Sub-total
| 6 | Mechanical and electrical
| 6.01 | Masonry | Toilet block | Toilet | Add hole for extractor fan | Make sure there are holes in place for the extractor fans in both toilets
| 6.02 | Plumbing | Toilet block | Toilet | Install toilet and basin | Install a toilet and basin in the outdoor toilet.
Supply
Installation
| 6.03 | Plumbing | Toilet block | Toilet | Install toilet and basin | Install a toilet and CORNER basin in the main building toilet.
Supply
Installation
| 6.04 | Heating | all | all | Installation of radiators | Installation of radiators and pipe runs in each room of the building
[5 empty] | Supply | Traditional style aluminium radiators anthracite grey.
| 6.05 | Electrics | Toilet block | Toilet | Fit extractor fan | Fit an appropriate extractor fan in each toilet
| 6.06 | Security | all | all | Install concertina blinds | Install concertina blinds on all ground floor windows and rear upstairs windows including room 7 Internaly. Using fillets to make them sit nicely in the reveals.
|  |  | all |  | Supply and install internal grilles as quotation
Supply
[5 empty] | Installation | Use fillets to make them sit nicely in the reveals
Sub-total
| 7 | Windows and External doors
First floor
| 7.01 | hardwood double glazed sash window full spray finish 2no primer 2no top coat approx 925x2300 | First floor |  | Replacement windows | Remove existing and provide new windows as described including decoration and ironmongery. Allow a PC sum of £50 per window for supply only of ironmongery. Note make good reveals with lime mortar
| 7.02 | hardwood double glazed sash window full spray finish 2no primer 2no top coat approx 925x2300 | First floor |  | Replacement windows | Remove existing and provide new windows as described including decoration and ironmongery. Allow a PC sum of £50 per window for supply only of ironmongery. Note make good reveals with lime mortar
| 7.03 | hardwood double glazed sash window full spray finish 2no primer 2no top coat approx 1150x2300 | First floor |  | Replacement windows | Remove existing and provide new windows as described including decoration and ironmongery. Allow a PC sum of £50 per window for supply only of ironmongery. Note make good reveals with lime mortar
| 7.04 | casement window hardwood double glazed full spray finish 2noprimer 2no topcoats 1040x1800 | First floor |  | Replacement windows | Remove existing and provide new windows as described including decoration and ironmongery. Allow a PC sum of £50 per window for supply only of ironmongery. Note make good reveals with lime mortar
| 7.05 | casement window hardwood double glazed full spray finish 2noprimer 2no topcoats 910x1500 | First floor |  | Replacement windows | Remove existing and provide new windows as described including decoration and ironmongery. Allow a PC sum of £50 per window for supply only of ironmongery. Note make good reveals with lime mortar
Ground floor
| 7.06 | hardwood double glazed sash window full spray finish 2no primer 2no top coats 1200 x2000 | Ground floor |  | Replacement windows | Remove existing and provide new windows as described including decoration and ironmongery. Allow a PC sum of £50 per window for supply only of ironmongery
| 7.07 | hardwood double glazed sash window full spray finish 2no primer 2no top coats1160x1950 | Ground floor |  | Replacement windows | Remove existing and provide new windows as described including decoration and ironmongery. Allow a PC sum of £50 per window for supply only of ironmongery
Sub-total
| 8 | Internal doors | Not applicable
| 9 | Flooring including finishes | Not applicable
| 9.1 | Masonry |  | Ground floor | Replacement floor structure | Remove existing timber boards and floor structure to ground floor reception ensuring that the cladding fireplace and timber details are retained, Retain the floorboards for future use. 2x offices and dispose of material off site.
Prepare pump and lay P300 Blinding mix, 175mm thick
Prepare concrete and lay 300mm EPS floor grade Insulation, DPM, Plastic Vapour barrier with joints taped and lapped to the wall with 100mm Perimeter strip to all perimeter walls and internal wall partitions in the 2x GF offices, Corridor and Reception.
Supply and lay single layer of A393 mesh over insulation in preparation for laying of New Concrete floor.
Supply and lay C35 S3 concrete with 10mm Aggregate, 125mm thick. Provide power float finished with graphite surface colour hardener incorporated into the finish
Sub-total
| 10 | Roof including attic
| 10.01 | Carpentry | Attic | 6 | Relocate opening for loft hatch and supply and fit new hatch and ladder | Create a bigger loft hatch 570x1150 and install a pull down ladder.
Form / adjust opening
[6 empty] | Supply and install ladder (provisional) |  |  | PS
| 10.02 | Carpentry | Attic | Attic | Insulate attic | Insulate the loft with 275mm insulation
| 10.03 | Carpentry | Attic | Attic | Create loft walkway and storage area | Create a walkway between the hatches and each gable wall above the insulation layer. Also create a small storage area at the top of the access hatch.
Sub-total
| 11 | Fixtures and fittings | Not applicable
| 12 | Decoration | External | Yard |  | Clean and prepare render in external courtyard and redecorate in colour to be confirmed
Sub-total
| 13 | External works
| 13.01 | Masonry | External | Yard | Lowering paving | Break up the concrete from around the walls of the building and lower the ground level so that the level is below the level of the internal floor level. Make sure all vents are clear and have pest covers. Have any excess material taken away
| 13.02 | Masonry | External | Yard | Gravel on weed suppressant membrane | Lay gravel on weed suppressant membrane
| 13.03 | Masonry | External | Yard | Disabled slope from back gate. | Create a sloped walkway 1:12 steepness from the back gate up to the height of the yard. This is for wheelchair access.
| 13.04 | Masonry | External | Yard | Foundation | Install any needed extra foundation for the stanchion posts if the ground level is lowe for aco drains
| 13.06 | Masonry | External | Yard | Drainage: installation of new drainage runs | Make sure all external drainage runs are in place and install new drainage runs from the safe room and outshot 2.
Install new Aco adjacent existing building entrance
| 13.07 | Masonry | External | Yard | Heat pump plinth | Build a concrete plinth for the heat pump to sit on. 1400mm x 800mm
Sub-total

## 4. Lot 2
Scott sched | Ref | Trade | Location | Room | Title | Description | Quantity | Unit | Rate | Price
MEASURED WORKS
| 1 | Preliminaries |  |  |  | Contractor to provide a breakdown of their proposed preliminary costs
Sub-total
| 2 | Roof |  |  |  | Not applicable
| 3 | Demolition and Removals
| 3.01 | Demolition | 1st floor | 5 | Remove internal wall | See section 5.02 room 1 for details.
| 3.02 | Carpentry | Ground floor | 13 | Make a doorway | Make a doorway into corridor 14 from room 13 at the room 10 end.
| 3.03 | Demolition | Ground floor | 14 | Remove internal wall | Remove internal north wall
| 3.04 | Demolition | Ground floor | 12 | Remove seating
| 3.05 | Demolition | Hallway | 9 | Staircase | Remove carpet and dispose off site
Sub-total
| 4 | External walls and metalwork |  |  |  | Not applicable
| 5 | Walls and Ceilings
| 5.01 | Carpentry | 1st floor | 1 | insulate west gable arches | Remove shelves from above the panelling. Scrape off loose paint and plaster in the arches. Dry line the arches with 62.5mm pir insulated plasterboard and plaster. Make good the dado rail extending it to match in.
| 5.02 | Carpentry | 1st floor | 1 | Remove the wall into room 5 | Open up the wall into room 1 to create a wide arch (allowed for above). Plaster and make good and add architrave to match the arches on the gable wall
| 5.03 | Plastering | 1st floor | 1 | Lime plaster any broken plaster | Scrape off and repair or re-plaster loose plaster in lime. Mainly on the gable walls
| 5.04 | Plastering | 1st floor | 1 | Make good electrical works | Make good any chasing or damage cause by electrics installation.
| 5.05 | Carpentry | 1st floor | 2 | Make good electrical works | Make good any chasing or damage cause by electrics installation.
| 5.06 | Carpentry | 1st floor | 2 | insulate west gable arches | Scrape off loose paint and plaster in the arches. Dry line the arches with 62.5mm pir insulated plasterboard and plaster. Make good the dado rail extending it to match in.
| 5.07 | Plastering | 1st floor | 3 | Make good electrical works | Make good any chasing or damage cause by electrics installation.
| 5.08 | Carpentry | 1st floor | 3 | Make good electrical works | Make good any chasing or damage cause by electrics installation.
| 5.09 | Carpentry | 1st floor | 5 | Make good plaster | Scrape off any loose plaster and make good using lime. Make good any chasing or damage caused by the electrics installation.
| 5.10 | Plastering | 1st floor | 6 | Make good electrical works | Make good any chasing or damage cause by electrics installation.
| 5.11 | Carpentry | Kitchen | 7 | Remove cladding and dry line | Remove all the internal cladding, dryline and insulate with at least 50mm PIR insulation. Thicker insulation to be used if there is space. Use an appropriate vapour barrier.
Plasterboard and skim coat of plaster to new walls
| 5.12 | Plastering | Ground floor | 10 | Make good electrical works | Electrics are being surface mounted on the ground floor but there will be some damage from old electrics removal. which will need to be repaired.
| 5.13 | Plastering | Ground floor | 10 | Replaster or repair walls | Scrape off loose paint and plaster and re plaster where required in lime or fill in lime plaster
| 5.14 | Carpentry | Ground floor | 12 | Stud wall the door into stairwell | Because the wall is moving we need to remove this door and architrave fill with stud wall and plaster and reinstate a matching piece of skirting.
| 5.15 | Plastering | Ground floor | 12 | Make good electrical works | make good electrics. They are being surface mounted but there will still be some damage caused by removal of the old electrics.
| 5.16 | Carpentry | Ground floor | 13 | Reinstate Dado and skirting | Replace or repair missing or rotten skirting or panelling with similar style woodwork
| 5.17 | Plastering | Ground floor | 13 | Make good plaster | Make good any broken or missing plaster after wall installation and electrics installation.
| 5.18 | Plastering | Ground floor | 14 | Make good plaster | Make good any broken or missing plaster after wall installation and electrics installation.
| 5.19 | Plastering | Ground floor | 13 | Make good plaster | Make good any broken or loose plaster. Make good the plaster after electrics installation
| 5.20 | Carpentry | Ground floor | 14 | Rebuild internal wall | Rebuild internal wall 1m to the closer to the window from it's original location making the corridor into a 2m Ish room. Soundproof with insulating batts and acoustic plasterboard. Remove the door the wall now covers and make good. Replaster
| 5.21 |  | Ground floor | 9 | Insulate East gable wall? | Need to add stairway/hallway wall resolution. Discuss with Justin
Sub-total
| 6 | Mechanical and electrical
| 6.01 | Carpentry | all | all | Remove wiring | Once the electrician has disconnected the electrics remove all surface mounted and unwanted wiring.
| 6.02 | Plumbing | 1st floor | 7 | Plumb kitchen | install drainage and hot and cold water to the kitchen sink along the east gable wall
| 6.03 | Carpentry | Ground floor | 10 | Electrics cupboard | build a small cupboard around the consumer units to match in with the tongue and groove cladding
| 6.04 | Plumbing | Ground floor | 10 | Plumb workshop sink | Install drainage and hot and cold water for the workshop sink
| 6.05 | Electrics | All | All | Re wire existing supplies | See the electrics plan
Sub-total
| 7 | Windows and External doors
| 7.01 | Carpentry | Ground floor | 9 | Back door | Supply and install new steel door https://www.lathamssteeldoors.co.uk/steel-security-doors/high-security-steel-door/
Sub-total
| 8 | Internal doors
| 8.01 |  | All | Ground floor | Existing internal doors | Fit fire doors matching the current doors as closely as possible FD30. All marked on the plan.
| 8.02 |  |  | Ground floor | External single door to WC | Refurbish and paint
| 8.03 |  |  | Ground floor | Existing double doors in hallway - allow a provisional sum for refurb | Redecorate current double doors and frame.
Sub-total
| 9 | Flooring including finishes
| 9.01 | Carpentry | Ground floor | All | Thresholds | Make thresholds between the tiled floor and floated concrete floor
| 9.02 | Carpentry | Ground floor | 9 | Repair broken steps | Repair broken steps and make good for the installation of a stair carpet.
| 9.03 | Flooring | Ground floor | 9 | Supply and install stair carpet. Allow a PC sum of £35/m2 supply only | Install the chosen stair carpet.
| 9.04 | Carpentry | 1st floor | Entire floor | Make floors good for sanding | Sand all the floor boards on the 1st floor.
| 9.05 | Carpentry | Ground and first floor | all | Skirtings and architraves - provisional allowance | Allow a provisional sum for repairs and replacement where necessary |  |  | PS
Sub-total
| 10 | Roof including attic |  |  |  | Not applicable
| 11 | Fixtures and fittings
| 11.01 | Carpentry | Kitchen | 7 | Supply and installation of kitchen including white goods - provisional | Install a simple flatpack kitchen with microwave, sink, small hob, fridge and oven. And shelves for microwaves |  |  | PS
| 11.02 | Carpentry | Kitchen | 7 | Install loft hatch and insulate | Create a bigger loft hatch opening, 570x1150 check the loft and roof timbers are okay.
| 11.03 | Carpentry | Ground floor | 12 | Window seat | Allow a provisional sum for the supply and installation of a window seat |  |  | PS
Sub-total
| 12 | Decoration
| 12.01 | Decorating | Generally | 1 | Decorating | Prepare new and existing internal walls and timber including doors ready for decoration
Decorate walls , ceilings and woodwork including doors and windows (mist coat and two top coats of emulsion for walls and ceilings and pimer, undercoat and two top coats for timber surfaces)
Sub-total
| 13 | External works
| 13.01 | Masonry | External | External Safe room | Build extraction housing | Build a small lean-to shed on the gable end of the safe room internally 1m deep 1.9m high and 2.4m wide. To be built on a new concrete slab comprising timber frame superstructure, walls lined with 18mm OSB internally and clad externally in powder coated corrugated cladding to walls and roof
Sub-total

## 5. Price summary
Scott sched | Item | Description | Price Grant Funded | Price Employer Funded
| 5.0 | PRICE SUMMARY
| 1 | Preliminaries | NA | NA
| 2 | Rates for dayworks, overheads and profit | NA | NA
| 3 | Provisional sums | 5750 | 6750
| 4 | Measured works:
|  | 1. Preliminaries | 0 | 0
|  | 2. Roof | 0 | NA
|  | 3. Demolition and Removals | 0 | 0
|  | 4. External walls and metalwork | 0 | NA
|  | 5. Walls and Ceilings | 0 | 0
|  | 6. Mechanical and electrical | 0 | 0
|  | 7. Windows and External doors | 0 | 0
|  | 8. Internal doors | NA | 0
|  | 9. Flooring including finishes | 0 | 0
|  | 10. Roof including attic | 0 | NA
|  | 11. Fixtures and fittings | NA | 0
|  | 12. Decoration | 0 | 0
|  | 13. External works | 0 | 0
|  | Total (Excluding VAT)- carry forward to form of tender | 5750 | 6750