Measuring heritage engagement by Lower Socio-Economic groups in Heritage Lottery Fund supported projects

Organisation	Heritage Lottery Fund

Department	Strategy and Business Development

Title of procurement	Measuring heritage engagement by Lower Socio-	Economic groups

Brief description of supply	Research project for use by HLF in strategic planning

Estimated value of tender	£15,000 maximum, including VAT

Estimated duration	January – March 2018

Name of HLF Contact	Liz Ellis

Timetable	Response deadline: 10am, 6 December 2017

Clarification and Negotiation meetings (if required): 11 December (am) or 13 December (pm)

Confirmation of contract: By 15 December 2017

Completion of research: 29 March 2018

# 1.	Overview

  - The Heritage Lottery Fund (HLF) was set up in 1994 under the National Lottery Act and distributes money raised by the National Lottery to support projects involving the national, regional and local heritage of the United Kingdom. We operate under the auspices of the National Heritage Memorial Fund (NHMF). Since April 2013 we have been operating under our current Strategic Framework: ‘A lasting difference for heritage and people’. See the HLF website for more details.

  - HLF invests in the full breadth of the UK’s heritage and, through our funding, we aim to make a lasting difference for heritage and people. This is reflected in the outcomes for heritage, people and communities which underpin our grant-making.

  - We want to ensure our grant-making is inclusive. To date, we have viewed inclusion with reference to the Equality Act, 2010 and focused on the impact of our funding on groups of people with protected characteristics, such as disabled people, LGBT communities, and black, Asian and minority ethnic communities. In our new strategic framework we plan to reach people from lower socio-economic groups more effectively as another dimension of our inclusion strategy.

  - First, this research will focus on increasing HLF’s understanding of how well HLF-supported projects have engaged lower-socio economic groups so far, based on an analysis of HLF data from two grant programmes (Our Heritage and Heritage Grants). Secondly, after reviewing our current performance, the research should recommend ways we can improve how we define and collect data and measure impact about lower-socio economic groups from HLF funded projects.

  - In our open grant programmes, Our Heritage (£3k-£100k) and Heritage Grants (over £100k), we currently collect data on lower socio-economic groups in three ways:

- We include a monitoring question within the application form which asks applicants:

‘If your organisation represents the interests of a particular group, tell us by filling in the table below’ and includes the option to tick a box ‘People in lower socio-economic groups’, accompanied by an explanatory note: ‘People living in households with incomes below the national average, or people living in the most deprived local authority wards in England, Scotland, Wales or Northern Ireland.’

The majority of applicants to HLF choose to tell us that their organisation represents 	everyone in society rather than particular groups. Since 2008, 203 successful 	applicants have told us their organisation represents the interests of ‘people in lower 	socio-economic groups’.

- We conduct a survey one-year after the end of projects with all of Our Heritage and Heritage Grant grantees. We ask three questions about the different types of beneficiary a project might engage:

‘Of the [visitors in the last 12 months/volunteers/trainees] approximately what percentage were from the following socio-economic groups?’ and provide options in line with ONS categories including ‘Semi-routine and routine’ and ‘Long-term unemployed and Never worked’.

Survey respondents are asked which survey method helped them arrive at the 	figures. In past surveys we have additionally asked ‘Do you currently have 	information on the breakdown of your visitors by social grade?’ and invited 	percentage returns based on four categories AB, C1, C2 and DE. Relatively few of 	our grantees provide data in response to these questions; perhaps up to 100 in each  	quarterly survey in recent years.

- In addition, all second-round applicants to the Heritage Grants programme submit an Activity Plan, which sets out which groups of people (beneficiaries) they aim to reach with their project. We provide guidance on producing an Activity Plan.

  - After the data above has been reviewed and cross referenced with a small number of other research and evaluation studies we have conducted, a baseline of our effectiveness in engaging lower-socio economic groups thus far will emerge. The review should highlight any issues with the robustness of current data, outline gaps in collection, and make clear recommendations for ways in which HLF can improve future practice.

  - The main audience for this research is senior HLF staff. The research may be shared on our website for the benefit of heritage sector colleagues and wider audiences.

# Method

  - A method for the work is open for consultants to propose. However, we anticipate that an initial review will entail analysis of secondary data from Our Heritage and Heritage Grants supplied by HLF. The recommendations could benefit from qualitative insights gained from, for example, telephone interviews with other grant making organisations, including Lottery Distributors, about their practice, and interviews with a sample of HLF supported projects to understand experiences of data collection and the challenges of reaching the lower-socio economic audience.

  - In order to make a meaningful impact with our funding, we want to understand more about what our current data tells us about our current reach to lower-socio economic groups and what we can do to improve how we collect data and how we report impact moving forward. These are some of the questions we anticipate the research will address directly or help to answer:

- How can we improve our data collection requirements across the life-cycle of a project?

- Are we using appropriate language and terminology?

- What are the gaps in our data or the ways in which we analyse the information we hold, and how might be address any gaps?

- What does the data we hold tell us about our engagement with and impact on lower-socio economic groups thus far?

- Is there any commonality amongst the types of grantee organisations who have told us at application stage that their organisations represent the interests of people in lower-socio economic groups?

- Do these grantee organisations have particular insights that we can learn from?

- Are some types of grantee organisations (e.g. local authorities, housing associations) better at collecting meaningful data than others and, if so, what might this mean for our process and requirements?

- How are other comparable funders, including Lottery Distributors such as Big Lottery Fund and Creative Scotland, collecting and reporting on data relating to their impact on lower-socio economic groups? Is there an opportunity to align work?

- What barriers, if any, do grantees face in collecting data on lower-socio economic groups?

- In what ways have grantees a) successfully benefited people in lower-socio

economic groups; b) faced barriers in successfully benefitting people in lower-socio economic groups?

- Where grantees have successfully reached people in lower-socio economic groups, what factors contribute to project success that might be shared with our applicants, e.g. the importance of partnership working with trusted community organisations, strong contacts with non-heritage sectors such as supported housing, employment, etc.

- How might we at HLF take forward our work in this area?

# Outputs

  - The following outputs will be required:

- a draft final report in Word, including a number of case studies demonstrating impact with beneficiaries from lower socio-economic groups;

- a final report in Word;

- any other reports as set out here or agreed between HLF and the contractor; and

- a set of research data, to be stored in a readily accessible electronic format such as Excel and accessible infographic formats.

  - All reports must adhere to HLF’s accessibility and formatting guidance (appended).

  - The initial findings will be confidential to HLF. HLF may prepare or commission summary reports and other materials for subsequent wider distribution, based on the results.

  - All reports to include appendices as agreed between HLF and the contractor. The contents and structure of the report to be agreed in advance of writing. All reports to be supplied in electronic format and hard copy if requested.

  - All bidders are required to adhere to all appropriate regulations and guidelines on the collection, storage, transmission and destruction of personal data (MRS/SRA, Data Protection Act 1998: Guidelines for Social Research, April 2013).

# Contract management

  - We expect the research/evaluation to begin in January 2018 and be completed by March 2018. The final report shall be submitted to HLF by 29 March 2018.

  - The anticipated budget is £15,000 to include all expenses and VAT. The contract will be let by the National Heritage Memorial Fund.

  - The payment schedule will be 20% to be invoiced at the start of the research in January 2018 with the remaining 80% on completion, to be invoiced by 3 April 2018.

  - The contract will be based on the HLF standard terms and conditions.

  - The research will be managed on a day to day basis for HLF by Liz Ellis.

# Award Criteria

  - A proposal for undertaking the work should include:

- a detailed method for undertaking the study;

- details of staff allocated to the project, together with experience of the contractor and staff members in carrying out similar projects. The project manager / lead contact should be identified;

- the allocation of days between members of the team;

- the daily charging rate of individual staff involved;

- a timescale for carrying out the project;

- an overall cost for the work.

  - Your Bid will be scored out of 100%.

50% of the marks will be awarded to Quality

Each question will be scored using the methodology in the table below.

Tender responses submitted will be assessed by HLF against the following Quality Questions:

- To what extent does the tender response demonstrate an understanding of the issues related to this research brief?

- To what extent is the method appropriate to the research requirements set out in this brief?

- What is the extent of the experience of similar heritage and social research?

- How well has the tenderer structured a research team in order to successfully manage the contract and deliver the required work to the budget and timetable required by HLF?

## Quality Questions scoring methodology

| Score | Word descriptor | Description |
| --- | --- | --- |
| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the HLF confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the HLF confidence in the ability of the Bidder to deliver the contract. Meets the HLF’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the HLF a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the HLF a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in most respects. |

50% of marks will be awarded for Price.

The evaluation of price will be carried out on the Schedule of charges you provide in response to Table A.

## Price Criterion at 50%

- 50 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in your schedule of charges table will be used to score this question.

- For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 50% (full marks) for price and the second placed bidder gets 46% and so on. (8/100 x 50 = 4 marks; 50-4 = 46 marks)

- The scores for quality and price will be added together to obtain the overall score for each Bidder.

## Table A - Schedule of Charges

Please show in your tender submission, the number of staff and the amount of time that will be scheduled to work on the contract with the daily charging rate.

Please complete the table below providing a detailed breakdown of costs against each capitalised description, detailing a total and full ‘Firm Fixed Cost’ for each element of the service provision for the total contract period. Bidders may extend the tables to detail additional elements/costs if required.

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this contract.

As part of our wider approach to corporate social responsibility the National Heritage Memorial Fund/Heritage Lottery Fund prefers our business partners to have similar values to our own. We pay all of our staff the living wage (in London and the rest of the UK) and we would like our suppliers and contractors to do likewise. Please highlight in you proposal/tender/bid whether you do pay your staff the living wage.

Bidders shall complete the schedule below, estimating the number of days, travel and subsistence costs associated with their tender submission.

TABLE A: (firm and fixed costs)

| Cost | Post 1 @cost per day (No of days) e.g. Project Manager/ Director @ £2 | Post 2 @cost per day (No of days) e.g. Senior Consultant/manager/researcher @£1.5 | Post 3 @cost per day (No of days) Junior Consultant/equivalent e.g. £1 | Total days | Total fees |
| --- | --- | --- | --- | --- | --- |
| Inception meeting to agree plans and finalise requirements with the Fund | Example 0.5 | 1 | 1.5 | 3 | £4 |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |

| Cost Type | Value (£) |
| --- | --- |
| Sub - Total |  |
| VAT |  |
| Total* |  |

*(This must include all expenses as well as work costs; this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements set out in the ITT).

Notes: HLF reserves the right to clarify quality and prices and to reject tenders that demonstrate an abnormally low quality response. HLF also reserves the right to amend the timetable of work where required.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

# Procurement Process

  - HLF reserves the right to reject abnormally low scoring tenders. HLF reserves the right not to appoint and to achieve the outcomes of the research/evaluation through other methods.

  - The procurement timetable will be:

- Deadline for clarification questions: 10am on 27 November 2017*

- Tender return deadline: completed proposal to be returned to HLF by 10am Wednesday 6 December 2017.

- Clarification/Negotiation meetings** may be held with shortlisted consultants and would take place on either Monday 11 December, afternoon, or Wednesday 13 December, morning. Please hold one or both slots if possible.

- HLF will notify bidders of our procurement decision by 15 December 2017.

*HLF will upload responses to clarification on our website by close of play on 29 November, here.  Please note that we will make the anonymised questions, and our responses to them, available to everyone on the HLF website; we will not respond to individual enquirers directly.

**We reserve the right to carry out clarifications if necessary; these may be carried out via email or by inviting bidders to take part in a clarification meeting. In order to ensure that both HLF’s and Bidder’s resources are used appropriately, we will only invite up to three (the ultimate number will depend on the closeness of the scores) highest scoring bidders to attend a clarification meeting. Scores will be moderated based on any clarifications provided during this meeting. You are responsible for all your expenses when attending such meetings in person.

  - Your tender proposals must be sent electronically via e-mail before the tender return deadline of 10am on Wednesday, 6 December 2017 to the following contact:

Diane La Rosa

Heritage Lottery Fund

Holbein Place

London

SW1W 8NL

Diane.la.rosa@hlf.org.uk

  - Please visit the HLF website for further information about the organisation.

# Appendix: Accessibility and formatting guidance

HLF is committed to providing a website that is accessible to the widest possible audience. Our site is annually tested by accessibility auditors and we must meet a AA compliance level. Our accessibility testing encompasses not just site functionality and design but all of our content, including downloadable documents.

Reports and other documents created for HLF (including the tender submissions) need to be clear, straightforward to use and ready to circulate internally, externally and online, as well as suitable for use by screen reading software. Best practice in accessibility is summarised below:

## Readability

In the final report, and all other documents that may be published online including the tender application consultants should ensure that:

- The size of the font is at least 11pt;

- There is a strong contrast between the background colour and the colour of the text. Black text on a white background provides the best contrast. This also applies to any shading used in tables and/or diagrams;

- Italics are only used when quoting book titles for citations and items on the reference list should be arranged alphabetically by author

- Colour formatting and use of photos should be of a resolution size that is easily printable and does not compromise the printability of the document.

For further guidance on ensuring readability of printed materials, please refer to the RNIB Clear Print guidelines. These can be found on the RNIB website.

## Accessibility

Reports should adhere to the following guidelines:

## Formatting

Headings and content in your document should be clearly identified and consistently formatted to allow easy navigation for users. Heading Styles should be used to convey both the structure of the document and the relationship between sections and sub-sections of the content. Heading styles should follow on from each other i.e. Heading 1 then Heading 2.

## Spacing

Screen readers audibly represent spaces, tabs and paragraph breaks within copy, so it is best practice to avoid the repetitive use of manually inserted spaces. Instead, indenting and formatting should be used to create whitespace (e.g., use a page break to start a new page, as opposed to multiple paragraph breaks).

## Alternative text

Alt text is additional information for images and tables. This extra information is essential for both document accessibility (screen reading software reads the Alt text aloud) and for the web. Alt text should be concise and descriptive, and should not begin with ‘Image of’ or ‘Picture of’.

## Images

These should be formatted in-line with text, to support screen readers. Crediting pictures may be necessary, usually in response to a direct request from a third party.

## Tables

These should be for used for presenting data and not for layout or design. They should be simple and include a descriptive title. The header row should be identified and there shouldn’t be more than one title row in a table. There should be no merged or blank cells.

## Additional documents

Any additional information, separate to the report, for example proformas and transcripts which may be used as standalone documents must be fully referenced to the piece of work being submitting and therefore dated, formatted and numbered appropriately.

## Acknowledgement

All reports should acknowledge HLF. Our logo can be found on the HLF website.

## Further resources

Please refer to the WCAG 2.0 article on PDF techniques for further information.

Submitting your report to HLF

Please check the accessibility of your document using the Word accessibility checker before submitting: File – Info – Check for Issues – Check Accessibility.

Please submit your document as a Word file.

HLF retains the right to amend documents in order to create accessible versions for publishing.