## Sheet1
Plymouth Marjon University Campus Development Plan
Clarification Log
Clarification No | Date Received | Clarification | Clarification Response | Date Issued
1 | 23rd May 2019 | Updates to Selection Questionniare Question 6.5 - OLD QUESTION - Weighting 20% Candidates are required to set out the processes that your organisation has deployed to previous projects to ensure consideration and application of current construction methods and best practise products and technologies that delivered a sustainably designed and constructed building that delivered low carbon emissions. Please provide details to demonstrate how you have used and considered current and proposed building construction methods, products and technologies to deliver a well-designed, usable and sustainable building with low carbon emissions. | The orignial Selection Questionnaire has been removed from Contracts Finder and replaced with the updated version. 6.5 - Now asks:- Weighting 20% Candidates are required to set out the processes that your organisation has deployed to previous projects to ensure consideration and application of current design and construction methods and best practise products and technologies that delivered a sustainably designed and constructed building that delivered low carbon emissions. Please provide details to demonstrate how you have used and considered current and proposed building design and construction methods, products and technologies to deliver a well-designed, usable and sustainable building with low carbon emissions. | 23rd May 2019
2 | 23rd May 2019 | Updates to Selection Questionniare Question 6.6 - OLD QUESTION - Weighting 5%. Candidates are required to provide details on how you have been proactive in raising awareness of relevant industry standards and best practise that during the delivery of the contact/project to reduce energy and water consumption. Please provide details of your approach together with the outcomes and effects you were able to influence and achieve. | The orignial Selection Questionnaire has been removed from Contracts Finder and replaced with the updated version. 6.6 - Now asks:- Weighting 5%. Candidates are required to provide details on how you have been proactive in ensuring relevant industry standards and best practise have been implemented during the delivery of the contact/project to reduce energy and water consumption and the results at post-occupancy stage. Please provide details of your approach together with the outcomes and effects you were able to influence and achieve. | 23rd May 2019
3 | 23rd May 2019 | Updates to Selection Questionniare Question 6.8 - OLD QUESTION - Weighting 5% Plymouth Marjon University are fortunate enough to have a deer herd on Campus; Please provide details of the measures that you have put in place to ensure that protected wildlife is not damaged or disturbed. Please provide details to explain how you have put appropriate measures in place that have been effective in ensuring that protected wildlife in not damages or disturbed throughout this project. | The orignial Selection Questionnaire has been removed from Contracts Finder and replaced with the updated version. 6.8 - Now asks:- Weighting 5% Plymouth Marjon University are fortunate enough to have a biodiverse campus of flora and fauna, including a deer herd which roams through the Campus; Please provide details of the measures that you have put in place to ensure that the biodiversity is enhanced rather than damaged or disturbed. Please provide details to explain how you have put appropriate measures in place that have been effective in ensuring that the biodiversity is enhanced rather than damaged or disturbed throughout this project. | 23rd May 2019
4 | 23rd May 2019 | We have acquired the information related to the above masterplan process but cannot see an indication of which specific disciplines the OJEU relates to. Are you only after an architect at this stage or a wider team? If you are after a wider team, can you clarify which disciplines need to be included within each bid? |  | 23rd May 2019
5 | 23rd May 2019 | Please can we clarify if the site visits stated below are for June or July? Plymouth Marjon University wishes to invite interested suppliers to attend a Site Visit on either: - (please note these will be allocated on a first come first serve basis) • 10th July 2019 @ 10:30 to 12:30 or 14:00 to 16:00 • 11th July @ 10:30 to 12:30 or 14:00 to 16:00 • 12th July @ 10:30 to 12:30 or 14:00 to 16:00 • 16th July 2019 @ 10:30 to 12:30 or 14:00 to 16:00 • 17th July 2019 @ 10:30 to 12:30 or 14:00 to 16:00 | Plymouth Marjon University are applying the Restricted Procedure; this is a two stage process. The first stage is the completion and return of the Selection Questionnaire only; This aspect of the procedure assesses supplier experiences, knowledge and skills, and is essentially backward looking. For those suppliers who are shortlisted – the 2nd stage of the process will involves the completion of the Statement of Requirements and pricing information; which is the quality and forward looking requirements, accordingly the site visits are part of this part of the process. The Public Contracts Regulations 2015; require procurers to make a full suite of tender documents available at the beginning of the process; Should you feel that a site visit would benefit you in completing and submitting your Selection Questionnaire please let me know and I will look to make the necessary arrangements. | 24th May 2019
6 | 24th May 2019 | In relation to section 4.3 of the Selection Questionnaire, please could you clarify what is the required annual turnover for candidates? | The estimated contract value is £200,000.00 which is the required turnover; As you know the 2015 Procurement Regulations allow contracting authorities to apply a turnover of up to twice the estimated contract value (£400,000.00); but we believe a more realistic and sensible value is the £200,000.00 contract value. | 4th June 2019
7 | 28th May 2019 | We would like to submit for the above-named tender and just wanted to clarify if the submission is to be made directly by email to this address (ie not to a portal), and that it should consist of simply the selection questionnaire (plus attachments) in the first instance? (We are assuming that the tender documents are provided for information at this stage.) | Yes the Selection Questionnaire are attachments are the only aspect that needs to be submitted at this stage. These are to be sent to the procurement@marjon.ac.uk email address as opposed to a portal. The Public Contract Regulations 2015 require a full suite of tender documents to be made available to all suppliers from day one and so yes these are for your information at this time. | 4th June 2019
8 | 28th May 2019 | Could you please confirm if the deadline is 17/06 as per the notice or 24/06 as per the selection Questionnaire? Also can you confirm that that Final Invitation to Tender word document is for information only at this stage? | The submission date and time for the Selection Questonnaire is midday on 24th June - an amendement to the OJEU Notice has been requested. | 4th June 2019
9 | 28th May 2019 | Please can you advise the FTP address to upload our SQ response onto | The Selection Questionnaire and associated attachments are to be submitted electronically to procurement@marjon.ac.uk email account as opposed to a portal. | 4th June 2019
10 | 28th May 2019 | Following the release of clarification questions with the tender documents, I am still unclear as to whether you would like us to submit a full design team, or if you are looking for architects only? | At this stage – Plymouth Marjon University only require the completion and submission of the Selection Questionnaire; however, noting that your clarification is fundamental to the next stage of the process. We can confirm that the delivery team will require the following disciplines and specialisms:- Project Management, Architectural and Design, Cost Consultancy, Civil and Structural Engineering etc | 4th June 2019
11 | 28th May 2019 | Please can you advise on the design services required for the Development Plan. | Please refer to clarification 4 for response information | 4th June 2019
12 | 28th May 2019 | Must we use the template provided or is ok to use our own in house template keeping in line with the page counts/font sizes as requested by you? | As we have received extensive interest in this opportunity we require responses to be returned on our templates as these will be familiar to our evaluations teams. | 4th June 2019
13 | 29th May 2019 | 1. For the avoidance of doubt, could you please confirm that it is only the Selection Questionnaire document to be answered and returned at this stage? i.e. The Commercial Pricing Schedule & the questions contained within the Specification document are just for reference at this stage and to be answered at ITT stage if shortlisted? 2. Is the University looking for a Project Manager led team? 3. Are we able to submit our responses to Section 6.0 of the SQ in a separate document that is clearly referenced? | 1. The Public Contracts Regulations 2015 have made it a compulsory requirement to issue a complete tender pack at day one of The Restricted Procedure; Stage one of this procedure requires the completion and submission of the Selection Questionnaire and associated attachments only – with the remaining documents being applied to those who are shortlisted. 2. In recognition of the required disciplines and specialisms – a project management and ethos will be required to support and manage a multi-disciplinary team. 3. Our preference is that the tables are used wherever possible as this is easier for the evaluations team. | 4th June 2019
14 | 31st May 2019 | Regarding this Tender opportunity. Please confirm whether the questions within the specification document need to be answered in addition to the Selection questionnaire? | The Public Contracts Regulations 2015 have made it a compulsory requirement to issue a complete tender pack at day one of The Restricted Procedure; Stage one of this procedure requires the completion and submission of the Selection Questionnaire and any associated attachments only – with the remaining documents – ITT, Specification & Pricing Schedule etc., being applied to only those who are shortlisted. | 4th June 2019
15 | 1st June 2019 | I note in the ITT document, that as regards terms and conditions, the following is included:- “By submitting a Tender, Tenderers are agreeing to be bound by the JCT Design and Build 2016 Terms and Conditions of this ITT and the form of Contract without further negotiation or amendment. PLYMOUTH MARJON UNIVERSITY CANNOT NEGOTIATE WITH ANY TENDERER ABOUT THE TERMS AND CONDITIONS OF THE CONTRACT.” Can you please confirm that this is the form of contract, and that there are no other terms and conditions, other than those contained within the ITT document. | I can confirm that no other terms and conditions will apply to this procurement and resultant project from those identified in the documents issued. | 4th June 2019
16 | 3rd June 2019 | If we are acting as a Lead Consultant with sub-consultants delivering, for example, landscape design are we required to provide a completed Standard Selection Questionnaire for each sub-consultant? If so, should this include a completed Part 3 for each sub-consultancy? Do you have page or word limits are set for the answers to questions 6.1 to 6.8 in Section 6 | No – only the ‘lead’ organisation is required to complete the Selection Questionnaire as any ultimate contract will be between Plymouth Marjon University and the lead organisation, and it is understood that the Lead Organisation will perform their own due diligence checks of their sub-contractors. – That said there are sections within the Selection Questionnaire that require completion when utilising the services of sub-contracts – namely:- Question Number 1.2(a) - (i) up to and including 1.2(b) - (ii). We haven’t included a word limit – but please ensure that your response targets/addresses the salient points of each question. | 4th June 2019
17 | 3rd June 2019 | Clarification 1 - In section 4.2 of the, Selection Questionnaire: ‘Where we have specified a minimum level of economic and financial standing and/ or a minimum financial threshold within the evaluation criteria for this procurement, please self-certify by answering ‘Yes’ or ‘No’ that you meet the requirements set out.’ Please confirm if there is a minimum level of economic and financial standing required? Clarification 2 - In section 6.1 of the Selection Questionnaire: Candidates are required to provide details of up to three relevant examples of contracts, that demonstrate your organisation’s experience in delivering similar services….. Where consultants will be a sub-consultants to a lead consultant, are sub consultant’s contract case studies able to be included or do these have to be only from the lead consultant? | Clarification 1 The estimated contract value is £200,000.00 which is the required turnover; As you know the 2015 Procurement Regulations allow contracting authorities to apply a turnover of up to twice the estimated contract value (£400,000.00); but we believe a more realistic and sensible value is the £200,000.00 contract value. Clarification 2 Our preference would be that the reference sites are linked to the lead organisation – as any resultant contract will be between Plymouth Marjon University and the lead organisation. (The lead organisation is essentially responsible for undertaking due diligence checks on their sub-contractors). As I am sure you have noted this section allows a statement to be submitted should it be difficult to provide 3 examples. | 4th June 2019
18 | 3rd June 2019 | Could you advise if there is a page count / limit for the responses to 6.5, 6.6, 6.7 and 6.8? Also should the responses to these questions be entered straight into MS Word document? Can we provide the response to 6.4 as a separate pdf attachment? | We haven’t included a word limit – but please ensure that your response targets/addresses the salient points of each question. Our preference would be that the template provided is used for all responses as the evaluators are familiar with this format – embedded documents are permitted – but please ensure that you don’t PDF the final version as to do so means that we will be unable to open/access the embedded documents. | 4th June 2019
19 | 3rd June 2019 | Please can you provide clarification on the following items 1. Address of the site we can upload information to (ref, p17) 2. Word limit and page limit for questions 6.1, 6.3 – 6.8 3. Can we submit our response using our own document format with the questions clearly identified. Or 4. Should we complete the word document and provide images, diagrams and certificates as appendices | 1. The Selection Questionnaire is to be submitted electronically at procurement@marjon.ac.uk by midday on Monday 24th June 2019 2. We have purposely not included a page limit to these questions – that said tenderers are encouraged to address the salient points of the questions 3 & 4. Our preference would be that the template provided is used for all responses as the evaluators are familiar with this format – embedded documents are permitted – but please ensure that you don’t PDF the final version as to do so means that we will be unable to open/access the embedded documents. | 4th June 2019
20 | 4th June 2019 | 1. Could you please confirm the word count for question 6.1 (details of where you have been able to demonstrate added value through the adoption of innovative solutions), and for questions 6.3 to 6.8). 2. Would you please confirm if the University will be commissioning a space utilisation analysis directly or whether this role should form part of our team’s role? 3. We assume the University will have already commissioned a detailed building condition survey – please confirm if you expect this to be provided as part of our team 4. Would you please confirm that the questions in the Specification and Statement of Requirements document are those to be answered for the ITT? | 1. Marjon have purposely not included a word count for the questions in the Selection Questionnaire that said it is imperative that tenders provide a succinct responses that address the salient points. 2. Marjon have conducted a week long space utilisation survey which will be made available to the successful bidder. 3 Marjon does have an existing condition survey, but with is approximately 3 or 4 years old so elements may need to be updated. – This may not be required as part of this programme – but could be included as an option. 4. The Public Contract Regulations 2015; require a full tender pack to be issued to all tenderers on day of the Restricted Procedure; the first phase of this process requires the completion and submission of the Selection Questionnaire only – as you have noted the remaining documents will be ‘applicable for completion’ by those suppliers who are shortlisted. | 5th June 2019
21 | 4th June 2019 | 1. As the SQ response is required within the PMU word document, can a separate document of images of the contract examples be provided by the applicant? 2. Is there a maximum limit to number of pages for the SQ? 3. Is there an anticipated timescale for completion of the development of the Campus masterplan? 4. There is a reference within the document to entering into contract for an initial 2 year period, does this relate to programme for the development of the Campus Masterplan? 5. The pricing schedule provided within the ITT implies the application team should be made up of 9 specialists – please can you confirm if this is what is expected – and within the £200k fee? 6. Is there a suggested scope of services available for the following: Business Strategist, Feasibility Consultant, Investment Specialist? 7. Will existing buildings conditions survey’s be appointed separately by the University? | 1 Our preference is that where possible documents are embedded – if this isn’t an option as long as any attachments are clearly referenced these are permitted. 2 No only where page limits have been stated are they applicable 3 We have purposely not included a timeline as these are difficult to determine at this point of the process – this will however, be a key topic post contract. 4 In recognition that the Campus development will essentially be a ‘live’ document – we have built in some flexibility to review and perhaps make amendments to the development should student numbers significantly increase etc., 5 The specialisms detailed are to recognise the key skills/input required – it maybe that some organisations have other skills or role titles to those we have identified – or some staff may be multi-skilled/disciplined etc., - The £200k fee is for the production of the Campus Development Plan in its entirety. 6. The scope of the project is detailed in the specification and the associated business plan 7. Marjon does have an existing condition survey, but with is approximately 3 or 4 years old so elements may need to be updated. – This may not be required as part of this programme – but could be included as an option. | 7th June 2019
22 | 4th June 2019 | Please can you confirm how the JCT Design and Build 2016 Contract would be implemented for a Campus Development Plan as the Contract is for Construction, not for professional services.' | Please accept our apolgies the Terms and Conditions will be the JCT CA (Consultancy Agreement) & NOT the JCT Design and Build | 7th June 2019
23 | 4th June 2019 | 1. Does the term ‘planner’ in the pricing schedule document refer to a Masterplanner or a Planning Consultant? 2. Can the architect as lead consultant carry out the role as Project Manager and Masterplanner? | 1. The term planner has been included to capture the skills of a Master-planner – that said, should you believe that the project would benefit from a planning consultant – this can be added to the pricing schedule. 2. If the lead consultant has the required skills and capacity to also be the Project Manager and Master-planner, this is acceptable | 7th June 2019
24 | 5th June 2019 | Could we also ask do we need to include CV’s for the full proposed design team including engineers, planners, cost consultants, etc. at this stage or would that be required at the ITT stage. | The procurement procedure does not allow us to replicate technical ability questions in the ITT stage of the procedure; therefore our requirements is seeking a short CV for each key team member. | 7th June 2019
25 | 5th June 2019 | 1. Is Product Liability Insurance of £2m required for this contract? We hold the other forms of cover, but not Product Liability Insurance. 2. The masterplan will inform the Universities Capital Project framework to 2025, which appears to conflict by the OJEU notice stipulating a 120 month (10 year) contract period, and the contract end date in the Contract Finder listed as September 2024 (5 years). The bidder’s day presentation states that implementation of the framework will occur from 2020-2025, does this mean the actual masterplan will be formed over roughly a year long process? 3. Section 6 contract examples – from the previous clarifications, are we to include project text and images as appendices to the back of the submitted SQ response in word document format? | 1. Please note it is not essential for suppliers to hold Product Liability Insurance of £2m; 2. It is the ambition that the Campus Development plan is delivered as soon as reasonably possible – the contract term …. is to enable Plymouth Marjon University to revisit/amend/update the Campus Development plan; should student numbers significantly increase/decrease - as we wouldn’t want to re-procure what would essentially be amendments/updates to the plan – our preference is to work with the original authors etc., 3. Where possible we ask for as much information to be added/embedded to the key document – that said, if this is not possible then as long as attachments are clearly referenced these are acceptable. | 10th June 2019
26 | 5th June 2019 | 4.1 – please could you advise if we are to provide copies of the accounts as appendix to the questionnaire of if this is a self-certification and to be provided on request. | The Selection Questionnaire is essentially a self-certification; that said if your organisation is happy to provide your accounts as part of the return this is acceptable. | 7th June 2019
27 | 5th June 2019 | Question 4.1 asks: ‘Are you able to provide a copy of your audited accounts for the last two years, if requested? Do you require our accounts to be included with the Selection Questionnaire to enable you to establish our economic and financial standing ? | The Selection Questionnaire is essentially a self-certification; that said if your organisation is happy to provide your accounts as part of the return this is acceptable. | 7th June 2019
28 | 5th June 2019 | 1 There is an emphasis on Sustainability & Zero Carbon design within the SQ and ITT documents, but an Energy/Sustainability MEP member is not specifically listed in the ITT pricing schedule, is there a reason for this? | This isn’t specifically included in the pricing schedule as this can often be a role/duly/skill embedded within other specialisms; | 7th June 2019
29 | 6th June 2019 | Regarding formatting of the SQ response, but would it be acceptable to provide team structure and CVs (as required in Q6.4) as a separate attachment? It is difficult to see how this information can be effectively presented within the word document itself. | Wherever possible our preference is to have attachments etc embedded – should this not be an option as long as any attachments are clearly referenced these are permitted. | 7th June 2019
30 | 6th June 2019 | We note that the contract Terms and Conditions as follows: By submitting a Tender, Tenderers are agreeing to be bound by the JCT Design and Build 2016 Terms and Conditions of this ITT and the form of Contract without further negotiation or amendment. PLYMOUTH MARJON UNIVERSITY CANNOT NEGOTIATE WITH ANY TENDERER ABOUT THE TERMS AND CONDITIONS OF THE CONTRACT. Can we please clarify if this should read ‘JCT Consultancy Agreement 2016’, the JCT Design and Build 2016 refers to a ‘build contract’ | Please accept our apolgies the Terms and Conditions will be the JCT CA (Consultancy Agreement) & NOT the JCT Design and Build | 7th June 2019
31 | 6th June 2019 | The Service Specification references Business Strategists, Feasibility Consultants, Investment Specialists, are you able to expand on the anticipated scope of these services and how they will overlap with the University Estates team? In relation to Part 3 Section 4: 1) You state you will be getting a credit report from an undisclosed source are you able to confirm where the report is coming from? 2) You state 30 marks will be allocated for turnover higher than the turnover requirement, but we can’t locate a figure – are you able to confirm? 3) The scoring mechanism you state appears to relate to the credit check score not 4.3 – please can you clarify? | 1. Plymouth Marjon University will undertake a Credit-check via CreditSafe 2. The value is detailed in the first paragraph of Section 4: (£200k) 3. The credit check is an aspect of the financial analysis; best practise recommended that further financial analysis should also be applied and undertaken to determine a pass. | 7th June 2019
32 | 6th June 2019 | The JCT CA 2016, and the ITT states that this is unamended. However, the limit of liability (Cl 2.11.1) is not defined. Can you please advise of this and of any other terms of the contract that require client definition. | The key terms and conditions are not amendable – the agreement does as you have noted include either square brackets and or aspects for completion – these will of course require input. – The key message is that the key terms and conditions are non-negotiable. | 7th June 2019
33 | 6th June 2019 | CVs are given a page limit of 2 sides of A4 – is there a limit to how many CVs we submit? Are there any page limits on questions 6.4-6.8? Can we use our own template and layout for questions 6.4-6.8? It is still unclear to us if a multi-disciplinary team is required, or architecture services only? Do we need to include fees for all disciplines listed in the spreadsheet ‘Commercial-Pricing Schedule.xlsx’ ? If not, please confirm it is acceptable to propose a Masterplanning team comprising Architect, MEP, Civil engineering, Landscape Architect & Transport Engineer only? If we chose to include and name subconsultants, are they required to complete parts 1 and 2 of the SQ separately, and for all relevant CVs to be submitted? Questions included in section 4 of the ‘Specification & Statement of Requirements’ document are to be answered at this stage or ITT stage? The ‘Final Invitation to Tender’ details the value of the contract at £200,000.00, with the contract term being an initial 2 years with the opportunity to extend a further 8 years (nb: 10yrs in total). Please confirm whether it is envisioned that the £200,000.00 applies to the first two years only. | There isn’t a limit - our requirements is seeking a short CV for each key team member. If page limits apply these are advised. Our preference is that the template provided is used where possible as our evaluations team are familiar with this version – embedded documents are permitted – but please don’t PDF the document as access to embedded documents is not available on PDF versions – should this not be an option – attachments are acceptable as long as these are clearly referenced to the particular sections. Plymouth Marjon University as seeking responses from a ‘lead’ organisation who will select and appointment those disciplines that are not currently employed by the lead contractor; - please note that the commercial-pricing schedule, Invitation to Tender and Specification and Statement of Requirements do not require completion and return at this stage of the process – these have been issued in line with The Public Contract Regulations 2015. No the lead contractor is essentially ‘responsible’ for their sub-contractors and are expected to completed their own due diligence checks before appointing/selecting them – therefore we only require the lead contractor/bidder to complete the document. Re CV’s - our requirements is seeking a short CV for each key team member. The only document that requires completion and submission by midday on 24th June is the Selection Questionnaire – the ITT etc., forms part of the 2nd stage of the procedure and will only be completed by the shortlisted suppliers Determining the value of a Campus Development Plan is difficult – however, the £200,000.00 is the amount envisaged for the whole life of the document – Plymouth Marjon University have added a 10 yr total lifespan to enable unforeseen changes to student numbers both up and down to be reflected in the Development Plan should this be necessary with our preference being to re-visit this with the Development Plan authors as opposed to undertaking a new procurement process. | 10th June 2019
Plymouth Marjon University have applied the 71000000 as the main CPV code - but this drill's down in to following:-
In addition to the above - our Specification Includes the following 'Acknowledging that the achievement of a detailed and meaningful analysis, will come to fruition from the scrutiny and exploration of several specialist disciplines, for example, Architects, Designers, Planners, Quantity Surveyors, Engineers, Landscapers, Business Strategists, Feasibility Consultants, Investment Specialists'.