# BANKING SERVICES AGREEMENT

SCHEDULE 6.1 | Transition

Schedule 6.1 | Transition

## DEFINITIONS

### In this Schedule, the following definitions shall apply:

| “Deliverable” | means the deliverables set out in Annex 1 to this Schedule 6.1; |
| --- | --- |
| "Detailed Transition Plan", | means the plan prepared in accordance with paragraph 3.3 of this Schedule 6.1 (Transition); |
| “Milestones” | means the milestones set out in Annex 1 to this Schedule 6.1; |
| "Outline Transition Plan" | means the plan in the form set out at Annex 1 to this Schedule 6.1; |
| "Supplier Transition Team" | has the meaning given to it at paragraph 5.1(a) of this Schedule 6.1 (Transition); |
| "Supplier's Transition Manager" | has the meaning given to it at paragraph 5.1(b) of this Schedule 6.1 (Transition); |
| "Transition" | the transition of services from the Incumbent Supplier to the Supplier to be provided pursuant to this Agreement (including where individual Service Recipients transition from an Incumbent Supplier to the Supplier) |
| "Transition Plan" | the Outline Transition Plan and the Detailed Transition Plan as described in this Schedule 6.1 (Transition); |

Part A | Transition

## INTRODUCTION

### This Schedule:

#### defines the process for the preparation and implementation of the Outline Transition Plan and Detailed Transition Plan;

#### identifies the Milestones (and associated Deliverables); and

#### sets out the reporting requirements, governance and management of the Transition Plan.

### The following documents form part of this Schedule:

#### Annex 1: Outline Transition Plan;

#### Annex 2: Minimum Set of Transition Components;

#### Annex 3: Responsibilities of the Supplier Transition Team.

### The Supplier shall:

#### provide to the Authority any reasonable assistance requested by the Authority to allow the services provided by the Incumbent Supplier to continue without interruption during Transition and to facilitate the orderly transfer of responsibility for and conduct of the services from the Incumbent Supplier to the Supplier without any adverse impact on current service levels and service delivery provided to the Authority;

#### use all reasonable endeavours to minimise the risk of Delay in accordance with Clause 6 and/or to service performance during Transition, including the provision of additional resources to carry out the Transition Plan at the Supplier's own cost;

#### comply with its obligations under the Outline Transition Plan, the Detailed Transition Plan and this Schedule 6.1  (Transition), and the Supplier shall be responsible for the costs associated with any failure by the Supplier to comply with such obligations. Any issue arising from the Supplier's performance of its obligations shall be escalated for resolution at the Entry Transition Board.

## OUTLINE TRANSITION PLAN

### All changes to the Outline Transition Plan shall be subject to the Change Control Procedure

### The requirements of the Outline Transition Plan are described in Annex 1

## APPROVAL OF THE DETAILED TRANSITION PLAN

### Within 5 Working Days of the Effective Date, the Parties shall meet to (i) discuss the Outline Transition Plan and any areas which need clarifying in advance of the Supplier submitting the draft Detailed Transition Plan in accordance with Paragraph 3.2, (ii) discuss any clarifications on the approach to the first iteration of the Detailed Transition Plan and (iii) discuss any clarifications on the content to be covered within the first and second iterations of the Detailed Transition Plan.

### The Supplier shall submit the first iteration of the Detailed Transition Plan to the Authority for approval within 30 Working Days of the Effective Date. The Supplier shall ensure that the Detailed Transition Plan is developed in accordance with the requirements set out in the Outline Transition Plan. The Supplier shall submit the second iteration of the Detailed Transition Plan to the Authority for approval within 90 Working Days of the Effective Date.

### The Supplier shall ensure that the draft Detailed Transition Plan:

#### clearly details all the steps required to implement the Milestones to be achieved up to and including the final Milestone, in conformity with the Authority Requirements;

#### incorporates as a minimum the set of components required to implement the activities of the Transition Plan as set out in Annex 2 (Minimum Set of Transition Components);

#### clearly outlines the required roles and responsibilities of both Parties, including staffing requirements;

#### is produced using a software tool as specified, or agreed by the Authority;

#### clearly details all the Supplier's dependencies on the Authority or Service Recipients in order to complete the activities under the Detailed Transition Plan; and

#### clearly details all the Supplier's assumptions in setting out the activities and timescales in the Detailed Transition Plan.

### Prior to the submission of the draft Detailed Transition Plan to the Authority in accordance with Paragraph 3.1, the Authority shall have the right to :

#### To request and review any documentation produced by the Supplier in relation to the development of the Detailed Transition Plan, including:

##### details of the Supplier's intended approach to the Detailed Transition Plan and its development;

##### copies of any drafts of the Detailed Transition Plan produced by the Supplier; and

##### any other work in progress in relation to the Detailed Transition Plan; and

#### to require the Supplier to include any reasonable changes or provisions in the Detailed Transition Plan.

### Following receipt of the draft Detailed Transition Plan from the Supplier, the Authority shall:

#### review and comment on the draft Detailed Transition Plan as soon as reasonably practicable; and

#### notify the Supplier in writing that it approves or rejects the draft Detailed Transition Plan no later than 20 Working Days after the date on which the draft Detailed Transition Plan is first delivered to the Authority.

### If the Authority rejects the draft Detailed Transition Plan:

#### the Authority shall inform the Supplier in writing of its reasons for its rejection; and

#### the Supplier shall then revise the draft Detailed Transition Plan (taking reasonable account of the Authority's comments) and shall re-submit a revised draft Detailed Transition Plan to the Authority for the Authority's approval within 20 Working Days of the date of the Authority's notice of rejection. The provisions of Paragraph 3.4 and this Paragraph 3.5 shall apply again to any resubmitted draft Detailed Transition Plan, provided that either Party may refer any disputed matters for resolution by the Dispute Resolution Procedure at any time.

### If the Authority approves the draft Detailed Transition Plan, it shall replace the Outline Transition Plan from the date of the Authority’s notice of approval.

## UPDATES TO AND MAINTENANCE OF THE DETAILED TRANSITION PLAN

### Following the approval of the Detailed Transition Plan by the Authority:

#### the Supplier’s performance against the Transition Plan shall be monitored at meetings of the Entry Transition Board (as defined in Schedule 8.1 (Governance).  In preparation for such meetings, the Supplier shall provide to the Authority not less than 5 Working Days in advance of each meeting of the Entry Transition Board:

##### the current Detailed Transition Plan; and

##### any reports as specified in the Detailed Transition Plan.

### Save for any amendments which are of a type identified and notified by the Authority (at the Authority's discretion) to the Supplier in writing as not requiring approval, any material amendments to the Detailed Transition Plan shall be subject to the Change Control Procedure provided that:

#### any amendments to elements of the Detailed Transition Plan which are based on the contents of the Outline Transition Plan shall be deemed to be material amendments; and

#### in no circumstances shall the Supplier be entitled to alter or request an alteration to any Milestone date except in accordance with Clause 30 (Authority Cause).

### Any proposed amendments to the Detailed Transition Plan shall not come into force until they have been approved in writing by the Authority.

## RESOURCE COMMITMENTS AND CHARGES

### The Supplier shall:

#### coordinate and provide sufficient and appropriately skilled resources to carry out the Supplier's obligations under this Schedule including the responsibilities set out in Annex 3 (Responsibilities of the Supplier Transition Team) ("Supplier Transition Team");

#### appoint an individual Supplier Personnel in accordance with Clause 14 with the responsibility for managing the Supplier's obligations under this Schedule and provide written notification of such appointment to the Authority within 3 Working Days of the Effective Date ("Supplier's Transition Manager").

## IMPLEMENTATION OF THE DETAILED TRANSITION PLAN

### The Supplier shall plan, prepare for and carry out the Transition activities in accordance with this Schedule, and shall:

#### comply with the Detailed Transition Plan;

#### deliver, as a minimum, the set of components required to implement the activities of the Transition Plan as set out in Annex 2 (Minimum Set of Transition Components);

#### be responsible for overall management of the activities under the Detailed Transition Plan in order to ensure the timely completion of each task and Milestone;

#### carry out the Detailed Transition Plan without causing any disruption to the Authority's and/or Service Recipient’s business operations unless:

##### the Supplier has procured the Authority's and/or Service Recipient’s agreement in writing no less than 6 weeks prior to the associated disruption; or

##### if the Supplier is unable to provide 6 weeks’ notice of such disruption to the Authority and/or Service Recipient, the Supplier has notified the Authority as soon as possible upon becoming aware of the disruption and the Authority has agreed to such disruption through the Fast-Track Change Procedure; and

#### not take any step (expressly or implicitly or directly or indirectly by itself or through any other person) to dissuade or discourage any employees engaged in the provision of the Services from transferring their employment from the Authority and/or Service Recipient and/or the Incumbent Supplier to the Supplier.

### Readiness Review

#### The Supplier shall cooperate with and assist the Authority in carrying out readiness reviews for the Transition no more than 8 (eight) weeks and no less than 2 (two) weeks prior to the Operational Service Commencement Date in order to satisfy key Authority stakeholders that the relevant Services can be transferred to the Supplier without impact on business operations (“Readiness Reviews”).

#### As part of the Readiness Review the Entry Transition Board shall agree a recovery plan to remedy the issues identified by the Readiness Review that have significant impact on business operations.

#### The Parties shall define and agree the conditions which form the basis of the Readiness Review reports within 30 Working Days after agreement of the Detailed Transition Plan.

### Third Parties

#### The Supplier shall cooperate with and provide assistance to the Authority and any relevant third party in order to achieve the transition of Services in accordance with this Schedule.

### Disputes

#### The Parties shall escalate any Disputes arising from the Transition Plan to the Entry Transition Board, and the Supplier shall provide to the Authority within 2 Working Days of its request all documentation relevant to the Dispute that is available at that time.  Where the Entry Transition Board have been unable to resolve such Dispute, the Parties shall follow the Dispute Resolution Procedure and the Parties agree to use the Expedited Dispute Timetable.

### Reporting

#### The Supplier shall provide to the Authority progress reports on a weekly basis, including a dashboard, against the Detailed Transition Plan, which will set out:

##### the current status of the transition activities;

##### the Supplier's progress against all Milestones and other activities set out in the Detailed Transition Plan, any actual or anticipated delays to the Detailed Transition Plan and anticipated remedial activities in respect of such delay;

##### the actual and anticipated delays to the Detailed Transition Plan as a result of any failure or delay by the Authority and/or Service Recipient as set out in Schedule 3 (Authority Responsibilities), the impact of such failures on the Supplier and the associated mitigation actions taken by the Supplier; and

##### the actual and anticipated risks and issues (including the RAID log as set out in Paragraph 6.8(a)(i)), the impact or likely impact of such risks and issues on the Detailed Transition Plan and the associated mitigation actions being taken by the Supplier.

#### The Supplier shall promptly provide other progress reports on the Detailed Transition Plan as reasonably requested by the Authority.

#### The Supplier shall promptly (and in any event, no later than 5 Working Days prior to the relevant governance meeting) provide all reports required in accordance with the Detailed Transition Plan and as reasonably requested by the Authority.

### Security and Safety

#### The Supplier shall carry out its obligations under this Schedule in compliance with all applicable site safety and security procedures of the Authority and the Incumbent Supplier to the Authority (as applicable) and in accordance with the relevant provisions of the Agreement.

### Service Documentation

#### Prior to each Operational Service Commencement Date and as part of the transition readiness signed off Milestone as set out in Annex 1, the Supplier shall provide to the Authority operational and service delivery documentation, including its operations manual and/or solutions design documentation defining how the Supplier will deliver the Services. This documentation shall include a description of all the operational and service management processes, procedures and tools which will be used by the Supplier in delivering the Services. In preparing this documentation the Supplier shall take into consideration the existing processes and procedures of the Incumbent Supplier in its provision of similar services to the Authority.

### Risks, Assumptions, Issues and Dependencies (RAID) Management

#### The Supplier shall:

##### maintain a RAID log which sets out any risks, assumptions, issues and dependencies in carrying out the Detailed Transition Plan, including risk mitigation strategies, preventive measures and contingency plans for rapid recovery from the occurrence of such risks and issues;

##### identify and promptly report to the Authority upon becoming aware of any risks, assumptions, issues and dependencies in carrying out the Detailed Transition Plan;

##### create and maintain (based upon consultation with and engagement of the Authority) a RAID management plan which will clearly list all technical, commercial, delivery, financial and legal risks, assumptions, issues and dependencies that impact the Parties and the Detailed Transition Plan. The RAID management plan shall be created by the Supplier within 20 Working Days of the Effective Date and provided to the Authority fortnightly; and

##### develop contingency plans for each identified risk and any risks that are categorised as 'High Impact and High Likelihood'. Such contingency plans shall be developed within 5 Working Days of being categorised and reported as 'High Impact and High Likelihood' risks and shall be provided to the Authority upon request.

## ACHIEVEMENT OF MILESTONES

### The Supplier's Achievement of the Milestones set out in the Detailed Transition Plan shall be assessed in accordance with the following testing procedure:

xxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxxx

### The Achievement of the relevant Milestone shall entitle the Supplier to the receipt of a payment in respect of that Milestone in accordance with Schedule 7.1 (Charging and Invoicing).

# ANNEX 1: OUTLINE TRANSITION PLAN

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

The Outline Transition Plan shall include:

  - XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX

# ANNEX 2: Minimum set of Transition COMPONENTS

| Transition component | Description |
| --- | --- |
| Transition management | To set up and manage the Transition Phase of the Supplier, based on industry standard good practice project and programme management frameworks. |
| Governance | To implement governance for the Detailed Transition Plan (for instance, the organisational forums) as detailed in Schedule 8.1 (Governance) and Schedule 6.1 (Transition), to enable the management of the relationship between the Supplier and the Authority from the Effective Date. |
| Communication | To plan, prepare and implement an effective communication approach from the Effective Date, as jointly agreed by the Supplier and the Authority. |
| Staff transfer | To carry out the staff consultation and engagement to effect the smooth transition and integration of In Scope Roles/Staff from Incumbent Supplier to the Supplier, as specified in Schedule 9.1 (Staff Transfer). |
| Post Contract Verification | To undertake the detailed discovery to validate assumptions in the contractual documentation and to prepare a final report to agree and approve all Changes prior to the defined period specified in the Agreement. |
| Operating model and service design | To design the operating model for service provision including (as a minimum): process and associated forms , operational service levels, organisation, location, data, applications, tooling, technology and commercials. |
| Finance | To set up all the processes defined in the Agreement, Schedule 7.1 (Charges and Invoicing) and Schedule 7.5 (Financial Reports and Audit Rights) that the Supplier and the Authority shall use to provide financial information, ensuring the accurate and timely billing and payment for the Service(s). |
| Contract management | To implement processes and procedures to effectively manage the contract from the Operational Service Commencement Date, and handle queries, issues and Changes as they arise during the Term. |
| Reporting | Ensure the continued production of reports as specified in Schedule 6.1 (Transition) and Schedule 8.2 (Reports and Records) in order to support Governance and operations. |
| Service continuity management | To perform gap analysis and report, agree and align the changes necessary to ensure no disruption to service throughout the transfer of Service(s). |
| Quality management | To provide assurance to the Supplier and the Authority that the Supplier’s Deliverables are complete, have met their quality criteria and the agreed processes have been observed. |
| Security management | To report, agree and align the activities necessary to ensure system security is maintained or enhanced during Transition, as specified in Schedule 2.4 (Security Management). |
| Transition readiness | To assess the state of Supplier readiness for a successful transfer and ongoing end to end provision of Service(s). |
| Post Transition aftercare | To plan and implement support arrangements for the period following transfer of Service(s). To resolve issues arising from the transfer of Service(s). |

ANNEX 3: RESPONSIBILITIES OF THE SUPPLIER TRANSITION TEAM

The Supplier’s Transition Team shall be responsible for carrying out the operation of the Transition Plans, including:

XXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXXX