Schedule 8 (Implementation Plan and Testing)

Part A - Implementation

- Definitions

  - In this Schedule, the following words shall have the following meanings and they shall supplement Schedule 1 (Definitions):

| "Delay" | (a) a delay in the Achievement of a Milestone by its Milestone Date; or (b) a delay in the design, development, testing or implementation of a Deliverable by the relevant date set out in the Implementation Plan; |
| --- | --- |
| "Deliverable Item" | an item or feature in the supply of the Deliverables delivered or to be delivered by the Supplier at or before a Milestone Date listed in the Implementation Plan; |
| "Implementation Period" | has the meaning given to it in Paragraph ‎7.1; |
| "Milestone Payment" | a payment identified in the Implementation Plan to be made following the issue of a Satisfaction Certificate in respect of Achievement of the relevant Milestone; |

- Agreeing and following the Implementation Plan

  - A draft of the Implementation Plan is set out in the Annex to this Schedule.  The Supplier shall provide a further draft Implementation Plan 20 days after the Effective Date.

  - The draft Implementation Plan:

    - must contain information at the level of detail necessary to manage the implementation stage effectively and as the Buyer may otherwise require; and

    - it shall take account of all dependencies known to, or which should reasonably be known to, the Supplier.

  - Following receipt of the draft Implementation Plan from the Supplier, the Parties shall use reasonable endeavours to agree the contents of the Implementation Plan. If the Parties are unable to agree the contents of the Implementation Plan within twenty (20) Working Days of its submission, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

  - The Supplier shall provide each of the Deliverable Items identified in the Implementation Plan by the date assigned to that Deliverable Item in the Implementation Plan so as to ensure that each Milestone identified in the Implementation Plan is Achieved on or before its Milestone Date.

  - The Supplier shall monitor its performance against the Implementation Plan and Milestones (if any) and report to the Buyer on such performance.

- Reviewing and changing the Implementation Plan

  - Subject to Paragraph ‎4.3, the Supplier shall keep the Implementation Plan under review in accordance with the Buyer’s instructions and ensure that it is updated on a regular basis.

  - The Buyer shall have the right to require the Supplier to include any reasonable changes or provisions in each version of the Implementation Plan.

  - Changes to any Milestones, Milestone Payments and Delay Payments shall only be made in accordance with the Variation Procedure.

  - Time in relation to compliance with the Implementation Plan shall be of the essence and failure of the Supplier to comply with the Implementation Plan shall be a Material Default.

- Security requirements before the Start Date

  - The Supplier shall note that it is incumbent upon them to understand the lead-in period for security clearances and ensure that all Supplier Staff have the necessary security clearance in place before the Start Date. The Supplier shall ensure that this is reflected in their Implementation Plan.

  - The Supplier shall ensure that all Supplier Staff and Subcontractors do not access the Buyer's IT systems, or any IT systems linked to the Buyer, unless they have satisfied the Buyer's security requirements.

  - The Supplier shall be responsible for providing all necessary information to the Buyer to facilitate security clearances for Supplier Staff and Subcontractors in accordance with the Buyer's requirements.

  - The Supplier shall provide the names of all Supplier Staff and Subcontractors and inform the Buyer of any alterations and additions as they take place throughout the Contract Period.

  - The Supplier shall ensure that all Supplier Staff and Subcontractors requiring access to the Buyer Premises have the appropriate security clearance. It is the Supplier's responsibility to establish whether or not the level of clearance will be sufficient for access. Unless prior approval has been received from the Buyer, the Supplier shall be responsible for meeting the costs associated with the provision of security cleared escort services.

  - If a property requires Supplier Staff or Subcontractors to be accompanied by the Buyer’s Authorised Representative, the Buyer must be given reasonable notice of such a requirement, except in the case of emergency access.

- What to do if there is a Delay

  - If the Supplier becomes aware that there is, or there is reasonably likely to be, a Delay under this Contract it shall:

    - notify the Buyer as soon as practically possible and no later than within two (2) Working Days from becoming aware of the Delay or anticipated Delay;

    - include in its notification an explanation of the actual or anticipated impact of the Delay;

    - comply with the Buyer’s instructions in order to address the impact of the Delay or anticipated Delay; and

    - use all reasonable endeavours to eliminate or mitigate the consequences of any Delay or anticipated Delay.

- Compensation for a Delay

  - If Delay Payments have been included in the Implementation Plan and a Milestone has not been achieved by the relevant Milestone Date, the Supplier shall pay to the Buyer such Delay Payments (calculated as set out by the Buyer in the Implementation Plan) and the following provisions shall apply:

    - the Supplier acknowledges and agrees that any Delay Payment is a price adjustment and not an estimate of the Loss that may be suffered by the Buyer as a result of the Supplier’s failure to Achieve the corresponding Milestone;

    - Delay Payments shall be the Buyer's exclusive financial remedy for the Supplier’s failure to Achieve a Milestone by its Milestone Date except where:

      - the Buyer is also entitled to or does terminate this Contract pursuant to Clause 14.4 (When the Buyer can end the contract); or

      - the delay exceeds the number of days (the "Delay Period Limit") specified in the Implementation Plan commencing on the relevant Milestone Date;

    - the Delay Payments will accrue on a daily basis from the relevant Milestone Date until the date when the Milestone is Achieved;

    - no payment or other act or omission of the Buyer shall in any way affect the rights of the Buyer to recover the Delay Payments or be deemed to be a waiver of the right of the Buyer to recover any such damages; and

    - Delay Payments shall not be subject to or count towards any limitation on liability set out in Clause 15 (How much you can be held responsible for).

- Implementation Plan

  - The Implementation Period will be a 2 week period.

  - During the Implementation Period, the incumbent supplier shall retain full responsibility for all existing services until the Start Date or as otherwise formally agreed with the Buyer. The Supplier's service obligations shall formally be assumed on the Start Date as set out in Award Form.

  - In accordance with the Implementation Plan, the Supplier shall:

    - work cooperatively and in partnership with the Buyer and incumbent supplier, where applicable, to understand the scope of Services to ensure a mutually beneficial handover of the Services;

    - work with the incumbent supplier and Buyer to assess the scope of the Services and prepare a plan which demonstrates how they will mobilise the Services;

    - liaise with the incumbent supplier to enable the full completion of the Implementation Period activities; and

    - produce an Implementation Plan, to be agreed by the Buyer, for carrying out the requirements within the Implementation Period including, key Milestones and dependencies.

  - The Implementation Plan will include detail stating:

    - how the Supplier will work with the incumbent supplier and the Buyer Authorised Representative to capture and load up information such as asset data; and

    - a communications plan, to be produced and implemented by the Supplier, but to be agreed with the Buyer, including the frequency, responsibility for and nature of communication with the Buyer and end users of the Services.

  - In addition, the Supplier shall:

    - appoint a Supplier Authorised Representative who shall be responsible for the management of the Implementation Period, to ensure that the Implementation Period is planned and resourced adequately, and who will act as a point of contact for the Buyer;

    - mobilise all the Services specified in the Specification within this Contract;

    - produce an Implementation Plan report for each Buyer Premises to encompass programmes that will fulfil all the Buyer's obligations to landlords and other tenants:

      - the format of reports and programmes shall be in accordance with the Buyer's requirements and particular attention shall be paid to establishing the operating requirements of the occupiers when preparing these programmes which are subject to the Buyer's approval; and

      - the Parties shall use reasonable endeavours to agree the contents of the report but if the Parties are unable to agree the contents within twenty (20) Working Days of its submission by the Supplier to the Buyer, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

    - manage and report progress against the Implementation Plan;

    - construct and maintain an Implementation risk and issue register in conjunction with the Buyer detailing how risks and issues will be effectively communicated to the Buyer in order to mitigate them;

    - attend progress meetings (frequency of such meetings shall be as set out in the Award Form) in accordance with the Buyer's requirements during the Implementation Period. Implementation meetings shall be chaired by the Buyer and all meeting minutes shall be kept and published by the Supplier; and

    - ensure that all risks associated with the Implementation Period are minimised to ensure a seamless change of control between incumbent supplier and the Supplier.

Annex 1: Implementation Plan

The Draft Implementation Plan is set out below and the Milestones to be Achieved are identified below. Amendments to Milestone Dates shall be agreed between the Supplier and Buyer and adjusted to meet the 02 April 2024 full Services live date:

| Milestone | Deliverable Items | Duration | Milestone Date | Buyer Responsibilities | Milestone Payments | Delay Payments |
| --- | --- | --- | --- | --- | --- | --- |
| Security clearance review | TRM will ensure that all relevant staff have the appropriate level of security clearance prior to the contract staff date | Open-ended | Prior to contract start date | N/A | N/A | N/A |
| Key stakeholder Kickoff Meeting | Establish the main point of contact(s) for HMRC, including names of all TRM staff involved in thei Confirm communication channel of preference (e.g. email, telephone) Confirm cadence of check-ins post go live. Regular check-ins will be scheduled to ensure proactive engagement, ad hoc check-ins are also welcome and encouraged Align expectations and understand strategic goals of HMRC Agree on any changes to Onboarding timeline and delivery milestones Discuss transition of data from incumbent suppler to TRM and agree date for transition Align on testing requirements and programme of testing | 2 hours | Prior to contract start date | Names and emails of users to be sent to TRM | N/A | N/A |
| Development of final Test Strategy | TRM will submit a Test Strategy, which includes: - An overview of how testing will be conducted - The process to be used to capture and record test results and categorisation of Test Issues - the procedure to be followed should a Deliverable fail a Test, fail to satisfy the Test Success Criteria or where the Testing of a Deliverable produces unexpected results, including a procedure for the resolution of Test Issues - the procedure to be followed to sign off each Test - the process for the production and maintenance of Test Reports and a sample plan for the resolution of Test Issues - the names and contact details of the Buyer and the Supplier's Test representatives - a high level identification of the resources required for Testing including Buyer and/or third party involvement in the conduct of the Tests - the technical environments required to support the Tests - the procedure for managing the configuration of the Test environments TRM’s platform is a SaaS cloud-based solution that is ready to deploy quickly to new users. It is not expected that significant testing will be required | 1-2 weeks | Prior to contract start date, but no later than 20 working days after |  | N/A | N/A |
| HMRC to evaluate Test Plan | HMRC will evaluate and if satisfied, approve the Test Plan |  |  |  |  |  |
| TRM to develop Test specification | TRM to provide test specification for delivery of the TRM platform, which includes: - Specification of test data - A plan to make the resources available for testing - Test scripts - Test prerequisites and mechanism for measuring them - Test results, including the mechanism used to capture results and method to process them |  |  |  | N/A | N/A |
| TRM performs internal testing | TRM will test relevant Deliverables against its own internal quality control measures |  |  |  | N/A | N/A |
| TRM notification of Testing details | TRM will notify HMRC of the date, time and location of relevant tests |  | 10 working days before proposed testing | HMRC to ensure Test witnesses can attend | N/A | N/A |
| Testing takes place | Testing of deliverables carried out Any test issues identified are maintained in the requisite format in the Test Issue Management Log | 10 working days | TBC | Test witnesses to be present | N/A | N/A |
| (Optional) HMRC performs a test quality audit | HMRC or an agent performs a quality audit on the Testing | TBC | 5 working days notice must be given |  | N/A | N/A |
| Draft Test report submitted | TRM to submit draft Test Report |  | 2 days before testing ends |  | N/A | N/A |
| Final Test Report submitted | TRM to submit final test report which includes: - An overview of the testing conducted - Identification of the relevant success criteria, whether or not it has been satisfied and any explanation of why this is - Details of any tests that were not carried out and why these were not carried out - The test success criteria that was satisfied, not satisfied or which was not tested grouped by severity level - The specification for any hardware and software used throughout testing and any changes that were applied to the hardware/software during testing |  | No more than 5 working days after completion of testing |  | N/A | N/A |
| HMRC to issue Satisfaction Certificate | HMRC to issue Satisfaction Certificate as soon as reasonably practical following successful completion of Test Where deliverables do not satisfy the Test Success Criteria, HMRC shall notify TRM and: - HMRC will issue a Satisfaction Certificate conditional upon the remediation of the Test Issues - HMRC may extend the Test Plan by such reasonable period or periods as the Parties may reasonably agree and require the Supplier to rectify the cause of the Test Issue and re-submit the Deliverables (or the relevant part) to Testing - where the failure to satisfy the Test Success Criteria results, or is likely to result, in the failure (in whole or in part) by TRM to meet a Milestone, then without prejudice to the HMRC’s other rights and remedies, such failure shall constitute a Material Default | TBC | As soon as practicable | TRM to have completed relevant tests | N/A | Payment agreed in respect of this milestone |
| (Optional( Rectification plan submitted | Where there are any non-material issues identified during testing or issues that do not exceed the test issues threshold, TRM to submit a rectification approval plan to HMRC |  | Within 10 working days of final test report issued |  | N/A | N/A |
| Meeting with incumbent supplier | Agree method and timeline for transition of data to ensure no disruption to HMRC | 1 hour | Prior to contract start date | To have introduced TRM to incumbent supplier POC | N/A | N/A |
| HMRC environment created | TRM will create the HMRC environment | 1 hour | On contract start date (T) | None | N/A | N/A |
| Existing data inputted to TRM | TRM ingests data provided by incumbent into | TBC | On contract start date (T) | Ensure incumbent supplier’s cooperation | N/A | N/A |
| Welcome emails sent to users | TRM will add users to the HMRC environment and they will receive welcome emails | 2 hours | Within (T) plus one week | HMRC must provide user’s names and emails | N/A | N/A |
| User onboarding call | TRM will deliver user onboarding call on how to use the platform, tailored to HMRC’s strategic needs TRM will also ensure all users have an appropriate training pathway for self-guided learning | 1 hour | Within (T) plus one week Weekly thereafter for two months in case of users being added on a rolling basis | HMRC must provide suitable times for users to attend onboarding | N/A | N/A |
| Key stakeholders check-ins | Check in on implementation process, user onboarding progress and any issues | 1 hour | Within (T) plus one week and biweekly thereafter for 60 days | HMRC must provide suitable times for key stakeholders attendance | N/A | N/A |
| Post implementation cadence calls | Regularly scheduled check in calls with key stakeholders |  | T plus 60 days on |  | N/A | N/A |
| The Milestones will be Achieved in accordance with this Part A of this Schedule For the purposes of Paragraph ‎6.1.2b) the Delay Period Limit shall be 2 working days. |  |  |  |  |  |  |