# Annex A

| Title of Project | Ocean Country Partnership Programme: Sri Lanka Sri Lanka MPA Network Mapping |
| --- | --- |
| Date and Time for Return of Bids | Monday 8 July 2024 @16:00 Hours GMT |
| Contract Reference Number | C24-0604-1907 |
| Address for Bid Submission | One electronic copy to be sent to TenderResponse@jncc.gov.uk PLEASE DO NOT SEND BIDS DIRECTLY TO HANNAH LAWSON, HOLLY BAIGENT OR A MEMBER OF THE JNCC PROCUREMENT TEAM VIA THEIR WORK EMAIL ADDRESSES AS THIS WILL INVALIDATE YOUR BID. Bids must be less than 10 MB in size. On receipt of your bid, you will receive an automated e-mail to confirm receipt by the JNCC Support Co. If you do not receive this automated email, please contact the number below: 00 44 1733866988 |
| Contacts for Technical Information relating to this Project Specification | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866987 |
| Contact for Queries Regarding the Procurement Procedure | Procurement Team Joint Nature Conservation Committee Email: contractqueries@jncc.gov.uk Telephone: 01733 866987 |
| Proposed Start Date | 15 July 2024 |
| Proposed End Date | 31 March 2025 |

Ocean Country Partnership Programme: Sri Lanka

Sri Lanka MPA Network Mapping

Contents

1.	Joint Nature Conservation Committee	3

2.	Project Background	3

3.	Project Aims	4

4.	Project Objectives	4

5.	Contractor Requirements	5

6.	Potential Follow-On Work	6

7.	Product Specification	6

8.	Timescale	6

9.	Health and Safety	7

10.	Project Management	7

11.	Instructions for Bid Submission	7

12.	Evaluation Criteria	8

13.	Payment	9

14.	Additional Requirements	9

15.	Procurement Timetable (which may be subject to change)	9

## Joint Nature Conservation Committee

The Joint Nature Conservation Committee (JNCC) is the statutory adviser to the UK Government and devolved administrations on UK and international nature conservation.

Our role is to provide scientific evidence, information, and advice to inform decisions to protect the natural environment. Our specific role is to work on nature conservation issues that affect the UK as a whole and internationally, by:

Advising Government on the development and implementation of policies for, or affecting, nature conservation in the UK and internationally;

Providing advice and disseminating knowledge on nature conservation issues affecting the UK and internationally;

Establishing common standards throughout the UK for nature conservation, including monitoring, research, and the analysis of results; and

Commissioning or supporting research which it deems relevant to these functions.

Background to JNCC can be found on JNCC’s website at: https://jncc.gov.uk/about-jncc/

## Project Background

JNCC is a delivery partner for the Ocean Country Partnership Programme (OCPP), a UK government-led programme under the Blue Planet Programme. More information on the OCPP can be found here: https://www.gov.uk/government/publications/blue-planet-fund/ocean-country-partnership-programme-ocpp.

Through OCPP we aim to support countries to strengthen marine science expertise, develop science-based policy and management tools and create educational resources for coastal communities. There are three main objectives for the OCPP:

- Marine Pollution:- supporting countries to be equipped with the skills and expertise needed to tackle, reduce and mitigate marine pollution through the development of science led policy and improve our understanding of the impacts of pollution, as well as identifying and supporting effective responses, we will make sure that communities are better equipped to prevent and manage marine pollution. This will improve health and livelihoods.

- Sustainable Seafood:- supporting the development of the skills and expertise needed to adopt sustainable seafood practices to reduce risks such as the spread of zoonotic diseases from unsustainable or unsafe activities and support trade in safe seafood. Assisting countries to crack down on illegal, unreported and unregulated fishing by supporting the development of better management, monitoring and enforcement capabilities.

- Marine Biodiversity:- supporting countries to develop the skills and expertise needed to establish designated, well-managed and enforced marine protected areas to support healthy ecosystems with thriving biodiversity and fisheries that communities rely on for food and livelihoods. Achieving these objectives by strengthening marine science expertise, developing evidence-based policy and management tools, and creating educational resources for coastal communities.

JNCC, on behalf of the OCPP, is working in collaboration with the Sri Lankan Government and other key stakeholders to provide technical advice and assistance on MPAs and marine biodiversity.

This contract is being delivered on behalf of the Government of Sri Lanka.

## Project Aims

This contract is focused on mapping the distribution and spatial extent of Sri Lanka’s existing MPA network, which includes the following designations:

- Marine Sanctuaries

- Marine Reserves

- Fisheries Management Areas

- Special Management Areas

This contract will also include geospatial analysis of Sri Lanka’s existing MPA network to identify areas of spatial overlap between individual designations.

The outputs of this contract will help inform the future sustainable management of Sri Lanka’s MPAs and its wider marine area.

## Project Objectives

The objectives of this contract are:

- Produce a publicly accessible map of Sri Lanka’s existing MPA network

The following activities are required to successfully complete this objective:

- Collate data on the extent and spatial distribution of Sri Lanka’s existing MPAs, including legislated boundaries and any associated metadata (for example, designating legislation, any existing management measures and designated features) for:

  - Marine Sanctuaries and Marine Reserves from the Department of Wildlife Conservation

  - Fisheries Management Areas from the Department of Fisheries and Aquatic Resources

  - Special Management Areas from the Coast Conservation and Coastal Resource Management

- Create a user-accessible map of Sri Lanka’s existing MPA network (including associated spatial layers) that can be shared and utilised by a range of stakeholders, including government departments and non-governmental organisations (NGOs).

- Ensure mapping outputs meet Crown Copyright requirements and are made publicly available.

- Expand and improve the map of Sri Lanka’s existing MPA network, produced under Objective 1.

- The following activities are required to successfully complete this objective:

  - Further develop the map of Sri Lanka’s existing MPA network map by adapting it to include more accurate MPA boundary data (where applicable/available) and data on the extent and distribution of important marine habitats and species.

- Undertake an assessment of Sri Lanka’s existing MPA network and provide recommendations within a summary report:

- The following activities are required to successfully complete this objective:

  - Identify and quantify existing spatial overlaps between protection designations i.e. Marine Sanctuaries, Marine Reserves, Fisheries Management Areas, and Special Management Areas.

  - Identify potential conflicts, or benefits, of existing spatial overlaps.

    - This could include if relevant, legislative and management requirements and restrictions, remits and responsibilities of differing government departments, other users of the marine space and local stakeholders understanding of existing protection and management.

  - Provide recommendations for areas of spatial overlap between existing MPA designations to support the ambition for an ecologically coherent, sustainably managed MPA network in Sri Lanka.

- Initiate MPA-specific working groups to enable regular communication and collaboration to improve outcomes for MPA management amongst key stakeholder groups.

  - Work alongside existing projects and programmes that have, or may be planning to, set up similar MPA-specific working groups to prevent duplication of effort and make best use of stakeholders time.

  - Undertake sufficient identification of relevant stakeholders to include in each MPA-specific working group, ensuring to include community groups where appropriate.

  - Ensure Terms of Reference and other relevant documentation produced, to allow the working groups to continue beyond the end of the contract period. The contractor should consider other avenues to ensure the work/ relationships are maintained beyond the life of the contract where appropriate.

  - Ensure that Safeguarding and Gender, Equality and Social Inclusion (GESI) principles are considered and implemented (where appropriate) when engaging with in-country stakeholders and establishing working groups.

## Contractor Requirements

The successful contractor should have:

- Good working knowledge and previous experience supporting conservation and biodiversity projects, or programmes, ideally in Sri Lanka’s marine environment

- Experience of successfully collaborating with government, NGOs, and Universities ideally in Sri Lanka and fostering an inclusive, equitable and accessible approach to engagement.

- Experience of producing scientific reports, collating a range of information sources to draw robust, evidence-based conclusions and recommendations.

## Potential Follow-On Work

Bidders should be aware that there is the potential for the successful bidder to be requested by JNCC to undertake additional work on this contract into the financial year 2025/26.

Please note however that the potential for additional work to be undertaken is subject to a continuing need, availability of funds and satisfactory contractor performance. For the avoidance of doubt, no guarantee can be given that you will be asked to undertake the potential additional work outlined within this Annex A document. Bidders are not asked to provide detailed project plans for these follow-on aspects at this stage.

## Product Specification

JNCC is committed to making its publicly available resources and documents accessible, in accordance with the Public Sector Bodies (Websites and Mobile Applications) (No. 2) Accessibility Regulations 2018.

Making material accessible means making sure it can be used by as many people as possible, including those with:

- impaired vision

- motor difficulties

- cognitive impairments or learning disabilities

- deafness or impaired hearing

The outputs and material that JNCC publishes should be compliant with the Web Content Accessibility Guidelines version 2.1 AA standard.

## Timescale

Provisional dates for delivery of the contract outputs are set out below. Exact dates are to be agreed at the start-up meeting based on Contractor and JNCC staff availability.

| Output | Provisional Date |
| --- | --- |
| Start-up meeting (via video call) | 15th July 2024 |
| Proposed workplan provided by contractor | 29th July 2024 |
| MPA network map and associated spatial layer files | 21st October 2024 |
| Expanded MPA network map and associated spatial layer files | 18th November 2024 |
| Report documenting analysis of overlapping protections and recommendations | 10th March 2025 |
| Final products delivered | 31st March 2025 |

## Health and Safety

The successful bidder is expected to follow appropriate Health and Safety Procedures including adhering to JNCC’ policy on safeguarding. For further information  https://jncc.gov.uk/about-jncc/corporate-information/safeguarding/ and to be able to undertake appropriate risk assessments, evidence of which should be supplied to JNCC.

Any incidents occurring within the contract period should be immediately reported to JNCC.

## Project Management

The successful bidder shall nominate a project manager who shall be responsible for ensuring the project is completed satisfactorily and who shall be the main contact point for JNCC.

JNCC’s main contact points will be:

Name: Hannah Lawson

Email: Hannah.lawson@jncc.gov.uk

Telephone: (+44) 07503535710

Name: Holly Baigent

Email:  holly.baigent@jncc.gov.uk

Telephone: (+44) (0) 1733 562626

## Instructions for Bid Submission

The bid submission should include the following:

A brief summary of the bidder’s experience in relation to the requirements of this contract

A proposed approach for achieving the objectives of the contract and delivering the detailed tasks identified within each objective. This should be sufficiently detailed to allow assessment against the evaluation criteria (Section 12)

A project plan and an estimate of time required to achieve each objective

Details of the project team including their roles and experience

Overall quote for the contract (in GBP) should include:

  - Attending virtual start-up, interim and final meetings with JNCC project team

  - Costs and time allocation should be clearly allocated to specific tasks within this contract/project

The following documentation (to submit in a zip folder separate from the proposal):

  - If your company includes more than five employees, please provide copies of health and safety policy statements where available or a note regarding such items as lone working, emergency procedures and accident reporting

  - Copies of current public and employer liability insurance certificates

The bid submission should provide sufficient information to allow assessment against the evaluation criteria outlined in section 12.

## Evaluation Criteria

JNCC is not bound to accept the lowest priced or any bid. Having the technical expertise and experience to complete the work to a high standard and being able to complete it within the timescale are of the essence for this contract.

The bid evaluation may be undertaken by JNCC staff.

For information on how we handle personal data please see our Privacy Notice at https://jncc.gov.uk/about-jncc/corporate-information/privacy-statement/

Bids will be evaluated using the following criteria:

|  | EVALUATION CRITERIA | Maximum Score | Score |
| --- | --- | --- | --- |
| 1. Quality of Bid (40% of the total for the three assessment categories) |  |  |  |
| 1 | Clarity of proposal particularly work programme and deliverables | 15 |  |
| 2 | Understanding of the requirements and adequacy of outputs | 15 |  |
| 3 | Soundness and logicality of methods | 5 |  |
| 4 | Identification and proposed solutions to potential risks/issues which threaten success | 5 |  |
|  | Sub Total | 40 |  |
| 2. Details of Contractor (45% of the total for the three assessment categories) |  |  |  |
| 5 | Relevant experience and knowledge of Sri Lanka’s marine environment. | 15 |  |
| 6 | Experience successfully collaborating with wide range of Sri Lanka marine stakeholders including government departments and NGOs. | 15 |  |
| 7 | Experience collating and analysing wide range of information to draw evidence-based observations and recommendations. | 15 |  |
|  | Sub Total | 45 |  |
| 3. Cost (15% of the total for the three assessment categories) |  |  |  |
| 8 | Transparency and correctness of presentation | 10 |  |
| 9 | Fairness/reasonableness for the level of work and expertise required | 5 |  |
|  | Sub Total | 15 |  |
| Total Score |  | 100 |  |

## Payment

PLEASE NOTE: All quotes and all payments must be based on British Pounds (£). If alternative currency payments are needed, please raise this at the earliest opportunity during the bid process so we can explore options.

Payment will be made on completion of the objectives following the submission of invoice(s) and based on the satisfactory undertaking of the contractual elements to the agreed standard of the JNCC Project Officer.

## Additional Requirements

All bidders are requested to carefully read the Terms and Conditions applying to this contract. Payment will only be made upon delivery of key outputs.

It is assumed that all costs associated with the production of figures, reproduction of photographs and the final report are accounted for within the rates/fees given.

The bidder is expected to supply all necessary equipment, software, licences, etc. to carry out the obligations required under the contract.

## Procurement Timetable (which may be subject to change)

| Activity | Date |
| --- | --- |
| Publication of Contract Notice | 24 June 2024 |
| Last date for receipt of clarification questions | 1 July 2024 |
| Final submission date for bids | 8 July 2024 |