|  |  | EXPRESSION OF INTEREST |  |  |  |
| --- | --- | --- | --- | --- | --- |
| PROJECT TITLE: |  | Teaching and Learning International Survey (TALIS) 2018 Video Study |  |  |  |
| PROJECT REFERENCE NUMBER: |  |  |  | 2015/030 |  |
| DEADLINE FOR EXPRESSIONS OF INTEREST: |  |  |  |  |  |
| Expressions of interest are sought for a contractor, or consortia with lead contractor, to implement the TALIS Video Study in England. This expression of interest was posted on w/c 14 March 2016. |  |  |  |  |  |
| BACKGROUND | The TALIS Video Study is an innovative complement to OECD’s Teaching and Learning International Study. It will involve the development of new research and instruments that have not been applied on such a large scale before, especially for cross-cultural comparisons. Several countries are taking part in the TALIS Video Study and an International Study Consortium has been set up to coordinate and oversee the work across the countries involved. It is anticipated that the following activities will take place in each country: - Gathering and analysing representative video evidence of teaching practice and associated classroom artefacts, such as lesson plans and pupil work; - Collecting additional data via surveys with teachers and pupils, including administering pre- and post- mathematics tests with pupils, developed by the International Study Consortium; and, - Reporting findings from all aspects. Due to the OECD timelines, some of the decisions on the development of the study instruments and procedures will be taking place, with DfE involvement, prior to the appointment of the successful contractor. It is therefore important that the successful contractor is flexible and can work with these internationally agreed processes. |  |  |  |  |
| EVALUATION AIMS | The objectives of the TALIS Video Study are to provide policy relevant knowledge, understanding and analysis about effective teaching practices and the relationship between teaching practices and pupils’ outcomes in a timely and cost effective manner. The research study will aim to achieve three main aims: - To observe and document the variety of mathematics teaching practices within England; - To identify aspects of “good teaching”, as identified in TALIS and other studies; and, - To examine the relationships between teaching practices, learning outcomes and other measures of teaching. |  |  |  |  |
| METHODOLOGY | The research will take place in three main stages, outlined below: study development, implementation, and data analysis and reporting. The contractor is expected to participate in planning meetings with both the DfE and the International Study Consortium at regular intervals throughout the study, as outlined below for the first phase. International travel will therefore be required. Phase 1: Study Development, February 2016 to April 2017 The TALIS video study development phase has already begun, with DfE involvement. We anticipate that the successful contractor will start in May/June 2016, which does mean that some decisions regarding the development of the study instruments and procedures will already be set in place: it is therefore important that the successful contractor is able to work within the agreed protocols for the study. DfE will provide the successful contractor with reports on all development activities thus far, and will provide support at meetings with the International Study Consortium. Activities expected from May/June 2016 to April 2017 include: - Finalising the development of all instruments, including observation protocols, guidelines, collection of classroom artefacts, pupil and teacher questionnaires, and pre- and post- pupils tests; - Identifying a sampling strategy and plan, and recruiting and working with schools to conduct pilot observations to capture lessons on a particular mathematical concept; and, - Conducting, analysing and reporting findings from pilot video observations in secondary schools in England in January/February 2017, with approximately 10 teachers, in two lessons each, on a as yet to be agreed aspect of the mathematics curriculum for Year 9 pupils. The aspect to be observed will be decided during Summer 2016. Key meetings in the first phase with the International Study Consortium include: - Meeting in June/July 2016 to discuss: the video and audio technology to be used; topics for inclusion in questionnaires; and plans for recruiting schools and teachers; - Meeting in December 2016 to review: plans for teacher and pupil questionnaires; sampling schools and teachers; and consent forms; and, - Meeting in Spring 2017 to review results across the countries involved, transference of data, and finalising the main sample. Phase 2: Implementation, January 2017 to May 2018 - Recruiting and working with schools to conduct the main stage video observations of a minimum of 85 teachers, in two lessons with Year 9 pupils, on a particular aspect of the mathematics curriculum, which will be agreed in Summer 2016. The contractor will be expected to work with schools over a wide study window to establish when that aspect is taught during the school year and to ensure those lessons are observed and videotaped; - Administering surveys to teachers and pupils, either online or via paper, and administering pre- and post- tests to pupils of selected teachers; - Analysis and reporting findings across the range of data collected during the main stage of the project Phase 3: Data Analysis and Reporting, January/February 2018 The main aspects of work allocated to this phase will be conducted by the International Study Consortium between January and December 2018. The contractor will be responsible for transferring data to the Consortium in January/February 2018. |  |  |  |  |
| TIMING | The main OECD timelines relevant to the work required for the TALIS Video Study are outlined above. Below are the timings for commissioning the England aspect. - Deadline for EOIs – 5pm Friday 8th April 2016 - Invitations to Tender issued – Thursday 14th April 2016 - Deadline for ITT submission – noon Thursday 5th May 2016 - Interviews – Wednesday 19th May 2016 - Set-up/initiation meeting – Wednesday 26th May 2016 |  |  |  |  |
| ASSESSMENT CRITERIA | Expressions of interest will be assessed against the following criteria: - Relevant research experience, i.e. conducting video observations of teachers and pupils; administering surveys with teachers and pupils; administering pre- and post- test with pupils; and coding, rating and analysing video observations and survey data (40%); - Project management and capacity to undertake the work within tight deadlines. Experience of conducting international research studies (or comparable studies involving collaboration across multiple organisations) would be an advantage. (40%); - An understanding of the teaching of mathematics and the mathematics curriculum in secondary schools in England (20%). CVs and references are not required at this stage. |  |  |  |  |
| Expressions of interests submitted must be no more than 1,000 words overall. Please do NOT include website links or references. Anything longer than 1,000 words wil be disregarded. Expressions of interest are welcome from collaborations or consortiums. |  |  |  |  |  |
| Closing date for EOIs: |  |  | 5pm Friday 8th April 2016 |  |  |
| Send your EOI form to: |  |  | Nicola.MACKENZIE@education.gsi.gov.uk Frances.FORSYTH@education.gsi.gov.uk |  |  |
| HOW TO SUBMIT AN EOI You must submit an expression of interest (EOI) in order to be considered to be invited to tender. To do so, please complete the Expression of Interest Research template found on the Department’s Research website. A submission of an EOI does not guarantee an invitation to tender and the Department does not routinely advise organisations that they have not been successful in being invited to tender. Feedback is however available on request. In order to express an interest you must be registered with us and you will need your ID number. If you need to register then please do so using the online Supplier Registration Form. If you have already registered and have forgotten your ID number, please send an email to Enquiries.RBU@education.gsi.gov.uk All contracts are let on the basis of the Department’s Terms and Conditions. You are encouraged to check these before submitting your expression of interest, as these form part of your contractual obligations. |  |  |  |  |  |