## Shiplake Specification
TITLE | PRICED RETURN - SCHEDULE OF WORKS
Client : | Environment Agency
Project: | Shiplake Lock House - Void Refurbishment
Address: | Shiplake Lock House, Mill Lane, Shiplake, Henley-on-Thames, RG9 3NA
Contract: | JCT Minor Works
Issue Date: | 2023-01-12
Version: | Tender Issue - SHIPVOID23PJS
Tender Return Date | Monday 30th January 16:00
Contractor: | TBC
Contents list
Section
A | Preambles
A1 - Environment Agency Priorities
A2 - General
A3 - The Site/Particulars of the Work
A4 - Contract
B | Preliminaries
C | Schedule of Work
D | Pricing Summary Page
Appendicies | Appendix A SHEW CoP
Appendix B - Pre-Construction Information
Appendix C - Drawings
Appendix D - Kitchen Design
ITEM | DESCRIPTION OF WORKS |  | Unit | Item | Rate | Total
A | PREAMBLES
A1 | ENVIRONMENT AGENCY PRIORITIES
A1.1 | CARE OF THE ENVIRONMENT AND WILDLIFE: The Environment Agency is committed to the care and sustainability of the natural environment and its wildlife. It is essential that the greatest possible care be taken at all times to prevent any damage or pollution to the natural environment and its plant and animal wildlife. |  | - | Note | - | -
A1.2 | ENVIRONMENT AGENCY SITES: Most Environment Agency Sites are located near water with working lock gates and lock staff private facilities. All contractors must liaise with the lock keeper daily and at times when crossing lock gates is necessary and will be directed to work safely and within appropriate timescales |  | - | Note | - | -
A1.3 | PUBLIC ACCESS: Some lock sites have public footpaths across the lock gates and the island sites and the EA are committed to ensuring this access is retained safely throughout the works. It is the contractors responsibility to ensure that all works, including deliveries and transport of materials and equipment to and from site is undertaken in a safe and considerate way limiting risks to the their staff, the general public, EA staff and river users. |  | - | Note | - | -
A1.4 | ENVIRONMENT AGENCYS CORE HEALTH AND SAFETY VALUES ARE: All of us have the right to remain healthy and injury free at work. We are all vital to improving health and safety and we will: · work to prevent all injuries and occupational illnesses · all be responsible for health and safety · always check and learn from what we are doing · challenge and respond to challenge Remember health and safety is a way of life both at home and at work. “Constructing a better environment” applies to all works to residential properties. In all instances the principal contractor and contractor’s performance will be expected to meet or exceed the minimum standards required under the appropriate legislation. |  | - | Note | - | -
A1.5 | COMPETANCE AND TRAINING: TheEnvironment Agency has very specific competence and training requirements as detailed in “Safety is Paramount constructing a better environment”. The PC must ensure these are adhered to: · All operatives must hold a current CSCS card · All supervisors must hold a current SMSTS or SSSTS or CSCS Gold Card · Specific and relevant current qualifications must be held by those undertaking such tasks as erecting and checking scaffolding (CISRS) and scaffold towers (PASMA) or operating MEWP (IPAF) · Full access scaffolding must be erected by a NASC registered scaffolding company and must be tagged prior to use and regularly inspected |  | - | Note | - | -
A2 | GENERALLY
A2.1 | Where proprietary items are specified within this Works section and the preceding section, they must be installed in strict accordance with the manufacturer's recommendations and instructions. |  | - | Note | - | -
A2.2 | All proprietary items are to be installed by contractors approved by the supplier and the Contract Administrator. |  | - | Note | - | -
A2.3 | All provisional sums, provisional quantities and PC Sums are to be directed by the Contract Administrator. |  | - | Note | - | -
A2.4 | The siting of builders skips shall be agreed prior to commencement of works and the Contractor must obtain a licence for any skips deposited on the public highway and to conform to all conditions contained therein. Skips are to be removed from site promptly when full and replaced and provided with a secured cover at all times |  | - | Note | - | -
A2.5 | The siting of contractor's plant and stored materials within the boundaries of the premises are to be agreed with the Contract Administrator. |  | - | Note | - | -
A2.6 | Note: Before tendering, the contractor should examine the drawings and specification documents visible in Appendix to this schedule of works document, visit the site, check all measurements and dimensions and ascertain all local conditions and restrictions, accessibility, the full extent and nature of the work, the supply and conditions affecting labour and the execution of the contract generally. No claims arising from failure to do so will be considered. |  | - | Note | - | -
A3 | THE SITE/PARTICULARS OF THE WORK
A3.1 | DESCRIPTION OF THE WORK: The work comprises the internal redecoration and minor upgrades of the lock keepers house at Shiplake Lock. The works include the upgrading of the insulation in the roofspace and to the bay window, full redecoration throughout, the replacement of the kitchen units and floor and the replacement of the first floor carpets as detailed in the Scope of the Works |  | - | Note | - | -
A3.2 | LOCATION: Shiplake Lock house is located on an island site accessed from a narrow lane where there is limited parking then along a public footpath over a footbridge to the lock and across the lock gates to the island site where the house is located. The lock keeper on the site will be moving into the lock house once it has been refurbished. The house stands within its own privave garden enclosed by low timber fencing separating it from the river and additional land which is owned by other land users. The property is vacant for the duration of the contract |  | - | Note | - | -
A3.3 | TIMESCALE FOR COMPLETION OF THE WORKS: The works will be started on site Date to be arranged - Mid February Suggested 2 weeks after the acceptance of the tender and the Construction Phase Plan The works will be completed during a 6-8 week period |  | - | Note | - | -
A3.4 | EMPLOYER: The Environment Agency, Estates Department, Kings Meadow House, Kings Meadow Road, Reading, RG1 8DQ |  | - | Note | - | -
A3.5 | CONTRACT ADMINISTRATOR: (hereinafter referred abbreviated as CA): Mrs P J Salbany, Environment Agency based at Kings Meadow House Mob 07425 620502 (SECONDARY POINT OF CONTACT: Mrs Kathryn Forster, Environment Agency Mob 07795 883547 |  | - | Note | - | -
A3.6 | EA PERSONELLE RESPONSIBLE FOR THE LOCK SITE: TBC Mob - to be provided once contract awarded |  | - | Note | - | -
A3.7 | EXISTING MAINS/SERVICES: Identify, protect, uphold and maintain any existing services, live drainage, ducts, water, electric, oil and other mains resources found during the carrying out of the Works. If any are damaged reinstate them before leaving site. Be liable for an indemnify The EA against any expense, liability or loss, claim or proceedings provided always that the damage is due to any negligence, omission or default of the Contractor's workpeople or sub-contractors |  | - | Note | - | -
A3.8 | A HEALTH & SAFETY FILE for the site is not available - however information will be passed to the contractor as part of this tender package including; EA SHEW CoP (Safety Health Environment & Wellbeing Code of Practice), Pre-Contruction Information including Asbestos Survey, Drawings including Site Plan, Existing Ground and First Floor Plans & Services Plan. |  | - | Note | - | -
A3.9 | RESTRICTION OF WORKING HOURS: Normal working hours will be 8am - 5.00pm, Monday to Friday - any working outside these hours must be agreed in advance with the CA Contractors are to report to the Lock Keeper daily upon arrival and departure |  | - | Note | - | -
A3.10 | ACCESS TO THE SITE FOR THE WORKS: The access road is Mill Lane and this is a public highway with limited parking to one side. The contractor is responsible for ensuring suitable delivery vehicles are provided when bringing materials and equipment to site. Access roads are not to be blocked at any time as access for emergency vehicles is required 24/7 for other residents along Mill Lane |  | - | Note | - | -
A3.11 | PARKING: Contractors and Employees vehicles - there is limited space for parking vehicles and limited turning space. Remote and limited parking for 1no. Contractor Van is usually available on Mill Lane any additional vehicles or deliveries to be managed by the contractor and agreed with the lock keeper and the CA prior to commencement. Space to be maintained for emergency vehicles 24/7 |  | - | Note | - | -
A3.12 | SITE WELFARE FACILITIES/SITE ACCOMMODATION - The house with its services and facilities are available for use througout the contract period. If at any time the kitchen is out of action due to the works there is an additional facility available for contractor use in the Lock Keepers mess room - this space must be kept clean and tidy and will be used by other EA staff working on site. |  | - | Note | - | -
A3.13 | SECURITY: Hording, Fences and Gates: There is no public footpath across this island site and the garden is private - however there is access to other areas of the island by members of the public who are making use of mooring facilities and camping. Public access is also permitted within the lock area for boat users and other small craft. It is the Contractors responsibility to keep the works secure and separate from members of the public and other personelle on site. |  | - | Note | - | -
A3.13 | SMOKING/VAPING: Not permitted on site |  | - | Note | - | -
A3.14 | NOISE: The use of radios or other audio equipment is not permitted |  | - | Note | - | -
A3.15 | SITE WASTE MANAGEMENT: The contractor is to separate out construction waste where possible and ensure that all opportunities to reuse and recycle site waste. Making use of a licenced waste carrier that carries out recycling of waste material is essential to this project to manage finite resources and prevent waste and a Waste Transfer Note will be required for all waste removed from site. Burning of waste materials is not permitted on site at any time The contractor must take all reasonable precautions to prevent pollution The use of pesticides and/or biocides is not permitted The site is on a septic tank and as such no waste material is to be flushed down sinks, WCs or drains especially with regards to painting, all brushes are to be cleaned in contractors buckets and any cleaners and thinners are to be taken off site and not discarded down the drains or anywhere else on site. All waste material will need to be carried across the lock gates, bridge and footpath safely and taken away in contractors vans - or if a skip is required then it is the contractors responsibility to obtain the necessary permits from the highways authority or local authority |  | - | Note | - | -
A3.16 | DEFECTS IN EXISTING CONSTRUCTION: Report to the CA without delay with possible solutions and prices for rectification where possible |  | - | Note | - | -
A3.17 | HOT WORKS: Hot works are not permitted without the prior approval of the CA and the issue of a Hot Works Permit which the contractor is to self manage |  | - | Note | - | -
A3.18 | NAME BOARDS/ADVERTISMENTS: Contractors name boards or advertisments will not be permitted except with the prior approval of the CA |  | - | Note | - | -
A4 | CONTRACT: JCT MINOR WORKS AGREEMENT
A4.1 | The contract to be used is the JCT Minor Works Contract |  | - | Note | - | -
A4.2 | DATE OF COMMENCEMENT OF THE WORKS: To be agreed |  | - | Note | - | -
A4.3 | LIQUIDATED DAMAGES: £250/week |  | - | Note | - | -
A4.4 | RECTIFICATION PERIOD: 12 months |  | - | Note | - | -
A4.5 | PERCENTAGE OF THE VALUE OF THE WORKS: 95% |  | - | Note | - | -
A4.6 | SUPPLY OF DOCUMENTATION: 3 months |  | - | Note | - | -
A4.7 | CONTRACTORS INSURANCE: Public Liability of £5,000,000.00 for single claim and suitable levels of insurance to cover the Insurance of the works and Employers Liabilty Before starting works on site the Contractor is to submit documentary evidence of the insurances required |  | - | Note | - | -
B | PRELIMINARIES
B1.1 | Allow for all necessary preliminaries, plant, machinery, scaffolding where required and attendance, in order to comply with the proceeding and foregoing sections. Any scaffolding must be erected by a NASC registered scaffolder and all mobile or tower access scaffolding must be erected by a PASMA certified opperator | £ | 1 | Item
B1.2 | CDM REGULATIONS: Allow for acting as Principle Contractor under CDM regulations, including Health and Safety in line with attached EA SHEW CoP. Include for all H&S Signage, fencing, fire extinguishers, notifications, safety plans and provide information for safety files. The contractor will need to provide details of their proposed working methods at the time of tender to ensure that they have fully considered these requirements. These will be assessed by the project team including the Client, Contract Administrator and Principal Designer/CDM Coordinator as part of the overall selection procedure. | £ | 1 | Item
B1.3 | PROJECT MANAGER - The contractor is to provide a suitably qualified and experience Project Manager and/or Site Foreman as necessary to manage the works throughout the project - With the minimum qualification of SSSTS, CSCS Gold Card and SMSTS for management of any sub-contractors (evidence to be provided) | £ | 1 | Item
B1.4 | REPORTING: The Contactor is to allow for regular weekly reporting of progress including any issues to the CA in the form of face to face or virtual meetings. The contractor must inform the CA of any issue as they arrise to ensure they can be dealt with quickly and not cause delay to the works. Should there be any time when the CA cannot be contacted the contractor must manage the works so that progress can be maintained in alternative locations of the site | £ | 1 | Item
B1.5 | WORKING AT HEIGHT: The contractor is to provide safe and suitable means of working at height where required and in accordance with CDM best practice. | £ | 1 | Item
B1.6 | SITE ACCESS: The contractor is to provide safe and suitable access for site operatives and materials. This will include a Site Traffic Managment Plan which must include details on deliveries and storage of materials. Safe passage across the lock gates to the island site must also be included - this could be by hand or by boat but it will be the contractor who must arrange and manage this alongside the direction of the lock keeper. Life jackets will be necessary when working close to water - this includes deliveries to and from the site across the lock gates and within 2m of the waters edge | £ | 1 | Item
B1.7 | SECURITY OF THE BUILDING: The contractor is responsible for ensuring the building is kept secure, wind and watertight at all times. Any damage caused to the building as a result of insufficient security, wind and weatherproofing measures during these works must be immediately remedied at the contractors cost. | £ | 1 | Item
|  | £ | 1 | Item
B1.8 | SEPARATION OF THE WORKS: The Contractor is to include for the provision of warning barriers around the works, including areas used for storage of materials during the course of the contract, inclusive of warning notices and safety tape/bollards etc. | £ | 1 | Item
B1.9 | COORDINATION OF THE WORKS: Allow to arrange, coordinate and monitor a programme with each subcontractor, supplier, local authority and statutory undertaker, and obtain and supply information as necessary for coordination of the work on site. | £ | 1 | Item
B1.10 | The contractor must provide product guarentees and site H&S plan at end of works, including opperating and maintenance manuals for any newly installed products and materials | £ | 1 | Item
B1.11 | The contractor is to provide progress photos of insulation upgrades | £ | 1 | Item
B1.12 | CLEANING: The site is to be kept tidy througout the building process and waste must be regularly cleared from site and not permitted to build up to excessive levels. | £ | 1 | Item
B1.13 | FINAL CLEAN: Prior to handover the contractor must allow for a Complete Builders Clean including all internal surfaces and internal glazing. | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C | SCHEDULE OF WORKS
C0.1 | Please note that existing plan drawings have been included in Appendix C of this tender document and Proposed Drawings of the new kitchen replacement are provided by Benchmarx. Drawings are to scale when printed at A3 however it is the Contractors responsibility to ensure dimentions are checked on site prior to the submission of any prices |  | - | Note | - | -
C0.2 | The Contractor must, when pricing this Schedule of Works, take into consideration the requirements within all sections of this specifiation and the attached Appendicies of this tender document. Failure to do so will be at the risk of the Contractor. |  | - | Note | - | -
C0.3 | Not withstanding the conditions set out in the ‘National Building Specification’ guidelines and the ‘Standard Method of Measurement’ 7th Edition. The Contractor’s general cost items are to be priced in accordance with the ‘RICS New Rules of Measurement’ volume 2, 1st edition, (RICS:NRM-2 v1). |  | - | Note | - | -
C1 | DEMOLITION AND STRIP OUT WORKS
C1.0 | The Contractor is to review the asbestos refurbishment survey which is included within the PCI Document and can be found in Appendix B of this tender document. Please note no Asbestos has been identified in the refurbishment survey. However should the contractor identify anything that he considers suspected to include Asbestos work must stop in the location and the EA must be contacted immediately. |  | - | Note | - | -
C1.1 | Remove the existing kitchen units, work tops and tiled fininshes and clear from site. Disconnect the sink and cap off the waste and water pipes and clear from site. Remove the floor covering to the kitchen and clear from site | £ | 1 | Item
C1.2 | Carefully remove the blinds to the kitchen windows and store on site temporarily for refitting following the addition of insulation and redecoration
C1.3 | Allow to remove all nails and fixtures to all walls. (investigate minor areas of damp in bedroom historic leak to ceiling of bedroom 1 & 2 Ceilings and front wall to bedroom 3 - possible staining below bath leak | £ | 1 | Item
C1.4 | Remove wall paper finishes from all walls and allow to wash down all walls, skeilings and ceilings with sugar soap and/or dilute bleach solution or alternative anti-fungal wash to remove adhesive residue and any black mould growth. | £ | 1 | Item
C1.5 | Ensure a full layer of 100mm loft insulation is provided to whole loft space filling all gaps, remove the areas of boarding and any stored material and rubbish from the loft space | £ | 1 | Item
C1.6 | Carefully remove bath panel and set aside for re-fitting. Remove section of rotten skirting board and clear from site (take care not to damage floor finish or tiling) Remove damaged silicon sealant around top of bath and shower screen and to wall where bath panel was fitted and clear from site Investigate what is causing leak and rectify | £ | 1 | Item
C1.7 | Allow to drain down heating system and remove radiator within bay window of kithchen prior to installing internal wall insulation to the external walls of the kitchen as detailed on attached plan | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C2 | PREPARATION AND REPAIR
C2.1 | Allow to replace section of rotten skirting to bathroom with pre-primed softwood to match the profile of existing (conceal joint behind WC) Re-seal around bath and shower screen with white anty fungal silicoln sealant in strict accordance with manufactures recommendations and test to ensure water is not getting around the back (reseal bath while it is filled with water or has weight in it to ensure seal doesn't break with added weight) Allow to refit and reseal bath panel Allow to refix floor covering following decoration of new length of skirting | £ | 1 | Item
C2.3 | Allow to fill all areas of minor cracking to plastered walls and ceiling prior to decoration. Rake out cracks to 3mm minimum or sound base and remove all loose material. Fill as required with suitable fine finishing filler and allow to dry and prepare to smooth finish ready to receive painted finish | £ | 1 | Item
C2.4 | Prepare all areas where plaster has been stained with previous damp marks with 1 no coat of stain block paint prior to redecoration | £ | 1 | Item
C2.5 | Allow to scrape off all areas of flaking paint to walls and ceilings and inappropriate paint to radiators and prepare prior to full redecoration | £ | 1 | Item
C2.6 | Allow to extend and adapt the heating pipes to accommodate the new internal wall insualtion within the bay window of the kitchen and to provide an additional radiator to the kitchen on the wall to the left of the wood burning stove
C2.7 | Allow to carefully lift the floor boards to the kitchen area and set aside for refitting following the installation of insulation between the joists Supply and fix 25mm treated timber battens fixed to the bottom inner face of each of the joists as detailed in manufacturers retrofit in instructions. Supply and fit 6mm OSB sheets between the joists supported on the battens. Supply and fix 100mm IndiNature IndiTherm Hemp Flexibatt Insulation between the floor joists supported on the OSB - ensure that the flexibatts are cut slightly larger than the gap between the floor joists so that they and slightly squashed when fitted and expand to fill the space completely right up to the edges of the joists https://cdn.shopify.com/s/files/1/0024/1270/7886/files/IndiNature_IndiThermInstallGuide_1_92022.pdf?v=1669134510 (Page 17) Refix floor boards to reinstate the floor to the kitchen prior to installing a new floor fininsh | £ | 1 | Item
|  | £ | 1 | Item
C2.8 | Allow to extend the water pipes and waste pipes from the kitchen sink and dishwasher to accommodate the internal wall insulation on this wall (as shown by blue line on plan)
C2.9 | NB - The EA Framework electrical contractor will remove the electrical sockets from the external walls in the kitchen where the internal wall insualtion is to be fixed - ensure the cables are pulled through as the insulation is fitted to the walls so that the electricians can refix the socket boxes following the fitting of the internal wall insulation |  |  | note
C2.10 | Allow to prepare all new areas of plaster with 2no. mist coats prior to full redecoration (NB - all areas of new lime plaster to receive suitable breathable waterbased paint fininsh such as Earthborne clay paint or similar alternative - not standard emulsion) |  | - | Note | - | -
C2.11 | Allow to rub down and prepare all areas of previously painted timber prior to full redecoration - remove all flaking paint, and prepare surface to ensure smooth finish ready to receive full redecoration including staircase (ensure carpets and floor coverings are protected) | £ | 1 | Item
C2.12 | Overhaul existing door handles and latches to internal doors and leave in full working order | £ | 1 | Item
C2.13 | Allow to upgrade the existing loft insulation to 300mm depth using Thermafleece, supersoft polyester insulation (made from recycled plastic bottles) new layers of insulation to be layed across the joists - ensure the insulatioin is held back from the eaves to allow ide an area of 2 sqm boarding on loft legs above the level of the insulation to provide a safe platform for future inspection | £ | 1 | Item
C2.14 | Supply and fix new 3 section aluminium loft ladder to provide safe access to the loft space. Adapt the existing loft hatch to accommodate the loft ladder - fix hinges to enable the loft hatch to swing down into the landing area - provide a loft hatch push catch and apply 40mm cellotex insulation to the back face of the loft hatch to provide suitable level of insulation | £ | 1 | Item
C2.15 | Supply and fix loft boards to provide an area of 1m wide to allow safe access into the loft and to the water tank for safe inspection - this boarded area is to be fixed on loft legs over the insulation to prevent it from being squashed down | £ | 1 | Item
C2.16 | Allow to take photographs of all works progressing especially the insulation upgrades which will be required as evidence for building regulations and future EPC surveys. Ensure that a measuring tape or rule is included in the photographs to detail the thickness of insulation provided within the floor voids, to the inner face of external walls and within the loft spaces. | £ | 1 | Item
C2.17 | Cut a new access hatch into the roof space over the utility room and provide a suitable part L compliant loft hatch | £ | 1 | Item
C2.18 | Supply and install Thermafleece supersoft polyester insulation to the roof space over the utiltiy room and adjoing external WC to ensure all areas are suitable insulated with 100mm insulation between the joists and 200 mm additional insulation over (to provide total 300mm covering) Ensure the eaves reamain open to provide adequate cross flow of air to vent the loft space. | £ | 1 | Item
C2.19 | Following the removal of all wall paper and all electrical fittings from the inner face of the external walls carefully remove the remove the skirting board within the bay window and any skirting board that has been retained behind the kitchen units and set aside for re-fixing. Prepare the wall to receive the internal wall insulation in strict accordance with manufacturers recommendations | £ | 1 | Item
C2.20
| Supply and fix insulation to inner face of 3 external walls to kitchen as detailed by the blue line on the basic proposed floor plan - from pantry to front wall around bay window and to return wall up to door to front hallway - provide a timber batten to the edge of the insulation by the pantry and the door to provide a suitable finishing point and protection to the edge of the insulation and to finish new plaster up to. Ensure that there is sufficiently strong fixing points where the kitchen wall cupboards are to be installed by providing timber battens over a thinner layer of insulation - to be discussed on site | £ | 1 | Item
C2.21 | Suppy and fix 60mm wood fibre insulation to all 3 external walls in kitchen in strict accordance with manufacturers recommendations and technical sheet for Ty-Mawr Internal Wall Insulation. https://www.lime.org.uk/applications/retrofit-insulation-systems-for-old-buildings/internal-wall-insulation-system/expanded-cork-insulation-system-7396.html Measure and cut boards to fit to wall with main bay window; 60mm below bay, to both angled sides of bay and returns into corners of wall facing over lock then extend to both returns to left side where sink unit is currently fitted to left of bay down to wall of pantry and to right of bay where cooker unit is currently fitted back to the doorway into the front entrance hall. Provide 20mm to window jambs and window heads and fininsh with the same lime plaster fininsh (detailed below). NB - if there is sufficient space to provid additional depth of insulation to the head of the bay window then increase the depth to upgrade this insulationprovide as much as possible Dampen surface of wall and ceiling and apply Iso-vit E-cork adhesive mortar using a 10mm notched trowel to ensure even coat Push room 140 wood fibre boards into the Iso-Vit adhesive mortar - drill and fix 2 anchors with large plastic washers into the middle of each board to hold in position - work from base up with staggered joints Allow to dry for 1 day prior to plastering Fix additional screws with engineered washers to each corner and 2 additional fixings to long sides and 1 to short sides (minimum) Provide a plaster finish in strict accordance with manufacturers recommendations using 9mm of lime hemp plaster applied in 2 layers while still wet with strenghthening mesh fixed between coats as detailed in manufacturers recommendations and leave to dry and brush to provide key When fully dry apply 1 no. 3mm finishing coat using Superfine fininsh coat as detailed in manufacturers recommendations and fininsh smooth with trowel or sponge ready to receive Clay paint finish. See Ty-Mawr Data Sheet for installation - https://drive.google.com/file/d/1-xlHLEyM1lO7Sgl5i-zDXutQb_-r2F7d/view Ensure photographs are taken throughout the process of each room to show level of insulation being installed to provide evidence of upgrade for EPC inspector - photographs to be forwarded to CA at end of contract as photographic evidence annotated to show what was done. | £ | 1 | Item
C2.22 | Allow to refix blinds to bay window and window over sink following re-decoration | £ | 1 | Item
C2.23 | Allow to refix skirting boards to front elevation within bay window make good or replace where required | £ | 1 | Item
C2.24 | Liaise with EA Electrical Framework contractor to return to site and refix electrical sockets and switches following the completion of the internal wall insualtion as required | £ | 1 | Item
C2.25 | Allow to replace bull nosed window board to bay window to extend 15mm further than fininshed face of new wall insulation Supply and fix new window board or splashback to provide a window board to window by sink - to be agreed on site | £ | 1 | Item
C2.26 | Supply and fix hardboard floor fininsh over existing floor boards prior to fitting new vinyl floor fininsh to kitchen | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C3 | KITCHEN
C3.1 | Allow to supply and install new Benchmarx Soho Midnight Blue kitchen as per layout plan and Benchmarx specification. Supply and install all base units, wall mounted units, plinths, doors and supports as necessary and as detailed in Benchmarx schedule of parts. NB - doors have integrated handles Allow to supply and install Leisure Linear 1 Bowl stainless steel sink and Chrome PPI Corte monobloc mixer tap. Sink located in similar position to existing sink unit ensure connections to all necessary water supplies and waste, trap and sink clips as per kitchen plan and seal the sink in place with clear silicon sealant. Existing cooker to be re-fitted and connected up by EA framework contractor. EA framework contractor to also fit cooker hood extracting externallyboth in the similar position as the existing. Supply and fit new 38mm Blocked Oak laminate work top. Supply and fix new splash back behind cooker and up to extractor fan and lower level upstand to other walls and behind sink. Fit new sink and taps and connect to hot and cold water and waste as required Provide new extended waster and water connections for plumbing in dishwasher | £ | 1 | Item
C3.2 | Allow to refix radiator within bay window to adapted pipework and supply and fix new radiator to left of wood burner (as big as space will accommodate - double panel radiator) | £ | 1 | Item
C3.3 | Supply and fix new double panel concector radiator within space to left of wood burner - length to be discussed onsite but as large as space will accommodate | £ | 1 | Item
C3.4 | Liaise with EA Framework Electrical Contractor to reinstate the electrical sockets and fused spurs for the cooker, cooker hood, undercounter fridge and dishwasher, to reconnect up the cooker and to provide additional double sockets and undercounter lights to the wall units and to reinstate the existing sockets |  |  | note
C3.5 | Allow to supply and fix new tiled wall fininsh or splash back finish to walls where kitchen units abut - full height behind cooker up to extract unit and to a height of 300mm or whatever suits chosen tiles to all other areas - this should include the upstand and window sill and reveals of the window adjacent to the sink unit. Colour of tiles or splash back to be agreed with EA prior to ordering | £ | 1 | Item
C3.6 | Supply and fit new Polyflor Expona Commercial Wood PUR floor finish in strict accordance with manufacturers recommendations. This floor fininsh it to be provided to the kitchen, into pantry and utility room by back door - French Vanilla Oak finish Floor to be fitted prior to the installation of the kitchen so that it goes right under the cupboards and into the spaces provided for the cooker, Dishwasher and fridge and no edges cut edges are provided to catch as white goods are moved in and out. | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C4 | EXTERNAL WORKS
C4.1 | Allow to carry out 10sq m of repointing in lime mortar with sharp sand to match the existing mortar as closely as possible - use NHL3.5 lime with no cement at a mix of 1:1:6 (1 part NHL 3.5 : 1 part stone dust : 6 parts sharp sand) - knock up using water but keep mixture as stiff as possible but fully mixed Rake out soft weathered and degraded pointing and locations where joints are not fulled sufficiently mostly under First floor windows over brick band and in sections of the brick band (possibly more areas at ground floor will be uncovered following vegetation cut back) - raking out to be undertaken using hand tools to a minimum depth of 20mm Brush out loose material from joints using stiff bristle brush Spray water into joints prior to adding mortar Push mortar into joints until almost flush with brick faces top and bottom - use a narrow pointing tool to ensure no lime mortar is smeared on brick faces Allow to partially cure and then using a piece of timber which has been cut to a 45 degree angle push mortar in further and finally tamp the surface of the mortar joints using a stiff bristle brush to reveal some of the sharp sand agregate Ensure that the new pointing is protected from extreme weather with hessian covering for at least 3 weeks until it has completely cured. Use similar lime mortar mix to provide mortar flaunching to the brick band to ensure water is shed away from the external wall of the house and to prevent water ingress. Ensure safe access is provided to carry out this work using either a scaffold tower | £ | 1 | Item
C4.2 | Cut back vegetation surrounding house to ground floor sill level and cut back from face of external walls to leave an air gap - remove the creaper growing over the front elevation and over the window of the hall and landing. | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C5 | DECORATION - DECORATE THROUGHOUT | £ | 1 | Item
C5.1 | The contractors internal redecoration costs are to include removal of isolated redundant fixings, making good any cracks, fixing holes and areas of damage prior to redecoration.
|  | £ | 1 | Item
C5.2 | Prior to decorating, allow to protect surfaces, floor finishes and all fixtures and fittings, allow to loosen light fittings, switches sockets and the like prior to decoration
|  | £ | 1 | Item
C5.3 | Allow to prepare all walls and ceilings where mould growth has been washed off and redecorate with Dulux Trade Mouldshield Fungicidal Matt paint in line with the manufacturers guidelines - colour to be brilliant white
C5.4 | Allow all areas of newly finished plaster to be allowed to dry out completely prior to redecoration. | £ | 1 | Item
C5.5 | Allow to decorate all new lime plaster to pitched ceilings with suitable breathable clay paint such as Earthborne paint or suitable alternative - apply in strict accordance with manufacturers recommendations - colour to be brilliant white and continue application onto main ceilings to obtain uniform finish to ceiling areas | £ | 1 | Item
C5.6 | Allow to decorate all previously painted walls and ground floor ceilings with 2 full coats of Dulux Trade Matt Emulsion paint fininsh in brilliant white | £ | 1 | Item
C5.7 | Allow to decorate all previously painted timber with 1no. undercoat and 2 no. full coats of Dulux satin wood pure brilliant white paint fininsh applied in strict accordance with manufacturers recommendations including hand rail and balustrading to staircase | £ | 1 | Item
CARRY FORWARD TO SECTION D (Summary Page)
C6 | ELECTRICS: For Information to be undertaken by EA Term Contractor Prior to construction works commencing
C6.1 | New Low Voltage down lighters to kitchen New Cabling for under counter lights to new kitchen Cabling for fused spur for extracting cooker hood - and fitting and connecting up cooker hood supplied by Benchmarx (including core drilling) New extractor fan to bathroom New shaver socket and light to bathroom Disconnect, store and reconnect cooker following new kitchen installation Mains wired smoke and heat detection system EICR 2 extra double sockets to kitchen; 1 to right of cooker with additional fused spur for fridge, 1 extra double socket to left of sink 1 additional double socket to understairs area Remove and refix electrical installations to external walls of kitchen prior to the installation of internal wall insulation |  |  | Note
C7 | Summary Page
| B -Preliminaries | £
C - Schedule of Works
| C1 - Demolition and Stripping out Works | £
| C2 - Preparation and Repair | £
| C3 - Kitchen | £
| C4 - External Works | £
| C5 - Decoration | £
| SUB-TOTAL | £
| CONTINGENCY SUM 10% | £
| GRAND TOTAL | £