## Cover
Ramp & Steps to Bat & Ball Station
including works to existing platform shelter
at
Sevenoaks Community Centre
Schedule of Works
30th January 2019

## Pricing Notes
£
PRICING NOTES
Pricing
1 | This section is to be read in conjunction with the following Documents accompanying the tender: | 1 | Item
Preliminaries and General Conditions
Drawings
Pre-Construction Information
2 | The items listed within this Schedule of Works are measured in accordance with the general principles of the New Rules of Measurement albeit that, due to the nature of the scheme, the work has been measured as ‘composite items’ and some of the descriptions require labours and items of a small nature to be included within the rates by the Contractor. The items are not exhaustive or intended to represent a detailed measurement of the works as required by the NRM but, by reference to the appropriate drawings, they are sufficient to identify the scope of the works involved and provide the necessary detail for the items to be priced. | 1 | Item
3 | Examples of classifications which have not been specifically measured as required by the NRM include the following and the Contractor’s rates are deemed to make due allowance as appropriate: | 1 | Item
Breaking up obstructions encountered in the ground
Excavating next to adjoining platforms, roads, buildings, in unstable ground, next to live services or below water level
Works to existing assets, e.g. the platform shelter
Ramp and step construction
Handrails and balustrades
Mechanical & Electrical Services
Drainage below ground water level or next to existing buildings, roads or services
4 | All sizes and dimensions quoted are approximate deemed to be finished sizes. | 1 | Item
The detailed composition of the items in the Measured Works is the responsibility of the Contractor. The rates and prices inserted are deemed to include for the following:
5 | The supply, delivery and installation of all items, unless specifically noted otherwise. | 1 | Item
6 | Everything necessary, including all items which, are reasonably apparent as being necessary, to execute the works to the satisfaction of the Employer | 1 | Item
7 | Executing the works in accordance with the programme, including any out-of-sequence working, piece-meal working, breaks in continuity and all non-productive overtime working deemed necessary. | 1 | Item
8 | Overheads and profit | 1 | Item
9 | A fully detailed breakdown of the Preliminaries costs is to be provided using the breakdown included within this Specification and Schedule of Works. | 1 | Item
10 | The Contractor’s tender is to be a fully fixed-price tender (excluding VAT). No allowance for fluctuations will be allowed over the duration of the works. | 1 | Item
11 | The Contractor is to fully price and extend all items in the Measured Works section and the totals carried forward to the Summary and General Summary to provide a fixed price tender sum. | 1 | Item
12 | This Specification and Schedules of Works contains formulae which require percentages and costs to be inserted into the 'rate' column for the totals to be calculated and transferred to the Summary and General Summary. Rates are to be inserted as numbers to 2 decimal places and not calculated from formulae or lump sums. The spreadsheets have not been protected and care should be taken not to overtype any of the formulae. Despite the inclusion of formulae within the pricing schedule, the Contractor must arithmetically check his tender prior to submission. | 1 | Item
13 | Unless specifically noted in the Contractor’s tender, the tender will be deemed to be fully compliant with the terms and conditions of the contract and to have been submitted without qualifications. | 1 | Item
14 | If the Contractor makes any amendments to the descriptions within the Measured Works section, these are to be readily identified. Failure to identify any such amendments will result in the original tender descriptions being deemed to be applicable. | 1 | Item
15 | The prices in the Measured Works section will be used for preparing valuations and for assessing the value of any variations to the scope of the works, which might be instructed. | 1 | Item
| PRICING NOTES |  |  | 0

## Preliminaries
£
PRELIMINARIES AND GENERAL CONDITIONS
The Contractor is to provide a breakdown of his Preliminaries costs for the items detailed within Section 1. The items listed below form the general format of the breakdown expected, but are not exhaustive; the Contractor is at liberty to insert additional items to suit his preferred requirements
EMPLOYER'S REQUIREMENTS
1 | Site welfare | 1 | Item
Completion and post completion requirements
2 | Handover documents | 1 | Item
3 | Operation and maintenance services | 1 | Item
MAIN CONTRACTOR'S COST ITEMS
4 | Management and staff | 1 | Item
5 | Site establishment | 1 | Item
6 | Security | 1 | Item
Safety and environmental protection
Safety programme
7 | Construction Phase Health & Safety Plan | 1 | Item
8 | method statements / risk assessments | 1 | Item
9 | site audits / visits | 1 | Item
10 | provision of PPE | 1 | Item
11 | site inductions / tool box talks | 1 | Item
12 | Barriers and safety scaffolding | 1 | Item
13 | Environmental protection measures | 1 | Item
Control and protection
14 | Survey, inspection and monitoring | 1 | Item
15 | Setting out | 1 | Item
16 | Protection of works including the requirements of the railway authorities | 1 | Item
17 | Samples | 1 | Item
18 | Mechanical plant | 1 | Item
19 | Temporary works | 1 | Item
20 | Site records | 1 | Item
Site records
21 | site photographs | 1 | Item
22 | site survey / schedule of conditions | 1 | Item
23 | O&M manuals / health & safety file / record drawings | 1 | Item
24 | other items (Contractor to insert) | 1 | Item
Completion and post completion requirements
Testing and commissioning plan
25 | testing and commissioning | 1 | Item
26 | training Employer | 1 | Item
27 | other items (Contractor to insert) | 1 | Item
Handover
28 | snagging / making good defects | 1 | Item
29 | other items (Contractor to insert) | 1 | Item
30 | Post completion services | 1 | Item
Cleaning
31 | Site tidy | 1 | Item
Maintenance of roads, platform, paths and pavings
32 | cleaning | 1 | Item
33 | other items (Contractor to insert) | 1 | Item
Final clean
34 | final builder's clean | 1 | Item
Fees and charges
Fees
35 | Considerate Constructors' Scheme | 1 | Item
36 | Charges | 1 | Item
Site services
Temporary works
37 | rubbish removal | 1 | Item
38 | other items (Contractor to insert) | 1 | Item
Insurance, bonds, guarantees and warranties
39 | Works insurance | 1 | Item
40 | Public liability insurance | 1 | Item
41 | Employer's (main contractor's) liability insurance | 1 | Item
Other insurances
42 | professional indemnity insurance | 1 | Item
43 | other items (Contractor to insert) | 1 | Item
44 | other items (Contractor to insert) | 1 | Item
| PRELIMINARIES AND GENERAL CONDITIONS |  |  | 0

## Prov Sums
£
PROVISIONAL SUMS
PROVISIONAL SUMS
Where works which are the subject of provisional sums are similar to items measured within the Measured Works sections, the Measured Works rates shall be used in valuing the works. Where suppliers' or sub-contractors' quotations are applicable, the works shall be valued using the nett cost of the quotation, after deduction of all discounts, together with the addition for overheads and profit which the Contractor is to insert where indicated below.
Provide for the following provisional sums
1 | Signs and lettering | 1 | Item | 250 | 250
2 | Protection of underground services | 1 | Item | 500 | 500
3 | Alterations to existing electrical services infrastructure | 1 | Item | 1000 | 1000
4 | Additional Builder's Work in Connection with Services | 1 | Item | 500 | 500
5 | Additional areas of hard landscaping | 1 | Item | 500 | 500
6 | Additional drainage works | 1 | Item | 500 | 500
7 | Contingencies | 1 | Item | 1000 | 1000
DAYWORK
Generally
The Contractor may be required to execute certain works on a 'daywork' basis; before commencing any such work, the prior approval of the Architect/Contract Administrator must be obtained.
The Contractor is to insert his 'all-in' rates against the provisional time allowances for the following trades of labour carried out on a 'daywork' basis:
8 | Roofers | 4 | hours
9 | Bricklayers | 4 | hours
10 | Carpenters; 1st fix | 4 | hours
11 | Labourers | 4 | hours
Materials
12 | Provide the provisional sum for the supply of materials in daywork | 1 | Item | 250 | 250
| Percentage addition for overheads and profit |  | % | 250 | 0
Plant
13 | Provide the provisional sum for the supply of plant in daywork | 1 | Item | 250 | 250
| Percentage addition for overheads and profit |  | % | 250 | 0
| PROVISIONAL SUMS AND DAYWORK |  |  | To General Summary | 4750
13
4750

## Enabling
£
| ENABLING AND SITE WORKS | Approx.
1 | Breaking up pavings as necessary; remove from site | 1 | item
2 | Undertake intrusive asbestos survey | 1 | item
3 | Remove established trees and clear from site; backfill resulting voids | 6 | no.
4 | Cut back and remove existing ivy and general vegetation from the rear of the existing platform shelter building | 1 | item
5 | Remove wire fences on concrete posts from the rear of the existing platform shelter to permit construction of new ramp and opening and remove from site | 1 | item
6 | Relocate fence post and make good fence to form opening for ramp, including all necessary additional support/restraint | 2 | no.
7 | Breaking out for new access ramp from Community Centre side of site | 1 | item
8 | Bonded gravel to all areas highlighted on the drawings, including levelling and substrate as necessary to architect's requirements | 1 | item
9 | Woodscape fixed round hardwood timber bollards at 1.8m centres along edge of car park; posts to be set in concrete base in accordance with manufacturer’s details | 10 | no.
10 | Brick edging to perimeter of resin-bound gravel | 1 | item
11 | Provision of grass border between ramp and fence, including all preparatory work to the existing areas | 1 | item
12 | Tarmac areas around existing shelter and new ramp/stairs to be made good as required | 1 | item
|  | 1 | item
13 | The Contractor should allow for all other work required under this section | 1 | item
| ENABLING AND SITE WORKS |  |  | 0

## Substructure & Ramp
£
| SUBSTRUCTURE, RAMP & STEPS | Approx.
1 | Undertake ground survey by scanning etc., for underground services | 1 | item
2 | Make up of ground level to engineer’s specification and dispose of materials off site | 1 | item
3 | Excavate for construction of the ramp and fill as required to form required falls | 1 | item
4 | Concrete footing for retaining wall to side of steps; 600mm wide, 350mm high (see Type 1); including excavation, spoil removal and temporary works | 3 | m
5 | Concrete footing for retaining wall to ramp and landing; footing 750mm wide, 250mm high (see Type 2); including excavation, spoil removal and temporary works | 69 | m
6 | Concrete base for (5m) lighting column to engineer's detail; allow 900mm deep, 650mm overall width; including sand packing and 450mm dia. sleeve | 3 | no.
7 | Concrete steps, 7 no., 400mm going, 150mm riser, f100mm concrete slab reinforced with A393 mesh and 30x200mm thickening to edge of slab; contrast nosing; with brick-on-edge band at base of steps | 1 | item
8 | Type II fill to underside of steps and slab, maximum 600mm depth; compacted in 150mm layers; additional depth made up with lean mix concrete; | 1 | item
9 | Concrete ramp structure and intermediate landing, 100mm th.; approximately 18m long, 2m wide; to falls in accordance with NR/SE code of practice; reinforced with A393 mesh top and bottom; 20mm bonded-gravel surface sure set natural aggregate | 1 | item
10 | Concrete platform landing structure, 100mm th., approximately 10.865 m long, 4.565 m wide, reinforced with A393 mesh top and bottom; laid to 1:50 cross-falls; 20mm bonded-gravel surface | 1 | item
11 | Tied joints within ramp, butt joint, H10 tie bars 450mm long @ 250mm c/s, with plastic joint strip stuck onto hardened edge to form sealing groove | 5 | no.
12 | Marshall tactile direction paving, 800mm wide, to bottom of steps | 1 | item
13 | Marshall tactile direction paving, 400mm wide, at top of steps | 1 | item
14 | The Contractor should allow for all other work required under this section | 1 | item
| SUBSTRUCTURE, RAMP & STEPS |  |  | 0

## Roof
£
| ROOF AND RAINWATER GOODS | Approx.
1 | New cast iron gutters and downpipes (alumasc cast iron heritgate range) to rear of shelter painted to match new metal railings. | 1 | Item
2 | Rainwater installation including gutters, downpipes etc. | 1 | Item
3 | The Contractor should allow for all other work required under this section | 1 | item
| ROOF AND RAINWATER GOODS |  |  | 0
3

## Brick Walls
£
| BRICK WALLS | Approx.
1 | Brick retaining wall to side of steps, 215mm thick, max. 700mm high (Type 1), Wienerberger Olde Southwester, laid in English bond; 325mm thick wall at foundation level; including movement joints @ maximum 15m c/s with water bar; brick-on-edge capping, on concrete | 3 | m
2 | Brick retaining wall, generally 215mm thick to side of ramp, 700mm to 1000mm high (Type 2), Wienerberger Olde Southwester, laid in English bond; including movement joints @ maximum 15m c/s with water bar; brick-on-edge capping, on concrete | 68 | m
3 | Synthprufe to inner face of brickwork, 2 costs, to form impervious layer | 1 | item
4 | Weep pipes through retaining wall, 60mm dia. @ 2m c/s | 1 | item
5 | The Contractor should allow for all other work required under this section | 1 | item
| BRICK WALLS |  |  | 0
5

## Metalwork
£
| BALUSTRADES & HANDRAILS | Approx.
Contractor's Designed Portion
Design warranty
The successful subcontractor will be required to sign a Sub-Contractor Collateral Warranty (SCWa/E) in favour of the Employer with a Professional Indemnity Limit of £1,000,000.
CDP Analysis
Design, supply, installation and testing of rainwater installation, drainage and soakaway
1 | The contractor is to appoint a specialist to design the system including all necessary ancillaries, fixings and bracketry | 1 | Item
2 | Railings, 1200mm high, powder coated steel, to steps, ramp and landings; top of guard railings minimum 1,200mm above FFL on platform landing; handrails to ramps 900mm and 600mm above FFL (to follow ramp fall); guard railings spaced maximum 99mm apart in 10mm painted galvanised steel with 10mm vertical top-rail to landing and landownership boundary; spogot-fixed to concrete under brick edge; post fixed to spigot with countersunk pignose security fixings; railing connection/ fixing details to be designed by contractor | 1 | item
3 | 'Temporary' guarding across location of porpoased ticket machine | 1 | item
4 | Balustrade, fixed to existing shelter timber posts using 8mm end plates and 2 no. M16 coach bolts per plate | 1 | item
5 | CDP Analysis | 1 | Item
End of Contractor's Designed Portion
6 | The Contractor should allow for all other work required under this section | 1 | item
| BALUSTRADES & HANDRAILS |  |  | 0
6

## Shelter
£
| WORKS TO TIMBER SHELTER | Approx.
1 | Shiplap cladding to existing shelter to be cleaned, repainted to match existing and repaired where required. | 1 | item
2 | Carefully remove area of timber panelling from the rear of the existing shelter to form new opening | 1 | item
3 | Carefully cut back shiplap cladding and internal vertical timber boarding to create new opening to expose existing timber shelter structure uprights | 1 | item
4 | Repair damage to built-in timber benches to shelter - subject to approval from SE/NR; paint to match existing | 1 | item
5 | Add timber lining, stud infill etc. to new opening in existing shelter; paint as required to match existing | 1 | item
6 | Remove existing bench and bin hoop; retain and set aside for future use by client/NR | 1 | item
7 | Carefully remove existing valence to shelter, 17m long, and replace with new to match valence on Platform 2 station building; paint as required | 1 | item
8 | Remove existing glazing, make good and repaint frames | 1 | item
9 | All external timber to existing shelter structure to be cleaned and redecorated, and repaired or replaced as and where required - subject to approval from SE/NR | 1 | item
10 | Allow here for general remedial works to the existing shelter not specifically detailed above | 1 | item
11 | The Contractor should allow for all work required under this section | 1 | item
| WORKS TO TIMBER SHELTER |  |  | 0
11

## Electrical
£
| ELECTRICAL INSTALLATIONS | Approx.
Contractor Designed Portion
Design warranty
The successful subcontractor will be required to sign a Sub-Contractor Collateral Warranty (SCWa/E) in favour of the Employer with a Professional Indemnity Limit of £1,000,000.
1 | Temporary disconnection and removal of electrical services, trunking, conduit and fuse/junction, distribution boxes from rear of shelter to permit new access route; provision of new infrastructure to serve new lighting and ticket machine | 1 | Item
2 | Provision of electrical infrastructure for new lighting, ticket machine and CCTV to shelter and ramp works | 1 | Item
3 | New lighting to shelter as per M&E engineers specification in accordance with NR/SE lighting requirements | 7 | no.
4 | New lighting columns, 5m high steel, to ramp/landings as indicated on engineer's drawings | 3 | no.
5 | Passive provision for power/data to be brought to locations to be confirmed by NR/SE to allow future installation of ticket machine | 1 | Item
CDP Analysis
6 | The Contractor is to provide an analysis of the sum inserted below within the CDP Analysis forming part of Section 5 | 1 | Item
Design, supply, installation and testing of elements of the electrical installations (see Preliminaries)
7 | It is the responsibility of the electrical sub-contractor to develop the design; this includes all containment etc. The subcontractor is to produce installation drawings for comment and agree with the contractor | 1 | Item
8 | CDP Analysis | 1 | Item
End of Contractor's Designed Portion
9 | The Contractor should allow for all work required under this section | 1 | item
Attendances
10 | Main Contractor's attendances | 1 | Item
Overheads and profit
11 | Main Contractor's overheads and profit | 1 | Item
generally
| ELECTRICAL INSTALLATIONS |  |  | 0
11

## Drainage
£
| DRAINAGE | Approx.
Contractor's Designed Portion
Design warranty
The successful subcontractor will be required to sign a Sub-Contractor Collateral Warranty (SCWa/E) in favour of the Employer with a Professional Indemnity Limit of £1,000,000.
CDP Analysis
Design, supply, installation and testing of drainage and soakaway
Surface water drainage including soakaways
1 | Contractor to provide suitably sized soakaway for all new areas of hardstanding | 1 | Item
2 | Drainage gullies, minimum 3 no., to contractor design | 1 | Item
3 | Aco drain, 2m long, at base of ramp | 1 | Item
4 | Aco drain, 2m long, mid-way along ramp | 1 | Item
5 | The contractor is to appoint a specialist to design the system including all necessary ancillaries, fixings and bracketry | 1 | Item
6 | CDP Analysis | 1 | Item
End of Contractor's Designed Portion
DRAINAGE BELOW GROUND
7 | The Contractor should allow for all necessary works | 1 | Item
Generally
Testing and commissioning
8 | of completed drainage | 1 | Item
| DRAINAGE |  |  | 0
8

## Summary
£
MEASURED WORKS SUMMARY
1 | ENABLING AND SITE WORKS |  | 0
2 | SUBSTRUCTURE, RAMP & STEPS |  | 0
3 | ROOF AND RAINWATER GOODS |  | 0
4 | BRICK WALLS |  | 0
5 | BALUSTRADES & HANDRAILS |  | 0
6 | WORKS TO TIMBER SHELTER |  | 0
7 | ELECTRICAL INSTALLATIONS |  | 0
8 | DRAINAGE |  | 0
| MEASURED WORKS | To General Summary | 0

## General Summary
£
GENERAL SUMMARY
SECTION 1 - PRELIMINARIES AND GENERAL CONDITIONS |  | 0
SECTION 2 - PRICING NOTES |  | 0
SECTION 3 - PROVISIONAL SUMS AND DAYWORK |  | 4750
SECTION 4 - MEASURED WORKS |  | 0
OVERHEADS AND PROFIT
| To Form of Tender | 4750