## Sheet1
Highways Agency Confirmation of Task Order Redactions made under FOIA 2000 exemptions sec 40: personal info and sec 43: commercial.
Supplier: | JMP | Fee Request for this CTO |  | 36934.7
Project Title: | GED National Mapping Expansion (to March 2016)
Contract Ref. | Redacted | CPA No.: | Redacted | BPA No.: | Redacted
PIN Description: | Independent Strategic Planning Advice BPA | Sub Pin: | 12 | PIN No.: | Redacted
HA Reference: | WM 61 15/16JMP | Start and End Date : |  | 10/12/2015 - 31/03/2016
Task Overview and Expected Outcomes
Project to further develop the GED national mapping tool to expand functionality and data scope, and to support users and the achievement of GED’s SEGP evidence base and stakeholder communication objectives. • Refine and increase functionality: specify, design, implement and test new functionality as further use of the tool leads to the evolution of Highways England and stakeholder requirements. In particular, to improve functionality in the short term to support the internal stakeholder consultations. • Improve and broaden the data displayed: again, with further use and the need to develop the evidence base for the Strategic Economic Growth Plan, further Highways England (non-Midlands) and external economic and related data will need to be mapped; this means acquiring and preparing new data for initial upload and display, testing it and then putting in place a process to keep it up to date. Immediate priority is to improve the level of visual intelligence to support the internal and external stakeholder consultations (see supporting spreadsheet showing outline scope of work). • Support an expanding base of users: admin support (lost passwords, technical fixes, etc.) and responding to functionality queries (“how do I do this?”). • Work with the SGED team to ensure the mapping tool is developed in the way that best supports the delivery of its objectives – primarily as an analytical tool to help provide the evidence base for SEGP and to provide a higher level of visual intelligence to support communications with internal and external stakeholders, but also as a reporting tool over the medium to longer term.
Task Objectives and Milestones
Milestone 1 - produce Method Statement and set up on TAPE Milestone 2 - specify, design, implement, test functionality Milestone 3 - display and keep fresh more data Milestone 4 - support users Milestone 5 - guide tool development to ensure objectives are achieved.
Expected Project Outcomes
In line with the 'Making Growth Happen' paper, the GED team will use the increasing data and functionality of this mapping tool to develop the evidence base for the Strategic Economic Growth Plan and communicate with stakeholders. The tool will be developed to contain the majority of currently envisaged data and functionality, plus yet to be decided elements, with national coverage where data is available, while maintaining clarity of use and presentation.
Project Risk and Management
The benefits of the tool will not typically be time-critical, except where the tool is required for stakeholder engagements, so brief down-time would constitute a small risk Internet Explorer 8, used by some HE staff, is believed to be the least favourable environment in which to use the tool, but the tool has been and will continue to be tested in IE8. However, the tool works well in Firefox and this is available to download by HE staff. In any case, JMP and Map Insight will ensure the GED client team is fully aware of progress over the duration of the project.
HA Project Sponsor | Sign: |  | Print Name: |  | Date:
Management Approver: | Sign: |  | Print Name: |  | Date:
Contractual Approval: | Sign: |  | Print Name: |  | Date: