Reporting and Meeting Requirements

This annex sets out the scope and timing of meetings, reports, and other products that the Supplier must deliver and/or submit to the Authority.

It is comprised of three subsections:

- Meetings

- Reports

- Audit Visits

## Sub Section A: Meetings

The Supplier may wish to conduct more frequent meetings with Recipients or relevant parties than set out in Table 5 below, but the below should be met as a minimum.

### Table 5 Schedule of regular meetings

| Frequency | Meeting Purpose | Further Information |
| --- | --- | --- |
| Monthly | Supplier / Authority check-in | - A standing monthly meeting slot will be available for the Authority and the Supplier to meet to discuss finances and risk, aligned with the submission of monthly risk and finance returns, amongst other things. - The Supplier will provide an update on their KPI performance. |
|  | Monthly Hub Partners Meeting: Supplier & Strategic Science Lead | - A chance for the Hub Partners to discuss MoA, Monitoring and Learning, Comms, and events. - The SSL can provide updates to the research strategy - The Supplier will provide updates on delivery of research, as well as research outputs and products - SSL and Supplier to discuss risks and challenges, as well as mitigation approaches - SSL and Supplier to discuss progress of the GCBC against targets and milestones. |
| Quarterly | Supplier / Recipient progress meeting | - One meeting per Recipient - Meeting to discuss progress of Recipient against grant agreement to discuss Reporting data and monitoring, as per logframes. - Strategic Science Lead and/or Independent Evaluator may be required to join these meetings as and when required |
|  | Supplier / Authority progress meetings | - Meeting with the Authority to discuss KPIs, progress, risk, finances - Every 6 months, these will also be used to review any contract issues. |
|  | Programme Board Meetings | - The Supplier will be required to attend the Authority’s Programme Board meetings as and when required |
| Quarterly and Annually | Learning Cycle meeting between Hub Partners (Strategic Science & The Supplier) | - Meeting organised and chaired by Supplier to discuss and agree adaptive programming recommendations, and evidence assessment by the Strategic Science Lead, that will be submitted to Authority ahead of annual learning Programme Board. This may be part of the quarterly Hub Partners Meeting. Agreed learning recommendations and meeting minute to be provided by Supplier to Authority at least ten (10) working days before annual Learning Board (see Quarterly Programme Board Meetings below). |
| Annually | Potential underspend meeting | - Meeting organised by Supplier with each Recipient to understand the occurrence of any potential underspend and/or incomplete milestones. This will be fed back to the Authority in quarterly financial and risk reports. |
| Ad-hoc | Update meetings requested by the Authority | - The Authority may require the Supplier to attend ad-hoc meetings throughout the programme. |

## Quarterly Programme Board Meetings

GCBC Programme Board meetings will be chaired by the Authority and will convene quarterly at a minimum. There will be a standing agenda at each Programme Board, and membership could vary by meeting, as need dictates.

The quarterly Programme Board meetings will have rotating themes, to allow extra attention to be given to specific areas. The following is an example of how such a rota might look, which will be set out and confirmed by the Authority after this Contract is awarded:

- Quarter 1: Grant Award review Board

- Quarter 2: Finance Board

- Quarter 3: Evidence review Board

- Quarter 4: Learning Board

## Sub Section B: Reports

The Authority’s reporting requirements are comprised of two elements:

- Inception reports; and

- Regular reporting.

## Inception reports

The Inception Phase will run for 6 months from the appointment of the Supplier.

### Table 6 Inception Reports

| Date Due | Report Title | Detail |
| --- | --- | --- |
| Within 4 weeks of the Supplier being appointed (and assuming the SSL provides a first iteration of the Research Strategy by April 2023) | Research Grant Competition Plan | Workplan which covers the stages from launching Grant competition/s to signing Grant agreements, to include: - specifications for research; - guidance, including to enable project logframe development; - evaluation questions; - due diligence; and - a grant award process. The Research Grant Competition Plan should be drawn up in alignment with the Research Strategy which will inform the thematic and geographic scope of the competitions. The Supplier will need to agree with the Authority the appropriate number and size of grants to be awarded through competition, as well as the process for allocating and awarding grants. The Plan will be subject to approval by the Authority. |
| Within 8 weeks of the Supplier being appointed | Hub Partners Ways of Working plan | A plan which details how the Supplier will work with the Strategic Science Lead, as per the MoA This includes standing agenda items on regular meetings between Hub Partners and a workplan detailing how regular reports will be co-authored, where required. Table 7 details regular reports the Authority requires. This should specifically address Learning Cycles, to create a plan which sets out project level, geographic and thematic level learning cycles, and how evidence synthesis products led by the Strategic Science Lead will feed into these cycles. |
| Within 10 weeks of the Supplier being appointed | Monitoring and Learning Plan | The Plan should set out: - the approach to providing the services relating to the management of Grant Agreements; - a monitoring framework describing how monitoring data will be collected at the project level. This should be written in consultation with the Strategic Science Lead; - an approach to managing learning cycles quarterly, and annually, and for various audiences. This should be written in consultation with the Strategic Science Lead, which will feed in how its evidence syntheses will contribute towards learning; - geographic and thematic logframes and an approach to how this monitoring data will be collected and aggregated. This should be written in consultation with the Strategic Science Lead; and - the Plan must set out the proposed structure of the quarterly and annual reports that the Supplier will submit to the Authority. |
| Within 6 months of the Supplier being appointed | Communications Plan | The Supplier will lead on the Communications Plan, working with the Strategic Science Lead to incorporate an approach to technical science communication. It should include at a minimum: - identification of stakeholders / audience (including IPLCS, local communities, governments, international policy makers etc.) and plans for their engagement; - website development; and - plans for learning events |

## Regular Reports

The Supplier will make the regular reports set out in Table 7 to the Authority

### Table 7 Regular reporting requirements

| Date Due | Report Title | Detail |
| --- | --- | --- |
| Monthly, by the second week of the month | Risk & Finance report | - one risk report per Research Project; - one finance report providing forecast and actuals for the previous month, created by the Supplier; - any risks that are materialising into issues must be captured in this report. As stated in the Specification, any urgent risks and/or issues including safeguarding and fraud issues must be escalated via email to the Authority via the Programme Board SRO and the relevant Authority contacts immediately; and - the risk reports can be discussed at the Supplier / Authority’s monthly check in meeting if required |
|  | Management Information update | - As specified in the KPIs (see Annex 23) the Supplier will submit a monthly Management Information update, which outlines their performance against agreed KPIs. - This update will be submitted 5 working days in advance of the Monthly Supplier Authority Check-in Meeting. |
| Quarterly submitted 10 (TEN) working days before the Authority’s Quarterly Programme Board | Risk report | - one risk report per Recipient research project; - one report across all the projects that captures key risks and risk trends. These must be high-level visual presentations with a deep dive into key risks. The Authority may require the Supplier to present the deep dive to the Programme Board; - any risks that are materialising into issues must be captured in this report. As stated in the Specification, any urgent risks and/or issues including safeguarding and fraud issues must be escalated via email to the Authority via the Programme Board SRO and the relevant Authority contacts immediately; and - the risk reports will be discussed at the Authority’s Programme Board |
| Quarterly submitted 10 (TEN) working days before the Authority’s Quarterly Programme Board | Finance report | To include: - claims for Funds received from Recipients, comprising one invoice per Recipient. Invoices must include a breakdown of costs per output and a final amount to pay; - expenditure and yearly forecast spend across the GCBC; - assurance statements and value for money assessment; - summary of payments-in-advance claims; and - data aggregated by research theme and geography |
| Quarterly submitted 10 (TEN) working days before the Authority’s Quarterly Programme Board | Light-touch monitoring report | One report indicating project progress against activities. |
| Annual | Annual report | This should be led by the Supplier but with strong contribution from the Strategic Science Lead on point iv, feeding thematic and geographic level evidence synthesis. This is a Report that summarises the main results achieved across the project. The structure of annual or quarterly reports is for the Supplier, together with the Strategic Science Lead, to propose during the inception phase and for the Authority to agree. The report must as a minimum include: - A summary of key points; - Financial information including: - Accounting on both a Financial Year and Calendar Year basis for both ‘cash’ and ‘resource’ accounting adherence; - Proportion of funds spent at thematic and geographic levels; - Main results achieved against the expected activities, outputs and outcomes detailed in the project logframe/s; - Main results achieved at thematic and geographic level (with input from the Strategic Science Lead); - Learning summary; - Risks identified and actions taken; - Forward look for the following year. |
| Annual | Learning recommendations | The Supplier will submit minutes of the learning meeting and consensus learning recommendations to the Authority ten (10) working days prior to the annual Learning Board. |