# Memorandum of Agreement

Global Centre on Biodiversity for Climate

## April 2023

© Crown copyright 2022

This information is licensed under the Open Government Licence v3.0. To view this licence, visit www.nationalarchives.gov.uk/doc/open-government-licence/

This publication is available at www.gov.uk/government/publications Any enquiries regarding this publication should be sent to us at Defra.Procurement@defra.gov.uk

www.gov.uk/defra

### Contents

1.	DEFINITIONS AND INTERPRETATION	5

PRINCIPLES OF THE RELATIONSHIP	7

DURATION	7

3	RESOURCES	7

4	FUNDING ARRANGEMENTS	7

5	FURTHER ASSURANCE	7

6	VARIATION AND WAIVER	7

7	SUCCESSORS AND ASSIGNS	7

8	NOTICES	8

9	RIGHT TO PUBLISH	9

10	CONFIDENTIALITY	9

11	INTELLECTUAL PROPERTY RIGHTS	10

12	INFORMATION	10

13	LIABILITY	11

14	TERMINATION	11

15	CONSEQUENCES OF TERMINATION	11

16	RECONCILIATION OF DISAGREEMENT	11

17	ANNOUNCEMENTS	12

18	GENERAL	12

19	GOVERNING LAW	13

PROJECT SCHEDULE	15

APPENDIX 1. Delivery Profile	21

APPENDIX 2. Monitoring & Learning	25

APPENDIX 3. Data Processing Terms	31

- THIS AGREEMENT is made on	xx day of XXX 2023

#### BETWEEN

- The Secretary of State for Environment, Food and Rural Affairs whose principal offices are at Marsham Street, London, SW1P 4DF (the “Authority”);

#### AND

- [name of Management Lead] of [address] registered in England with company number xx (the “Management Lead”).

- AND

- Royal Botanic Gardens, Kew whose principal offices are at Royal Botanic Gardens, Kew, Richmond, TW9 3AE (the “Strategic Science Lead”);

- The Independent Evaluator (“the IE”) will become party to this MoA in due course. However, the distinctive roles of the IE are detailed within this agreement. There will be iterative developments to this agreement as and when all parties are onboard.

#### BACKGROUND

- This Agreement sets out how the Management Lead and Strategic Science Lead (collectively referred to as the “The Hub”) will work together to meet the Authority’s objectives. This Agreement describes the roles and responsibilities of The Hub and the Independent Evaluator which will be procured separately by the Authority and will provide evaluation across the ODA portfolio.

- This Agreement shall be subordinate to the Overarching Agreements in place between the Authority and the Management Lead and the Authority and the Strategic Science Lead. The Overarching Agreements shall in all cases take precedence.

- This Agreement sets out the principles which shall govern the relationship between the Authority and The Hub including their respective obligations and rights.

- IT IS AGREED as follows:

# DEFINITIONS AND INTERPRETATION

In this Agreement, unless the context otherwise requires, a reference to:

“Agreement” means this document, including all schedules and appendices hereto. Any schedule or appendix is an integral part of this Agreement and shall be interpreted accordingly;

“GCBC” means the Global Centre on Biodiversity for Climate, a Defra-led Research and Development programme as more particularly described in the Overarching Agreements;

“ICF R&D Programme” means the International Climate Finance Research and Development Programme;

“The Hub” means the Management Lead and the Strategic Science Lead;

“The Spokes” means the priority research themes operating within specific geographic areas which will deliver high-quality, high-impact research, in respect of which research grants will be awarded by competition;

“The SSL” means the Strategic Science Lead. This party, which will form part of The Hub, will be Royal Botanic Gardens, Kew;

“The Management Lead” means the chosen supplier procured commercially through Defra Group Commercial to carry out the administrative functions as required to effectively manage this project, and as outlined by the Authority;

“The Independent Evaluator (IE)” means the party procured independently by the Authority to carry out evaluation of the GCBC;

“ODA” Official Development Assistance and refers to the UK Government’s commitment to overseas aid;

“Confidential Information” means any information which has been designated as confidential by either Party in writing or that ought reasonably to be considered as confidential (however it is conveyed or on whatever media it is stored) including information which relates to the business, affairs, properties, assets, trading practices, services, developments, trade secrets, intellectual property rights, know-how, personnel, Authorities and suppliers of either Party and all Personal Data;

“Controller, Processor, processing, Data Subject, Personal Data, Data Protection Officer” take the meaning given in the UK GDPR or, in respect of processing of personal data for a law enforcement purpose to which Part 3 of the DPA 2018 applies, the meaning in that Part if different;

“Data Protection Legislation” means (i) the UK GDPR; (ii) the DPA 2018 to the extent that it relates to processing of personal data and privacy; and (iii) all applicable Law about the processing of personal data and privacy;

“Delivery Profile” means the detailed timetable for outputs in Appendix 1;

“DPA 2018” means the Data Protection Act 2018;

“EIR” means the Environmental Information Regulations 2004;

“FOIA” means the Freedom of Information Act 2000;

“Law” means any law, subordinate legislation within the meaning of Section 21(1) of the Interpretation Act 1978, bye-law, enforceable right within the meaning of Section 2 of the European Communities Act 1972, regulation, order, regulatory policy, mandatory guidance or code of practice, judgment of a relevant court of law, or directives or requirements with which the relevant Party is bound to comply;

“Non-Commercial Purposes” refers to any purpose not primarily intended for, or directed towards, commercial advantage or monetary compensation in any way;

“Overarching Agreements” means the contract between the Authority and the Management Lead and the MoU between the Authority and the Strategic Science Lead, for the provision of the Project; ‘

A “Party” means any party to this Agreement individually and “Parties” refers to all of the parties to this Agreement collectively. A Party shall include all permitted assigns of the Party in question;

“Personal Data” has the same meaning as that, which is given in Article 4(1) of the UK GDPR;

“Project” means the project which the Overarching Agreements, supplemented by this Agreement, is intended to deliver (the GCBC) and as such sits within the wider ICF R&D Programme;

“UK GDPR” means Regulation (EU) 2016/679 of the European Parliament and of the Council of 27 April 2016 on the protection of natural persons with regard to the processing of personal data and on the free movement of such data (United Kingdom General Data Protection Regulation), as it forms part of the law of England and Wales, Scotland and Northern Ireland by virtue of section 3 of the European Union (Withdrawal)

Act 2018 (and see section 205(4) of the DPA 2018); and

“Working Day” means a day (other than a Saturday or Sunday or a public holiday in the UK).

# PRINCIPLES OF THE RELATIONSHIP

2.1	The Parties shall work together collaboratively in delivering the Project and in particular shall perform their respective obligations to the timetables set out in the Project Schedule.

The Parties shall each be responsible for meeting their own obligations within the Overarching Agreements and under this Agreement and no Hub Party shall be responsible or liable for any other Hub Party act or omission under this Agreement.

  - None of the Parties shall be entitled to impose any duties or responsibilities on other Parties beyond those set out in the Overarching Agreements and this Agreement.

# 3	DURATION

- This Agreement shall be effective from the date of its execution and shall continue until termination in accordance with clause 19.

# 3	RESOURCES

  - The Parties shall provide the resources identified in the relevant Overarching Agreements, as at the date of this Agreement being as identified in the schedule as being their responsibility to provide.

  - If any of the individuals named as a resource being provided by a Party is unavailable for whatsoever reason, that Party shall offer an alternative member of staff with equivalent skill sets to the reasonable satisfaction of the other Party and the Authority.

# 4	FUNDING ARRANGEMENTS

- This Agreement does not give rise to any financial obligations.

# 5	FURTHER ASSURANCE

- The Authority and The Hub shall promptly execute and deliver all such documents and do all such things as may from time to time be reasonably required for the purpose of giving full effect to the provisions of this Agreement.

# 6	VARIATION AND WAIVER

  - No variation of this Agreement shall be valid unless it is in writing and signed by or on behalf of each of the Parties.

  - No delay by any Party in exercising any provision of this Agreement constitutes a waiver of such provision or shall prevent any future exercise in whole or in part.

# 7	SUCCESSORS AND ASSIGNS

  - The agreements reached between the Parties pursuant to this Agreement shall continue for the benefit of the Authority’s successors and assigns.

  - The Hub cannot assign, sub-contract or in any other way dispose of the Agreement or any part of it to any person, firm or company without the prior written consent of the Authority.

# 8	NOTICES

  - Any notice or other communication required to be given under this Agreement, shall be in writing and shall be delivered personally, or sent by pre-paid first-class post or recorded delivery or by commercial courier, to each Party required to receive the notice or communication as set out below:

Authority (Contract Managers): 		Dave Bull-Edwards, ICF R&D Programme

Manager, 2 Marsham Street, London, SW1P 4DF

Authority (Procurement Manager):	Jacqueline Hurley, Foss House, Peaseholme 	Green, York YO1 7PX

Management Lead:	[CONTACT NAME AND ADDRESS]

Strategic Science Lead:	Prof. Monique Simmonds, Royal Botanic Gardens Kew, 	Richmond, TW9 3AE

or as otherwise specified by the relevant Party by notice in writing to the other Parties.

  - Any notice or other communication shall be deemed to have been duly received:

    - if delivered personally, when left at the address and for the attention of the contact referred to in clause 12.1; or

    - if sent by pre-paid first-class post or recorded delivery, at 11.00 am on the second Working Day after posting; or

    - if delivered by commercial courier, on the date and at the time that the courier's delivery receipt is signed.

  - A notice or other communication required to be given under this Agreement shall be validly given if sent by email. Notice sent via email must clearly state the email is a notice pertinent to this Agreement.

  - The provisions of this clause shall not apply to the service of any proceedings or other documents in any legal action.

# 9	RIGHT TO PUBLISH

  - The Hub acknowledges that, except for any information which is exempt from disclosure in accordance with the provisions of the EIR or FOIA, the content of this Agreement is not Confidential Information for purposes of this Agreement except as set out below in clause 15. The Authority shall be responsible for determining in its absolute discretion whether any of the content of the Agreement is exempt from disclosure in accordance with the provisions of the EIR or FOIA. Notwithstanding any other term of this Agreement, The Hub hereby give their consent for the Authority to publish the Agreement in its entirety (but with the redaction of any information exempt from disclosure in accordance with the provisions of the EIR or FOIA), including from time to time agreed changes to the Agreement, to the general public.

  - The Authority may consult with The Hub to inform its decision regarding any right to publish or exemptions, but the Authority shall have the final decision in its absolute discretion.

# 10	CONFIDENTIALITY

  - The Parties acknowledge that pursuant to this Agreement, Confidential Information may be disclosed between the Parties.  In consideration of the provision of such Confidential Information, each Party undertakes to the other:

    - to keep all Confidential Information disclosed to it, (including its employees, agents or advisers) by or on behalf of another in relation to the agreement or the business of the other Party which is of a confidential nature and not to use such Confidential Information for any purpose other than for the purposes of this Agreement or the performance of its Overarching Agreement; and

    - not to disclose to any third party (other than its professional advisers or as required by law or any competent regulatory authority) any such Confidential Information other than that which comes into the public domain other than by breach of the undertakings contained in this clause 15.

  - These confidentiality undertakings shall subsist indefinitely so far as permissible by law.

  - The obligations of confidentiality set out in this clause 15 shall not apply to information already known to either Party or information in the public domain (in each case other than through a breach of a confidentiality undertaking) or information required to be disclosed by law or information lawfully received from an independent third party without any restrictions and without any obligation of confidentiality or information independently developed by the receiving Party without reference to the Confidential Information unless such independently developed information is deemed to be Confidential Information in its own right

# 11	INTELLECTUAL PROPERTY RIGHTS

- Party’s rights to use pre-existing intellectual property of another and ownership of and rights to use any foreground intellectual property rights arising from or as a result of the Project are governed by the relevant Overarching Agreement (as between the Authority and the ML and as between the Authority and the SSL). In broad terms, Project related foreground intellectual property generated by the ML vests in the Authority, and Project related foreground intellectual property generated by the SSL vests in the SSL with licence to the Authority for project related purposes.

# 12	INFORMATION

EIR AND FOIA

  - The Hub acknowledge that the Authority and the SSL is each subject to the requirements of the EIR and FOIA and The Hub shall assist and co-operate with the Authority and the SSL as necessary to comply with these requirements. Once a request from the Authority or SSL to a Partner is made, the Partner shall comply by searching and supplying the required information within the time the Authority specifies.

  - In responding to a request for information, including information in connection with the Project, the Authority and the SSL shall use reasonable endeavors to consult with the relevant Party. Notwithstanding this, The Hub acknowledge that the Authority and the SSL may disclose information without consultation or following consultation with the relevant Party having taken its views into account.

DATA PROTECTION

  - The Parties agree to comply with the Data Protection Legislation. In particular the Parties agree to comply with the requirements of [the Data Processing Terms at 0 in respect of Personal Data of which one Party is the Controller and the other is the Processor (as identified in Appendix 2)

PUBLICATION AND COMMUNICATION

  - The Parties acknowledge that to achieve the outcomes of the Project, certain Project related data and information will be published and disseminated; the publication and dissemination of Project related data shall be in accordance with communication plans and protocols to be developed by the ML in consultation with the SSL, for approval by the Authority.

    - It is acknowledged that in accordance with academic protocols, the SSL may wish to publish academic articles directly arising from its solely owned Foreground IPR (as defined in its Overarching Agreement with the Authority); such publication shall be consistent with the communication plans and protocols for the Project, and in any event the SSL shall circulate the proposed publication to the Authority and the ML at least 30 days in advance of submission for publication.  As provided for in the Overarching Agreement, the Authority may, acting reasonably, instruct a delay in publication if publication would reasonably prejudice the Project.  Notification of the requirement for delay in submission for publication must be received by the SSL within thirty (30) days after the receipt of the material by the Authority.

# 13	LIABILITY

  - Each Party’s total liability arising under, or in connection with, this Agreement, whether in tort (including negligence or breach of statutory duty), contract, misrepresentation, restitution or otherwise, shall be limited to £5 (FIVE) pounds.

  - No Party excludes or limits liability to the other for:

    - death or personal injury caused by its negligence;

    - fraud or fraudulent misrepresentation;

    - any breach of any obligations implied by section 12 of the Sale of Goods Act 1979 or section 2 of the Supply of Goods and Services Act 1982; or

    - any other matter which, by law, may not be excluded or limited.

Subject to clause 13.2, no Party shall be liable to another Party for:

    - any indirect, special or consequential loss or damage; or

    - any loss of profits, turnover, business opportunities, savings or damage to goodwill (whether direct or indirect).

# 14	TERMINATION

- This Agreement shall terminate when either of the Overarching Agreements held between the Authority and the Management Lead or Strategic Science Lead terminates.

# 15	CONSEQUENCES OF TERMINATION

- On termination of the Agreement each Party shall comply with the requirements set forth in the Overarching Agreements.

# 16	RECONCILIATION OF DISAGREEMENT

  - Disputes between the Authority and a Party shall be resolved in line with the Overarching Contract.

  - Disputes between The Hub in connection with this Agreement shall normally be resolved amicably at a working level. In the event of failure to reach consensus between The Hub, such failure shall be handled in the following manner:

    - the dispute shall, in the first instance, be referred to the Authority’s Contract Manager or manager in the organisation of similar standing and The Hub’s contract manager for resolution at a meeting to be arranged as soon as practicable after the failure to reach consensus arises, but in any event within ten (10) Working Days;

    - if the dispute cannot be resolved in accordance with clauses 21.2 and 21.2.1 above within ten (10) Working Days after such referral, or within any other period agreed between the Parties, the dispute shall be referred to the Authority’s Procurement Manager for resolution at a meeting to be arranged as soon as practicable after such referral, but in any event within ten (10) Working Days;

    - if the dispute has not been resolved following a referral in accordance with clause then the Parties shall settle the dispute by mediation in accordance with the CEDR Model Mediation Procedure. Unless otherwise agreed between the Parties, the mediator will be nominated by CEDR.

# 17	ANNOUNCEMENTS

  - The Parties shall not make, or permit any person to make, any public announcement concerning the Project (whether before, at or after completion) except as required by law or with the prior written consent of the Authority.

  - In accordance with government restrictions on marketing and advertising expenditure by public bodies, no part of this Project may be used for such activities.

# 18	GENERAL

  - The Parties do not intend that any term of the Agreement shall be enforceable by virtue of the Contracts (Rights of Third Parties) Act 1999 by any person that is not a party to it.

  - Each of the Parties represents and warrants to the other that it has full capacity and authority, and all necessary consents, licences and permissions to enter into and perform its obligations under the Agreement, and that the Agreement is executed by its duly authorised representative.

  - No Party shall have any liability under or be deemed to be in breach of the Agreement for any delays or failures in performance of the Agreement which result from circumstances beyond the reasonable control of the party affected. Each Party shall promptly notify the other parties in writing when such circumstances cause a delay or failure in performance and when they cease to do so.

  - The Parties confirm that they have not entered into the Agreement on the basis of any representation that is not expressly incorporated into the Agreement or the relevant Overarching Agreement. Nothing in this clause shall exclude liability for fraud or fraudulent misrepresentation.

  - The Agreement shall not constitute or imply any partnership, joint venture, agency, fiduciary relationship or other relationship between the Parties other than the contractual relationship expressly provided for in the Agreement. Neither Party shall have, nor represent that it has, any authority to make any commitments on the other Party’s behalf.

  - Except as otherwise expressly provided by the Agreement, all remedies available to either Party for breach of the Agreement (whether under the Agreement, statute or common law) are cumulative and may be exercised concurrently or separately, and the exercise of one remedy shall not be deemed an election of such remedy to the exclusion of other remedies.

  - If any provision of the Agreement is prohibited by law or judged by a court to be unlawful, void or unenforceable, the provision shall, to the extent required, be severed from the Agreement and rendered ineffective as far as possible without modifying the remaining provisions of the Agreement and shall not in any way affect any other circumstances of or the validity or enforcement of the Agreement.  The management of Conflicts of Interest are governed by the Conflict of Interest principles set out in the relevant Overarching Agreement; the parties will agree protocols for working arrangements between the ML and the SSL to facilitate compliance with those principles.

# 19	GOVERNING LAW

  - The validity, construction and performance of the Agreement, and all contractual and non-contractual matters arising out of it, shall be governed by English law and shall be subject to the exclusive jurisdiction of the English courts to which the Parties submit.

Each Party hereby confirms its agreement to the terms contained in this Agreement.

| Signed on behalf of the AUTHORITY: | Signed on behalf of the MANAGEMENT LEAD: |
| --- | --- |
| Print Name: | Print Name: |
| Job Title: | Job Title |
| Date: | Date: |

Signed on behalf of the

STRATEGIC SCIENCE LEAD:

Print Name:

Job Title:

Date:

Should the Independent Evaluator become a party to this MoA, formal agreement to the terms set out will be done via a Change Control Notice (a “CCN”) once the Independent Evaluator is procured.

# PROJECT SCHEDULE

This Agreement sets out the relationships between the parties which form The Hub in order to ensure both the Management Lead and the Strategic Science Lead can effectively fulfil their obligations of the Overarching Agreements alongside the Independent Evaluator who will be procured separately by the Authority.

#### PROJECT DESCRIPTION

1.1 The purpose of this Agreement is to support The Hub in fulfilment of their obligations of the Overarching Agreements. This agreement also sets out the role of the IE and how all parties will interact to achieve the goals of the project.

1.2 This Agreement describes how The Hub shall collaboratively work together. This Agreement details what and how products, information and resources will be shared between The Hub. However the products, information and resources outlined in this Agreement are not exclusive and further detail of the responsibilities will be set out in the agreement formally establishing the SSL and the Management Lead.  Any subsequent changes to responsibilities may be made only in conjunction with, and via approval of, the Authority.

1.3 Principles underlying the working of the partnership are transparency and collaboration.

#### OBJECTIVES OF THE COLLABORATION BETWEEN THE PARTIES (“The Hub”)

#### 2.1 The objectives of the collaboration between The Hub and its associated parties are set out below, with specific outputs and outcomes identified in the Delivery Profile in Appendix 1.

#### 2.2 The GCBC will be delivered through a “Hub” and “Spoke” model where the hub partners will operate synergistically. The spokes will allow for focused research grant calls, operated across specific thematic research areas and geographical regions (to be informed by the Research Strategy).

#### 2.3 The hub parties will:

#### 2.3.1 ensure effective and collaborative working to ensure the Authority’s expectations for how The Hub shall work together is clearly communicated and carried out.

#### 2.3.2 share information, products and resources in a timely manner to enable both the Management Lead and Strategic Science Lead (as well as the IE) to meet their obligations of the Overarching Agreements. This includes but is not limited to:

    - The transfer of data to allow for project and programme accountability and reporting.

    - The connection of knowledge and skills.

    - Effective communication for the development and betterment of the programme and project delivery and wider impacts.

    - Management and escalation of any risks or issues

#### RESOURCES

3.1 The Management Lead is to ensure that all monitoring data (any data relating to the performance of a grantee) from grant recipients is stored on their project management e-platform, and that the data is in line with the requirements of the UK International Development Assistance Act 2002. Agreement by the Authority is required as to the type, quantity and focus of said data and this will be agreed in the first month following their on-boarding.

3.2 The Management Lead is to ensure the Strategic Science Lead and IE has access to the relevant information held on the e-platform to ensure the Strategic Science Lead and the Independent Evaluator can effectively fulfil their obligations of the Overarching Agreements such as the evaluation activities. The Authority will also be granted access.

#### TIMETABLES AND REPORTING

4.1 Specific outputs for the agreement and timescales for their delivery are set out in the Delivery Profile in Appendix 1. The Delivery profile identifies the Party who are responsible for reporting progress towards delivery. The Delivery profile also sets out the anticipated products that will be shared between the Parties.

4.2 As all Parties shall collaborate through the learning cycles, the scope and inputs are set out in Appendix 2.

4.3 The Independent Evaluator will be responsible for programme level Evaluation including process, theory-based, and impact evaluation. It will be the role of an Independent Evaluator to refine and answer key evaluation questions to ultimately understand to what extent the GCBC has contributed towards achieving more effective climate resilient development via systems-research on the conservation and sustainable use of biodiversity. The Management Lead will have responsibility for operationalising learning from the Independent Evaluator at programme and project level, at appropriate frequencies.  More information is provided in Appendix 3.

4.4 Formal Quarterly meetings between the Management Lead and Strategic Science Lead (and Independent Evaluator where required) shall be documented in the form of minutes, to be submitted to the Authority no later than 5 (FIVE) working days after the meeting. Monthly meetings between these parties will also be held to help progress the project, manage finances and escalate any risks or issues. The meeting agenda shall include progress, challenges, risks and issues as well as any other topics deemed appropriate. Minutes must be maintained and submitted by the Management Lead. Each party must provide their own assessment. The Authority may require involvement as required.

4.5 An assessment of the working relationship must be submitted to the Authority on the annual anniversary of this MoA. The remit of the assessment will be agreed with the Authority.

#### DISTINCTIVE RESPONSIBILITIES OF THE AUTHORITY

5.1 The Authority shall:

- decide which recommendations from the Independent Evaluator that the Management Lead shall implement;

- approve the project level evaluation products that the Independent Evaluator shall develop;

- settle any arising disputes from The Hub as a result of this Agreement;

- review progress of contracts and meeting minutes;

- establish an “Evidence Advisory Group (EAG)”, to provide independent advice and scrutiny on the design, scope, and outputs of the GCBC.

#### DISTINCTIVE RESPONSIBILITIES OF THE HUB

6.1 The Hub, through the activities of each Hub party under its respective responsibilities under the applicable Overarching Contract and this Agreement shall commission, coordinate, and communicate research activity and outcomes. It will hold overall responsibility for:

  - ensuring the strategic coherence of the research direction;

  - contracting and management of research;

  - research quality;

  - research communication, translation, and uptake; and

  - monitoring and learning of the GCBC programme outcomes on poverty, climate and biodiversity, and will underpin its reputation in the UK and internationally.

6.2 The hub will:

  - meet on a monthly basis to discuss the following:

    - updated monitoring data and progress of logframes and Key Performance Indicators;

    - real-time review of the evaluation products; and

    - recommended adaptive changes that shall be submitted to the Authority’s learning cycles.

  - The Hub shall take alternate turns in minuting this meeting. Minutes must be provided to the Authority’s Contract Manager within ten (10) Working Days of the quarterly meeting.

  - The Hub will work with the IE as required in line with the evaluation process.

#### DISTINCT RESPONSIBILITIES OF THE MANAGEMENT LEAD

7.1 The MANAGEMENT LEAD will be responsible for the following core deliverables:

Core Deliverable 1: Planning and administration of research grant competitions
The ML is required to award Grant Agreements acting on behalf of the Authority.  The Route to Market may be via a direct award or open competitions. The Authority will direct the ML on the most appropriate Route to Market on a case-by-case basis.

Core Deliverable 2: Managing Commercial Instruments

The ML will:

    - develop a secure e-management platform (or utilise an existing one) that is accessible to all required parties and which will be used as a project, data and knowledge management tool.

    - manage Grants  in accordance with the agreed upon terms and conditions

    - manage delivery of commercial partners

    - disburse monies in the way set out by the Authority in the Overarching Agreement and specification

Core Deliverable 3: Monitoring and learning

The ML will have responsibility for leading implementation of Monitoring and Learning at the (i) Recipient project level, (ii) thematic and geographic spoke level and (iii) across the GCBC programme level, to improve GCBC management and implementation of research.

The ML will work closely with the Strategic Science Lead which will produce evidence synthesis products to progress thematic and geographic level priorities and inform learning. 

The ML will co-operate with the annual review of the GCBC that will be conducted by the Authority

Core Deliverable 4: Stakeholder Learning and Communications

The ML will develop a communications plan identifying relevant stakeholders and plans for active engagement; develop a learning platform/website to optimise lessons learnt and share best practice; and develop thematic and/or geographic level stakeholder learning events.

Core deliverable 5: Collaboration 

The ML will have overall responsibility for GCBC programme management and will be the main link between Recipients and the Authority, Strategic Science Lead and Independent Evaluator. It should develop a robust framework for communication and reporting between the Recipients, Supplier and Strategic Science Lead.

#### DISTINCTIVE RESPONSIBILITIES OF THE STRATEGIC SCIENCE LEAD

8.1 The STRATEGIC SCIENCE LEAD (comprised of interdisciplinary research experts) shall:

- oversee the development of a Research Strategy to guide the strategic focus and implementation of GCBC research calls which will include:

# proposed priority research themes and geographies by which to define the spokes and associated research grant calls, together with a research plan;

# priority research questions to be addressed through grant calls in relation to the research themes and geographies of interest; and

# a workplan for the SSL to develop yearly evidence products at systems-level from GCBC outputs and using wider input where required.

- contribute to GCBC operationalisation and administration which will include:

- support the development of the Management Lead’s Research Grant Competition Plan including helping to develop evaluation questions;

- contribute to the Management Lead’s Monitoring, Reporting and Learning Plan

- contribute to the Management Lead’s Communications Plan

- implementation of Research Strategy and oversight of research cycles which will include:

- develop yearly evidence products at the systems-level from a review of GCBC outputs with the incorporation of wider input where required;

- lead the synthesis of evidence created through thematic- and geographic- focused research projects and produce high quality learning outputs for both operational and policy audiences, which are greater than the sum of the individual parts; and

- undertake additional analysis or evidence collection across geographic and/or thematic research areas where appropriate to complement project-level evidence to support the synthesis process and development of learning outputs.

- reporting and meeting requirements, which will include:

- monthly dashboard snapshot reports of activities against core deliverables and associated expenditure

- quarterly expenditure and risk reports against core deliverables and any amended forecasts and risks

- contributing to the Management Lead’s Annual Monitoring Report of the GCBC

- appropriate research analysis and evidence synthesis products which should include a yearly review and forward look

#### DISTINCTIVE RESPONSIBILITIES OF THE INDEPENDENT EVALUATOR

#### 9.1 An “Independent Evaluator” will be responsible for evaluating the GCBC process, performance and impact, which the Authority will appoint.

#### 9.2 The Independent Evaluator will be responsible for programme level Evaluation including process, theory-based, and impact evaluation. It will be the role of an Independent Evaluator to refine and answer key evaluation questions to ultimately understand to what extent the GCBC has contributed towards achieving the objectives of the progamme.

# APPENDIX 1. Delivery Profile

DELIVERY PROFILE FOR: Jan 2023 – March 2025

[the months set out in this Annex assume the management lead will be appointed by end March 2023

| Deliverable | Delivering Partner Responsible | Date for completion / rate of recurrence * | Receiving Partner |
| --- | --- | --- | --- |
| GCBC Programme Management | The Hub | On-going | The Authority, Strategic Science Lead (SSL), Grant Recipients, IE |
| Grant Recipient agreement management | The Management Lead | On-going | The Authority |
| “The Research Grant Competition Plan” | The Management Lead | Within 4 weeks of the Management Lead being appointed First grant agreements signed by end October 2023 | The Authority |
| Competition specifications and ITA packs for each competition | The Management Lead | Within 5 weeks of The Research Grant Competition Plan being agreed. On-going competitions up to March 2025 as required | The Authority |
| Develop evaluation questions for each competition | The Management Lead | As part of the research grant call specification process | The Authority |
| Administer grant recipient applications | The Management Lead | Reactively | The Authority |
| Evaluation of grant recipient bid technical envelopes | The Management Lead and The Authority (Evaluation Panel Members) | Reactively | The Authority |
| Evaluation of grant recipient bid qualification and commercial envelopes and associated due diligence assessments | The Management Lead (distinct evaluators from Evaluation Panel) | Reactively | The Authority |
| Grant award report for each competition | The Management Lead | Reactively | The Authority |
| Grant Recipient Due Diligence assessments | The Management Lead | One month after the grant award reports for each competition are produced | The Authority |
| Develop e-platform (project, data and knowledge management tool) | The Management Lead | Within the first 3 months | The Authority, Strategic Science Lead, IE, Commercial Partners |
| Hub Partners Ways of Working Plan | The Management Lead and Strategic Science Lead | Within 8 weeks of the Management Lead being appointed | The Hub, The Authority |
| Communications plan | The Management Lead and Strategic Science Lead | Within 6 months of the Management Lead being appointed | The Hub, The Authority |
| Regular reporting (project, finance, risk) | The Management Lead | Monthly / Quarterly / Annually as set out in Annex 16 | The Authority |
| Monitoring | The Management Lead; as applicable (as per Appendix 2 Monitoring & Learning) in consultation with the SSL | On-going | The Authority |  |
| Monitoring & Learning Plan (ToCs, KPIs) | The Management Lead as applicable (as per Appendix 2 Monitoring & Learning) in consultation with the Strategic Science Lead | Within 10 weeks of the Management Lead being appointed | The Authority |
| Programme level evaluation | Independent Evaluator (IE) | At intervals from 23/24 FY onwards | The Management Lead / The Authority |
| Learning cycles | The Management Lead and IE and SSL | Quarterly / Annually | The Authority |
| GCBC website | The Management Lead | Within 4 weeks of the Authority’s approval of the Communications plan | The Authority |
| Thematic/Geographic stakeholder learning events | The Management Lead | On-going | The Authority, IPLCs, Government, other relevant sectors etc. |
| Research strategy, evidence coordination and synthesis | SSL with input from wider research community | April 2023 (First iteration for use by the ML) and on-going | The Hub, The Authority |
| Develop thematic/geographic level Theories of Change | The Management Lead | April 2023 | The Authority / The Hub |
| Lead scoping analyses (PETA) and stakeholder/organisational mapping | SSL with input from wider research community | By May 2023 | The Authority / The Hub |
| Knowledge and data management strategy and work plan | SSL and The Management Lead | By May 2023 | The Authority / The Hub |
| Synthesis of thematic and regional level evidence | SSL with input from wider research community | On-going | The Authority / Policy audiences |
| Dissemination of evidence outputs | Management Lead | On-going | The Authority / Research audiences |
| Develop international network of research organisations | SSL | On-going | The Authority / Management Lead |

* With regards to rates of recurrence which are listed as annually or quarterly the deliverable must be provided within 10 working days following the end of the period. Annually and quarterly shall run in line with the Authority’s financial year (1 April – 31 March).

# APPENDIX 2. Monitoring & Learning

Overview

The Management Lead will have responsibility for leading implementation of Monitoring and Learning at the (i) Recipient project level, (ii) thematic and geographic spoke level and (iii) across the GCBC programme level, to improve GCBC management and implementation of research.

The Management Lead will work closely with the Strategic Science Lead which will produce evidence synthesis products to progress thematic and geographic level priorities and inform learning.

An Independent Evaluator will be responsible for programme level Evaluation including process, theory-based, and impact evaluation. It will be the role of an Independent Evaluator to refine and answer key evaluations questions to ultimately understand to what extent the GCBC has contributed towards achieving more effective climate resilient development via systems-research on the conservation and sustainable use of biodiversity.

The Management Lead will lead on a Monitoring and Learning Plan during the Inception Phase, to set out how it will collect monitoring data from grant recipients and how it will implement learning. It will do so in consultation with the Strategic Science Lead, which will feed in technical science information and that relating to the nature of research themes and geographies as per its Research Strategy. The Authority will approve the Monitoring and Learning Plan.

As part of the Monitoring and Learning Plan, the Management Lead will lead work, with contribution from the Strategic Science Lead, to develop geographic and/or thematic ToCs, logframes and KPIs based on the priority themes and geographies from the Research Strategy.

The Management Lead will be responsible for developing and implementing a monitoring structure which ensures monitoring data is collected effectively at Recipient project level to feed into thematic and regional analyses to be conducted by the Strategic Science Lead. The Management Lead and the Strategic Science Lead must agree how monitoring data will be presented, how it will be used by the Strategic Science Lead and how such data can be used to facilitate learning, and this should be detailed in the Monitoring and Learning Plan.

Monitoring

Projects must be monitored in line with the International Development Act 2002.

The Management Lead must ensure each Recipient project has a project-level logframe which contributes to thematic and GCBC-level theories of change. The Management Lead should provide guidance in the grant application stage to help prospective grant Recipients develop effective logframes.

The Management Lead will be responsible for communicating and implementing a monitoring plan with Recipients, as per the Monitoring and Learning Plan. Ensuring collection of monitoring data is the responsibility of the Management Lead, including baseline data, and it should ensure standardisation of monitoring data across the projects as far as possible to enable thematic and geographic aggregation.

The Management Lead will monitor Recipient projects against their project logframes to ensure delivery of activities, outputs and outcomes. The Management Lead must ensure the requirements are reflected in the Grant Agreements with Recipients.

The Management Lead must share relevant monitoring data with the Strategic Science Lead and any Independent Evaluator to inform GCBC-level evidence synthesis and evaluation cycles, respectively.

Monitoring information should be available at project level and aggregated at the thematic research level and at geographical spoke level by the Management Lead and will be submitted to the Authority 10 (TEN) working days ahead of each quarterly Authority Programme Board.

The Management Lead will as a minimum:

- Set out a Monitoring and Learning plan, including:

  - leading and working with the Strategic Science Lead to take identified thematic and regional research priorities, and developing corresponding theories of change and logframes that sit within the programme level ToC;

  - detailing how data will be collected;

  - how the Recipient projects will be monitored and progress tested against their logframe; and

  - how progress will be communicated to the Authority.

- Ensure that all Recipients have project logframes and a monitoring plan.

- Ensure that all monitoring data is collected in line with the requirements of the International Development Assistance Act 2002; that all monitoring data collected is submitted to the Supplier’s e-platform; and that all Recipient monitoring data is standardised and complete.

- Aggregate monitoring data at the thematic and/or regional level, where appropriate, so it can be used to evaluate the progress against relevant ToC’s, including by the Strategic Science Lead.

- Where requested, provide access to monitoring data to the Independent Evaluator to aid in its evaluation.

- Test progress against deliverables of each Recipient on a quarterly and annual basis, using the quarterly monitoring data submitted by Recipients.

- Test progress against thematic and regional level logframe activities, outputs and outcomes on an annual basis. The methodologies for testing should be developed in consultation with the Strategic Science Lead, and submitted for approval to the Authority.

- Assessments of activities, outputs, outcomes and KPIs must be submitted as part of the relevant quarterly or annual report, to the Authority.

- Collect and compile analyses and products produced by Strategic Science Lead for programme annual reviews.

- Draft inputs for programme annual reviews for the Authority if required.

- For any Phase One projects (22/23 FY) which continue into financial year 2023/24, work to implement effective monitoring alongside the research grant projects

Learning

Monitoring and Reporting Data will form a major contribution to the evidence base for learning throughout the GCBC.

There will be two in-programme levels of learning conducted on quarterly and annual cycles, led by the Management Lead:

- Quarterly and annual accountability, to improve management and implementation of research, drawing on both Monitoring and Reporting Data.

- Annual learning at thematic and geographic spoke level, drawing on monitoring data using theory-based learning, and reviewing evidence synthesised by the Strategic Science Lead

- A third level of learning will require the Management Lead to operationalise and facilitate GCBC-programme level learning, from theory-based evaluation outputs produced by an Independent Evaluator (the frequency of this will be determined in the Inception Phase by the Authority but will not be more frequent than yearly).

The Management Lead will co-ordinate and manage the two in-programme learning cycles (annual and quarterly cycles) to facilitate strategic decision making, including by the Authority, and by the Strategic Science Lead in its cyclical assessment of research priorities.

The Management Lead’s responsibility in the learning cycles include:

- Developing the structure of the learning cycles, with the Authority and Strategic Science Lead, during the Inception Phase as part of its lead on producing a Monitoring and Learning Plan. This includes working with the Strategic Science Lead to plan how to facilitate learning for a variety of audiences.

- Convening the quarterly and annual learning cycle meetings. This includes minuting, ensuring relevant parties are invited and present, and submitting recommendations and/or reports to the Authority.

- An annual learning cycle meeting will involve the Management Lead, the Strategic Science Lead, the Authority and where relevant, Recipients. Once appointed, the Independent Evaluator should also be invited to these meetings. The meeting will be focused on discussing adaptive programming recommendations for both theory-based learning and accountability.

- The Management Lead will submit recommendations to the Authority ten (10) working days prior to the annual Programme Board dedicated to learning, the “Learning Board”, and a minute of the annual learning cycle meeting.

- Disseminating to Recipients and incorporating into GCBC management, the adaptive programming decisions made by the Authority, including making any changes to logframes or grant agreements or documentation to reflect decisions. The Management Lead must support Recipients in implementing decisions and following up with review meetings to check implementation is continually carried out.

Table 1 describes the inputs and outputs expected from the Management Lead in relation to the learning cycles:

| Learning cycle | Lead | Aims / Research Questions | Inputs | Outputs from The Management Lead |
| --- | --- | --- | --- | --- |
| Quarterly | The Management Lead | Review progress against logframes for each Recipient project (activities, outputs outcomes) | Recipient quarterly reports | The Management Lead’s quarterly reports. Propositions to adapt, including risks and opportunities Documentation amendments if applicable, once adaptive programming decisions taken by the Authority. |
| Annual | The Management Lead | The Management Lead: Review processes including management and governance Review project, thematic and geographic level progress against logframes. The Strategic Science Lead: Review Research Strategy and priorities, including evidence syntheses at thematic and geographic level on an ongoing basis. | Any evaluations conducted by an Independent evaluator. Learning from quarterly meetings and reports The Strategic Science Lead’s evidence products Literature, publications etc | The Management Lead’s annual report, including sub-reports/contributions by the Strategic Science Lead Learning events Communications, including those via the GCBC website Documentation amendments if applicable, once adaptive programming decisions taken by the Authority |
| Ad hoc (maximum frequency to be annual) | The Management Lead | Identify and communicate whether the programme is effective in progress against the GCBC level ToC. | Any evaluation products produced by an Independent Evaluator, for example using theory, geographic, thematic, process, and/or impact evaluation methodologies. | Learning events based on independent evaluation. Communications, including those via the GCBC website. Documentation amendments if applicable, once adaptive programming decisions taken by the Authority. |

# APPENDIX 3. Data Processing Terms

DEFINITIONS

Terms defined in this Agreement have the same meaning for the purposes of this Appendix and, in addition, the following terms have the following meanings:

Controller, Processor, processing, Data Subject, Personal Data, Data Protection Officer take the meaning given in the UK GDPR or, in respect of processing of personal data for a law enforcement purpose to which Part 3 of the DPA 2018 applies, the meaning in that Part if different;

Data Protection Impact Assessment: an assessment by the Controller of the impact of the envisaged processing on the protection of Personal Data;

Data Subject Rights Request: a request made by, or on behalf of, a Data Subject in accordance with rights granted pursuant to the Data Protection Legislation in respect of their Personal Data;

Personal Data Security Breach: a breach of security leading to the accidental or unlawful destruction, loss, alteration, unauthorised disclosure of, or access to, Personal Data transmitted, stored or otherwise processed;

Processor Personnel: means all directors, officers, employees, agents, consultants and contractors of the Processor and/or of any Sub-processor engaged in the performance of its obligations under this Agreement;

Protective Measures: appropriate technical and organisational measures which may include: pseudonymising and encrypting Personal Data, ensuring confidentiality, integrity, availability and resilience of systems and services, ensuring that availability of and access to Personal Data can be restored in a timely manner after an incident, and regularly assessing and evaluating the effectiveness of the such measures adopted by it;

Sub-processor: any third party appointed to process Personal Data on behalf of that Processor related to this Agreement;

REQUIREMENTS OF PARTIES TO THIS AGREEMENT

Where there is a Controller-Processer relationship, each Party shall co-operate with the other Party to complete Schedule 1 to this Appendix prior to entering into the relationship.

DATA PROTECTION – WHEN ONE PARTY IS CONTROLLER AND THE OTHER PARTY IS THE PROCESSOR

Schedule 1 identifies the Party acting as Controller and the Party acting as Processor for Personal Data processed under this Agreement. Subject to paragraph 3.4 (a), the only processing that the Processor is authorised to do is listed in Schedule 1 by the Controller and may not be determined by the Processor.

The Processor shall notify the Controller immediately if it considers that any of the Controller's instructions infringe the Data Protection Legislation.

The Processor shall provide all reasonable assistance to the Controller in the preparation of any Data Protection Impact Assessment in respect of any processing. Such assistance may, at the discretion of the Controller, include:

- a systematic description of the envisaged processing operations;

- an assessment of the necessity and proportionality of the processing operations in relation to the Project;

- an assessment of the risks to the rights and freedoms of Data Subjects; and

- the measures envisaged to address the risks, including safeguards, security measures and mechanisms to ensure the protection of Personal Data.

The Processor shall, in relation to any Personal Data processed in connection with its obligations under this Agreement:

- process that Personal Data only in accordance with Schedule 1, unless the Processor is required to do otherwise by Law. If it is so required the Processor shall promptly notify the Controller before processing the Personal Data unless prohibited by Law;

- ensure that it has in place Protective Measures, which are appropriate to protect against a Personal Data Breach, which the Controller may reasonably reject (but failure to reject shall not amount to approval by the Controller of the adequacy of the Protective Measures), having taken account of the:

  - nature of the data to be protected;

  - harm that might result from a Personal Data Breach;

  - state of technological development; and

  - cost of implementing any measures;

  - ensure that :that:

  - the Processor Personnel do not process Personal Data except in accordance with this Agreement (and in particular Schedule 1);

- it takes all reasonable steps to ensure the reliability and integrity of any Processor Personnel who have access to the Personal Data and ensure that they:

  - are aware of and comply with the Processor’s duties under this paragraph;

  - are subject to appropriate confidentiality undertakings with the Processor or any Sub-processor;

  - are informed of the confidential nature of the Personal Data and do not publish, disclose or divulge any of the Personal Data to any third Party unless directed in writing to do so by the Controller or as otherwise permitted by this Agreement; and

  - have undergone adequate training in the use, care, protection and handling of Personal Data

- not transfer Personal Data outside the UK or the EEA, including by cloud computing, unless the prior written consent of the Controller has been obtained and the following conditions are fulfilled:

  - the Controller or the Processor has provided appropriate safeguards in relation to the transfer (whether in accordance with UK GDPR Article 46 or Chapter 5 of the DPA 2018) as determined by the Controller;

  - the Data Subject has enforceable rights and effective legal remedies;

  - the Processor complies with its obligations under the Data Protection Legislation by providing an adequate level of protection to any Personal Data that is transferred (or, if it is not so bound, uses its best endeavours to assist the Controller in meeting its obligations); and

  - the Processor complies with any reasonable instructions notified to it in advance by the Controller with respect to the processing of the Personal Data;

- at the written direction of the Controller, delete or return Personal Data (and any copies of it) to the Controller on termination of the Agreement unless the Processor is required by Law to retain the Personal Data.

- Subject to paragraph 3.6, the Processor shall notify the other Party without delay if it, in connection with Personal Data processed under this Agreement:

  - receives a Subject Request (or purported Subject Request);

  - receives a request to rectify, block or erase any Personal Data;

  - receives any other request, complaint or communication relating to either Party's obligations under the Data Protection Legislation;

  - receives any communication from the Information Commissioner or any other regulatory authority;

  - receives a request from any third party for disclosure of Personal Data where compliance with such request is required or purported to be required by Law; or

  - becomes aware of a Personal Data Breach, such notification in any event to be within 24 hours of becoming aware of the Personal Data Breach.

The Processor’s obligation to notify shall include the provision of further information to the Controller in phases, as details become available.

Taking into account the nature of the processing, the Processor shall provide the Controller with full assistance in relation to either Party's obligations under Data Protection Legislation in connection with Personal Data processed under this Agreement and any complaint, communication or request made (and insofar as possible within the timescales reasonably required by the Controller) including by promptly providing:

- the Controller with full details and copies of the complaint, communication or request;

- such assistance as is reasonably requested by the Controller to enable the Controller to comply with a Data Subject Rights Request within the relevant timescales set out in the Data Protection Legislation;

- the Controller, at its request, with any Personal Data it holds in relation to a Data Subject;

- assistance as requested by the Controller following any Personal Data Breach;

- assistance as requested by the Controller with respect to any request from the Information Commissioner’s Office, or any consultation by the Controller with the Information Commissioner's Office.

The Processor shall maintain complete and accurate records and information to demonstrate its compliance with this Appendix 3. This requirement does not apply where the Processor employs fewer than 250 staff, unless:

- the Controller determines that the processing is not occasional;

- the Controller determines the processing includes special categories of data as referred to in Article 9(1) of the UK GDPR or Personal Data relating to criminal convictions and offences referred to in Article 10 of the UK GDPR

- the Controller determines that the processing is likely to result in a risk to the rights and freedoms of Data Subjects; or

- the processing is processing to which Part 3 of the DPA 2018 applies

The Processor shall allow for audits of its Personal Data processing activity by the Controller or the Controller’s designated auditor.

The Parties shall designate a Data Protection Officer if required by the Data Protection Legislation.

Before allowing any Sub-processor to process any Personal Data related to this Agreement, the Processor must:

- notify the Controller in writing of the intended Sub-processor and processing;

- obtain the written consent of the Controller;

- enter into a written agreement with the Sub-processor which give effect to the terms set out in this Appendix 3 such that they apply to the Sub-processor; and

- provide the Controller with such information regarding the Sub-processor as the Controller may reasonably require.

The Processor shall remain fully liable for all acts or omissions of any of its Sub- processors.

The Controller may, at any time on not less than 30 Working Days’ notice, revise this clause by replacing it with any applicable Controller to Processor standard clauses or similar terms forming part of an applicable certification scheme (which shall apply when incorporated by attachment to this Agreement).

The Parties agree to take account of any guidance issued by the Information Commissioner’s Office. The Controller may on not less than 30 Working Days’ notice to the Processor amend this Agreement to ensure that it complies with any guidance issued by the Information Commissioner’s Office.

RECORDS

Each Party shall maintain complete and accurate records and information to demonstrate its compliance with this Agreement and the Data Protection Legislation.

Each Party shall provide the other full access to the other Party’s data security and privacy procedures relating to Personal Data.

Schedule 1 - Details of Personal Data Exchange

The contact details of the Controller Data Protection Officer are: data.protection@defra.gov.uk

The contact details of the Processor Data Protection Officer are:

For the Management Lead: [TBC]

For the Strategic Science Lead:  Digital Trust Consulting Services, BSI c/o privacy@kew.org

The Processor shall comply with any further written instructions with respect to processing by the Controller.

Any such further instructions shall be incorporated into this Schedule.

| Description | Details |
| --- | --- |
| Identity of the Controller and Processor | The Parties acknowledge that for the purposes of the Data Protection Legislation the Controller and Processor are: Controller: insert as appropriate Processor(s): insert as appropriate |
| Project Name and Subject Matter of the Processing | The processing of personal data is to evaluate the effectiveness of the Authority’s Official Development Assistance with the regards to the GCBC. This shall enable the Authority to take any required adaptive programming decisions and capture any lessons learnt for future Official Development Assistance programmes. |
| Duration of the processing | Current funding runs until 31st March 2025 with possible programme extension of up to 3 years (subject to funding) |
| Nature and purposes of the processing | To be determined once The Hub are in place, and once the Strategic Science Lead has developed the Research Strategy and the Management Lead and IE have developed their evaluation approach and questions approved by the Authority. |

| Type of Personal Data (including identifying any special category data or data relating to criminal convictions and offences) | To be determined once the Lead Delivery The Hub are in place, and once the Strategic Science Lead has their methodology and evaluation approach and questions approved by the Authority. |
| --- | --- |
| Categories of Data Subject | To be determined once the Lead Delivery The Hub are in place, and once the Strategic Science Lead has their methodology and evaluation approach and questions approved by the Authority. |
| Plan for return and destruction of the data once the processing is complete UNLESS requirement under union or member state law to preserve that type of data | To be determined once the Lead Delivery The Hub are in place, and once the Strategic Science Lead has their methodology and evaluation approach and questions approved by the Authority. |
| Transfers to third countries or international organisations | Data shall be gathered in multiple foreign nations. Data will be transferred to the UK once gathered and remain in the UK until destroyed. |
| Legal Basis for Processing | Consent: the individual has given clear consent for the Parties to process their personal data for a specific purpose. OR Contract: the processing is necessary for a contract the Controller has with the individual, or because they have asked you to take specific steps before entering into a contract. OR Public task: the processing is necessary for you to perform a task in the public interest or for your official functions (i.e. official authority vested in you), and the task or function has a clear basis in law. |
| Special Terms | N/A |