## Sheet1
CLARIFICATION LOG
Tender: | Solar Panels - Princess Pavilion, Melvill Road, Falmouth TR11 4AR
Tender Reference:
Published Date: | 2024-06-16
Version number: | 0.3
Number | Clarification | Response | Reply date
1 | We have come across your tender request but could not find the format you are wanting the respond returned to you | We do not have a prescribed format for the tender submissions but would expect all the questions to be answered including a visual outline of where you felt solar panels should be installed, how many and at what cost. | 2024-06-12
2 | Which buildings are you looking for Solar to be installed on. If you can highlight that would be appreciated | The updated plan on Contracts Finder is an approximate drawing of where the solar panels could be installed on the pitched roofs of the theatre and the café (not the veranda area or the flat roofs). This is very rough but should give you an idea of the size / area that could be utilised for the panels. | 2024-06-12
3 | Please can you provide a copy of your half hour data, Mpan Number and current cost you pay per Kilowatt. | Please see attached document indicating Data Usage indicating the actual readings for the year 2022/23 with the cost that year. Please note that that the Council has since changed supplier and have a more advantageous unit rate with British Gas. If we are able to obtain more up to date information then we will look to further update via Contracts Finder. | 2024-06-12
4 | Where is the tender submission to be returned to? | Please return your tender submission by email to: | 2024-06-16
5 | With the quality part of the tender does this mean just answering the bullet points on your documents or is there any other documents needed for this tender. | Alongside the price element it would be helpful as part of tender submission to include a summary in relation to the quality elements referenced e.g. Start date for installation, Performance information for panels and battery, Location of head office and manufacture of products, Proven track record for other installations in the county, Ability to deliver on time (completion date must be no later than 31 March 2025 | 2024-06-16
6 | I would like to express our interest in tendering for the solar pv scope of works for the Princess Pavilion project. Could you please provide us with the tender details for this scope and any other relevant information to prepare a competitive bid. | Details in relation to this tender are included as part of the contract notice on Contracts Finder. Should specific additional information be required then please raise as a separate clarification question. | 2024-06-16
7 | Is there are any pre-qualification requirements or criteria that we need to meet in order to be eligible for the tender | There is no pre-qualification requirement with this tender, all details are included in the accompanying RFT document to this contract notice. Please also refer to response to question 1 above. | 2024-06-16
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: