## Cover
Appendix A5: ASC Service Provider PMF Scoring Guidance - Mobilisation
ASC
Service Provider Performance Management Framework
Mobilisation
Scoring Guidance
Version 1.0
April 2012

## Guidance
Goal Ref | HA Goal | Lever Ref | Lever | Aspect Ref | MST Area of Measure | Aspect | Aspect Evidence / Measures Scoring of performance should include consideration of the following typical evidence / measures | GREEN | AMBER | RED
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | THE RIGHT PEOPLE, PROCESSES AND SYSTEMS ARE IN PLACE – EFFECTIVE MOBILISATION | 2.1a | Right First Time | Mobilisation process designed and documented in accordance with Service Information requirements | Demonstrate: - Mobilisation process designed and documented in accordance with Service Information requirements Evidence - Mobilisation Process | Mobilisation process designed and documented in accordance with Service Information requirements and Process submitted within specified timescale or on track to be submitted on time | Mobilisation process exists but has not been designed and documented in accordance with Service Information requirements or Process not submitted within specified timescale or not on track to be submitted on time | Mobilisation process does not exist
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | MOBILISE THE CONTRACT | 2.1b | Right First Time | Facilities, accommodation, plant and equipment required by Provider and Employer effectively established | Demonstrate: - Facilities, accommodation, plant and equipment required by Provider and Employer effectively established Evidence - Agreement of resources | Facilities, accommodation, plant and equipment required by Provider and Employer effectively established | Facilities, accommodation, plant and equipment required by Provider and Employer mostly established with minor issues to be resolved | Facilities, accommodation, plant and equipment required by Provider and Employer not established with major issues to be resolved
2 | WE SET THE STANDARD FOR DELIVERY | 2.1 | MOBILISE THE CONTRACT | 2.1c | Right First Time | Quality Plan prepared and suitable for acceptance by Service Manager including adequate time provided for review | Demonstrate: - Quality Plan prepared and suitable for acceptance by Service Manager including adequate time provided for review Evidence - Quality Plan - Date of submission | Quality Plan prepared and suitable for acceptance by Service Manager including adequate time provided for review | Quality Plan prepared but not suitable for acceptance by Service Manager or Inadequate time provided for review | Quality Plan not prepared
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MOBILISE THE CONTRACT | 2.1d | Right First Time | Asset Maintenance and Operational Requirements plans prepared and suitable for acceptance by Service Manager including adequate time provided for review | Demonstrate: - Asset Maintenance and Operational Requirements (AMOR) plans prepared and suitable for acceptance by Service Manager including adequate time provided for review Evidence - AMOR - Date of submission | AMOR plans prepared and suitable for acceptance by Service Manager including adequate time provided for review | AMOR plans prepared but not suitable for acceptance by Service Manager or Inadequate time provided for review | AMOR plans not prepared
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MOBILISE THE CONTRACT | 2.1e | Right First Time | Reasonable steps taken to obtain all records, programmes and other necessary information from the Outgoing Provider | Demonstrate: - Reasonable steps taken to obtain all records, programmes and other necessary information from the Outgoing Provider Evidence - Records, programmes and other necessary information from the Outgoing Provider - Communications with Outgoing Provider - Meetings with Outgoing Provider and minutes from meetings | Reasonable steps taken to obtain all records, programmes and other necessary information from the Outgoing Provider | N/A | Reasonable steps have not been taken to obtain all records, programmes and other necessary information from the Outgoing Provider
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MOBILISE THE CONTRACT | 2.1f | Right First Time | Comprehensive review undertaken of financial planning carried out by Outgoing Provider including recommendations for any changes and attendance at budget planning workshops as necessary | Demonstrate: - Comprehensive review undertaken of financial planning carried out by Outgoing Provider including recommendations for any changes and attendance at budget planning workshops as necessary Evidence - Comprehensive review undertaken of financial planning carried out by Outgoing Provider - Recommendations made - Communications with Outgoing Provider - Meetings with Outgoing Provider and minutes from meetings - Attendance at budget planning workshops and minutes from workshops | Comprehensive review undertaken of financial planning carried out by Outgoing Provider including recommendations for any changes and attendance at budget planning workshops as necessary | A review has been undertaken but it is not comprehensive in scope or Recommendations have not been made | A review has not been undertaken
2 | WE SET THE STANDARD FOR DELIVERY | 2.2 | MOBILISE THE CONTRACT | 2.1g | Right First Time | Preparation of detailed Annual Commercial Plan for first Financial Year submitted no later than six weeks prior to access date | Demonstrate: - Preparation of detailed Annual Commercial Plan for first Financial Year submitted no later than six weeks prior to access date Evidence - Annual Commercial Plan - Date of submission | Preparation of detailed Annual Commercial Plan for first Financial Year submitted no later than six weeks prior to access date | Annual Commercial Plan for first Financial Year submitted but without the required detail or Submitted between five and six weeks prior to access date | Annual Commercial Plan for first Financial Year not produced or Submitted later than five weeks prior to access date
Note: For all Aspects, if a requirement has an end date in the future then score the Aspect on likelihood of meeting the requirement by the target date.