# Reason for Change

The findings from the Critical Skills Analysis currently under contract with PA Consulting have presented a number of opportunities to increase the rate of recovery of critical skills through the adoption of a time bounded programme of work.  By broadening the scope of the current arrangement but not changing the overall requirement, a contract amendment is requested to realise the benefit earlier, direct the response plan, and implement workable solutions ahead of previously planned time.

The amendment required is in respect of value (an additional £379,500 ex VAT) and time (an additional 4 weeks).

# Additional Deliverables

The additional deliverables are made up of the following:

| Ref | Description | Timeframe |
| --- | --- | --- |
| 1 | Clarify the purpose and ambition of the programme | 31 Aug 18 |
| 2 | Document strategic narrative and refine scope | 31 Aug 18 |
| 3 | Design programme’s ongoing ways of working | 28 Sep 18 |

# Roles

The following resources will be engaged in this work:

| Name | Role |
| --- | --- |
| REDACTED | Assignment Team Leader and Project Manager |
| REDACTED | Vision , Mission, and Case for Change |
| REDACTED | Strategic Outcome, Design Principles, and Stakeholder Management |
| REDACTED | Work Based Structure, Plan and Programme Management |
| REDACTED | Baseline and Benefits |

# Fees

Funding (inclusive of expenses) will be apportioned as follows:

| Deliverables | Funding |
| --- | --- |
| Total (Excluding VAT) | £379,500 |
| VAT | £75,900 |
| Total (Including VAT) | £455,400 |