## Sheet1
Clarification Questions & Responses - Tender for Kresen Kernow – Exhibition Design and Fit-Out and Wayfinding
Clarification Number | Date Clarification Query Sent to the Council | Document | Section | Subject | Page/s | Clarification Question | Response | Date Responded | Provided To
1 | 2016-01-13 16:17 | ITT | 6.6 Commercial Documentation | Providing price information | 57-61 | Pages 58 - 61 require price breakdown of all deliverables zones 1-4. As this can only be done once the detail design scheme has been developed with and signed off by the client team can you please clarify how you see this being included in the tender return. | As the tender covers the design, delivery and installation of products for all of the zones we need to have a price quoted for the overall works in order to make our assessment. The price quoted in the tender return will be used to assess the price element of the tender which is worth 40% of the tender total. We expect Tenderers to provide us with a “guaranteed maximum price” for the tender as set out in the terms and conditions embedded in section 6.7 of the ITT. We appreciate that the choice of final materials has not yet been made, however, we would hope that a “guaranteed maximum price” can be given based on Tenderers’ knowledge and experience of possible materials and the details in the specification and appendices. | 2016-01-19 | All Tenderers
2 | 2016-01-19 | All Tender Documents | All | Plans | All | because your request for the reconstruction / new building in Kressen Kernow Achiv Center I had a few more questions because of requirements on your part. Unfortunately I can not tell what kind of conversion to be performed in Contracts Finder. Are there any documents and drawings, etc. for an accurate quote. | As the contract is for the design, fabrication and installation of the exhibition zones and wayfinding there are no more detailed drawings available at this stage. The floor plans in the appendices are to scale, but it has not yet been decided exactly where each exhibition will be located, what it will look like or what it will be made of, therefore no further drawings or documents are available. | 2016-01-20 | All Tenderers
3 | 2016-01-19 | N/A | N/A | Exhibition Designer / Interpretive Concepts | N/A | Please can you confirm whether any interpretation consultants or exhibition designers have been involved in the project so far? | Exhibition designers were involved during the Development Phase of the Kresen Kernow project to help write an Exhibition Plan for the Heritage Lottery Fund submission. The plan included indicative drawings of what exhibition zones in the building could look like and cost. The themes for the various zones are based on consultation undertaken during the Development Phase. As stated in the Specification, we are committed to the concept of themed exhibition zones, but not the drawings in the Exhibition Plan. | 2016-01-20 | All Tenderers
4 | 2016-01-20 | All Tender Documents | N/A | Site Visits | N/A | We’ve recently received the tender for the Kresen Kernow project, we’re exhibition designers and fit out specialists ** and from reviewing the information provided would be really interested in putting in a tender response for the project delivery. In order to understand the site and requirements further would it be possible to meet up with you at all on site? if so could you kindly let me know when would be a suitable time? | We cannot access Kresen Kernow or the wider site at the moment as there is ongoing demolition work on one side of the building. Currently it is only possible to look through the gates on the boundary to view the exterior of Kresen Kernow building in Redruth. There are public tours of the wider site and outside areas for the local community as part of the Kresen Kernow Activity Programme scheduled for Friday 5th and Saturday 6th February. Anyone can book on to one of these by calling 01872 323127. | 2016-01-20 | All Tenderers
5 | 2016-01-20 | N/A | N/A | Exhibition Designer / Interpretive Concepts | N/A | Thank you for the previous clarification about the prior involvement of an exhibition designer. Are you able to say who the company was that was involved? And secondly, are they eligible to bid at this stage? | There is nothing to restrict the designers who contributed to the Development Phase from tendering for this project and for that reason we cannot disclose the name of the organisation. However, the ITT and appendices include all the relevant extracts from the Exhibition Plan, except the indicative drawings and an example budget. The Development Phase is completely distinct from this Delivery Phase and will be conducted in accordance with the conditions in the ITT. The Council is conducting this procurement process in accordance with the Open Procedure and the requirements outlined in the ITT and welcomes as many tender submissions from suitable candidates as possible. | 2016-01-21 | All Tenderers
6 | 2016-01-27 | ITT | ITT | Exhibition Plan | N/A | We understand that some parts of the exhibition plan have been provided but we would appreciate the opportunity to review this in full. Is it possible to see a full copy of the Exhibition Plan please? | The Kresen Kernow Exhibition Plan is a specific document created for the Heritage Lottery Fund application. It cannot be made available as it contains one interpretation of some of the current brief and an indicative budget. We do not want to influence the designs or ideas of any potential tenderers by sharing this. All the relevant content of the Exhibition Plan has been included in the ITT, specifically in section 6.5 (throughout the background to the brief, objectives of the spaces and requirements) and within the tables and text in Appendix 3f Space allocations and exhibition zones. | 2016-01-28 | All Tenderers
7 | 2016-01-28 | Appendix 3f and ITT | Appendix 3f (all pages) and ITT (pages 58-60) | Cases | 58-60 and Appendix 3f | The scope appears to require 10 cases, including some upstairs which are to be fully climate controlled. As this is likely to significantly impact on the budget, can you please provide clarification about the spec required for each zone and proposed sizes? | The Space allocation and exhibition zone document in Appendix 3f contains as much information as is currently available. The exact size of the cases will be dependent on the design of the zones. We have indicated the number of cases and type of items that will need to be displayed in each zone and the cases will need to be large enough to allow flexibility. Our collections contain fairly standard local authority archives and we do not intend to display oversized items. The cases in the first floor exhibition space need to be large enough to allow maximum flexibility in terms of their contents and maximum accessibility in terms of the floor space they take up, yet they also need to be affordable. | 2016-01-28 | All Tenderers
8 | 2016-01-28 | N/A | N/A | Design Considerations and Site Constraints | N/A | Regarding Installation of the units and signage - Are there onsite facitiies for parking for workmen and is storage of items onsite allowed during installation? | Yes | 2016-02-04 | All Tenderers
9 | 2016-01-28 | N/A | N/A | Design Considerations and Site Constraints | N/A | Are the power requirements and layout to be included in the main contractor works once tender is completed and the exhibition layout confirmed? Therefore not included in the installation works submitted in the tender. | Yes, the main contractor will be responsible for the installation of power and data cabling and access points. The current drawings for these have been uploaded onto the Contracts Finder website: https://www.contractsfinder.service.gov.uk/Notice/593deb8f-e24d-4a81-bbc9-c50393d59085 | 2016-02-04 | All Tenderers
10 | 2016-01-28 | N/A | N/A | Design Considerations and Site Constraints | N/A | Will text panels and cabinets be allowed to be fixed to walls? If so is there any information on the make up of the wall to provide an accurate quote and appropriate fixings? | Some may be fixed to the walls, but we envisage the majority being free standing. The internal walls will be mainly plasterboard, except for the interior north and south walls on the ground floor, which will be exposed masonry. | 2016-02-04 | All Tenderers
11 | 2016-01-28 | N/A | N/A | Design Considerations and Site Constraints | N/A | Is there a type of cabinet lock and cabinet lighting prefered or being used in other parts of the building to be matched? | Locks and lighting will need to conform to the security standards referred to in PD5454:2012 Guide for the storage and exhibition of archival materials and recommendations in the Government Indemnity Scheme Guidelines for national institutions January 2016. Decisions have not yet been made about any furniture and fixings in the rest of the building. | 2016-02-04 | All Tenderers
12 | 2016-01-28 | N/A | N/A | Design Considerations and Site Constraints | N/A | Is audio and visual equipment to be supplied by tenderer? | The appointed Contractor for Exhibition Design and Fit-Out and Wayfinding is required to work with the Activity Programme Team and the Digital Development Team to identify the requirements for digital (AV) hardware. AV screens and digital hardware will be sourced by the Council, however depending on the design of the interactives, the appointed Contractor may supply additional integrated audio headsets or handsets for example. | 2016-02-04 | All Tenderers
13 | 2016-01-28 | N/A | N/A | Design Considerations and Site Constraints | N/A | Are there internal elevations available or architect models available to use to assertain sight lines and heights of walls? | Elevations of the ‘brewhouse’ part of Kresen Kernow (i.e. the public section containing the exhibition areas) have been uploaded onto the Contracts Finder website: https://www.contractsfinder.service.gov.uk/Notice/593deb8f-e24d-4a81-bbc9-c50393d59085. No computer model of the building is available and all the existing internal renders are included in the Appendices. | 2016-02-04 | All Tenderers
14 | 2016-01-28 | N/A | N/A | Design Considerations and Site Constraints | N/A | Is there a brand guidelines for so that we can get fonts correct etc? | We have provided the Kresen Kernow Logo (Refer to Appendix 3j). There are currently no brand guidelines. | 2016-02-04 | All Tenderers
15
16
17
18
19
20
21
22