AUTHORITY: The Secretary of State for the Home Department

acting through Border Force

statement of requirements

PLANNED MAINTENANCE AND MCA LOAD LINE DOCKING TO

HMC SEEKER

May 2019

CONTENTS

Sect		Sub-heading

DEFINITIONS

Part 1: General

- Background

Part 2: Requirements and Constraints

- Requirements

- Location

- Constraints

Part 3: Provision of Services

- General Requirements

Part 4: Warranty

- Warranty Requirements

Part 5: Trials, Documentation, Acceptance and Payment

- Basin and sea trials

- Documentation

- Acceptance

- Charges and Payment

Annex A	Docking Specification

Annex B	Vessel Drawings

Annex C	Vessel Details

Annex D	Handover Document

Annex E	Launching Certificate

Annex F	Seaworthiness Certificate

Annex G	Acceptance Document

Annex H	Reimbursable expenses

Annex I	Cathodic Protection

DEFINITIONS:

| Acceptance | The issuing of an acceptance document, signed by the Authority following the completion of an Annual Maintenance & Repair Period to the satisfaction of the Authority. |
| --- | --- |
| Additional Work | Unprogrammed work outside of the scope of planned or scheduled work. |
| Agreed Facility | A single phone number for the Supplier giving access to a point of contact able to give user friendly assistance to persons experiencing technical problems with any part or operation of the Cutters |
| Alongside Berth | A suitable quay/berth with at least 1m depth below LWS at all times Complete with access by gangway/brow |
| Cardinal Date Plan (CDP) | A plan provided by the Supplier mapping out the significant dates for a project |
| Cutter | The Vessel as detailed in Annexes B & C |
| Defect Rectification | Work undertaken to resolve any kind of defect identified and listed in the work package. |
| Emergent work | Any work that emerges from the Planned Maintenance, which is notified to the Supplier in this Statement of Requirements. Any repairs which are required as a direct result of defects found with during this package of works. |
| Highlight Reports | A report highlighting the details, cause and effect, of a deviation from the agreed Cardinal Date Plan. |
| Lloyd Register | Lloyd’s Register’s Rules and Regulations set standards for the design, construction and lifetime maintenance of ships, offshore units and land-based installations. |
| Major Defect | Any defect or fault which reduces the performance of the Cutter, so it is unable to perform its duties. |
| Milestone Payment Plan | A plan setting out the significant milestone payments process for each Maintenance and Repair period |
| Minor defect | Any defect or fault which reduces the performance of the Cutter while allowing it to be safely operated for its duties. |
| Original Equipment Manufacturer (OEM) | The original manufacturer of a piece of equipment. |
| Planned Maintenance | The package of works as detailed at Annex A |
| Project Manager | A member of the Suppliers personnel who is responsible for the overall planning and execution of a project. |
| Progress Report | A report giving details of progress against the agreed CDP |
| Rectification Plan | A plan to rectify a specified defect, giving dates and reasons for relevant actions to effect full rectification of the defect. |
| Safe Working Load (SWL) | The maximum load a piece of equipment can safely lift. |
| Slipway/Dry Dock | A Slipway or Dry Dock of suitable size, complete with dock blocks in accordance with the supplied docking plan and to the satisfaction of the Border Forcer Overseeing Officer Complete with safe permanent means of access to the Cutter |
| Warranty | A guarantee, issued to the Authority by the Supplier, promising to repair or replace something if necessary within a specified period of time. |
| Working Location | The area in which the Cutter is operational |

Part 1:GENERAL

- Background

1.1 	The Authority currently operates a fleet of eleven sea going patrol craft operating in both UK National and International waters. This consists of five Cutters and six Coastal Patrol Vessels (CPV).

1.2	The four Damen 4207 patrol vessels of which HMC Vigilant is one, are built in accordance with Lloyds 100A+ and hold valid MCA International Loadline certification.

  - The primary roles of the Cutters are: -

1.3.1	To provide a mobile, flexible seaborne force capable of maintaining an effective deterrent against illegal immigration, smuggling and other breaches of the law administered by Border Force both within and outside the territorial waters of the UK.

1.3.2	To increase maritime intelligence, undertake surveillance and improve international liaison in combating illegal immigration, the smuggling of drugs and movement of instruments of terrorism by sea;

    - To intercept suspect vessels in territorial and international waters; and

1.3.4	To provide mutual assistance to other EC countries, the Channel Isles, the Isle of Man and other partners on the UK border.

1.4	In addition to these primary responsibilities, Border Force also undertake tasks on behalf of the Ministry of Defence, Maritime and Coastguard Authority, National Crime Authority, Police and UK Fisheries Agencies.

Part 2: REQUIREMENTS AND CONSTRAINTS

- Requirements

2.1	The objective of this specification is to provide requirements for;

- The annual MCA Hull Survey

- The Planned Maintenance and Defect Rectifications

- Location

3.1	Due to the operating area of the vessels, the package is to be undertaken in the geographic area between Portland and Firth of Forth.

4.0	Constraints

  - All work carried out must be compliant to all applicable standards or regulations and in accordance with best industry standards.

  - All new parts and equipment fitted should be supportable for a period of five years following installation

  - All new equipment shall be provided with relevant operator & maintenance    documentation, and any applicable certification.

  - The crew of HMC Seeker will remain onboard during normal working hours

  - All work is to be completed as follows:

    - – CRITICAL – Vessel must be lifted out of the water and available to for MCA inspection  on the 3rd June 2019.

    - - Vessel works aimed to be completed by week ending 14th June 2019.

3: PROVISION OF SERVICES

5.0	General Requirements

5.1	The Supplier will appoint a dedicated Project Manager, as a single point of contact, for the duration of the Project.

5.2	The Authority will delegate a Border Force Overseeing Officer (BFOO) for the duration of this contract, who shall be entitled to inspect any work or to have it inspected by his duly authorised representative.

5.3	On arrival at the supplier’s premises the respective Cutter will be formally handed over in the case of a docking to the Supplier using the formal handover document at Annex D.  Thereafter, the Supplier will be formally approached for consent in respect of any Authority activity or the activity of any Authority designated / arranged Supplier onboard.

5.4	The Supplier shall submit a draft CDP covering the completion of all planned work with the formal quotation for this work package, in an accessible Microsoft Office document format (word or excel), for approval by the Authority, once agreed by the Authority this will form the final CDP to be followed.

5.5	The Supplier is to provide Highlight Reports within twenty-four hours of all identified deviations from the CDP.

5.6	During the contract period the BFOO shall during normal working hours, have        access to all premises of the yard or its suppliers where any parts are being manufactured, repaired or serviced.

5.7	During the contract period the Supplier shall provide reasonable office accommodation for use by the Authority, to include printing facilities.

5.8	All tasks shall be completed by appropriately qualified and experienced personnel in relation to the equipment being worked upon.

5.9	The Supplier will be expected to clean the working area and remove and dispose of those component parts that are replaced and all waste created during this project.

5.10	All minor consumable fixings, sealants etc required to rectify defects to be provided by the Supplier.

5.11.	On completion of all work and prior to handback, the vessel shall be cleaned to an acceptable standard for operational use as accepted by the Authority.

5.12  A secure alongside berth is to be provided for the duration of the LSA period and following docking to enable the Basin trial programme to be completed

5.13  Provision of 415 volt 3 pH 125 amp electrical supply for the duration of the LSA/Docking period, payment of electrical supply to be via the Emergent Work process with meter readings before and after to support costs

5.14  A suitable dry dock or slipway complete with dock blocks in accordance with the Border Force supplied docking plan for the duration of the docking period

5.15	If using a slipway the maximum incline should be no more than 1:12.

5.16 The contractor is to provide security and insurance of the vessel for the duration of the slipping and alongside set to work trials

Part 4: WARRANTY

6.0	Warranty Requirements

6.1	The Supplier shall provide an Agreed Facility for reporting faults and obtaining technical advice, covering the hours between 08:00 and 16:30, Monday to Friday, for the logging of faults or data. Response times for such service shall allow for all faults to be logged, given a reference number and Rectification plan agreed between all parties within a maximum of forty-eight hours of the fault being logged.

6.2	The Supplier shall provide warranty repairs in the event that any of the supplied or repaired parts develops a fault during the parts warranty period.

6.3	All Work carried out by the Supplier during the period of this contract shall be covered by a one year Warranty.

6.4	All new parts supplied or fitted during the period of this contract shall be covered by a one year warranty or such other provided warranty if it is longer than the minimum one year.

6.5	In the event that a Warranty Major Defect is notified to the Supplier that will render a Cutter non-operational.  The Supplier shall provide services to ensure the Cutter is restored to full working condition within forty-eight hours, calculated from the date and time on which the Authority agrees the Supplier personnel can gain access to the Cutter. In the event a Major Defect cannot be rectified within the assigned period, a Rectification Plan must be agreed with the Authority within forty-eight hours of identification of the fault.

6.6	In the event that a Warranty Minor Defect is notified to the Supplier, other than those that will render the Cutter non-operational, the Supplier shall provide services to ensure the Cutter is restored to full working condition, as quickly as possible, and in any event, within ten working days, calculated from the date and time on which the Authority agrees the Supplier personnel can gain access to the Cutter. In the event a Minor Defect cannot be rectified within the assigned period, a Rectification Plan must be agreed with the Authority within forty-eight hours of identification of the fault.

Part 5: TRIALS, DOCUMENTATION, ACCEPTANCE AND PAYMENT

7.0 	Basin & Sea Trials

7.1	On completion of all work and once the Supplier has satisfied themselves that the Cutter is seaworthy this will be demonstrated to the Authority who will provide an Acceptance Certificate and confirm the hand back of the Cutter into the Authority’s custody and responsibility. Where propulsion work has been undertaken, this shall include propulsion and manoeuvring trials measured against original trials data for comparison and include OEM service engineer alongside the supplies own mechanical and electrical service engineers

The Authority will provide

- Launching certificate form as at Annex E

- Seaworthiness certificate as at Annex F

In respect of launching and pre-sea trails, for completion by the Supplier

7.2 	Any trials required shall be to prove that the executed work has been carried out satisfactorily and that the various systems can be checked and confirmed as fully and effectively re-commissioned. Other than fuel, all costs related to the operations of test and trials will be the responsibility of the Supplier.

7.3	Because of the specialist nature of the vessel, the Authority will provide a crew members familiar with the navigational controls and engineering systems of the Cutter.

8.0 	Documentation

8.1	All certification required for regulatory compliance or requested by the Authority shall be supplied enclosed in clear envelopes within four-ring binders complete with an index. An electronic copy shall be forwarded by e-mail to the Authority in an accessible Microsoft Word format.

8.2	All certificates and reports specified as required are to be provided before acceptance.

8.3	All certificates and reports specified as required are to be provided in a hard copy folder to the vessel before departure and electronically emailed to the Authority.

8.4	Certifications are required in the following format:

A. Two sets of hard copies

B. One set of electronic copy with index

Although these sets of certifications are to be presented at the Acceptance Meeting, to minimize time spent in checking these during the acceptance meeting prior opportunity shall have been given to the Border Force Overseeing Officer to check the contents and the index.

9.0     Acceptance

9.1	Final acceptance will be the issuing of a Final Acceptance document as at Annex G, signed by the Authority.

9.2	The Acceptance document will be issued after:

9.2.1      Delivery of Certificates of Conformity for all new equipment fitted.

9.2.2	Delivery of all documentation and certificates as specified in part 8 of this Statement of Requirements.

9.2.4    Outstanding actions listed at wash-up meeting

10.0  Charges and Payment

10.1	On completion the Supplier shall provide the Authority with a completed schedule showing the individual cost breakdown for each item of Planned Work and Emerging Work for approval. Following approval of this schedule the Supplier will invoice the Authority for 90% of the total amount.

10.2		The remaining 10% shall be invoiced following a one calendar month snag free period in relation to the work completed.

10.3  All travel and subsistence costs related to defect repairs shall be recharged at the Home Office reimbursable T&S rates as stipulated in Annex H.

ANNEX A – Docking Specification

- DOCKING

Prior to docking and after re-launch the Cutter is to be berthed on a secure berth: preferably non-tidal with good access (vertical ladders are in general considered as un-acceptable). It is to be provided with a shore power supply, the cost of which shall be borne by the Maintenance Contractor until the day following acceptance.

a. The Cutter is to be slipped, dry-docked or Syncro-lifted on a Border Force approved facility.

b. The underwater area is to be pressure washed off with fresh water to remove all slime, marine growth and loose flaking paint (to prevent re-contamination with salt, this should be done in conjunction with the hull and superstructure washing of required to prepare for the subsequent painting of these areas).

c. The Cutter is then to be moved into a secure covered facility where the painting and out of water maintenance work is to be carried out. Outside slipway facility will be considered

d. When clean and dry, the contractor is to carry out a full inspection of the underwater areas photographing and identifying any paint film damage, indentations or shell plate cracking. On completion a report is to be issued by the contractor and duly witnessed by the Border Force Overseeing Officer.

e. A full survey of existing antifouling paint condition and adhesion to the rudders, appendages, sea inlet, bow thruster, stabilizers etc., is to be carried out by the International Paint Representative and duly witnessed by the Border Force Overseeing Officer.

f. On completion of all underwater work inclusive of the re-application of the anti-fouling coating, the Contractor and the Border Force Overseeing Officer are to conduct a joint inspection and complete documentation in respect of a safe to launch certificate in the form of M&AO SMS: “MSP-10 Annex B: Contractor Launching Certificate”.

g. On approval of the Border Force Overseeing Officer, the Cutter is to be re-launched and moved to the alongside working berth.

- HULL VALVES

| The following valves are to be either replaced, removed, dismantled, cleaned, reassembled and pressure tested (to Lloyds requirements) as appropriate. |  |
| --- | --- |
| - Port and Starboard sea chests (2 x 200mm Butterfly valves); Border Force supply |
| - Bow thruster sea chest (1x 200mm Butterfly valve); Border Force supply |
| - Grey & Black water overboard discharge (1 x 75mm SDNR valve); |
| - Port and Starboard Stabiliser Cooling water overboard discharge (1 x 40mm SDNR valve); |
| - A/C cooling water overboard discharge (1 x 75mm SDNR valve); and |
| - Bow thruster room manual bilge pump overboard discharge (1 x 40mm SDNR valve). |
| - New jointing as appropriate |
| On completion of the pressure tests they are to be re-preserved with International Paints, Interguard 5000. |  |

- GRATINGS

- Remove, thoroughly clean and inspect the gratings to the following sea-chests: - - Port & Starboard Engine Room; and - Bow thruster Space. - Thoroughly clean and inspect the internal structure of the sea chests as detailed in 3.a.i and 3.a.ii. - On completion of inspection and cleaning of the gratings, they are to be re-preserved in accordance with the anti-fouling paint scheme and safely stored until all other hull and hull valve maintenance including anti-fouling painting within the sea-chests has been carried out. - Re-install grating: inclusive of wire locking the fixings, isolating washers and present the re-installed gratings to the Border Force Overseeing Officer prior to launch.

- HULL ANODES

Remove and replace all 27 Sacrificial Anodes: with like for like model anodes

After completion of anti-fouling painting re-install 27 new anodes with new rubber backing sheets. Complete continuity checks to the satisfaction of the Border Force Overseeing Officer.

On completion of installation, present the anodes to the Border Force Overseeing Officer.

- MAIN ENGINE GEARBOX DANFOSS SWITCH

Annual Inspection of Gearboxes by an approved Reintjes Service agent, test and adjust (as necessary) all Danfoss Sensors on both Port and Stbd Reintjes WLS 930 gearboxes.

- MCA LOAD LINE SURVEY

Border Force will arrange for an MCA surveyor to attend HMC Seeker during the docking period before the 5th June, to conduct an underwater hull survey, with the Border Force Overseeing Officer present The contractor is to facilitate all access required to complete the MCA surveyor’s hull survey

7.0 PAINTING OF EXTERNAL DECKS

- The ships decks including upper and Flying Bridge decks are to be washed (Not pressure washed ) off with fresh water to remove  all slime, marine growth and loose flaking paint.

- When clean and dry the contractor, in conjunction with the International Paints representative in attendance, is to carry out a full inspection/survey of the deck areas identifying any indentations or shell plate cracking and recommendations

- A report is to be issued by the contractor/International Paints Representative and duly witnessed by the Border Force Overseeing Officer

- The contractor is to ensure, subject to the above survey approval, that a suitable sound substrate base has been provided for the application of new deck non slid paint in accordance with the paint refurbishment specification detailed below.

- All deck and Helicopter markings are reapplied in accordance with the existing (Red/Yellow) colours and the attached paint refurbishment specification.

- On completion of all the above work, present to the Border Force Overseeing Officer for acceptance.

NB

1. A full paint survey and application report is to be produced, detailing all application temperatures, humidity, wet film thickness, paint types etc..

2. International Paints representative to be present for survey of the existing system and application

3. Paint Specification

- External Decks Overcoating Existing [0m²]

- Surface Preparations International Paints Intershield 851 MOD Type II hard wearing epoxy non-skid deck coating.

- Product Sales Code Coats DFT Microns WFT Microns PSR (m²/lt)

- Overcoating 15 C Min Max Pot Life 15 C Thinner Cleaner Volume lt

- International Intershield 851 ADA172/A FC 400 519 1.73 30hrs ext 7hrs GTA007 GTA220 0.0 400 519

- Scheme Notes: ADD GMA 131 NON-SKID AT UP 200g PER LITRE OF FINISH

Annex B: Vessel Drawings

See separate documents for the General Arrangements and Docking plans. Drawing references: General Arrangements - 549852-000-002, and Docking Plan - 549852-100-050

Annex C: Vessel Details

Length O.A :     42.80m

Breadth o.a. ;     6.95m

Depth mid:         3.77m

Summer Draught : 2.15m (to base)

Displacement : 251.1 tons

Deadweight : 69.3 tons

Gross Tonnage : 235 tons

Built to Lloyds : 100A1 SCC

Annex D: Handover Document

| Name of vessel …………………… |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| This Handover to Supplier Certificate is to be duly signed by a representative of the Authority and the Supplier upon the commencement of the contract for Planned Maintenance & Docking |  |  |  |  |  |
| Immediately upon signing this Handover Certificate by the Supplier, the responsibility and safe custody of HMC Seeker is accepted by the Supplier and the responsibility and safe custody will thereafter remain at all times with the Supplier until completion of the contract and an Acceptance Certificate duly signed by the Authority and the Supplier representative. |  |  |  |  |  |
| Statement of Condition by the Authority |  |  |  |  |  |
| HMC Seeker is in a safe and stable condition. All systems have been shut down, (except those as listed below, commensurate with the systems as required by the Supplier). |  |  |  |  |  |
| Tank Contents |  |  |  |  |  |
| Fuel |  |  | litres |  |  |
| Fresh water |  |  | litres |  |  |
| Black Water Tank |  |  | litres |  |  |
| Systems Still Operational |  |  |  |  |  |

| Signed: …………………………………………. For and on Behalf of the Supplier ……………………………….. | Signed: ……………………………………………… For and on Behalf of the Authority |
| --- | --- |
| Name: …………………………………………. | Name: ……………………………………………… |
| Position / Capacity: …………………………………………. | Position / Capacity ……………………………………………… |

Annex E: Launching Certificate

| Statement of Condition by the Docking Supplier |  |
| --- | --- |
| HMC ………….….. has now completed all underwater work and is in a fit state to be re-launched and we confirm that: - |  |
| 1. | All inlet and outlet valves below the waterline have been closed |
| 2. | All stern gear and steering gear has been correctly re-installed with all locking procedures verified. |
| 3. | All anodes have been verified as to their security of fixing and installation. |
| 4. | All underwater survey and inspection reports have been completed. |
| 5. | All anodes have had a continuity check, to ensure correct contact with the hull |
| 6. | Docking Supplier’s personnel are to be available onboard to check and rectify any water ingress or egress. |
|  | Note: The launching will be stopped upon discovery of water ingress from a source which can not be rectified whilst afloat and re-launching shall be halted or abandoned until rectified to the satisfaction of the Overseeing Officer has been achieved. |
| 7. | The UK Border Force: M&AO Overseeing Officer has conducted a joint pre-launch inspection with the Docking Supplier’s representative |

Signed…………………………………………………………………………..

Position in the Suppliers’s Company…………………………………………..

Print Name …………………………………..     Date……………………………..

Launch Date……………………………………..

Annex F: Seaworthiness Certificate

| We are about to move HMC ……………………. for the programme of sea trials / passage attached. |  |  |  |
| --- | --- | --- | --- |
| We certify that HMC ………………….. is in all respects, fit to undertake the sea trials / passage and in particular, that: - |  |  |  |
| a.) | The: - |  |  |
|  |  | Hull structure; |  |
|  |  | Internal water-tight sub-division; |  |
|  |  | Arrangements for exclusion of water from the interior (eg doors hatches, shaft glands, valves, etc); |  |
|  |  | Plumbing, flooding and draining arrangements; |  |
|  |  | Main and auxiliary machinery; |  |
|  |  | Electrical supply and distribution arrangements; |  |
|  |  | Steering gear; |  |
|  |  | Anchor and cable arrangements; |  |
|  |  | Navigation and communication arrangements; |  |
|  |  | Lighting, ventilation, accommodation and messing arrangements; |  |
|  |  | Fire-detection and fire-fighting arrangements; |  |
|  |  | Life-saving appliances and associated equipment; |  |
|  |  | Guards on moving machinery and other precautions for protection of personnel; and |  |
|  |  | All machinery controls of the Cutter are in a sufficient and satisfactory state of completion and that all specified tests, trials and inspection have so far as is practicable: without the Cutter being under way, been satisfactorily completed. |  |
| b.) | The stability of the Vessel is, and will, throughout the trials/passage be maintained to a normal condition. |  |  |
| c.) | All seamanlike precautions for the seaworthiness and safety of the Vessel have been taken and will be maintained during the trials / passage. |  |  |
| The Master for this sea trial / passage will be: ……………………………………. |  |  |  |
| This SUPPLIERS CERTIFICATE OF SEAWORTHINESS has been submitted by: - |  |  |  |
| Signed: ………………………………………… |  |  | For & On Behalf of Messrs. ………………………………………… |
| Name: ………………………………………… |  |  |  |
| Position: ………………………………………… |  |  |  |

Annex G:  Acceptance Document

| PART 1: to be completed by Supplier |  |  |  |
| --- | --- | --- | --- |
| Vessel Name: HMC Seeker |  |  |  |
| HMC Seeker having completed its Docking & Maintenance by…………………………………………….. to the satisfaction of the Authority and having successfully completed all trials and provided all documentation required under the Authority’s Contract No……….is this day offered for acceptance by the Border Force. |  |  |  |
| Signed: ……………………………………………… |  | For and on Behalf of the Supplier …………………………………………………… |  |
| - Print Name - …………………………………………………. |  | Date: …………………………… |  |
| PART 2: to be completed by The Authority |  |  |  |
| By Vessel Commander: |  |  |  |
| I attended basin and sea trials of HMC Vigilant and have satisfied myself that all systems, machinery and equipment are working satisfactorily. I have inspected the Cutter and consider she is in a condition suitable for return to operational service. Outstanding items are noted as attached. |  |  |  |
| Signed: …………………………………………… |  | Print Name / Post …………………………………………………… |  |
| By Border Force Overseeing Officer: HMC Vigilant having completed its Planned Maintenance & LSA to the satisfaction of the Authority and having completed all trials and documentation required under the Contract is hereby accepted at ..…......... hours. |  |  |  |
| Signed: …………………………………………… |  | Border Force Overseeing Officer |  |
| Print Name: …………………………………………... |  | Date: ……………………………. |  |
| Last Emergent Work Authorisation Issued was: |  |  | EM ………….. |
| Outstanding Items |  |  |  |
| Any outstanding items are to be noted, appended to this form and signed by both the Supplier and the Authority. Dates when these outstanding items are to be “completed by” are to be agreed and shown. |  |  |  |
| Distribution ## Original - Retained by the Supplier Copies to - Border Force Overseeing Officer; and Cutter Chief Engineer (for Ships Book). |  |  |  |

ANNEX H: Reimbursible Expenses

The Supplier may claim the following Reimbursable Expenses at the rates set out below:

1.  Travel

Standard rate of allowance for private cars

Initial 10,000 miles						40p per mile

Additional miles over the initial 10,000				25p per mile

Public transport rate 						23.8p per mile

2. Hotel rates

London 							£125 per night

All other locations other than London 				£90 per night

Annex I – Cathodic Protection

Please refer to technical drawings provided. Drawing reference 549852-163-001