Annex 1 to Framework Schedule 1 (Framework Implementation Plan and Framework Testing)

PART A - Implementation

- Agreeing and following the Framework Implementation Plan

A draft of the Framework Implementation Plan is set out in Appendix 1 to Part A of this Annex.  The Supplier shall provide CCS with a further updated draft Framework Implementation Plan no later than twenty (20) days after the Framework Contract Start Date.

The draft Framework Implementation Plan:

must contain information at the level of detail necessary to manage the Framework Contract implementation stage effectively and as CCS may otherwise require; and

it shall take account of all dependencies known to, or which should reasonably be known to, the Supplier and in particular with those arising from the Migration Approach at Appendix 2 hereto.

Following receipt of the draft Framework Implementation Plan from the Supplier, the Parties shall use reasonable endeavours to agree the contents of the Framework Implementation Plan.  If the Parties are unable to agree the contents of the Framework Implementation Plan within twenty (20) Working Days of its submission, then such Dispute shall be resolved in accordance with the Dispute Resolution Procedure.

The Supplier shall carry out each activity identified in the Framework Implementation Plan by the date assigned to completion of that activity in the Framework Implementation Plan so as to ensure that each Framework Milestone identified in the Framework Implementation Plan is achieved on or before its Framework Milestone Date.

The Supplier shall monitor its performance against the Framework Implementation Plan and Framework Milestones (if any) and report to CCS on such performance.

- Reviewing and changing the Framework Implementation Plan

Subject to Paragraph ‎3.3, the Supplier shall keep the Framework Implementation Plan under review in accordance with CCS’ instructions and ensure that it is updated on a regular basis.

CCS shall have the right to require the Supplier to include any reasonable changes or provisions in each version of the Framework Implementation Plan.

Changes to any Framework Milestones shall only be made in accordance with the Variation Procedure.

Where the Supplier is responsible for the failure to achieve a Framework Milestone by the relevant Framework Milestone Date this shall constitute a material Default.

- Security requirements before the Start Date

The Supplier shall note that it is incumbent upon them to understand the lead-in period for security clearances and ensure that all Supplier Staff have the necessary security clearance in place before the Framework Contract Start Date. The Supplier shall ensure that this is reflected in their Framework Implementation Plan.

The Supplier shall ensure that all Supplier Staff and Subcontractors do not access CCS or Buyer or End Customer systems, or any IT systems linked to the CCS or Buyers or End Customers, unless they have satisfied CCS’ security requirements.

The Supplier shall be responsible for providing all necessary information to CCS to facilitate security clearances for Supplier Staff and Subcontractors in accordance with the Buyer's and End Customer’s requirements.

The Supplier shall ensure that all Supplier Staff and Subcontractors requiring access to CCS Premises have the appropriate security clearance. It is the Supplier's responsibility to establish whether or not the level of clearance will be sufficient for access. Unless prior approval has been received from CCS, the Supplier shall be responsible for meeting the costs associated with the provision of security cleared escort services.

If a property requires Supplier Staff or Subcontractors to be accompanied by CCS’ Authorised Representative, CCS must be given reasonable written notice of such a requirement, except in the case of emergency access.

- What to do if there is a Delay

If the Supplier becomes aware that there is, or there is reasonably likely to be, a Delay it shall:

notify CCS as soon as practically possible and no later than within two (2) Working Days from becoming aware of the Delay or anticipated Delay;

include in its notification an explanation of the actual or anticipated impact of the Delay;

comply with CCS’ instructions in order to address the impact of the Delay or anticipated Delay; and

use all reasonable endeavours to eliminate or mitigate the consequences of any Delay or anticipated Delay.

- PART A Appendix 1: Framework Implementation Plan

- The Framework Implementation Plan is set out below and the Framework Milestones to be achieved are identified below:

| Framework Milestone | Activities & Outputs | Duration | Framework Milestone Date | CCS Responsibilities |
| --- | --- | --- | --- | --- |
| [ ] | [ ] | [ ] | [ ] | [ ] |

- PART A: APPENDIX 2 MIGRATION APPROACH

PSN Core Services Migration requirements

Support is required from the legacy GCF Core Service provider, Vodafone (the exiting supplier), the new PSN DNS Supplier and the new PSN Email Relay Supplier to execute migrations, as described below, to replace GCF legacy DNS and Email Relay services with Supplier Deliverables.

## Migration phases

Vodafone and the new PSN DNS Supplier must support the phasing of the migration of DNS in the following order:

- technical migration phase

- customer migration phase

- final close-down

Vodafone and the new PSN Email Relay Supplier must support the phasing of the migration of Email Relay in the following order:

- customer pre-migration phase

- technical migration phase

- final close-down

### Technical migration

Technical migration is actioned by Vodafone and the new suppliers. The actions that occur shall impact all customers simultaneously, and so will be governed by a Change Advisory Board.

During the technical migration phases, each step will be supported by a change management process, overseen by a Change Advisory Board (CAB). The CAB will be chaired by CCS and supported by the Government Digital Services (GDS). Vodafone, the new PSN DNS Supplier and the new PSN Email Relay Supplier must attend the CAB. The CAB will also include representatives from organisations that depend on the DNS or Email Relay service for large citizen-facing services. All customer representatives on the CAB can, subject to CCS agreement, exercise a veto (supported by a disclosed business justification) to minimise the risk of a change materially impacting citizen-facing services.

### Customer migration/ pre-migration

Customer migration, or customer pre-migration is a phase where each customer is expected to make a configuration change to their own systems. The changes required are simple, and will take each customer less than a day. Customers do not need to schedule their changes with Vodafone or the new suppliers. Customers are, however, required to make their changes within a published time window of a number of weeks in order to maintain service.

### Final close down

Final close down is the point after all technical migration is complete, and after the customer migration/ pre-migration windows are closed, where customers who have not done their changes are in danger of losing service because the Vodafone service will soon be switched off. It may be technically possible for some customers to be redirected to the new service by Vodafone and/or the new suppliers, but this cannot be guaranteed.

# DNS data quality and regression

Vodafone and GDS have spent a number of months cleansing and improving the quality of the GCF DNS data to make it suitable for transfer to a new service. Vodafone must ensure that the data on the GCF DNS does not regress. Hence Vodafone must:

- Ensure that all GCF Change Requests meet the New guidance on GCF DNS Change Requests

- Ensure that all GCF Change Requests are passed to the PSN Service Desk for review against this guidance.

# Working together

Vodafone must provide the necessary configuration data and documentation in order for the new suppliers to replicate current functionality. For the Email Relay, this might include mail re-writes, static mail routes, etc. For the DNS this might include support for conditional forwarders.

Vodafone and the new PSN DNS Supplier must work together to create an integrated DNS migration plan, containing all necessary configurations and steps, to be agreed with CCS.

Vodafone and the new PSN Email Relay Supplier must work together to create an integrated Email Relay migration plan, containing all necessary configurations and steps, to be agreed with CCS.

Vodafone must provide the new PSN DNS Supplier with the following DNS volumetrics and performance information. For each hour in a 24 hour period (averaged over a typical month), aggregated across all PSN and legacy networks:

- Hourly average number of queries

- Peak number of queries per second

- Rough ratio of inbound queries to recursed queries

Vodafone must provide a reasonable proxy measure for the volume of DNS queries hitting the internet-facing DNS, with any appropriate caveats.

Vodafone must provide the new PSN Email Relay Supplier with the following Email Relay volumetrics and performance information. For each hour in a 24 hour period (averaged over a typical month), aggregated across all PSN and legacy networks:

- Hourly average number of emails

- Peak arrival rate, emails per minute

- Average processing time (between email receipt and sending to the next hop)

- Peak (longest) processing time

- Average email size

# DNS migration

Technical migration

A key rationale for this approach is that there is always only one authoritative set of DNS data on the PSN and another authoritative set of DNS data on the internet.  A key principle is that, during the migration, Vodafone must configure its systems to use these authoritative data sets, so that customers always have a consistent experience, before and after migration from Vodafone to the new PSN DNS Supplier.

Technical migration consists of the following steps

- Vodafone must provide the necessary clean authoritative DNS data for the new internet-facing DNS nameserver.

- The new PSN DNS Supplier must load this data onto its internet-facing DNS nameserver.

- Vodafone and the new PSN DNS Supplier must together test the data for live use.

- The new PSN DNS Supplier must perform testing with CCS invited customers.

- GDS switches Joint Information Systems Committee (JISC) records, causing the internet-facing DNS nameserver to become authoritative. Hence Vodafone and all internet users use this new service.

- Vodafone must provide the necessary clean authoritative DNS data for the PSN-facing DNS services.

- The new PSN DNS Supplier must load this data onto the PSN-facing DNS Nameserver.

- Vodafone and the new PSN DNS Supplier must together test the data for live use, as per Vodafone’s agreed DNS Test Plan.

- The new PSN DNS Supplier must perform testing with CCS invited customers.

- Vodafone must point its DNS services to the new PSN DNS Supplier’s PSN-facing DNS Nameserver as the authority.

The CAB will confirm whether the new PSN DNS service is operational, tested and configured for use, and when and whether any changes to live systems can proceed.

### Customer migration

During customer migration, customers are asked to configure their PSN-facing systems to point to the new PSN-facing DNS service, and are given a period to do so.

The new PSN DNS Supplier must provide customers with the necessary information for customers to execute their migrations.

CCS will engage with customers to execute their migrations. Customers who do not switch will be warned that their service will cease when technical migration takes place.

Customers who are still on legacy networks, such as Government Secure Internet (GSI), may not be able to reach the new service directly. They may be required to migrate to PSN.

### Final close-down

Vodafone and the new PSN DNS Supplier, supported by CCS, must engage with any remaining customers with notification that the legacy service has ceased.

Vodafone decommissions the legacy service. Any customers who have not switched will lose service.

# Email migration

### Customer pre-migration

The pre-migration approach removes customer activity from the critical path. All customers will be asked to pre-migrate to an Email Relay with a new name and IP range. Vodafone must point these new names to existing legacy GCF services until the replacement Email Relay service is operational. This pre-migration allows customers to do the work they need to do well in advance, so that the actual migration to the new Email Relay involves a single switchover (for all customers together) executed by Vodafone and the new PSN Email Relay Supplier.

Vodafone must choose which of its legacy Email Relay services is reached when a customer uses the new names and IP addresses. Vodafone must:

- configure the existing service to accept and route email destined for the new DNS name and IP address range while maintaining existing security and performance.

- configure Symantec.cloud to route traffic correctly.

- ensure that the platform continues to support the guidance Securing government email.

- amend any relevant customer support processes.

In addition to removing customer activity from the critical path, pre-migration also allows customers to move away from using IP addresses in use by Vodafone that are not easily portable to new services, and it also allows government to track actual customer commitments to using the new services.

The steps in the customer pre-migration phase are:

- CCS registers and provides the name of the new Email Relay service. GDS provides the necessary IP addresses. CCS, or its nominated representative, procures the necessary certificates.

- Vodafone must set up the new name and IP range to point to one of its existing Email Relay services. Vodafone must make the necessary adjustments to its customer support processes, scales the chosen service and configures the certificates to enable Transport Layer Security (“TLS”) connections (https://www.gov.uk/government/publications/email-security-standards/transport-layer-security-tls ).

- Vodafone must create the necessary information for customers to execute their pre-migrations.

- CCS engages with customers to execute their pre-migrations. Customers who do not switch will be warned that their service will cease when technical migration takes place.

### Technical migration

Technical migration refers to the architectural reconfigurations of major components required to facilitate migration of customers off the GCF service.

At the beginning of technical migration, Vodafone must give the new Supplier the data needed for the new service provider to operate an equivalent service.

Vodafone and the new PSN Email Relay Supplier must work together to ensure that customers always have a consistent experience, before and after migration from Vodafone to the new PSN Email Relay Supplier.

Migration will be executed by GDS providing a suitable IP range, and this range will be split into two equal subnets. One subnet must be used by Vodafone, the other must be used by the new PSN Email Relay Supplier. Customers will be required to allow inbound and outbound email across the whole range.

Switchover will be affected by the current DNS provider switching the Smart Host names from the Vodafone mail servers to the new PSN Email Relay Supplier’s mail servers. If Vodafone is running the DNS at this stage, Vodafone must execute this switch. If the new PSN DNS Supplier is running the DNS at this stage, the new PSN DNS Supplier must execute this switch.

Technical migration consists of the steps below.

- Vodafone must provide the necessary configuration data.

- The new PSN Email Relay Supplier must configure the Email Relay in accordance with the configuration data.

- Vodafone and the new PSN Email Relay Supplier must together test the data for live use, as per Vodafone’s agreed Email Relay Test Plan.

- The new PSN Email Relay Supplier must perform testing with invited customers.

The CAB will confirm whether the new PSN Email service is operational, tested and configured for use, and when and whether any changes to live systems can proceed.

During a short change window, which is likely to be around two hours for execution, fault finding and rollback time.

- The new PSN Email Relay Supplier must make the new PSN Email Relay service reachable.

- The current DNS provider (which may be Vodafone or the new PSN DNS Supplier) must redirect the Smart Host name to point to the new Email Relay.

## Final close-down

Vodafone and the new PSN Email Relay Supplier, supported by CCS, must engage with any remaining customers with notification that the legacy service has ceased, and they must complete their customer migration.

Vodafone decommissions the legacy service. Any customers who have not switched will lose service.

- Part B: Framework Testing

- Definitions

In this Part B, the following words shall have the following meanings and they shall supplement Joint Schedule 1 (Definitions):

| "Component" | - any constituent parts of the Test Items; |
| --- | --- |
| "Confirmation Certificate" | - a certificate materially in the form of the document contained in Annex 2 of Part B of this Schedule issued by CCS when a Test Item and/or Framework Milestone has satisfied its relevant Framework Test Success Criteria; |
| "Framework Test Issue Management Log" | - a log for the recording of Framework Test Issues as described further in Paragraph ‎8.1 of Part B of this Annex; |
| "Framework Test Issue Threshold" | - in relation to the Framework Tests applicable to a Framework Milestone, a maximum number of Severity Level 3, Severity Level 4 and Severity Level 5 Framework Test Issues as set out in the relevant Framework Test Plan; |
| "Framework Test Reports" | - the reports to be produced by the Supplier setting out the results of Framework Tests; |
| "Framework Test Specification" | - the specification that sets out how Framework Tests will demonstrate that the Framework Test Success Criteria have been satisfied, as described in more detail in Paragraph 6.2 of Part B of this Annex; |
| “Framework Test Strategy” | - a strategy for the conduct of Framework Testing as described further in Paragraph ‎3.2 of Part B of this Annex; |
| “Framework Test Success Criteria” | - in relation to a Framework Test, the Framework Test success criteria for that Framework Test as referred to in Paragraph ‎5 of Part B of this Annex; |
| “Framework Test Witness” | - any person appointed by CCS pursuant to Paragraph ‎9 of Part B of this Annex; |
| “Framework Testing Procedures” | - the applicable Framework Testing procedures and Framework Test Success Criteria set out in Part B to this Annex. |
| "Material Framework Test Issue" | - a Framework Test Issue of Severity Level 1 or Severity Level 2; |
| "Severity Level" | - the level of severity of a Framework Test Issue, the criteria for which are described in Annex 1 of Part B of this Annex; and |
| Test Item | - an entity to be delivered and/or implemented by the Supplier and subject to defined Framework Testing Procedures. |

- How Framework Testing should work

All Framework Tests conducted by the Supplier shall be conducted in accordance with the Framework Test Strategy, Framework Test Specification and the Framework Test Plan.

The Supplier shall not submit any Test Item for Framework Testing:

unless the Supplier is reasonably confident that it will satisfy the relevant Framework Test Success Criteria;

until CCS has issued a Confirmation Certificate in respect of any prior, dependant Test Item(s); and

until the Parties have agreed the Framework Test Plan and the Framework Test Specification relating to the relevant Test Item(s).

The Supplier shall use reasonable endeavours to submit each Test Item for Framework Testing or re-Framework Testing by or before the date set out in the Framework Implementation Plan for the commencement of Framework Testing in respect of the relevant Test Item.

Prior to the issue of a Confirmation Certificate, CCS shall be entitled to review the relevant Framework Test Reports and the Framework Test Issue Management Log.

- Planning for Framework Testing

The Supplier shall develop the final Framework Test Strategy as soon as practicable after the Start Date but in any case no later than twenty (20) Working Days after the Start Date.

The final Framework Test Strategy shall include:

an overview of how Framework Testing will be conducted in relation to the Framework Implementation Plan;

the process to be used to capture and record Framework Test results and the categorisation of Framework Test Issues;

the procedure to be followed should a Test Item fail a Framework Test, fail to satisfy the Framework Test Success Criteria or where the Framework Testing of a Test Item produces unexpected results, including a procedure for the resolution of Framework Test Issues;

the procedure to be followed to sign off each Framework Test;

the process for the production and maintenance of Framework Test Reports and a sample plan for the resolution of Framework Test Issues;

the names and contact details of the CCS and Supplier’s Framework Test representatives;

a high level identification of the resources required for Framework Testing including CCS and/or third party involvement in the conduct of the Framework Tests;

the technical environments required to support the Framework Tests; and

the procedure for managing the configuration of the Framework Test environments.

- Preparing for Framework Testing

The Supplier shall develop Framework Test Plans and submit these for Approval as soon as practicable but in any case no later than twenty (20) Working Days prior to the start date for the relevant Framework Testing as specified in the Framework Implementation Plan.

Each Framework Test Plan shall include as a minimum:

the relevant Framework Test definition and the purpose of the Framework Test, the Framework Milestone to which it relates, the requirements being tested and, for each Framework Test, the specific Framework Test Success Criteria to be satisfied; and

a detailed procedure for the Framework Tests to be carried out.

CCS shall not unreasonably withhold or delay its approval of the Framework Test Plan provided that the Supplier shall implement any reasonable requirements of CCS in the Framework Test Plan.

- Passing Framework Testing

The Framework Test Success Criteria for all Framework Tests shall be agreed between the Parties as part of the relevant Framework Test Plan pursuant to Paragraph ‎4.

- How Framework Test Items will be tested

Following approval of a Framework Test Plan, the Supplier shall develop the Framework Test Specification for the relevant Test Items as soon as reasonably practicable and in any event at least ten (10) Working Days prior to the start of the relevant Framework Testing (as specified in the Framework Implementation Plan).

Each Framework Test Specification shall include as a minimum:

the specification of the Framework Test data, including its source, scope, volume and management, a request (if applicable) for relevant Framework Test data to be provided by CCS and the extent to which it is equivalent to live operational data;

a plan to make the resources available for Framework Testing;

Framework Test scripts;

Framework Test pre-requisites and the mechanism for measuring them; and

expected Framework Test results, including:

a mechanism to be used to capture and record Framework Test results; and

a method to process the Framework Test results to establish their content.

- Performing the Framework Tests

Before submitting any Test Items for Framework Testing the Supplier shall subject the relevant Test Items to its own internal quality control measures.

The Supplier shall manage the progress of Framework Testing in accordance with the relevant Framework Test Plan and shall carry out the Framework Tests in accordance with the relevant Framework Test Specification. Framework Tests may be witnessed by the Framework Test Witnesses in accordance with Paragraph ‎9.3.

The Supplier shall notify CCS at least ten (10) Working Days in advance of the date, time and location of the relevant Framework Tests and CCS shall ensure that the Framework Test Witnesses attend the Framework Tests.

CCS may raise and close Framework Test Issues during the Framework Test witnessing process.

The Supplier shall provide to CCS in relation to each Framework Test:

a draft Framework Test Report not less than two (2) Working Days prior to the date on which the Framework Test is planned to end; and

the final Framework Test Report within five (5) Working Days of completion of Framework Testing.

Each Framework Test Report shall provide a full report on the Framework Testing conducted in respect of the relevant Test Items, including:

an overview of the Framework Testing conducted;

identification of the relevant Framework Test Success Criteria that have/have not been satisfied together with the Supplier’s explanation of why any criteria have not been met;

the Framework Tests that were not completed together with the Supplier’s explanation of why those Framework Tests were not completed;

the Framework Test Success Criteria that were satisfied, not satisfied or which were not Framework Tested, and any other relevant categories, in each case grouped by Severity Level in accordance with Paragraph ‎8.1; and

the specification for any hardware and software used throughout Framework Testing and any changes that were applied to that hardware and/or software during Framework Testing.

When the Supplier has completed a Framework Milestone it shall submit any Test Items relating to that Framework Milestone for Framework Testing.

Each party shall bear its own costs in respect of the Framework Testing.  However, if a Framework Milestone is not achieved CCS shall be entitled to recover from the Supplier, any reasonable additional costs it may incur as a direct result of further review or re-Framework Testing of a Framework Milestone.

If the Supplier successfully completes the requisite Framework Tests, CCS shall issue a Confirmation Certificate as soon as reasonably practical following such successful completion.  Notwithstanding the issuing of any Confirmation Certificate, the Supplier shall remain solely responsible for ensuring that the Test Items are implemented in accordance with this Framework Contract.

- Discovering Problems

Where a Framework Test Report identifies a Framework Test Issue, the Parties shall agree the classification of the Framework Test Issue using the criteria specified in Annex 1 and the Framework Test Issue Management Log maintained by the Supplier shall log Framework Test Issues reflecting the Severity Level allocated to each Framework Test Issue.

The Supplier shall be responsible for maintaining the Framework Test Issue Management Log and for ensuring that its contents accurately represent the current status of each Framework Test Issue at all relevant times.  The Supplier shall make the Framework Test Issue Management Log available to CCS upon request.

CCS shall confirm the classification of any Framework Test Issue unresolved at the end of a Framework Test in consultation with the Supplier.  If the Parties are unable to agree the classification of any unresolved Framework Test Issue, the Dispute shall be dealt with in accordance with the Dispute Resolution Procedure.

- Framework Test witnessing

CCS may, in its sole discretion, require the attendance at any Framework Test of one or more Framework Test Witnesses selected by CCS, each of whom shall have appropriate skills to fulfil the role of a Framework Test Witness.

The Supplier shall give the Framework Test Witnesses access to any documentation and Framework Testing environments reasonably necessary and requested by the Framework Test Witnesses to perform their role as a Framework Test Witness in respect of the relevant Framework Tests.

The Framework Test Witnesses:

shall actively review the Framework Test documentation;

will attend and engage in the performance of the Framework Tests on behalf of CCS so as to enable CCS to gain an informed view of whether a Framework Test Issue may be closed or whether the relevant element of the Framework Test should be re-tested;

shall not be involved in the execution of any Framework Test;

shall be required to verify that the Supplier conducted the Framework Tests in accordance with the Framework Test Success Criteria and the relevant Framework Test Plan and Framework Test Specification;

may produce and deliver their own, independent reports on Framework Testing, which may be used by CCS to assess whether the Framework Tests have been Achieved;

may raise Framework Test Issues on the Framework Test Issue Management Log in respect of any Framework Testing; and

may require the Supplier to demonstrate the modifications made to any defective Test Item before a Framework Test Issue is closed.

- Auditing the quality of the Framework Test

CCS or an agent or contractor appointed by CCS may perform on-going quality audits in respect of any part of the Framework Testing (each a “Framework Testing Quality Audit”).

The Supplier shall allow sufficient time in the Framework Test Plan to ensure that adequate responses to a Framework Testing Quality Audit can be provided.

CCS will give the Supplier at least five (5) Working Days’ written notice of CCS’ intention to undertake a Framework Testing Quality Audit.

The Supplier shall provide all reasonable necessary assistance and access to all relevant documentation required by CCS to enable it to carry out the Framework Testing Quality Audit.

If the Framework Testing Quality Audit gives CCS concern in respect of the Framework Testing Procedures or any Framework Test, CCS shall prepare a written report for the Supplier detailing its concerns and the Supplier shall, within a reasonable timeframe, respond in writing to the report.

In the event of an inadequate response to the written report from the Supplier, CCS (acting reasonably) may withhold a Confirmation Certificate until the issues in the report have been addressed to the reasonable satisfaction of CCS.

- Outcome of the Framework Testing

CCS will issue a Confirmation Certificate when the Test Items satisfy the Framework Test Success Criteria in respect of that Framework Test without any Framework Test Issues.

If the Test Items (or any relevant part) do not satisfy the Framework Test Success Criteria then CCS shall notify the Supplier and:

CCS may issue a Confirmation Certificate conditional upon the remediation of the Framework Test Issues;

CCS may extend the Framework Test Plan by such reasonable period or periods as the Parties may reasonably agree and require the Supplier to rectify the cause of the Framework Test Issue and re-submit the Test Items (or the relevant part) to Framework Testing; or

where the failure to satisfy the Framework Test Success Criteria results, or is likely to result, in the failure (in whole or in part) by the Supplier to meet a Framework Milestone, then without prejudice to CCS’ other rights and remedies, such failure shall constitute a material Default.

CCS shall be entitled, without prejudice to any other rights and remedies that it has under this Contract, to recover from the Supplier any reasonable additional costs it may incur as a direct result of further review or re-testing which is required for the Framework Test Success Criteria for that Test Item to be satisfied.

CCS shall issue a Confirmation Certificate in respect of a given Framework Milestone as soon as is reasonably practicable following:

the issuing by CCS of Confirmation Certificates and/or conditional Confirmation Certificates in respect of all Test Items related to that Framework Milestone which are due to be Framework Tested; and

performance by the Supplier to the reasonable satisfaction of CCS of any other tasks identified in the Implementation Plan as associated with that Framework Milestone.

If a Framework Milestone is not Achieved, CCS shall promptly issue a report to the Supplier setting out the applicable Framework Test Issues any other reasons for the relevant Framework Milestone not being Achieved.

If there are Framework Test Issues but these do not exceed the Framework Test Issues Threshold, then provided there are no Material Framework Test Issues, CCS shall issue a Confirmation Certificate.

If there is one or more Material Framework Test Issue(s), CCS shall refuse to issue a Confirmation Certificate and, without prejudice to CCS’ other rights and remedies, such failure shall constitute a material Default.

If there are Framework Test Issues which exceed the Framework Test Issues Threshold but there are no Material Framework Test Issues, CCS may at its discretion (without waiving any rights in relation to the other options) choose to issue a Confirmation Certificate conditional on the remediation of the Framework Test Issues in accordance with an agreed Rectification Plan provided that:

any Rectification Plan shall be agreed before the issue of a conditional Confirmation Certificate unless CCS agrees otherwise (in which case the Supplier shall submit a Rectification Plan for approval by CCS within ten (10) Working Days of receipt of CCS’ report pursuant to Paragraph ‎10.5); and

where CCS issues a conditional Confirmation Certificate, it may (but shall not be obliged to) revise the failed Framework Milestone Date and any subsequent Milestone Date.

- Risk

The issue of a Confirmation Certificate and/or a conditional Confirmation Certificate shall not:

operate to transfer any risk that the relevant Test Item or Framework Milestone is complete or will meet and/or satisfy CCS’ requirements for that Test Item or Framework Milestone; or

affect CCS’ right subsequently to reject all or any element of the Test Items and/or any Framework Milestone to which a Confirmation Certificate relates.

PART B Appendix 1: Framework Test Issues – Severity Levels

- Severity 1 Error

This is an error that causes non-recoverable conditions, e.g. it is not possible to continue using a Component.

- Severity 2 Error

This is an error for which, as reasonably determined by CCS, there is no practicable workaround available, and which:

causes a Component to become unusable;

causes a lack of functionality, or unexpected functionality, that has an impact on the current Framework Test; or

has an adverse impact on any other Component(s) or any other area of the Test Items;

- Severity 3 Error

This is an error which:

causes a Component to become unusable;

causes a lack of functionality, or unexpected functionality, but which does not impact on the current Framework Test; or

has an impact on any other Component(s) or any other area of the Test Items;

but for which, as reasonably determined by CCS, there is a practicable workaround available;

- Severity 4 Error

This is an error which causes incorrect functionality of a Component or process, but for which there is a simple, Component based, workaround, and which has no impact on the current Framework Test, or other areas of the Test Items; and

- Severity 5 Error

This is an error that causes a minor problem, for which no workaround is required, and which has no impact on the current Framework Test, or other areas of the Test Items.

PART B Appendix 2: Confirmation Certificate

To:		[insert name of Supplier]

From:		Crown Commercial Service

[insert Date dd/mm/yyyy]

Dear Sirs,

Confirmation Certificate

Test Item/Framework Milestone(s): [insert relevant description of the agreed Test Items/Framework Milestones].

We refer to the agreement ("Framework Contract") Contract reference number RM6167 between Crown Commercial Service ("CCS") and [insert Supplier name] ("Supplier") dated [insert Framework Contract  Start Date dd/mm/yyyy].

The definitions for any capitalised terms in this certificate are as set out in the Framework Contract.

[We confirm that all the Test Items relating to [insert relevant description of Test Items/agreed Framework Milestones and/or reference number(s) from the Framework Implementation Plan] have been Framework Tested successfully in accordance with the Framework Test Plan [or that a conditional Confirmation Certificate has been issued in respect of those Test Items that have not satisfied the relevant Framework Test Success Criteria].

[OR]

[This Confirmation Certificate is granted on the condition that any Framework Test Issues are remedied in accordance with the Rectification Plan attached to this certificate.]

Yours faithfully

[insert Name]

[insert Position]

acting on behalf of CCS