## Section 3
CROSBY COB - ACTIVITY SCHEDULE
Item No. | Item | Notes | Cost (£)
1 | SCOPE OF THE WORKS
1.1 | The works comprise the following: - Demolition of the existing internal walls within the Quarantine Building - Internal fit out of the existing Quarantine Building to form a new Coastal Store - Internal fit out of the existing Generator Building to form a new Drying Room
2 | PREAMBLES
2.1 | STANDARDS OF PRODUCTS AND EXECUTIONS
2.1.1 | WORKMANSHIP SKILLS • Operatives: Appropriately skilled and experienced for the type of work. • Registration: With Construction Skills Certification Scheme. • Evidence: Operatives must produce evidence of skills/ qualifications when requested.
2.1.2 | QUALITY OF PRODUCTS • Generally: New (Proposals for recycled may be considered). • Supply of each product: From the same source or manufacturer. • Whole quantity of each product required to complete the works: Consistent kind, size, quality and overall appearance. • Tolerances: Where critical, measure a sufficient quantity to determine compliance. • Deterioration: Prevent. Order in suitable quantities to a programme and use in appropriate sequence.
2.1.3 | QUALITY OF EXECUTION • Generally: Fix, apply install or lay products securely, accurately, plumb, neatly and in alignment. • Colour batching: Do not use different colour batches where they can be seen together. • Dimensions: Check on-site dimensions. • Finished work: Without defects, e.g. not damaged, disfigured, dirty, faulty, or out of tolerance. • Location and fixing of products: Adjust joints open to view so they are even and regular.
2.1.4 | MANUFACTURER’S RECOMMENDATIONS/ INSTRUCTIONS • General: Comply with manufacturer’s printed recommendations and instructions current on the date of the invitation to tender. • Changes to recommendations or instructions: Submit details. • Ancillary products and accessories: Use those supplied or recommended by main product manufacturer. • Agreement certified products: Comply with limitations, recommendations and requirements of relevant valid certificates.
2.1.5 | MAKING GOOD DEFECTS • Remedial work: Arrange access with Project Manager. • Rectification: Give reasonable notice for access to the various parts of the works. • Completion: Notify when remedial works have been completed.
2.2 | SECURITY, HEALTH AND SAFETY
2.2.1 | EXECUTION HAZARDS • Common hazards: Not listed. Control by good management and site practice. • Significant Hazards: The design of the project includes the following: • Hazard: Excavation of existing drainage • Precautions assumed: Screening to be provided • Specification reference: N/A • Drawing reference: N/A
2.2.2 | SECURITY • Protection: Safeguard the site, the Works, products, materials, and any existing buildings affected by the Works from damage and theft. • Access: Take all reasonable precautions to prevent unauthorised access to the site, the Works and adjoining property. • Special requirements: Secure scaffolding to prevent unauthorised access to the building(s).
2.3 | PROTECT AGAINST THE FOLLOWING
2.3.1 | NUISANCE • Duty: Prevent nuisance from smoke, dust, rubbish, vermin and other causes. • Surface water: Prevent hazardous build-up on site, in excavations and to surrounding areas and roads.
2.3.2 | ASBESTOS CONTAINING MATERIALS • Duty: Report immediately any suspected materials discovered during the execution of the Works. • Do not disturb. • Agree methods for safe removal or encapsulation.
2.3.4 | DANGEROUS OR HAZARDOUS SUBSTANCES • Duty: Report immediately any suspected materials discovered during the execution of the Works. • Do not disturb. • Agree methods for safe removal or encapsulation.
2.3.5 | FIRE PREVENTION • Duty: Prevent personal injury or death, and damage to the Works or other property from fire. • Standard: Comply with Joint Code of Practice ‘Fire Prevention on Construction Sites’ published by the Construction Confederation and The Fire Protection Association (The ‘Joint Fire Code’).
2.3.6 | SMOKING ON SITE • Smoking on site not permitted.
2.3.7 | BURNING ON SITE • Burning on site not permitted.
2.3.8 | INFECTED TIMBER/ CONTAMINATED MATERIALS • Removal: Where instructed to remove material affected by fungal/ insect attack from the building, minimise the risk of infecting other parts of the building. • Testing: Carry out and keep records of appropriate tests to demonstrate the hazards presented by concentrations of airborne particles, toxins and other micro organisms are within acceptable levels.
2.3.9 | WASTE • Includes: Rubbish, debris, spoil, containers and surplus material. • Minimise: Keep the site and Works clean and tidy. • Remove; Frequently and dispose off site in a safe and competent manner: • Non hazardous material: In a manner approved by the Waste Regulation Authority. • Hazardous Material: As directed by the Waste Regulation Authority and in accordance with relevant regulations. • Voids and cavities in the construction: Remove rubbish, dirt and residues before closing in. • Waste transfer documentation: Retain on site.
2.4 | PROVISIONAL WORK/ ITEMS
2.4.1 | PROVISIONAL ITEMS AND QUANTITIES • All Provisional Items and Quantities are to be expended at the discretion of the Project Manager and Client. • No works are to be undertaken without prior written consent from the Project Manager. The contractor proceeds at their own risk when undertaking works without a written instruction.
2.4.2 | CONTINGENCIES • All Contingencies are to be expended at the discretion of the Project Manager and Client. • No works are to be undertaken without prior written consent from the Project Manager. The contractor proceeds at their own risk when undertaking works without a written instruction.
3 | GENERALLY (EXTRACTED FROM PRELIMS AND PREAMBLES)
QUALITY OF DESIGN AND WORKMANSHIP
3.1 | All mechanical and electrical items specified herein are to be reviewed, designed and installed by a suitably qualified electrical and gas engineer as appropriate (NICEIC and GasSafe respectively).
3.2 | All works should be completed to a high standard, fit for purpose and in accordance with the preambles, current British Standards, industry best practice and relevant Regulations for each work element.
CONTRACT
3.3 | The works will be undertaken in accordance with the NEC3 Engineering and Construction Short Form of Contract.
GENERAL SPECIFICATION
3.4 | All items referenced within the specification are to include all sundry items required to fully complete their installation.
3.5 | All disturbed surfaces must be made good.
3.6 | All waste / arisings from the works are to be disposed of by the contractor in accordance with relevant regulations.
HEALTH AND SAFETY
3.7 | The works will be undertaken under the full remit of the CDM Regulations 2015. At this stage we do not anticipate that the project will be notifiable.
3.8 | Contractor Extra Over (E/O) cost for acting as Principal Contractor under CDM regulations 2015, if needed. Should another contractor be working on site, contractor is required to notify project manager and provide copy of the pre construction information, health and safety plan and construction phase plan prior to the works commencing. | EO
3.9 | The Designers Risk Assessment for this contract is contained in Appendix 2 and you are required to have regard to this when pricing and undertaking the works.
SITE ACCESS RESTRICTIONS
3.1 | Contractor to park in designated contractor compound, taking in to account parking restrictions across the site. Specifically, the Contractor is not to park to the front of the garage door. Plan to be provided once parking arrangement has been agreed with MCA.
3.11 | Contractor is not to use welfare facilities throughout the duration of the works. MCA to confirm arrangement, contractor to provide there own welfare facilities.
3.12 | The site incorporates a fully operational emergency service building and at all times access will need to be maintained for the coastguard and their vehicles - you contractor to liaise directly with MCA to coordinate your access into the building. Contact details are available on request.
HANDOVER
3.13 | The Contractor is to provide a Handover File for the property, including copies of all Electrical Safety and Gas Safe Test Certificates, maintenance/servicing information, building control certification and copies of drainage tests as may be applicable.
4 | QUARANTINE BUILDING
EXTERNAL AREAS
DEMOLITION AND REMOVAL
4.1 | Temporarily move external container away from external wall of quarantine building.
4.2 | Strip out 3no. personnel doors including all associated joinery.
4.3 | Remove existing louvre vents and cart away from site.
ROOF
4.4 | Thoroughly clean down roof covering to remove all moss and algae growth.
4.5 | Strip out existing rainwater goods and brackets and supply and install new Upvc rainwater goods in type style and colour to match existing.
4.6 | Rub down, prepare and redecorate existing timber soffit, fascia and bargeboards in a type style and colour to match existing. Rainwater goods laid to 1:80 fall.
4.7 | Supply and install 2no. dry verge tiles where missing. Type, style and colour to match existing.
NEW DOORS
4.8 | Supply and install new personnel door to location shown on Appendix D - Drawing No. WLIMC059-SK01. Contractor to provide proposal for new doors to be timber to match existing. To be secure by design standard or equivalent.
EXTERNAL WALLS
4.9 | Block up 2no. Door openings to form design shown on Appendix D - Drawing No. WLIMC059-SK01. To be blockwork construction to match existing.
4.1 | Block up opening formed by removal of louvre vent. To be blockwork construction to match existing.
4.11 | Hack off defective render, re-render and decorate including newly formed blockwork walls. Type, style and colour to match existing.
4.12 | Hack off all render and replace with new to match existing.
4.13 | Strip out any defective bellcasts and replace with new. Type style and colour to match existing.
4.14 | Allow Provisional Sum (PS) to undertake mortar repairs to brickwork below DPC level. Not to be expended unless confirmation received from project manager. | PS | 500
INTERNAL AREAS
DEMOLITION AND REMOVAL (FABRIC AND M & E)
4.15 | Strip out and dispose of 3no. existing light fixings to ceiling. Strip all wiring back to distribution board and ensure it is left safe.
4.16 | Demolish all existing blockwork walls internally and cart away from site. As shown on Appendix D.
4.17 | Strip out existing plasterboard ceiling and cart away from site.
INTERNAL PARTITIONS/WALLS
4.18 | Install 1 layer of 12.5 mm thick marine grade plasterboard to the internal face of all external blockwork walls affixed with plaster dabs.
CEILINGS
4.19 | Fire resistant 12.5mm plasterboard to be fitted to existing timber joists in newly formed storage room. Ceiling void to be filled with 100mm Rockwool Flexi insulation or similar, approved by Project Manager.
FLOORING
4.2 | Install Altro Reliance 25 Safety flooring system to newly formed store room. To include 150mm coved upstands to perimeters. Allow latex screed and other sundry items as required to achieve a level, Ruck free finish. Colour to be grey.
DECORATIONS
4.21 | Decorate newly formed plasterboard walls, and all affected ceilings and other walls forming the new room with vinyl silk emulsion paint. Colour to be white.
MECHANICAL AND ELECTRICAL INSTALLATIONS
GENERALLY
4.22 | All electrical works and installations to be undertaken by an NICEIC Approved Contractor to the current Regulations. The exact location of the electrical installations to be agreed on site with the Project Manager.
4.23 | All electrical conduit to be surface mounted.
4.24 | Where applicable, mechanical and electrical design to be undertaken in accordance with CIBSE requirements.
4.25 | Where relevant, supply and fit 1 no. fused spur for each appliance contained within the specification.
LIGHTING
4.26 | Lighting provisions to include the following: LED Bulkhead light fittings (IP60 certified) within the newly formed storage room
4.27 | Allow to install associated switches to walls with associated surface mounted metal electrical conduit.
4.28 | Allow a Provisional Sum (PS) of £1,000 (ONE THOUSAND POUNDS) to reconfigure / supply new emergency light fittings as required to comply with regulations. To be determined by NICEIC qualified engineer. Work not to be undertaken without prior approval of Project Manager. | PS | 1000
| QUARANTINE BUILDING TOTAL |  | Subtotal 1
5 | GENERATOR BUILDING
EXTERNAL AREAS
DEMOLITION AND REMOVAL (FABRIC AND M & E)
5.1 | Strip out 2no. Ventilation grills and cart away from site.
ROOF
5.2 | Thoroughly clean down roof to remove all moss and algae growth.
5.3 | Strip out existing rainwater goods and cart away from site and supply and install new Upvc good, type style and colour to match existing.
5.4 | Rub down, prepare and redecorate existing timber soffit, fascia and bargeboards in a type style and colour to match existing.
NEW DOORS
5.5 | Strip out and replace existing double door and supply and install new double doors to location shown on Appendix D - Drawing No. WLIMC059-SK01. Contractor to provide proposal for new timber panel doors to match existing.
5.6 | Strip out, cart away and replace 3no. Single timber personnel doors. Replace boiler cupboard door and service cupboard door with new doors to match existing. To be secure by design standard or equivalent.
EXTERNAL WALLS
5.7 | Block up 1no. Door openings to form design shown on proposed drawing Appendix D - Drawing No. WLIMC059-SK01. To be blockwork construction to match existing.
5.8 | Block up opening formed by removal of louvre vents. To be blockwork construction to match existing.
5.9 | Hack off defective render, re-render and decorate. Type, style and colour to match existing.
5.1 | Allow Extra Over (E/O) cost to hack off all render and replace with new to match existing. | EO
5.11 | Allow extra over cost to strip out any defective bellcasts and replace with new. Type style and colour to match existing.
5.12 | Allow provisional sum to undertake mortar repairs to brickwork below DPC level.
INTERNAL AREAS
DEMOLITION AND REMOVAL
5.13 | Strip out and dispose of 2no. existing strip light fixings to ceiling and any associated electrical conduit. To including stripping out of any electrical conduit associated with generator.
5.14 | Strip out existing plasterboard ceiling and cart away from site.
INTERNAL PARTITIONS/WALLS
5.15 | Install 1 layer of 12.5 mm thick moisture resistant plasterboard to the internal face of all external blockwork walls affixed with plaster dabs. Plasterboard to be tape and jointed to achieve smooth finish.
5.16 | Extra Over (E/O) cost to supply and install 100mm Rockwool GA4000. Install batts to inside edge of external wall prior to fitting plasterboard. | EO
CEILINGS
5.17 | Moisture resistant 12.5mm plasterboard to be fitted to existing roof structure in newly formed Drying Room. Ceiling void to be filled with 100mm Rockwool Flexi insulation or similar, approved by Project Manager.
FLOORING
5.18 | Build up screed to create 1:40 fall to drainage channel. Cut out section of slab and supply and fit Aco Deckline drainage channel to location shown on Appendix G - Drawing No. WLIMC059-SK01. Lay channel to permit water to flow to gully at 1:80 fall. Cut out section of slab and supply and fit gully to connect Aco drain to mains drainage.
5.19 | Install Altro Reliance 25 Safety flooring system to newly formed drying room room. To include 150mm coved upstands to perimeters. Allow latex screed and other sundry items as required to achieve a level, Ruck free finish. Colour to be grey.
MECHANICAL AND ELECTRICAL
5.2 | Install drainage in accordance with Appendix G - Drainage Design.
5.21 | Contractor to connect drainage to existing main sewer and to ensure pipework is designed to withstand sufficient imposed and dead loads for parking area.
EXTERNAL AREAS - NEW HARDSTANDINGS
5.22 | Contractor to allow for reinstatement of external hardstandings and any structural work to external wall / foundation. Design to be in accordance with building regulations.
5.23 | Install Altro Reliance 25 Safety flooring system to newly formed drying room. To be installed with 150mm upstands to perimeters. Allow latex screed and other sundry items as required to a level, ruck free finish. Colour to be grey.
DECORATIONS
5.24 | Decorate newly formed plasterboard walls, and all affected ceilings and other walls forming the new room with vinyl silk emulsion paint. Colour to be white.
WORK BENCH AND SEATING
5.25 | Supply all materials and construct seating to the specification identified within Appendix 3. Location to be confirmed. Timber to be C16 treated softwood.
IRONMONGERY - RAILS AND HOOKS
5.26 | Supply and fit 42mm galvanised steel key clamp / railings, location to be confirmed with MCA. The purpose of the installation is to form drying racks for Coastguard equipment. Provide diagonal intermediate supports to bear onto walls to provide structural stability for the installation. Mount with a horizontal rail height of 2000mm from slab level.
5.27 | Supply and fit 6no. Aluminium aerial brackets to the wall, upside down to hang ropes as per information in Appendix E - Example Bracket. Location to be confirmed with MCA.
MECHANICAL AND ELECTRICAL INSTALLATIONS
GENERALLY
5.28 | All electrical works and installations to be undertaken by an NICEIC Approved Contractor to the current Regulations. The exact location of the electrical installations to be agreed on site with the Project Manager.
5.29 | All electrical conduit to be surface mounted armoured sheathing.
5.3 | Where applicable, mechanical and electrical design to be undertaken in accordance with CIBSE requirements.
5.31 | Where relevant, supply and fit 1 no. fused spur for each appliance contained within the specification.
LIGHTING
5.32 | Lighting provisions to include the following: • LED light fittings (IP65 certified) within the newly formed drying room
5.33 | Allow to install associated switches to walls with associated metal electrical conduit to be surface mounted.
5.34 | Allow a Provisional Sum (PS) of £1,000 (ONE THOUSAND POUNDS) to reconfigure / supply new emergency light fittings as required to comply with regulations. To be determined by NICEIC qualified engineer. Work not to be undertaken without prior approval of Project Manager. | PS | 1000
SMALL POWER
5.35 | The following power installations will need to be supplied and fitted: 1No fused spur switch for each tubular heater, note these will need to be appropriate for a wet/damp environment.
HEATING
5.36 | Supply and fit tubular radiant heaters, the sizes, numbers and locations of which are to be suitable for drying coastguard PPE and rescue equipment (to dry within three hours) within the designated space. Note that this will be a wet area, and the electrical installations must be to a specification suitable for this environment. Contractor to appoint a suitably qualified mechanical and electrical engineer to specify the heater, and provide proposals to the Project Manager for approval prior to order and installation.
5.37 | Timers to be installed on tubular heaters with associated thermostat. To be linked to mechanical extraction.
VENTILATION
5.38 | Supply and fit mechanical air / humidity extraction, sized to suit, to Building Regulations and CIBSE requirements. Allow for all switching / cabling as required to achieve specification. Mechanical extracts to be ceiling mounted with associated pipe to ridge vents. Contractor to supply and install ventilation grilles and ductwork to affix to external wall and link to contained duct vent via the rear external wall.
| GENERATOR BUILDING TOTAL |  | Subtotal 2
6 | STATUTORY
6.1 | Please see attached Asbestos Report.
6.2 | Should asbestos be encountered during the course of the works, the contractor is to halt works immediately and notify the Project Manager.
7 | GENERALLY UPON COMPLETION
7.1 | Upon completion of all works, Contractor to clear away all builders’ materials and wash down all glazing, vacuum clean carpets mop/polish all vinyl floors and leave the building in a state ready for occupation. Clean/polish all retained fixtures and fittings.
7.2 | Upon completion, contractor to provide copies of the operation and maintenance manual within lever arch file as well as all necessary test certificates and left with building manager.
8 | CONTINGENCY
8.1 | Provide provisional sum of £1,000 (ONE THOUSAND POUNDS) as a contingency. Funds not to be expelled without prior approval authorisation from Project Manager. | PS | 1000
8.2 | All additional works will be notified by way of an early warning notice and subsequent compensation event.
9 | TOTALS
Quarantine Building Total
Generator Building Total
Preliminaries
Preambles
Activity Schedule
OH&P
Total
10 | Additonal Information
Quarantine Building
10.1 | 4 x No. of lighting units, LED as per discription above.
10.2 | 4 x No. double 13amp dado rail plug sockets to be installed, location to be discussed at start up meeting
10.3 | On commencement of the works on site, if necessary, the appointed contractor will provide a quote to install an additional sub main distribution board.
10.4 | proposed design for store room provided, to assist in final desired use.
Generator Building
10.5 | move existing main distribution board in generator room into adjoining electrical mains cupboard’.
10.6 | 4 x No. of lighting units, LED as per discription above.
10.7 | proposed design for Drying room provided, to assist in final desired use.
10.8 | heating requirements for drying room, link below.
10.9 | http://www.ambirad.co.uk/en/uk/node/3116
11 | Appendix 4 is key pole example.