## Sheet1
CLARIFICATION LOG
Tender: | Falmouth Harbour – Destination Development Feasibility Study
Tender Reference: | SPF
Published Date: | 22nd December 2023
Version number: | 2
Number | Clarification | Response | Reply date
1 | Could you confirm if you require the tender return to include all the roles listed within the brief? i.e. do we need to have a full design team in place as part of the tender submission? | Given the scope of the works, we believe that these are the skill sets required to undertake the Feasibility. If you believe that the work can be undertaken without all of the roles listed, then this should be detailed within your proposal. The proposed team should be detailed within your proposal. | 2024-01-05
2 | I am writing with regard to the above opportunity and in particular, Section 6.1, c, i of the tender submission that requires a Professional Indemnity Insurance limit of not less than five million (£5,000,000). In our experience this limit seems unduly high relative to the scope of work, fee budget and ‘risk’ at this stage of the project, and as a consequence is likely to have both financial and practical implications that are not necessarily in the interests of all parties or the project. May we request the limit be reviewed, possibly applying methodologies such as multiple of likely fee (e.g. 10 X budget). | PI Cover required to be reduced to £1.5m. | 2024-01-05
3 | Are you looking for the full design team to be presented under the tender as a consortia or could your tender be for part of this. | We are looking for a full design team. A consortia is acceptable with a lead consultant identified. FHC will only contract with the Lead organisaation. As per section 7 of the ITT: Tenderers should note that a consortia can submit a tender but the sub-contracting of aspects of this commission after appointment will only be allowed by prior agreement with Falmouth Harbour Commissioners. Partnering and collaboration will be evaluated and weighted at 20% of the overall score. | 2024-01-05
4 | Point 6.5 Past experience and how you will bring this experience to Falmouth. No more than 2 sides of A4. As our proposed consortia has a great deal of experience of working in Falmouth, is it possible to include some additional past examples within a separate appendix to demonstrate this? | Yes, track record examples would be helpful max 4 sides of A4. Maximum of 4 examples. Please ensure relevance to this commission. | 2024-01-09
5 | The Site Plan indicates a boundary of the inner harbour area only. It is possible to also consider the wider Falmouth Harbour Commissioners controlled areas adjacent to, but outside of this described red line plan area? | We would expect consultants to consider the dynamic and plans in the wider Harbour, but the focus of the work has to be focused on the red line. Other development should be put into context such as Church Street Car park and Falmouth Docks. The Port of Falmouth Masterplan is still relevant for reference: https://planforfalmouth.info/wp-content/uploads/2016/12/Falmouth-Masterplan-Masterplan-Executive-Summary.pdf | 2024-01-09
6
7
8
9
10
11
12
13
14
Clarifications will be published against the Contract Notice on Contracts Finder.
If interested in tendering for this project please ensure you add a "watch this notice" for alerts as from time to time additional information or clarifications may be published related to this tender.
It will be the responsibility of Bidders to ensure they are aware of all published clarifications and ensure that their bid has taken these into account.
In the event of any queries please contact: jackie@jackiegeorge.co.uk