## Rules and Constrainst
| RB24 | Nuclear Waste Services - STIM project
1 | Project Delivery Requirements / Curfew details
By acceptance of an Order for provision of materials, the following rule and procedures are deemed to be included for and forms part of the perfomance of Purchase Order / and or Supply Agreement. Note - Costs incurred in breach of these will be recovered from you in the event of breach of these rules and or constraints
2 | DO NOT DRIVE THOUGH THE VILLAGE IN CURFEW TIMES
All deliveries must be booked in 24hrs prior to delivery with Paul Burns – Time Zone B Hours
As part of the Planning conditions for the Low Level Waste Repository Site there are approved times for deliveries to the site. It is therefore essential you adhere to these to both comply with the planning conditions and also to minimise
any impact on the residents of Drigg. Any failure to comply with the approved times will likely lead to refusal to access the site, and GRAHAM will not cover the cost of any aborted delivery.
If your company is not directly delivering then it is still your duty to ensure that your approved courier has read, understood and agreed to comply with these rules. Again any failure to comply and GRAHAM will not cover any aborted delivery costs.
ALL deliveries must adhere to the site approved delivery time of Time Zone B, between 9:00am and 15:00pm, and must have on their person photographic ID and Need to know their National Insurance number
Drigg village speed limit is 30mph BUT we heavily recommend that you adhere to 25MPH MAX and DON’T drive through the speed bumps located throughout the village
There is No parking in ANY laybys within the village of Drigg for any deliveries to the site.
No attempt must be made to deliver to site without complying with these instructions.
| Contact details | Delivery Address
GRAHAM
| Paul Burns | Old Shore Road
| GRAHAM Construction | Drigg
| Works Manager | Holmrook
| Tel no. 07395295802 | Cumbria
| E-mail – paul.burns@graham.co.uk | CA19 1XP
| Time Zone A |  | Curfew | Time Zone B | Curfew | Time Zone C
| 06:00 - 07:30 |  | 07:30 - 09:00 | 09:00 - 15:00 | 15:00 - 16:30 | 16:30 - 18:00
| LLW Containers and emergency/special deliveries |  |  | All good vehicles |  | LLW Containers and emergency/special deliveries