Form of Subcontract

Between

John Graham Construction Ltd

And

To be advised

For the provision of

Dewatering for Stockpile C Diversion

At

Nuclear Waste Services STIM Project

Subcontract to be advised

Please ensure that the above reference are used in all documentation

| NEC 4 Engineering and Construction. Short Subcontract SC1038229. |
| --- |
| A contract between | John Graham Construction Limited |  |  |  |
| And | tba |  |  |  |
| For | Provision of Train Offloading and provision of Plant and Operatives for Stockpile Management, Haul Road, Drainage and Capping Works. |  |  |  |
|  | Contents……………………………………………………………………........................ |  |  |  |
|  | Contract Forms……………………………………………………………………………… |  |  |  |
|  |  |  | Subcontract Data The Subcontractor’s Offer and Contractor’s Acceptance Price List Scope Site Information Conditions of Subcontract Additional and Amended Conditions CIS Requirements List of Appendices to this subcontract | 3 7 8 11 11 12 29 52 53 |
| Subcontract Data. The Contractor’s Subcontract Data. |
|  |  | The Contractor is |  |  |
| Name |  | John Graham Construction Limited |  |  |
| Address for communications |  | 5 Ballygowan Road, Hillsborough, Co Down, Northern Ireland, BT26 6HX |  |  |
| Address for electronic communications |  | richard.wilson@graham.co.uk |  |  |
|  |  | The Client in the main contract is |  |  |
| Name |  | Nuclear Waste Services (Company 05608448) |  |  |
| Address for communications |  | Pelham House, Pelham Drive, Calderbridge, Cumbria, CA20 1DB |  |  |
| Address for electronic communications |  | Rhys.coyles@llwrsite.com |  |  |
|  |  | The Project Manager in the main contract is |  |  |
| Name |  | Rhys Coyles |  |  |
| Address for communications |  | NWS Site, Old Shore Road, Holmrook, CA19 1XP |  |  |
| Address for electronic communications |  | Rhys.coyles@llwrsite.com |  |  |
|  |  | The Supervisor in the main contract is |  |  |
| Name |  | Mike Welsh |  |  |
| Address for communications |  | NWS Site, Old Shore Road, Holmrook, CA19 1XP |  |  |
| Address for electronic communications |  | Mike.Welsh@nuclearwasteservices.uk |  |  |
| The main contract works are |  | Southern Trenches Interim Membrane (STIM) Contract |  |  |
| The subcontract works are |  | Design, Supply, Deliver and Install Soil Testing Facility at Nuclear Waste Service. Low Level Waste Repository at Drigg, Cumbria |  |  |
|  |  | In this subcontract |  |  |
| The site is |  | NWS Site, Low Level Repository, Old Shore Road, Holmrook, CA19 1XP, within the Repository perimeter fence |  |  |
| The starting date is |  | The anticipated commencement on tba |  |  |
| The completion date is |  |  |  |  |
| The delay damages are |  | Nil per day |  |  |
| The period for reply is |  | 7 days |  |  |
| The defects date is |  | One week |  |  |
| The defect correction period is |  | One week |  |  |
| The assessment day is the |  | 1st day of each month |  |  |
| The retention is |  | Nil |  |  |
| The United Kingdom Housing Grants, Construction and Regeneration Act (1996) does apply |  |  |  |  |
|  |  | The Adjudicator is |  |  |
| Name |  | As selected by the adjudicator nominating body |  |  |
| Address for communications |  | Not Applicable |  |  |
| Address for electronic communications |  | Not Applicable |  |  |
|  |  | The main contract Adjudicator is |  |  |
| Name |  | Chair of the Technology and Construction Court Solicitor’s Association |  |  |
| Address for communications |  | Not Applicable |  |  |
| Address for electronic communications |  | Not Applicable |  |  |
| The interest rate on late payment is two % per complete week of delay |  |  |  |  |
| The period within which the Contractor replies after the Subcontractor’s submission of a quotation is two weeks (three weeks for design) |  |  |  |  |
| The minimum amounts of cover for and the time until which the Subcontractor maintains insurance in respect of the following events and matters are as set out in the following table |  |  |  |  |
|  |  | Insurance against; Minimum amount of cover; Period following Completion or earlier termination. Loss of or damage to Plant and Materials and Equipment; The replacement cost; 1 year. Loss of or damage to property (excluding Plant and Materials and Equipment) and liability for bodily injury to or death of a person not an employee of the Contractor arising from or in connection with the Subcontractor providing the Service; £10,000,000 (ten million pounds) for any one event with cross liability so insurance applied to the Parties separately; 1 year. Death of or bodily injury to employees of the Subcontractor arising out of and in the course of their employment in connection with this Contract; The greater of the amount required by the applicable law and £10,000,000 (ten million pounds) for any one event; 1 year. Fully Comprehensive motor insurance; The amount required by law. |
| The Adjudicator nominating body is |  | The chair of the Technology Construction Court Solicitor’s Association |  |  |
| The tribunal is |  | Arbitration |  |  |
| If the tribunal is arbitration, the arbitration procedure is |  | The London Court of International Arbitration (LCIA) arbitration rules current as at the date of the request for arbitration |  |  |
| The conditions of contract are the NEC4 Engineering and Construction Short Subcontract June 2017 (with amendments January 2019) and the following additional conditions |  |  |  |  |
| Option for resolving and avoiding disputes - Option W2 Secondary Options None Additional conditions as included within the document – consisting of NDA flow down terms and CIS requirements |  |  |  |  |

| Subcontract Data. The Subcontractor’s Subcontract Data. |
| --- |
|  |  | The Subcontractor is |  |  |  |  |
| Name |  | To be advised |  |  |  |  |
| Address for communications |  |  |  |  |  |  |
| Address for electronic communications |  |  |  |  |  |  |
| The fee percentage is |  |  |  | To be advised |  |  |
| The people rates are Nil |  |  |  |  |  |  |
| The published list of Equipment is | Not Applicable |  |  |  |  |  |
| The percentage for adjustment for Equipment is |  |  |  |  | Not Applicable |  |
| The Subcontractor’s Offer and Contractor’s Acceptance. |
| The Subcontractor offers to Provide the Works in accordance with these conditions of subcontract for an amount to be determined in accordance with these conditions of subcontract. |  |  |  |  |  |  |
| The offered total of the Prices is |  |  | To be advised |  |  |  |
| Signed on behalf of the Subcontractor |  |  |  |  |  |  |
| Name |  |  | ………………………………………………………………………………………………. ………………………………………………………………………………………………. |  |  |  |
| Position |  |  | ………………………………………………………………………………………………. ………………………………………………………………………………………………. |  |  |  |
| Signature |  |  |  | ………………………………………………………………………………………………. ………………………………………………………………………………………………. |  |  |
| Date |  |  |  | ………………………………………………………………………………………………. ………………………………………………………………………………………………. |  |  |
| The Contractor accepts the Subcontractor’s Offer to Provide the Works |  |  |  |  |  |  |
| Signed on behalf of the Contractor |  |  |  |  |  |  |
| Name |  |  | ………………………………………………………………………………………………... ………………………………………………………………………………………………... |  |  |  |
| Position |  |  | ………………………………………………………………………………………………... ………………………………………………………………………………………………... |  |  |  |
| Signature |  |  | ………………………………………………………………………………………………... ………………………………………………………………………………………………... |  |  |  |
| Date |  |  | ………………………………………………………………………………………………... ………………………………………………………………………………………………... |  |  |  |
| Price List. |
| Scope. |
| Description of the subcontract works |  |  |  |  |  |  |
| As per tender enquiry . |  |  |  |  |  |  |
| Constraints on how the Subcontractor Provides the Works |  |  |  |  |  |  |
| As per tender enquiry Service and other things provided by the Client |  |  |  |  |  |  |
| All Welfare |  |  |  |  |  |  |
| Site Information. |
| As per tender enquiry |  |  |  |  |  |  |

| Conditions of Subcontract. |
| --- |
| 1. General |  |  |
| Actions | 10 |  |
|  | 10.1 | The Parties shall act as stated in this subcontract. |
|  | 10.2 | The Parties act in a spirit of mutual trust and co-operation. |
| Identified and defined terms | 11 |  |
|  | 11.1 | In these conditions of subcontract, terms identified in the Subcontract Data are in italics and defined terms have capital initials. |
|  | 11.2 | 1) Completion is when the Subcontractor has completed the subcontract works in accordance with the Scope except for correcting notified Defects which do not prevent the Client or the Contractor from using the subcontract works or others from doing their work. (2) The Completion Date is the completion date unless later changed in accordance with the subcontract. (3) A Corrupt Act is • the offering, promising, giving, accepting or soliciting of an advantage as an inducement for an action which is illegal, unethical or a breach of trust or • abusing any entrusted power for private gain in connection with this subcontract or any other contract with the Contractor. This includes any commission paid as an inducement which was not declared to the Contractor before the date of the Contractor’s Acceptance. (4) A Defect is a part of the subcontract works which is not in accordance with the Scope. (5) The Defects Certificate is either a list of Defects that the Contractor has notified before the defects date which the Subcontractor has not corrected or, if there are no such Defects, a statement that there are none. (6) Defined Cost is the cost of the following components incurred by the Subcontractor in Providing the Works. • People employed directly or indirectly by the Subcontractor on the site, calculated by multiplying each of the People Rates by the total time appropriate to that rate. • Plant and Materials, the amount paid by the Subcontractor including, if applicable, delivery to the site. • Work subsubcontracted by the Subcontractor, the amount paid by the Subcontractor to the subsubcontractor. • Equipment on site, as follows: –– For Equipment in the published list of Equipment calculated by applying the percentage for adjustment for Equipment to the rates in the published list of Equipment and by multiplying the resulting rate by the time for which the Equipment is required. –– For Equipment which is not in the published list of Equipment calculated by multiplying open market or competitively tendered rates for that Equipment by the time for which it is required. –– For the transport of Equipment and for Equipment which is consumed, the amount paid by the Subcontractor, to the extent that the rates do not include transport or consumables. (7) Equipment is items provided and used by the Subcontractor to Provide the Works and which the Scope does not require the Subcontractor to include in the subcontract works. (8) The Fee is the amount calculated by applying the fee percentage to the amount of Defined Cost. (9) The Parties are the Contractor and the Subcontractor. (10) The People Rates are the people rates unless later changed in accordance with the subcontract. (11) Plant and Materials are items intended to be included in the subcontract works. (12) The Price for Work Done to Date is the total of • the Price for each lump sum item in the Price List which the Subcontractor has completed and • where a quantity is stated for an item in the Price List, an amount calculated by multiplying the quantity which the Subcontractor has completed by the rate. (13) The Prices are the amounts stated in the Price column of the Price List. Where a quantity is stated for an item in the Price List, the Price is calculated by multiplying the quantity by the rate. (14) To Provide the Works means to do the work necessary to complete the subcontract works in accordance with the subcontract and all incidental work, services and actions which the subcontract requires. (15) Scope is information which • specifies and describes the subcontract works or • states any constraints on how the Subcontractor Provides the Works and is either • in the document called Scope or • in an instruction given in accordance with the subcontract. (16) Site Information is information which describes the site and its surroundings and is in the document called Site Information. |
| Interpretation and the law | 12 |  |
|  | 12.1 | In the subcontract, except where the context shows otherwise, words in the singular also mean in the plural and the other way round. |
|  | 12.2 | The subcontract is governed by the law of the country where the site is. |
|  | 12.3 | No change to the subcontract, unless provided for by these conditions of subcontract, has effect unless it has been agreed confirmed in writing and signed by the Parties. |
|  | 12.4 | The subcontract is the entire agreement between the Parties. |
| Communications | 13 |  |
|  | 13.1 | Each communication which the subcontract requires has effect when it is received in a form which can be read, copied and recorded at the last address notified by the recipient for receiving communications. |
|  | 13.2 | If the subcontract requires the Contractor or the Subcontractor to reply to a communication, unless otherwise stated in these conditions of subcontract, they reply within the period for reply. |
| The Contractor’s authority | 14 |  |
|  | 14.1 | The Subcontractor obeys an instruction which is in accordance with the subcontract and is given by the Contractor. |
|  | 14.2 | The Contractor may give an instruction to the Subcontractor which changes the Scope. |
|  | 14.3 | The Contractor gives an instruction to correct a mistake in the Price List which is • a departure from the method and rules stated in the Price List and used to compile it or • due to an ambiguity or inconsistency. |
|  | 14.4 | The Contractor’s acceptance of a communication from the Subcontractor or acceptance of the work does not change the Subcontractor’s responsibility to Provide the Works or liability for its design. |
| Early warning | 15 |  |
|  | 15.1 | The Subcontractor and the Contractor give an early warning by notifying the other as soon as either becomes aware of any matter which could • increase the total of the Prices, • delay Completion or • impair the performance of the subcontract works in use. The Contractor or the Subcontractor may give an early warning by notifying the other of any other matter which could increase the Subcontractor’s total cost. Early warning of a matter for which a compensation event has previously been notified is not required. |
|  | 15.2 | The Subcontractor and the Contractor co-operate in making and considering proposals for how the effect of each matter which has been notified as an early warning can be avoided or reduced and deciding and recording actions to be taken. |
| Access to the site and provision of services | 16 |  |
|  | 16.1 | The Contractor allows access to and use of the site to the Subcontractor as necessary for the work included in the subcontract. |
|  | 16.2 | The Contractor provides services and other things as stated in the Scope. |
| Corrupt Acts | 17 |  |
|  | 17.1 | The Subcontractor does not do a Corrupt Act. |
|  | 17.2 | The Subcontractor takes action to stop a Corrupt Act of a subsubcontractor or supplier of which it is, or should be, aware. |
|  | 17.3 | The Subcontractor includes equivalent provisions to these in subsubcontracts and contracts for the supply of Plant and Materials and Equipment. |
| 2. The Subcontractor’s Main Responsibilities |  |  |
| Subsubcontracting and people | 21 |  |
|  | 21.1 | If the Subcontractor subsubcontracts work, it is responsible for Providing the Works as if it had not subsubcontracted. |
|  | 21.2 | The subcontract applies as if a subsubcontractor’s employees and equipment were the Subcontractor’s. |
|  | 21.3 | The Contractor may, having stated the reasons, instruct the Subcontractor to remove a person. The Subcontractor then arranges that, after one day, the person has no further connection with the work included in the subcontract. |
| Access for the Contractor | 22 |  |
|  | 22.1 | The Subcontractor provides access for the Contractor and others named by the Contractor to work being done for the subcontract and to stored Plant and Materials. |
| 3. Time |  |  |
| Starting and Completion | 30 |  |
|  | 30.1 | The Subcontractor does not start work until the starting date and does the work so that Completion is on or before the Completion Date. |
|  | 30.2 | The Subcontractor submits a forecast of the date of Completion to the Contractor each week from the starting date until Completion. |
|  | 30.3 | The Contractor decides the date of Completion and certifies it to the Subcontractor within one week of the date. |
|  | 30.4 | The Contractor may instruct the Subcontractor to stop or not to start any work. The Contractor subsequently issues an instruction to the Subcontractor to • re-start or start the work or • remove the work from the Scope. |
| The programme | 31 |  |
|  | 31.1 | The Subcontractor submits programmes to the Contractor as stated in the Scope. |
| 4. Quality Management |  |  |
| Tests and inspections | 40 |  |
|  | 40.1 | The Contractor and the Subcontractor carry out tests and inspections required by the Scope. If a test or inspection shows that any work has a Defect, the Subcontractor corrects the Defect, and the test or inspection is repeated. |
| Searching for and notifying Defects | 41 |  |
|  | 41.1 | Until the defects date, the Contractor may instruct the Subcontractor to search for a Defect. |
|  | 41.2 | The Contractor may notify a Defect to the Subcontractor at any time before the defects date. |
| Correcting Defects | 42 |  |
|  | 42.1 | The Subcontractor corrects a Defect whether or not the Contractor has notified it. |
|  | 42.2 | Before Completion, the Subcontractor corrects a notified Defect before it would prevent the Client, the Contractor or others from doing their work. |
|  | 42.3 | After Completion, the Subcontractor corrects a notified Defect before the end of the defect correction period. This period begins at the later of Completion and when the Defect is notified. |
|  | 42.4 | The Contractor issues the Defects Certificate at the defects date if there are no notified Defects, or otherwise at the earlier of • on the end of the last defect correction period and • the date when all notified Defects have been corrected. |
| Accepting Defects | 43 |  |
|  | 43.1 | The Subcontractor and the Contractor may each propose to the other that the Scope should be changed so that a Defect does not have to be corrected. If the Subcontractor and the Contractor are prepared to consider the change, the Subcontractor submits a quotation for reduced Prices or an earlier Completion Date or both to the Contractor for acceptance. If the Contractor accepts the quotation, it changes the Scope, the Prices and the Completion Date accordingly. |
| Uncorrected Defects | 44 |  |
|  | 44.1 | If the Subcontractor has not corrected a notified Defect within its defect correction period, the Contractor assesses the cost of having the Defect corrected by other people and the Subcontractor pays this amount. |
| 5. Payment |  |  |
| Assessing the amount due | 50 |  |
|  | 50.1 | The Subcontractor assesses the amount due and applies to the Contractor for payment before each assessment day. There is an assessment day in each month from the starting date until the earlier of • the month after the Contractor issues the Defects Certificate and • either Party gives notice to the other to terminate the Subcontractor’s obligation to Provide the Works. |
|  | 50.2 | The Subcontractor’s application for payment includes details of how the amount has been assessed. |
|  | 50.3 | If the Subcontractor submits an application for payment before the assessment day, the amount due at the assessment day is • the Price for Work Done to Date • plus other amounts to be paid to the Subcontractor, • less amounts to be paid by or retained from the Subcontractor. |
|  | 50.4 | If the Subcontractor does not submit an application for payment before the assessment day, the amount due at the assessment day is the lesser of • the amount the Contractor assesses as due at the assessment day, assessed as though the Contractor has submitted an application before the assessment day, and • the amount due at the previous assessment day. If the Contractor assesses an amount due it gives details of the how the amount has been calculated. |
|  | 50.5 | If the Subcontractor has incorrectly assessed the amount due in an application made before the assessment day, the Contractor corrects the amount due and gives details of how the corrected amount has been calculated before payment. |
|  | 50.6 | The Subcontractor pays delay damages for each day from the Completion Date until Completion. |
|  | 50.7 | An amount is retained from the Subcontractor in the assessment of each amount due until Completion. This amount is the retention applied to the Price for Work Done to Date. The amount retained is halved in the first assessment made after Completion and remains at this amount until the assessment day after the Defects Certificate is issued. No amount is retained in the assessment made after the Defects Certificate has been issued. |
|  | 50.8 | If the Contractor requires a programme to be submitted, one quarter of the Price for Work Done to Date is retained in assessments of the amount due until the Subcontractor has submitted a first programme to the Contractor showing the information which the Scope requires. |
| Payment | 51 |  |
|  | 51.1 | A payment is made within four weeks after the assessment day. The first payment is the amount due. Other payments are the change in the amount due since the previous assessment. A payment is made by the Subcontractor to the Contractor if the amount due is less than the amount due in the previous assessment. Other payments are made by the Contractor to the Subcontractor. |
|  | 51.2 | Interest is paid if a payment is late or includes a correction of an earlier payment. Interest is assessed from the date by which the correct payment should have been made until the date when it is paid. Interest is calculated at the rate stated in the Subcontract Data or, if none is stated, at 0.5% of the delayed amount per complete week of delay. |
|  | 51.3 | Any tax which the law requires a Party to pay to the other Party is added to any payment made under the subcontract. |
| 6. Compensation Events |  |  |
| Compensation events | 60 |  |
|  | 60.1 | The following events are compensation events. (1) The Contractor gives an instruction changing the Scope unless the change is in order to make a Defect acceptable. (2) The Contractor does not allow access to and use of the site to the Subcontractor as necessary for the work included in the subcontract. (3) The Contractor does not provide something which it is to provide by the date stated in this subcontract. (4) The Contractor gives an instruction to stop or not to start any work. (5) The Contractor does not work within the conditions stated in the Scope. (6) The Contractor does not reply to a communication from the Subcontractor within the period required by the subcontract. (7) The Contractor changes a decision which it has previously communicated to the Subcontractor. (8) The Subcontractor encounters physical conditions which • are within the site, • are not weather conditions and • an experienced subcontractor would have judged, at the date of the Subcontractor’s Offer, to have such a small chance of occurring that it would have been unreasonable to have allowed for them. Only the difference between the physical conditions encountered and those for which it would have been reasonable to have allowed is taken into account in assessing a compensation event. (9) The Subcontractor is prevented by weather from carrying out all work on the site for periods of time, each at least one full working day, which are in total more than one seventh of the total number of days between the starting date and the Completion Date. In assessing this event, only the working days which exceed this limit and on which work is prevented by no other cause are taken into account. (10) Either Party notifies the other of a correction to an assumption made for the assessment of a compensation event. (11) An event which • stops the Subcontractor completing the subcontract works or • stops the Subcontractor completing the subcontract works by the Completion Date and which • neither Party could prevent, • an experienced subcontractor would have judged, at the date of the Subcontractor’s Offer, to have such a small chance of occurring that it would have been unreasonable to have allowed for it and • is not one of the other compensation events stated in the subcontract. (12) The Contractor gives an instruction to correct a mistake in the Price List. |
|  | 60.2 | In judging the physical conditions for the purposes of assessing any compensation event, the Subcontractor is assumed to have taken into account • the Site Information, • publicly available information referred to in the Site Information, • information obtainable from a visual inspection of the site and • other information which an experienced subcontractor could reasonably be expected to have or to obtain. |
| Notifying compensation event | 61 |  |
|  | 61.1 | The Contractor and the Subcontractor notify the other of an event which has happened or which they expect to happen as a compensation event. |
|  | 61.2 | If the Contractor notifies the compensation event, it also instructs the Subcontractor to submit a quotation for the compensation event. The Subcontractor submits the quotation within one week of being instructed to do so by the Contractor. If the Subcontractor notifies the compensation event, it submits a quotation with the notification. |
|  | 61.3 | If the Subcontractor does not notify a compensation event within three weeks of becoming aware that the event has happened the Prices and Completion Date are not changed unless the event arises from a correction to an assumption stated by the Contractor or the Contractor giving an instruction or changing an earlier decision. |
|  | 61.5 | A compensation event is not notified by the Contractor or Subcontractor after the issue of the Defects Certificate. |
| Quotations for compensation events | 62 |  |
|  | 62.1 | A quotation for a compensation event comprises proposed changes to the Prices and Completion Date assessed by the Subcontractor. The Subcontractor submits details of its assessment with each quotation. If the effects of a compensation event are too uncertain to be forecast reasonably, the Subcontractor states assumptions about the compensation event in the quotation. Assessment of the compensation event is based on these assumptions. If any of them is later found to have been wrong, either Party may notify a correction to the other Party. |
|  | 62.2 | The Contractor replies within the period stated in the Subcontract Data after the Subcontractor’s submission. If the Contractor decides that an event notified by the Subcontractor • arises from the fault of the Subcontractor, • has not happened and is not expected to happen, • has not been notified within the timescales set out in these conditions of subcontract or • is not one of the compensation events stated in the subcontract the Contractor notifies the Subcontractor that the Prices and Completion Date are not to be changed. If the Contractor decides otherwise, it notifies the Subcontractor accordingly and includes in the notice • acceptance of the Subcontractor’s quotation or • a statement that it does not agree with the quotation and details of the Contractor’s own assessment. |
|  | 62.3 | If the Contractor does not reply to a quotation in accordance with the subcontract and within the time allowed, it is treated as acceptance by the Contractor of the quotation. |
|  | 62.4 | If the Subcontractor does not provide a quotation which the subcontract requires it to submit in the time allowed, the Contractor assesses the compensation event and notifies the Subcontractor of the Contractor’s assessment within one week of when it should have received the Subcontractor’s quotation. |
|  | 62.5 | The Contractor includes details of its assessment of a compensation event when it notifies the Subcontractor of the assessment. If the effects of the compensation event are too uncertain to be forecast reasonably, the Contractor states assumptions about the compensation event in the assessment. Assessment of the compensation event is based on these assumptions. If any of them is later found to have been wrong, either Party may notify a correction to the other Party. |
| Assessing compensation events | 63 |  |
|  | 63.1 | For a compensation event which only affects the quantities of work shown in the Price List, the change to the Prices is assessed by multiplying the changed quantities of work by the appropriate rates in the Price List. |
|  | 63.2 | For other compensation events, the change to the Prices is assessed as the effect of the compensation event upon • the actual Defined Cost of the work already done, • the forecast Defined Cost of the work not yet done and • the resulting Fee. |
|  | 63.3 | The Contractor and the Subcontractor may agree rates or lump sums to assess the change to the Prices. |
|  | 63.4 | The effects of compensation events upon the Defined Cost are calculated using rates and percentages stated in the Subcontract Data and other amounts at open market or competitively tendered prices with deductions for all discounts, rebates and taxes which can be recovered. |
|  | 63.5 | If, when assessing a compensation event the People Rates do not include a rate for a category of person required, the Contractor and Subcontractor may agree a new rate. If they do not agree the Contractor assesses the rate based on the People Rates. The agreed or assessed rate becomes the People Rate for that category of person. |
|  | 63.6 | A delay to the Completion Date is assessed as the length of time that, due to the compensation event, Completion is forecast to be delayed. |
|  | 63.7 | An assessment of the effect of a compensation event made using Defined Cost • includes risk allowances for cost and time for matters which have a significant chance of occurring and are not compensation events and • is based upon the assumptions that –– the Subcontractor reacts competently and promptly to the event and –– any additional Defined Cost and time due to the event are reasonably incurred. |
|  | 63.8 | A compensation event which is an instruction to change the Scope in order to resolve an ambiguity or inconsistency is assessed as if the Prices and the Completion Date were for the interpretation most favourable to the Subcontractor. |
|  | 63.9 | Assessments for changed Prices for compensation events are in the form of changes to the Price List. |
|  | 63.10 | If • the Contractor has accepted a Subcontractor’s quotation, • a Subcontractor’s quotation is treated as accepted or • the Contractor has notified the Subcontractor of a Contractor’s own assessment for a compensation event, the assessment of that compensation event is not revised except as stated in these conditions of subcontract. |
| 7. Title |  |  |
| Objects and materials within the site | 70 |  |
|  | 70.1 | The Subcontractor has no title to an object of value or of historical or other interest within the site. The Subcontractor does not move such an object unless instructed to do so by the Contractor. |
|  | 70.2 | The Subcontractor has title to materials from excavation and demolition unless the Scope states otherwise. |
| 8. Liabilities and Insurance |  |  |
| Client’s and Contractor’s liabilities | 80 |  |
|  | 80.1 | The following are Client‘s or Contractor’s liabilities. • Claims and proceedings from others and compensation and costs payable to others which are due to –– use or occupation of the site by the main contract works or the subcontract works or for the purpose of the main contract works or subcontract works which is the unavoidable result of the main contract works or subcontract works, –– negligence, breach of statutory duty or interference with any legal right by the Client or the Contractor or by any person employed by or contracted to them except the Subcontractor. • A fault of the Client or the Contractor or any person employed by or contracted to them, except the Subcontractor. • A fault in the design contained in –– the Scope or –– an instruction from the Contractor changing the Scope. • Loss of or damage to Plant and Materials supplied to the Subcontractor by the Client or Contractor, or by others on the Client’s or Contractor’s behalf, until the Subcontractor has received and accepted them. • Loss of or damage to the subcontract works, Plant and Materials due to –– war, civil war, rebellion, revolution, insurrection, military or usurped power, –– strikes, riots and civil commotion not confined to the Subcontractor’s employees or –– radioactive contamination. • Loss of or damage to the subcontract works after Completion except loss or damage occurring before the issue of the Defects Certificate which is due to –– a Defect which existed at Completion, –– an event occurring before Completion which was not itself a Client’s or Contractor’s liability or –– the activities of the Subcontractor on the site after Completion. • Loss of or damage to the Client’s or Contractor’s property, other than the subcontract works, unless the loss or damage arises from or in connection with the Subcontractor Providing the Works. |
|  | 81.1 | The following are Subcontractor‘s liabilities unless they are stated as being Client‘s or Contractor’s liabilities. • Claims and proceedings from others and compensation and costs payable to others which arise from or in connection with the Subcontractor Providing the Works. • Loss of or damage to the subcontract works, Plant and Materials and Equipment. • Loss of or damage to the Client’s or Contractor’s property, other than the subcontract works, which arises from or in connection with the Subcontractor Providing the Works. • Death or bodily injury to the employees of the Subcontractor. |
| Recovery of costs | 82 |  |
|  | 82.1 | Any cost which the Client or the Contractor has paid or will pay as a result of an event for which the Subcontractor is liable is paid by the Subcontractor. |
|  | 82.2 | Any cost which the Subcontractor has paid or will pay to others as a result of an event for which the Contractor or the Client is liable is paid by the Contractor. |
|  | 82.3 | The right of a Party to recover these costs is reduced if an event for which it was liable contributed to the costs. The reduction is in proportion to the extent that the event for which that Party is liable contributed, taking into account each Party’s responsibilities under the subcontract. |
|  | 82.4 | For any one event, the liability of the Subcontractor to the Contractor for loss of or damage to the Client’s or Contractor’s property is limited to the amount stated in the Subcontract Data. The Subcontractor is not liable to the Contractor for the Contractor’s indirect or consequential loss except as provided for in these conditions of subcontract. Exclusion or limitation of liability applies in contract, tort or delict and otherwise and to the maximum extent permitted in law. |
| Insurance cover | 83 |  |
|  | 83.1 | The Contractor provides the insurances which the Contractor is to provide as stated in the Subcontract Data. |
|  | 83.2 | The Subcontractor provides the insurances stated in the Insurance Table except any insurance which the Contractor is to provide as stated in the Subcontract Data. |
|  | 83.3 | The insurances in the Insurance Table are in the joint names of the Parties except the fourth insurance stated. The insurances provide cover for events which are the Subcontractor’s liability from the starting date until the Defects Certificate or a termination certificate has been issued. |
|  | Insurance Table. Insurance Against; Minimum Amount of Cover. Loss of or damage to the subcontract works, Plant and Materials; The replacement cost. Loss of or damage to Equipment; The replacement cost. Loss of or damage to property (except the subcontract works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Subcontractor) arising from or in connection with the Subcontractor Providing the Works; The amount stated in the Subcontract Data for any one event with cross liability so that the insurance applies to the Parties separately. Death of or bodily injury to employees of the Subcontractor arising out of and in the course of their employment in connection with the subcontract; The greater of the amount required by the applicable law and the amount stated in the Subcontract Data for any one event. |
| 9. Termination and Resolving Disputes |  |  |
| Termination and reasons for termination | 90 |  |
|  | 90.1 | A Party may terminate the Subcontractor’s obligation to Provide the Works for a reason stated in these conditions of subcontract by notifying the other Party and giving details of the reason for terminating. After a notification to terminate has been issued, the Subcontractor does no further work necessary to Provide the Works. |
|  | 90.2 | Either Party may terminate if the other Party has become insolvent or its equivalent (Reason 1). |
|  | 90.3 | The Contractor may terminate if the Contractor has notified the Subcontractor that the Subcontractor has not stopped one of the following defaults within one week of the date when the Contractor notified the Subcontractor of the default. • Substantially failed to comply with the subcontract (Reason 2). • Substantially hindered the Contractor (Reason 3). • Substantially broken a health or safety regulation (Reason 4). |
|  | 90.4 | The Subcontractor may terminate if • the Contractor has not paid an amount due under the subcontract within thirteen weeks of the assessment day which followed receipt of the Subcontractor’s application for it (Reason 5) or • the Contractor has instructed the Subcontractor to stop or not to start any substantial work or all work for a reason which is not the Subcontractor’s fault and an instruction allowing the work to re-start or start or removing work from the Scope has not been given within nine weeks (Reason 6). |
|  | 90.5 | The Contractor may terminate if an event occurs which • stops the Subcontractor completing the subcontract works or • stops the Subcontractor completing the subcontract works by the Completion Date and is forecast to delay Completion by more than thirteen weeks, and which • neither Party could prevent, • an experienced subcontractor would have judged, at the date of the Subcontractor’s Offer, to have such a small chance of occurring that it would have been unreasonable to have allowed for it (Reason 7). |
|  | 90.6 | The Contractor may terminate if the Subcontractor does a Corrupt Act, unless it was done by a subsubcontractor or supplier and the Subcontractor • was not and should not have been aware of the Corrupt Act or • informed the Contractor of the Corrupt Act and took action to stop it as soon as the Subcontractor became aware of it (Reason 8). |
|  | 90.7 | The Contractor may terminate for any other reason (Reason 9). |
| Procedures on termination | 91 |  |
|  | 91.1 | On termination, the Contractor may complete the subcontract works. The Subcontractor leaves the site and removes the Equipment. |
| Payment on termination | 92 |  |
|  | 92.1 | The amount due on termination includes • an amount due assessed as for normal payments, • the cost of Plant and Materials provided by the Subcontractor which are on the site or of which the Subcontractor has to accept delivery and • any amounts retained by the Contractor. |
|  | 92.2 | If the Contractor terminates for Reason 1, 2, 3, 4 or 8 the amount due on termination also includes a deduction of the forecast additional cost to the Contractor of completing the subcontract works. |
|  | 92.3 | If the Subcontractor terminates for Reason 1, 5 or 6 or if the Contractor terminates for Reason 9, the amount due on termination also includes 5% of any excess of a forecast of the amount due at Completion had there been no termination over the amount due on termination assessed as for normal payments. |
|  | 92.4 | Within fourteen weeks of termination, the Contractor assesses the final amount due. The final payment is the amount due on termination less the total of previous payments. The Contractor gives the Subcontractor details of the assessment. Payment is made within three weeks of the Contractor’s assessment. |
| Dispute resolution | 93 |  |
|  | 93.1 | A dispute arising under or in connection with the subcontract is referred to and decided by the Adjudicator. A Party does not refer a dispute to the Adjudicator that is the same, or substantially the same, as one that has already been referred to the Adjudicator. |
| The Adjudicator | 93.2 | (1) The Parties appoint the Adjudicator under the NEC Dispute Resolution Service Contract current at the starting date. The Adjudicator acts impartially and decides the dispute as an independent adjudicator and not as an arbitrator. (2) If the Adjudicator is not identified in the Subcontract Data or if the Adjudicator resigns or is unable to act, the Parties choose a new adjudicator jointly. If the Parties have not chosen an adjudicator, either Party may ask the Adjudicator nominating body to choose one. The Adjudicator nominating body chooses an adjudicator within four days of the request. The chosen adjudicator becomes the Adjudicator. (3) The Adjudicator and the Adjudicator’s employees and agents are not liable to the Parties for any action or failure to take action in an adjudication unless the action or failure to take action was in bad faith. |
| The adjudication | 93.3 | (1) A Party may refer a dispute to the Adjudicator if • the Party notified the other Party of the dispute within four weeks of becoming aware of it and • between two and four further weeks have passed since the notification. If a disputed matter is not notified and referred within the times set out in the subcontract, neither Party may subsequently refer it to the Adjudicator or the tribunal. (2) The Party referring the dispute to the Adjudicator includes with its referral information to be considered by the Adjudicator. Any more information from a Party to be considered by the Adjudicator is provided within two weeks of the referral. This period may be extended if the Adjudicator and the Parties agree. (3) The Adjudicator may • review and revise any action or inaction of the Contractor related to the dispute and alter a matter which has been treated as accepted or correct, • take the initiative in ascertaining the facts and the law related to the dispute, • instruct a Party to provide further information related to the dispute within a stated time and • instruct a Party to take any other action which is considered necessary for the Adjudicator to reach a decision and to do so within a stated time. (4) A communication between a Party and the Adjudicator is communicated to the other Party at the same time. (5) If the Adjudicator’s decision includes assessment of additional cost or delay caused to the Subcontractor, the assessment is made in the same way as a compensation event is assessed. (6) The Adjudicator decides the dispute and informs the Parties of the decision and reasons within four weeks of the referral. This period may be extended by up to two weeks with the consent of the referring Party, or by any period agreed by the Parties. If the Adjudicator does not inform the Parties of the decision within the time allowed, either Party may act as if the Adjudicator has resigned. (7) Unless and until the Adjudicator has informed the Parties of the decision, the Parties proceed as if the matter disputed was not disputed. (8) The Adjudicator’s decision is binding on the Parties unless and until revised by the tribunal and is enforceable as a matter of contractual obligation between the Parties and not as an arbitral award. The Adjudicator’s decision is final and binding if neither Party has notified the other within the times required by the subcontract that it intends to refer the matter to the tribunal. |
| The tribunal | 93.4 | A Party may refer a dispute to the tribunal if • the Party is dissatisfied with the Adjudicator’s decision or • the Adjudicator did not inform the Parties of a decision within the time allowed and a new adjudicator has not been chosen, except that neither Party may refer a dispute to the tribunal unless they have notified the other Party of their intention to do so not more than four weeks after • the Adjudicator informs the Parties of the decision, or, if the Adjudicator did not inform the Parties of the decision within the time allowed, • the end of the time allowed for the Adjudicator’s decision. |
| Combining procedures | 93.5 | If there is any matter arising under or in connection with the subcontract which is also a matter arising under or in connection with the main contract and the main contract allows a subcontractor to attend a meeting or an adjudication, the Subcontractor attends the meeting or the adjudication and provides any information which a party in the main contract may require. |
| If the United Kingdom Housing Grants, Construction and Regeneration Act 1996 as amended by the local democracy, economic development and Construction Ace 2009 (The Act) applies to the contract, the following additional conditions apply |  |  |
| Definitions | 1.1 | (1) In this clause, time periods stated in days exclude Christmas Day, Good Friday and bank holidays. (2) Each assessment day is a payment due date. If there is a termination, the payment due date is thirteen weeks after the notice of termination. (3) The final date for payment is three weeks after payment due date. |
| Assessing the amount due | 1.2 | If the Subcontractor makes an application for payment before a payment due date, the application is the notice of payment specifying the sum that the Subcontractor considers to be due at the payment due date (the notified sum). The Subcontractor’s application states the basis on which the amount is calculated and includes details of the calculation. |
|  | 1.3 | If the Subcontractor does not make an application for payment before a payment due date, the notified sum is zero or, if an amount is to be paid to the Contractor, the amount which the Contractor considers is to be paid. The Contractor notifies the Subcontractor of the notified sum. |
|  | 1.4 | The following replaces clause 50.5 If a Party intends to pay less than the notified sum, it notifies the other Party of its assessment of the amount due not later than seven days (the prescribed period) before the final date for payment. The notification states the basis on which the amount due is calculated and includes details of the calculation. A Party pays the notified sum unless it has notified its intention to pay less than the notified sum. |
| Compensation event | 1.5 | If the Subcontractor exercises it right under the Act to suspend performance, it is a compensation event |
| The adjudication | 1.6 | The following replaces clause 93.3(1) A party may issue to the other Party a notice of its intention to refer a dispute to adjudication at any time. The Party refers the dispute to the Adjudicator within seven days of the notice. |
|  | 1.7 | The Adjudicator may in the decision allocate the Adjudicator’s fees and expenses between the Parties. |
|  | 1.8 | The Adjudicator may, within five days of giving the decision to the Parties, correct the decision to remove a clerical or typographical error arising by accident or omission. |
|  | 1.9 | If the Adjudicator’s decision changes an amount notified as due, payment of the sum decided by the Adjudicator is due not later than seven days from the date of the decision or the final date for payment of the notified amount, whichever is the later. |

Additional and Amended Conditions

ANNEX A TO THE CONTRACT DATA PART ONE

works contract relating to the SOUTHERN TRENCHES INTERIM MEMBRANE AT HOLMBROOK, CUMBRIA, CA19 1XH Nuclear Waste Services limited

option z: AMENDMENTS AND ADDITIONS TO EXISTING CLAUSES

Z1	The terms used in this Z clauses are to be read as per table below

| Term in Z clause | Term used in this subcontract. |
| --- | --- |
| Contracts Data | Subcontract Data and/or Subcontract Offer |
| Client | Contractor |
| Contractor | Subcontractor |
| Contract Date | Subcontract Date |
| this contract | this subcontract |
| subcontract | Subsubcontract (any co employed by the subcontractor to undertake any part of the Subcontractors obligations under this subcontract |

ADDITIONAL DEFINITIONS and interpretation

Insert the following new clauses:

| "11.2(36) | Authority Field of Use | means carrying out the NDA's functions, duties and powers as prescribed by the Energy Act 2004 from time to time. |
| --- | --- | --- |
| 11.2(36A) | Commercial Appendix | means the commercial appendix a copy of which is set out in the Appendix to the Agreement. |
| 11.2(37) | Contract Period | the period commencing on the date of this contract and ending on the date of expiry or termination of this contract (whichever is earlier). |
| 11.2(38) | Contractor's Affiliates | means any entity that directly or indirectly controls, is controlled by or is under common control with, the Contractor. |
| 11.2(39) | Contractor's Documents | means all existing and future designs, drawings, models, plans, specifications, design details, BIM models and databases (to the extent the Contractor has responsibility for design under this contract), all costings, budgets, estimates and valuations, any photographs, brochures, reports, notes of meetings, CAD materials and any other materials provided by or prepared on behalf of the Contractor in connection with this contract and/or the works and all amendments and additions to them and any works, designs or inventions of the Contractor incorporated or referred to in them. |
| 11.2(40) | Contractor Personnel | means all directors, officers, employees, agents, consultants and contractors of the Contractor and/or of any Sub-processor engaged in the performance of its obligations under this contract. |
| 11.2(41) | Contracts Finder | means the Government's publishing portal for public sector procurement opportunities |
| 11.2(42) | Criminal Conviction Data | means the Personal Data relating to criminal convictions and offences, as described in Article 10 of the GDPR. |
| 11.2(43) | Controller | has the meaning given in the DPA. |
| 11.2(44) | Processor | has the meaning given in the DPA. |
| 11.2(45) | Data Loss Event | any event that results, or may result, in unauthorised access to Personal Data held by the Contractor under this contract, and/or actual or potential loss and/or destruction of Personal Data in breach of this Agreement, including any Personal Data Breach. |
| 11.2(46) | Data Protection Laws | means (a) any law, statute, declaration, decree, directive, legislative enactment, order, ordinance, regulation, rule or other binding restriction (as amended, consolidated or re-enacted from time to time) which relates to the protection of individuals with regards to the Processing of Personal Data and privacy to which a party is subject, including but not limited to the DPA and the UK GDPR; and (b) any code of practice or guidance published by the UK Information Commissioner's Office or other applicable Regulator or the European Data Protection Board from time to time. |
| 11.2(47) | Data Subjects | has the meaning given in the DPA. |
| 11.2(48) | DPA | means the Data Protection Act 2018. |
| 11.2(49) | EIR | means the Environmental Information Regulations 2004. |
| 11.2(50) | Client's Affiliates | means NDA and any entity that directly or indirectly controls, is controlled by or is under common control with, the Client and/or NDA. |
| 11.2(50A) | Fair Wear and Tear | means wear and tear that arises in the normal course or use or operation of a wagon within its operational thresholds and permitted use or is a natural consequence of the passage of time. Small dents, scrapes and scratches caused by aggregate and loading/unloading operations will be classed as fair wear and tear. |
| 11.2(51) | FOIA | means the Freedom of Information Act 2000. |
| 11.2(52) | Force Majeure Event | means any of the events or circumstances listed in paragraphs (a) to (e) below, provided that the relevant event or circumstance occurs in the United Kingdom, is beyond the reasonable control of the Party that seeks to rely on the Force Majeure Event (such Party having exercised Good Industry Practice), and could not reasonably have been foreseen by such Party prior to entering into the contract: (a) war, hostilities (whether war declared or not), invasion, act of foreign enemies; (b) rebellion, terrorism (or threat of terrorism), revolution, insurrection, military or usurped power or civil war; (c) riot or civil commotion or disorder, strike or lockout by persons other than the Contractor's personnel and other employees, Subcontractors or any other person for whom the Contractor is responsible; (d) munitions of war, explosive materials, except as may be attributable to the Contractor's work or otherwise use (or that by any of the Contractor's personnel and other employees, Subcontractors or any other person for whom the Contractor is responsible) of such munitions, radiation or radio-activity; (e) natural catastrophes such as earthquake, hurricane, typhoon or volcanic activity save that adverse weather conditions alone shall not in any circumstances qualify as a Force Majeure Event save where the same amounts to a natural catastrophe; (f) any event that causes a loss of rail routes to the Site for a period of more than seven (7) days; save that the following events shall not under any circumstances constitute a Force Majeure Event: (g) a lack of labour and/or financial resources on the part of the Contractor, Subcontractors or any other person for whom the Contractor is responsible; (h) any unlawful act of a third party who has gained entry to a Site due to a failure of the Contractor to comply with any security requirements or other failure to comply with its obligations under this contract; (i) any radioactive, chemical or biological contamination on a Site or emanating from a Site or matter in the course of transportation to or from a Site save to the extent that such contamination is caused by any of the events listed in paragraphs (a) to (e) above. |
| 11.2(53) | UK GDPR | has the meaning as defined in section 3 of the DPA; |
| 11.2(54) | Good Industry Practice | means the exercise of all of the skill and care, diligence, prudence and foresight which would reasonably and ordinarily be expected from a skilled and experienced contractor engaged in activities of a similar scope and complexity to those that are the subject of this contract and under the same or similar circumstances, where such contractor is seeking to comply with its contractual obligations and all applicable Law and Regulatory Requirements. |
| 11.2(55) | Intellectual Property Rights | means any and all current and future intellectual or industrial rights (whether legal or equitable), including, patents, copyrights (including related moral rights), design rights, trade marks, service marks internet domain names, trade-secrets, topography rights, know-how, methodologies, processes, rights in databases, whether registered or unregistered, together with applications for or any right to apply for or register any of the foregoing and any other intellectual property rights of a similar nature or having equivalent effect anywhere in the world. |
| 11.2(56) | Law | means any Act of Parliament or subordinate legislation within the meaning of section 21(1) of the Interpretation Act 1978, any exercise of the Royal Prerogative, any other applicable law, common law proclamation, by-law, directive, decision, regulation, rule, notice or court ruling in each case in the United Kingdom and all applicable laws, regulations, directives, orders, decisions or other rules having the force of law in the jurisdiction (including in relation to international waters) where the Contractor's obligations under this contract are carried out. |
| 11.2(57) | NDA | means the Nuclear Decommissioning Authority established pursuant to the provisions of the Energy Act 2004. |
| 11.2(58) | NDA Agent | means any one of the duly authorised representatives of the NDA (including but not limited to auditors, advisers, consultants, and agents) acting on behalf of the NDA. |
| 11.2(59) | Not used | Not used. |
| 11.2(60) | Personal Data | has the meaning given in Article 4 of the UK GDPR. |
| 11.2(61) | Personal Data Breach | has the meaning given in Article 4 of the UK GDPR. |
| 11.2(62) | Persons | means all staff, including directors, officers and employees, as well as the agents and workers of either Party together with the directors, officers and employees of such Party's sub-contractors or contractors and further down any contractual chain, and "Person" shall mean any one of them individually as the context dictates. |
| 11.2(63) | Processing | has the meaning given in Article 4 of the UK GDPR and "Process" and "Processed" shall be construed accordingly. |
| 11.2(64) | Protective Measures | appropriate technical and organisational measures designed to ensure compliance with obligations of the parties arising under Data Protection Laws and this contract, which may include: pseudonymising and encrypting Personal Data, ensuring confidentiality, integrity, availability and resilience of systems and services, ensuring that availability of and access to Personal Data can be restored in a timely manner after an incident, and regularly assessing and evaluating the effectiveness of the such measures adopted by it; |
| 11.2(65) | Regulators | means the Health and Safety Executive (HSE), the Environment Agency (EA), the Scottish Environment Protection Agency (SEPA), the Office for Civil Nuclear Security (OCNS), the Scottish Executive, the Financial Services Authority (FSA) and Ofgem, the Pensions Regulator, the Pension Protection Fund and any replacement body assuming responsibility for the functions thereof, others specific to the Contractor's obligations under this contract and as applicable in the relevant jurisdiction (including in relation to international waters) where the Contractor's obligations under this contract are carried out and "Regulator" shall mean each or any one of them). |
| 11.2(66) | Regulatory Requirements | means any legally enforceable requirement of any Regulator. |
| 11.2(67) | Not used | Not used. |
| 11.2(68) | Relevant Policies | means the Ministry of Justice guidance in respect of anti–bribery published in March 2011 (as updated from time to time). |
| 11.2(69) | Request for Information | has the meaning given in the Freedom of Information Act 2000. |
| 11.2(70) | Requirements | means all applicable laws and codes relating to anti-bribery and anti-corruption including but not limited to the Bribery Act 2010. |
| 11.2(71) | Reverse Charge Order | means the Value Added Tax (Section 55A) (Specified Services and Excepted Supplies) Order 2019/892. |
| 11.2(72) | Senior Representatives | Nuclear Waste Services: Mike Piggott and Tony Buchanan. |
| 11.2(73) | Special Categories of Personal Data | means the special categories of Personal Data, as described in Article 9 of the GDPR. |
| 11.2(74) | Statutory Bodies | means any local highways authority, a statutory undertaker, a public or private utility, and any person, body or organisation formed or exercising powers pursuant to statute. |
| 11.2(75) | SME | means an enterprise falling within the category of micro, small and medium-sized enterprises defined by the Commission Recommendation of 6 May 2003 concerning the definition of micro, small and medium-sized enterprises. |
| 11.2(76) | Sub-processor | any third party appointed to process Personal Data on behalf of the Contractor related to this contract. |
| 11.2(77) | Supply Chain Member | is any contractor or supplier not being the Client or the Contractor entering into any contract at any level in the supply chain in connection with the performance of the Contractor's obligations under this contract |
| 11.2(78) | VCSE | means a non-governmental organisation that is value-driven and which principally reinvests its surpluses to further social, environmental or cultural objectives. |
| 11.2(79) | End User | has the meaning given to it in Article 2 of the Value Added Tax (Section 55A) (Specified Services and Excepted Supplies) Order 2019. |

Insert as a new clause 12.5: "In this contract where a gender neutral term is used, for the purpose of interpretation, legal precedent and legal rules, the historic masculine meaning of the word shall continue to apply."

Change of Control

- The Contractor shall not be entitled to terminate the contract or make any amendment to this contract as a result of any change in ownership, management or control of the Client.

Termination

In Clause 91.1:

In relation to (R5) after the word "it" insert: "or the presentation of a petition for its winding-up unless it is withdrawn within three (3) Business Days from the date on which it is notified of the presentation";

In relation to (R6) after the word "it" insert: "or a liquidator, supervisor, compulsory manager, trustee or similar officer in respect of it or any of its assets";

In relation to (R8) after the word "it" insert: "or entered administration in accordance with any of the provisions of the Insolvency Act 1986 or the presentation of a petition for the appointment of an administrator has been made against it unless it is withdrawn within three (3) Business Days from the date on which it is notified of the presentation";

In relation to (R10) after the word "creditors" insert: "or a moratorium is declared in relation to its indebtedness or any other corporate action, legal proceedings or other procedure or step is taken in relation to (a) the suspension of payments, a moratorium or any indebtedness, winding up, dissolution, administration or reorganisation (by way of voluntary arrangement, scheme of arrangement or otherwise) of it other than a solvent liquidation or reorganisation, b) a composition, compromise, assignment or arrangement with any of its creditors; or c) the appointment of any of the persons referred to in this clause; or where it is a company registered other than in England, events occur or are carried out which, within the jurisdiction to which it is subject, are similar in nature or effect to those specified in this clause".

The Client shall be entitled to terminate this contract at any time upon giving reasonable notice to the Contractor.  For the purposes of this Clause Z4.1 'reasonable notice' shall not be less than 30 days' notice.

Where the Client terminates the contract pursuant to Clause Z4.1 above, save for the sums due on termination in accordance with the Termination Table, the Contractor shall (without prejudice to Clauses 93.4 and 93.6) not be entitled to recover any payment in respect of loss of anticipated profits, loss of opportunity or consequential losses.

Insert as a new clause 91.9 "The Client may terminate for any reason including pursuant to Clause Z4.1 (R23)".

Insert a new Clause 91.10 as follows:

- "The Client may terminate if the Project Manager has notified that a breach of Clause Z8.1 by the Contractor or any persons associated with it (as defined in section 7 of the Bribery Act 2010) in connection with this contract (in all cases whether or not acting with the Contractor's knowledge) has occurred (R24)."

Insert a new Clause 91.11 as follows:

"The Client may terminate if the Project Manager has notified that:

  - A breach of Clause Z16 by the Contractor has occurred (R25)."

Insert a new Clause 91.12 as follows:

"The Client may terminate if the Project Manager has notified that:

- The Contractor has substantially failed to comply with health, safety and environmental legislation, Regulatory Requirements and/or the requirements of the Scope in so far as they relate to health, safety and the environment (R26).

- The Client has suspended the works in accordance with Clause Error! Reference source not found. and the Contractor has failed to remedy the relevant breach to the Client's satisfaction within 72 hours of the works being suspended (R27)."

Insert a new Clause 91.13 as follows:

- "The Client may terminate if the Contractor is unable or admits inability to pay its debts as they fall due or has no reasonable prospect of being able to pay debts which are not immediately payable, suspends making payments on any of its debts or, by reason of actual or anticipated financial difficulties, commences negotiations with one or more of its creditors with a view to rescheduling any of its indebtedness (R28)."

At Clause 90.2, delete the termination table and replace with the following termination table:

| - TERMINATION TABLE |  |  |  |
| --- | --- | --- | --- |
| - TERMINATING PARTY | - REASON | - PROCEDURE | - AMOUNT DUE |
| - The Client | - R1-R15, R18 or R22-R28 - R17 or R20 - R21 | - P1, P2 and P3 - P1 and P3 - P1 and P4 | - A1 and A3 - A1 and A2 - A1 and A2 |
| - The Contractor | - R1-R10, R16 or R19 - R17 or R20 | - P1 and P4 - P1 and P4 | - A1 and A2 - A1 and A2 |

In clause 93.2 delete the reference to and all text related to "A4".

Rights of Third Parties

The NDA shall, pursuant to the Contracts (Rights of Third Parties) Act 1999, be entitled to enforce any of the Client's rights under the contract and any term in this contract which directly or indirectly prevents or attempts to prevent the NDA from exercising those rights shall have no legal effect.  Save for the aforesaid, for the purposes of the Contracts (Rights of Third Parties) Act 1999, nothing in the contract confers or purports to confer on any third party any benefit or any right to enforce a term of the contract.

Exclusion from CompetitioN

The Contractor shall immediately notify the Client if it becomes aware of any economic operator (that the Contractor wants to include in any of its procurements) who has committed or omitted acts in one of the situations referred to in the Public Contracts Regulations 2015, Regulation 57(8). The Client shall be entitled to instruct the Contractor to exclude from competition in any of the Contractor's procurements, any economic operator who has committed or omitted acts in one of the situations referred to in the Public Contracts Regulations 2015, Regulation 57(8).  Where the economic operator concerned can demonstrate it has undertaken steps to remedy the situation giving rise to the exclusion which meet the requirements of Regulation 57(15) of the Public Contracts Regulations 2015 and the Client is satisfied that those steps are sufficient, then any such instruction to exclude shall no longer be valid or binding.

Rights of Inspection and Access for Inspection Purposes

Subject to compliance with applicable legislation and regulatory requirements, the Client, NDA, any NDA Agents and any government body, department or agency (including, but not limited to, the National Audit Office) shall be entitled periodically, and at times and in a manner agreed by the Contractor, to inspect, review and monitor the performance of the Contractor and spot check for the purposes of:

Z7.1.1	reviewing the Contractor's activities in connection with, and performance in respect of, this contract;

Z7.1.2	verifying the accuracy of the Prices and any costs of suppliers (including Subcontractors) of the works, which shall include the verification of any supporting documentation in respect of the Prices, provided that if Option A or Option B applies, this Clause Z7.1.2 shall only apply to the assessment of Compensation Events;

Z7.1.3 	reviewing all information required to be kept by Contractor pursuant to this contract;

Z7.1.4	verifying the accuracy and completeness of any management information delivered or required by this contract;

Z7.1.5	reviewing the integrity, confidentiality and security of the information required to be kept by the Contractor pursuant to this contract;

Z7.1.6	 reviewing the Contractor's compliance with the FOIA, Environmental Information Regulations 2004, the General Data Protection Regulation (EU) 2016/679 (GDPR) and the DPA (in accordance with Clause Z8.3), compliance with the Bribery Act 2010 (in accordance with Clause Z8) and any other Requirements or legislation applicable to the works.

Where appropriate, the Client shall discuss the outcome of the inspection and investigation with the Contractor.  In such circumstances, the Contractor shall maintain records of the findings together with details of any corrective action taken as a result of such findings.

Anti-Bribery and Corruption

The Contractor shall and shall procure that persons associated with it (as defined in section 7 of the Bribery Act 2010) in connection with this contract shall:

Z8.1.1	comply with relevant Requirements and Relevant Policies;

Z8.1.2	 not engage in any activity, practice or conduct which would constitute an offence under sections 1, 2 or 6 of the Bribery Act 2010 if such activity, practice or conduct had been carried out in the UK;

Z8.1.3	not do, or omit to do, any act that will cause or lead NDA, the Client and/or the Contractor to be in breach of any of the relevant Requirements or Relevant Policies;

Z8.1.4	have and shall maintain in place throughout the term of this agreement its own policies,	procedures or processes, including but not limited to adequate procedures under the Bribery Act 2010, to ensure compliance with the relevant Requirements, the Relevant Policies and this Clause Z8, and will enforce them where appropriate;

Z8.1.5	promptly report to the Client any request or demand for any undue financial or other advantage of any kind received by the Contractor or any person working for or engaged by Contractor in connection with the performance of this contract;

Z8.1.6	if requested, other than in relation to a breach of this Clause Z8, provide NDA and/or the Client with any reasonable assistance, at the Contractor's reasonable cost, to enable NDA and/or the Client to perform any activity required by any relevant government or agency in any relevant jurisdiction for the purpose of compliance with any of the relevant Requirements or Relevant Policies;

Z8.1.7	within 30 days of the date of this contract, certify to the Client in writing signed by an officer of the Contractor compliance with this Clause Z8 by the Contractor.  The Contractor shall provide such supporting evidence of compliance that the Client may reasonably request.

The Contractor shall immediately notify NDA and the Client if, at any time during the term of this contract, its circumstances, knowledge or awareness changes such that it would not be able to comply with this Clause Z8.

If the Contractor notifies the Client that it suspects or knows that there may be a breach of Clause Z8, the Contractor must respond promptly to the Client's enquiries, co-operate with any investigation, and allow Client and/or NDA to audit books, records and any other relevant documentation.

ANTi-FACILITATION OF TAX EVASION

The Contractor does not engage in any activity, practice or conduct which would constitute either:

Z9.1.1	a UK tax evasion facilitation offence under section 45(5) of the Criminal Finances Act 2017; or

Z9.1.2	a foreign tax evasion facilitation offence under section 46(6) of the Criminal Finances Act 2017.

The Contractor:

Z9.2.1	has and maintains in place throughout the contract such policies and procedures as are both reasonable to prevent the facilitation of tax evasion by another person (including without limitation employees of the Contractor) and to ensure compliance with Clause Z9.1 above;

Z9.2.2	notifies the Client in writing if it becomes aware of any breach of Clause Z9.1 above or has reason to believe that it or any person associated with it has received a request or demand from a third party to facilitate the evasion of tax within the meaning of Part 3 of the Criminal Finances Act 2017, in connection with the performance of this contract; and

Z9.2.3	at such times as the Client may require, certifies to the Client in writing signed by an officer of the Contractor, compliance with Clause Z9 by the Contractor and by all persons associated with it as referred to in Clause Z9.3 below. The Contractor provides such supporting evidence of compliance as the Client may reasonably request

The Contractor ensures that any person associated with the Contractor who is performing any work or service or supplying any goods in connection with this contract does so only on the basis of a written contract which imposes on and secures from such person terms equivalent to those imposed on the Contractor in this Clause Z9. The Contractor is responsible for the observance and performance by such persons of such terms and shall be directly liable to the Client for any breach by such persons of any such terms.

For the purposes of this Clause Z9, the meaning of reasonable prevention procedure is determined in accordance with any guidance issued under section 47 of the Criminal Finances Act 2017 and a person associated with the Contractor includes any Supply Chain Member.

Data Protection

The Contractor shall comply at all times with the DPA or such other equivalent data protection legislation and shall not perform its obligations under this contract in such a way as to cause the Contractor, the Client or NDA to breach any of its obligations under the Data Protection Laws.

Subject to Clause Z10.5, for the purpose of this contract the Contractor is the Processor.

Appendix 2 to this Annex A to this contract describes:

Z10.3.1	the subject matter of the Processing;

Z10.3.2	the duration of the Processing;

Z10.3.3	the nature and purpose of the Processing;

Z10.3.4	the type of Personal Data being Processed; and

Z10.3.5	the categories of Data Subjects.

Notwithstanding the general obligation in Clause Z10.1, where the Contractor is Processing Personal Data as a Processor for the Client, the Contractor shall:

Z10.4.1	process the Personal Data only for the purpose of performing its obligations under this contract or otherwise on the instructions of the Client as authorised and set out under Appendix 2 of this Annex A by the Client (which may not be determined by the Contractor).  If the Contractor is required by law to act other than in accordance with the instructions of the Client, the Contractor shall promptly, and in any event within twenty-four (24) hours of becoming aware of the same, notify the Client;

Z10.4.2	ensure that it has in place Protective Measures, which are appropriate to protect against a Data Loss Event, which the Client may reasonably reject.  In the event of the Client reasonably rejecting Protective Measures put in place by the Contractor, the Contractor must propose alternative Protective Measures to the satisfaction of the Client.  Failure to reject shall not amount to approval by the Client of the adequacy of the Protective Measures.  Protective Measures must take account of the:

nature of the data to be protected;

harm that might result from a Data Loss Event;

state of technological development; and

cost of implementing any measures;

Z10.4.3	ensure that:

the Contractor Personnel do not process Personal Data except in accordance with this Agreement (and in particular Appendix 2 of this Annex A);

it takes all reasonable steps to ensure the reliability and integrity of any Contractor Personnel who have access to the Personal Data and ensure that they:

are aware of and comply with the Contractor's duties under this clause;

are subject to appropriate confidentiality undertakings with the Contractor or any Contractor acting as Sub-processor;

are informed of the confidential nature of the Personal Data and do not publish, disclose or divulge any of the Personal Data to any third party unless directed in writing to do so by the Client or as otherwise permitted by this contract; and

have undergone adequate training in the use, care, protection and handling of Personal Data;

Z10.4.4	not sub-contract any Processing of the Personal Data, replace an existing Subcontractor who is Processing the Personal Data or alter the scope or location of Processing carried out by an existing sub-contractor (a "Sub-Processing Change") unless all of the following have been met:

      - the Contractor has given the Client 60 days' written notice of the relevant Sub-Processing Change;

the Contractor has undertaken due diligence on the subcontractor with all due skill and care, including a risk assessment of the information governance related practices and processes of the sub-contractor and has established that the outcome of the due diligence is a determination that the subcontractor and the arrangements made for the sub-processing would objectively be adequate and sufficient to ensure compliance with the applicable requirements of the DPA, and has given notice of the outcome to the Client;

the Contractor provides the Client with such information regarding the sub-processing as the Client may reasonably require;

the Contractor undertakes to ensure that the sub-processing contract will be on terms that are substantially the same as the terms set out in this Clause Z8.3 (Data Protection);

the Client has not objected to the use of the Sub-processor within the 60 day notice period; and

the Contractor shall remain fully liable for all acts or omissions of any of its Sub-processors;

Z10.4.5	notify the Client immediately following its receipt of any request or notice from a Data Subject exercising their rights under the DPA (a "Data Subject Request") or any written correspondence or consultation from the UK Information Commissioner's Office ("ICO Correspondence"), or any request from a third party for disclosure of Personal Data where compliance with such request is required or purported to be required by Law ("Third Party Request") and will:

      - provide full details and copies of the Data Subject Request, ICO Correspondence, or Third Party Request;

not disclose any Personal Data in response to any Data Subject Request or ICO Correspondence or Third Party Request without the consent of the Client;

provide the Client with full co-operation and assistance (including providing copies of all data held) as required by the Client (taking into account the timescales reasonably required by the Client) in relation to any such Data Subject Request, ICO Correspondence or Third Party Request;

Z10.4.6	at the end of the Agreement or otherwise where required by the Client in writing securely delete or return Personal Data and all copies of the Personal Data, except to the extent the Contractor is required to retain copies by any law;

Z10.4.7	taking into account the nature of the Processing, notify the Client immediately upon becoming aware of any actual or suspected breach of Clause Z10.4.2 and

      - `

fully assist the Client to make any notifications to the UK Information Commissioner's Office and affected Data Subjects; and

include the provision of further information to the Client as details become available;

Z10.4.8	provide the Client with full cooperation and assistance to ensure compliance with its obligations under the DPA including:

      - obligations relating to the security and integrity of the Personal Data; and

undertaking any data protection impact assessments (as required by the DPA and defined under the DPA) prior to commencing any Processing.  Such assistance may, at the discretion of the Client, include:

a systematic description of the envisaged Processing operations and the purpose of the Processing;

an assessment of the necessity and proportionality of the Processing operations in relation to the Services;

an assessment of the risks to the rights and freedoms of Data Subjects; and

the measures envisaged to address the risks, including safeguards, security measures and mechanisms to ensure the protection of Personal Data;

Z10.4.9	notify the Client immediately if it considers in its opinion any of the Contractor's instructions infringe the DPA;

Z10.4.10	maintain complete and accurate records and information to demonstrate its compliance with this Clause Z10.4;

Z10.4.11	not transfer any Personal Data outside of the UK except as permitted by the Client in writing and the following conditions are fulfilled:

      - the destination country has been recognised as adequate by the UK government in accordance with Article 45 UK GDPR or section 74 of the DPA;

the Client or the Contractor has provided appropriate safeguards in relation to the transfer (whether in accordance with UK GDPR Article 46 or section 75 DPA 2018) as determined by the Client;

the Data Subject has enforceable rights and effective legal remedies;

the Contractor complies with its obligations under Data Protection Laws by providing an appropriate level of protection to any Personal Data that is transferred (or, if it is not so bound, uses its best endeavours to assist the Client in meeting its obligations); and

the Contractor complies with any reasonable instructions notified to it in advance by the Client with respect to the Processing of the Personal Data;

Z10.4.12	allow for audits of its Processing activity by the Client or the Client's designated auditor.

Where the Client Processes the Contractor's Personal Data (in its capacity as a Controller) in order to administer the contract, the Client shall:

Z10.5.1	Process the Contractor's Personal Data for the purposes set out in Appendix 2 of this Annex A in accordance with the Client's privacy policy and the Data Protection Laws; and

Z10.5.2	where required to share the Contractor's Personal Data with its affiliates and other relevant parties, within or outside the country of origin, for the purposes set out in Appendix 2 of this Annex A, ensure that the sharing and use of the Contractor's Personal Data complies with the applicable Data Protection Laws.

Each Party shall designate its own data protection officer if required by Data Protection Laws.

Each of the Parties agree that where acting as a Controller for the purposes set out in Appendix 2 of this Annex A:

Z10.7.1	each Party shall make available to the other a copy of their applicable privacy policy and the receiving Party shall ensure that this policy is provided to the applicable Persons whose Personal Data has been shared with the other Party; and

Z10.7.2	ensure that all fair processing notices have been given (and/or, as applicable, consents obtained), including in relation to any Special Categories of Personal Data and/or Criminal Conviction Data, and are sufficient in scope to allow the Parties to comply with the obligations imposed under the Data Protection Laws.

The Parties agree to take account of any guidance issued by the UK Information Commissioner's Office.  The Client may upon giving the Contractor not less than 30 working days' notice amend this contract to ensure that it complies with any guidance issued by the UK Information Commissioner's Office.

Insurance

In Clause 83.1, at the beginning of the clause insert: "Subject to Clauses Z11.5 and Z11.8,".

Delete Clause 86.

The Client shall notify the Contractor of the relevant insurance arrangements put in place by NDA ("NDA Insurances"), including any information provided by NDA from time to time in respect of such NDA Insurances.  A letter of confirmation shall be provided by the NDA's broker after the annual insurance renewal which currently takes place on 1 April of each year, and the Client shall provide a copy upon the Contractor's request.

The Contractor shall comply with (and shall procure that its Subcontractors agree to comply with) any instructions issued by the Client from time to time in relation to the NDA Insurances, claims handling and other procedures relevant to this contract.

The Contractor shall, for contracts requiring construction all risks insurance:

Z11.5.1	not purchase insurance that duplicates NDA Insurances; and

Z11.5.2	consent to being composite insured under NDA Insurances the construction all risks policy and agree to comply with all the conditions of the construction all risks policy.

The Contractor shall arrange with a reputable insurer (for example only, a minimum B rated by Standard and Poor's) appropriate insurance cover to reflect the nature of the works to be performed (including, for the avoidance of doubt professional indemnity insurance) which must be kept in full force and effect for the period of this contract and for a minimum of twelve (12) years after Completion of the works.  Any cancellation of any insurance detailed in this Clause Z11 by the Contractor or insurer or any non-renewal must be notified to the Client immediately.

The Contractor shall notify the Client if any Subcontractor's employer's liability insurance, public liability insurance, motor insurance and/or property insurance policies contain an exclusion in respect of working on nuclear site, and shall procure that the relevant Subcontractor seeks an extension to the relevant policies.  All damage/injury caused by nuclear incidents should not be insured by the Contractor.

In Clause 83, the Insurance Table is amended to include the following additional insurances:

| - Insurance against / type of insurance required | - Minimum amount of cover or minimum limit of indemnity |
| --- | --- |
| - professional indemnity insurance | - £5million in the annual aggregate with round the clock reinstatements |
| - motor third party liability insurance | - as per minimum statutory requirements in the UK |
| - property damage to the property of the Contractor and Subcontractors caused by nuclear matters defined within section 7 of the Nuclear Installations Act 1965 | - to be maintained by the Client in accordance with Clause Z12 |

Without prejudice to Clause 84.1, the Client reserves the right to request copies of Contractor's insurance policies outlined in this Clause Z11 at any time.

All such Contractor's insurance policies, with the exception of any professional indemnity and motor liability insurance, shall contain a provision which obliges the insurers to indemnify Client in respect of claims made against them arising from the performance of the works by the Contractor.

NUCLEAR Liability

Pursuant to section 12(3A) of the Nuclear Installations Act 1965 ("the Act"), the Client and the Contractor agree as follows:

Z12.1.1	In the event of an occurrence involving nuclear matter as defined within section 7 of the Act, the Client shall be liable to the Contractor for damage to the property of the Contractor and / or the property of the Subcontractors which is located at Old Shore Road, Drigg, Holmbrook, Cumbria CA19 1XH for the purposes of the contract.

Z12.1.2	The liability in Clause Z12.1.1 shall be limited to liability for property damage as would otherwise exist if section 7(3) of the Act did not apply and claims under this Agreement for property damage shall be governed by the Act as if section 7(3) of the Act did not apply.  Furthermore, the Client shall only be liable under Clause Z12.1.1 to the extent that the Contractor has used reasonable endeavours to mitigate its losses under Clause Z12.1.1 and provided further that any losses that the Contractor has incurred under Clause Z12.1.1 are reasonably foreseeable.

Z12.1.3	The Client shall not be liable under Clause Z12.1.1 unless and to the extent that the Contractor has notified the Client and NDA of:

the estimated value of the Contractor's plant, equipment and assets and any such plant, equipment and assets of its Subcontractors brought onto Old Shore Road, Drigg, Holmbrook, Cumbria CA19 1XH on an annual basis for the purposes of the contract in accordance with the NDA's insurance renewal requirements, provided always that such notification shall only be required where the estimated value is in excess of £1,000,000; and

where the value of such property has changed by (20%) or more during any one (1) year.

Z12.1.4	The liability in Clause Z12.1.1 shall be limited to the market value of the property, taking account of its age and condition, notified in writing pursuant to Clause Z12.1.3 above.

Z12.1.5	The Client shall not be liable under Clause Z12.1.1 to the extent that the occurrence involving nuclear matter was attributable to any act or omission of the Contractor or any employee, servant or agent of the Contractor, or the Subcontractor or any employee, servant or agent of the Subcontractor done with the intent to cause injury or damage or done with reckless disregard for the consequences of the act or omission.

Nothing in this contract is or shall be deemed to be an agreement for the Contractor to incur liability under Section 12(3A) of the Act.

Agreements with trade unions or other bodies representing employees

The Contractor shall comply with the terms of all agreements which the Contractor has entered into with trade unions or other bodies representing the employees of the Contractor which relate to those employees of the Contractor.

PROMPT PAYMENT

The Contractor shall ensure that each amount to be paid to a Subcontractor pursuant to a subcontract shall be paid no later than:

- 30 days after receipt of a valid and undisputed invoice; or

- where under any other provision of the subcontract that amount is payable on an earlier date, in accordance with that other provision.

The Contractor shall consider and verify invoices submitted by Subcontractors in a timely fashion, and for the purposes of Clause Z14.1, undue delay in considering and verifying invoices is not sufficient justification for failing to regard an invoice as valid and undisputed.

The Contractor shall ensure that the payment terms in any subcontract that is a construction contract, as defined in the Housing Grants, Construction and Regeneration Act 1996 (as amended), comply with the requirements of that legislation.

The Contractor shall include provisions equivalent to this Clause Z14 in each subcontract, and shall require Subcontractors to include the same provision in each sub-subcontract.

Nothing in this Clause Z14 overrides any provision of this contract relating to payment to the Contractor following termination of this contract or termination of the Contractor's obligations under this contract by reason of any breach or failure on the part of the Contractor.

DISALLOWED COST

Disallowed Cost shall, in addition to the costs defined in Clause 11.2(26), include those costs set out in Appendix 1.

The Contractor shall ensure that principles rendering costs as Disallowed Costs in accordance with Clause Z15.1 above are incorporated (where applicable) into each and every subcontract.

Modern Slavery Act 2015

In performing its obligations under this contract, Contractor shall:

Z16.1.1  comply with all applicable anti-slavery and human trafficking laws, statutes, regulations and codes from time to time in force including the Modern Slavery Act 2015;

Z16.1.2 have and maintain throughout the term its own policies and procedures to ensure their compliance;

Z16.1.3 not engage in any activity, practice or conduct that would constitute an offence under sections 1, 2 or 4, of the Modern Slavery Act 2015 if such activity, practice or conduct were carried out in the United Kingdom; and

Z16.1.4 include in its contracts with its Subcontractors and suppliers anti-slavery and human trafficking provisions that are at least as onerous as those set out in this Clause Z16.1.

The Contractor represents, warrants and undertakes that neither it nor any of its officers, employees or other persons associated with it:

Z16.2.1 has been convicted of any offence involving slavery and human trafficking; and

Z16.2.2 has been or is the subject of any investigation, inquiry or enforcement proceedings by any governmental, administrative or regulatory body regarding any offence or alleged offence of or in connection with slavery and human trafficking.

The Contractor shall implement due diligence procedures for its Subcontractors, suppliers and other participants in its supply chains, to ensure that there is no slavery or human trafficking in its supply chains.

The Contractor shall immediately notify the NDA and the Client if, at any time during the term of this contract, it becomes aware of a breach of its obligations in this Clause Z16.

intellectual property

Delete Clause 22.1 and insert "Not used."

The copyright in the Contractor's Documents shall remain vested in the Contractor, but the Contractor hereby grants to the Client and NDA an irrevocable, royalty-free, non-exclusive licence to copy, use and reproduce the Contractor's Documents and the Intellectual Property Rights contained therein for any and all purposes relating to this contract, the works, the Site and/or any other sites owned or operated by any Client's Affiliates.  The licence includes the right to grant sub-licences in the terms of this licence and is freely assignable without the Contractor's consent.  The Contractor shall procure from its Subcontractors and sub-Subcontractors equivalent rights for the Client to use Contractor's Documents prepared by the Subcontractors and sub-Subcontractors.

The Contractor unconditionally and irrevocably waives and shall procure that its Subcontractors and sub-Subcontractors unconditionally and irrevocably waive such moral rights as may be conferred by Chapter IV of Part I of the Copyright Designs & Patents Act 1988 or other laws in force from time to time enacted conferring analogous rights.

The Contractor warrants that it has not infringed and will not infringe the Intellectual Property Rights of any third parties to Provide the Works and shall indemnify and hold harmless the Client against and from any and all claims, liability, losses, damages, costs and expenses (including legal costs) arising out of a breach of this warranty.

The Contractor is not responsible for any loss resulting from use of the Contractor's Documents for any purpose which would have been beyond the reasonable contemplation of the Parties at the time at which it was prepared.

Confidentiality

Confidential Information

Subject to Clause Z17 and Clauses Z18.4 to Z19 (inclusive) below, each Party shall hold in confidence all documents, materials and other information, whether technical or commercial, supplied by or on behalf of the other Parties (including all documents and information supplied in the course of proceedings under the dispute resolution procedure of this contract) and all documents, materials and other information of any nature relating to a third party which it may acquire or have access to directly or indirectly and shall not, except with the written authority of the other Party, publish or otherwise disclose the same otherwise than as expressly provided for in this contract unless or until the recipient Party can demonstrate that any such document, material or information is in the public domain through no fault of its own and through no contravention of this contract, whereupon to the extent that it is in the public domain this obligation shall cease.

The Contractor shall not make use of this contract or any information issued or provided by or on behalf of the NDA and/or Client in connection with this contract otherwise than for the purpose of complying with its obligations under this contract and otherwise than as expressly provided for in this contract except with the written authority of the NDA and/or the Client.

The Contractor shall share information and know-how relating to the Authority Field of Use with the NDA and with third parties as directed by the NDA.

Disclosure by the Client

The Client may disclose without the consent of the Contractor, any and all information acquired by it under or pursuant to this contract save for information which is judged by the Office of Civil Nuclear Security ("OCNS") to be security sensitive (unless the recipient of information pursuant to this Clause Z18.4 holds all relevant security clearances) to:

- the Parliamentary Commissioner for Administration, a Minister of the Crown, any department of the government of the United Kingdom, the UK Parliament, the Scottish Parliament, the National Assembly of Wales, the Mayor of London, Greater London Authority or any department, officer, agent, representative, employee, consultant or adviser of any of them;

- the Regulators;

- the extent required by applicable Law or pursuant to an order of any court of competent jurisdiction or under the dispute resolution procedure;

- bidders who have pre-qualified to participate in any relevant forthcoming tender process, upon obtaining an undertaking of confidentiality equivalent to that contained in Clause Z18.1;

- insurers, upon obtaining an undertaking of confidentiality equivalent to that contained in Clause Z18.1;

- professional advisers, upon obtaining an undertaking of confidentiality equivalent to that contained in Clause Z18.1;

- to the National Audit Office; and/or

- consultees under the Energy Act 2004;

So far as is practicable, the Client and/or NDA gives the Contractor reasonable notice of any proposed disclosure pursuant to Clause Z18.4.

In deciding whether or not to disclose material or information the Client will have due regard to the provisions of the Energy Act 2004.  The Client's and/or the NDA decision to disclose material or information under Clause Z18.4 may not be challenged by the Contractor.

Notwithstanding the provisions of Clause Z18.1, the Client may with the consent of the Contractor not to be unreasonably withheld or delayed further disclose such information to persons not referred to in Clause Z18.4.  Any determination as to whether it is reasonable for the Contractor to withhold its consent to disclosure this Clause Z18.6 shall have regard to:

- compliance with the NDA's statutory functions and duties, including in particular the promotion of effective competition and value for money;

- relevant government policy;

- the requirement to maintain security;

- the public interest;

- the degree of commercial sensitivity of the information; and

- the requirement to maintain openness and transparency.

Contractor's right to request confidentiality

The Contractor may at any time request in writing, stating reasons, that the Client and/or the NDA keeps particular information confidential and does not disclose it to third parties.  The Contractor may further request in writing at any time that, where the Client discloses such confidential information, the Client shall make representations to the recipient of such information as to the desirability of keeping such information confidential.  Any such request by the Contractor shall be accompanied by a document setting out in writing the requested representations.  The Client shall consider whether to make such representations.

Publication

The Client may publish, in such form and at such times as it sees fit, the following (in relation to this contract and the Contractor's performance of it):

- amounts of payments to the Contractor under this contract and any reductions made from the Contractor under this contract;

- performance statistics;

- monitoring reports; and

- such information as the Client reasonably requires to publish having regard to the list of considerations set out in Clause Z18.7 above, including information it includes in its annual report.

Disclosure by the Contractor

The Contractor may disclose without the consent of the Client, any and all information acquired by it under or pursuant to this contract save for information which is judged by OCNS to be security sensitive (unless the recipient of information pursuant to this Clause Z18.9 holds all relevant security clearances) to:

- any department, officer, agent, representative, employee, consultant or adviser of any of the entities referred to in this Clause Z18.9 subject, in any case where the entity in question would be required to provide an undertaking of confidentiality equivalent to that contained in Clause Z18.1;

- the Regulators;

- insurers upon obtaining an undertaking of confidentiality from any such supplier and insurer equivalent to that contained in Clause Z18.1;

- professional advisers, upon obtaining an undertaking of confidentiality from any such supplier and insurer equivalent to that contained in Clause Z18.1;

- Subcontractors, provided an undertaking of confidentiality equivalent to that contained in Clause Z18.1 is obtained, except that such an undertaking shall not be required where and to the extent that it is necessary to disclose information for the purpose of advertising subcontract opportunities on Contracts Finder under Clause Error! Reference source not found.;

- the extent required by parliamentary obligation, applicable Law or pursuant to an order of any court of competent jurisdiction or under the dispute resolution procedure.

Damages not the only remedy

Without prejudice to any other rights or remedies that the Client and/or NDA may have, the Parties acknowledge and agree that damages alone would not be an adequate remedy for any breach by the Contractor of this Clause Z17.5 and that the remedies of injunction and specific performance as well as any other equitable relief for any threatened or actual breach of this Clause Z17.5 by the Contractor would be more appropriate remedies.

National Audit Office

The Parties acknowledge and agree that the National Audit Office has the right to publish details of this contract (including information considered by the Parties to be commercially sensitive) in its relevant reports to Parliament.

Delivery Up

On expiry or termination of this contract, the Contractor shall ensure or procure that the Contractor Personnel return to the Client or the NDA (as applicable) all documents, materials or any information which is confidential (in accordance with Clause Z17.5) belonging to the Client or the NDA.

Publicity

A Party shall notify the other Party as soon as reasonably practicable of any fact or occurrence of which the notifying Party is aware relating to the NDA, the Client, or the Contractor which could in the reasonable opinion of the notifying Party be expected to cause adverse publicity to the Contractor or the Client in relation to this contract or to the NDA generally.

Subject to the remaining provisions of this Clause Z21.2, no Party shall release any announcement or despatch any announcement or circular, relating to this contract unless the form and content of such announcement or circular have been submitted to, and agreed by, the other Party.

Nothing in Clause Z21.2 shall prohibit any Party from making any announcement or despatching any circular as required by law or the rules of the UK Listing Authority or of the London Stock Exchange or any other regulatory body in which case, to the extent not inconsistent with legal obligations or the rules of the UK Listing Authority or of the London Stock Exchange, the announcement shall only be released or the circular despatched after consultation with the other Party and after taking into account the reasonable requirements of the other Party as to the content of such announcement or circular.

records and performance management

The Contractor retains and makes available to the Client copies of the following records, in a form acceptable to the Client (acting reasonably, which may for the avoidance of doubt include a requirement that records are provided in native electronic format and are searchable):

- all statutory and regulatory records and reports required to be kept by the Contractor in connection with this contract;

- books of account and other information consistent with an open book system (including without limitation all invoices in respect of labour, Plant and Materials, all labour and time records and time-sheets);

- the following records to demonstrate Fee, Defined Cost, Price for Work Done to Date claims or compensation events;

- all necessary information for the evaluation of Fee, Defined Cost, Price for Work Done to Date claims or compensation events, whether or not relating to Subcontractors;

- management accounts, information from management information systems and any other management records;

- accounting records (in hard copy as well as computer readable data);

- subcontract files (including proposals of successful and unsuccessful bidders, bids, rebids, etc.);

- original estimates;

- estimating worksheets;

- correspondences;

- compensation event files (including documentation covering negotiated settlements);

- schedules including capital works costs, timetable and progress towards Completion;

- general ledger entries detailing cash and trade discounts and rebates;

- commitments (agreements and leases) greater than £5,000 (five thousand pounds);

- detailed inspection records;

- materials prepared in relation to the invitation to tender and subsequent tendering process relating to cost breakdowns which have not already been provided to the Client;

- technical data, including drawings, designs and any other relevant technical information;

- accounts and records of the Price for Work Done to Date and all other amounts to be paid to the Contractor under this contract; and

- such other information as would normally be expected to be created, received and maintained as evidence and information by an organisation or person carrying on the business of the Contractor in pursuance of legal obligations or in the transaction of business and which may be reasonably required from time to time:

by the Client; or

by the NDA in order to comply with the NDA's statutory functions and/or duties,

(together the "Records"), provided that if Option A or Option B applies, the Records shall not include any pricing information other than in relation to the assessment of Compensation Events.

The Records shall be retained:

- and made available in accordance with the open book principles set out clauses Z22.3 and Z22.4:

- in a condition, in a format and in such detail as ensures that they are suitable for their intended purpose; and

- for the period specified in clause Z22.5 below.

The Contractor undertakes their obligations and exercises any rights which relate to the performance of this contract on an open-book basis.  The Contractor ensures that their Subcontractors undertake their obligations on an open book basis.

The Contractor allows the Client, Project Manager, Supervisor and their agents to have rights' of access, inspection and audit over the Records; they may visit the offices of the Contractor within the normal working hours to inspect and copy such records.  The Contractor maintains copies of such records at the Site or by prior agreement from the Client at the Contractor's office for inspection by the Client, Project Manager, Supervisor and their agents.  The Client's rights pursuant to this sub-clause include the right to audit and check, and to take copies of and extracts from, any document or record of the Contractor or its Subcontractors, including (without limitation) records outlined in this clause Z22.4.

Retention of Records

The Contractor shall retain all Records for either:

- a period of twelve (12) years after the expiry or earlier termination of this contract or such longer period as may be required by applicable Law or Regulatory Requirement; or

- in relation to certain Records as identified by the NDA and notified to the Contractor by the Client from time to time, for such longer period as may reasonably be required by the NDA.

The Contractor ensures the back-up and storage in safe custody of all electronic data, material and documents required to be maintained and retained under the contract in accordance with the Client's internal procedures relating to records and data management as notified to the Contractor from time to time

Flowdown of Terms

Subject to Clauses Z23.2 and Z23.3, Nuclear Waste Services shall require all of Clauses 0 to Z22 (inclusive) to be incorporated into any subcontracts

Without prejudice to Clause Z23.3, Clause Z23.1 shall not apply in respect of any subcontracts and sub-subcontracts which have a value of less than the threshold amount applicable to contracts of the same type under Regulation 5 of Public Contracts Regulations 2015 (notwithstanding whether or not such subcontract or sub-subcontract actually falls within the scope of the Public Contracts Regulations 2015).

The Contractor shall ensure that all subcontracts and sub-subcontracts shall incorporate the contractual provisions set out in Clauses Z8 (Anti-bribery and Corruption), Z16 (Modern Slavery Act 2015), Z18 (Confidentiality) and Z22 (Records and Performance Management).

# CIS reqUIREments

# PF08-PR08-01-F006

# John Graham Construction Ltd

INTRODUCTION

As a sub-contractor you are engaged to provide your services on the specific understanding that you are an independent contractor/sub-contractor. You also understand and confirm to and agree that any payment made to you under this contract falls to be taxed under the legislation covering the Construction Industry Scheme (CIS). Signing this subcontract means that you understand and accept that we, John Graham Construction Ltd (JGCL), will operate the CIS scheme as required to do so by law. You are advised to make yourself aware of both your own and our requirements.

The main terms of your engagement are covered by contract agreement included with this declaration. This Schedule only highlights the way in which we will administer your payments with regard to CIS.

The purpose of this declaration is to highlight important aspects of the CIS scheme which may impact on your payments and how JGCL are required by law to consider the appropriate tax treatment of these issues.

LABOUR

Labour on site shall not be deducted when calculating your CIS liability for tax.

Labour used for off-site fabrication shall be deducted however the cost of this must be proven. Where no evidence is provided JGCL shall estimate the cost and deduct this from your application prior to calculation of tax due.

MATERIALS

When claiming material costs you must provide evidence of the cost incurred before an application for payment is approved.

Where no suitable evidence is provided the legislation allows JGCL to estimate the cost of materials to deduct from the application for payment prior to the calculation of tax due.

PLANT & MACHINERY HIRED FROM THIRD PARTIES

Where you have to hire plant from a third party in order to carry out construction work, the cost of the plant hire and any consumable items such as fuel needed for its operation may be treated as materials for the purposes of calculating any deduction when calculating CIS deductions.

Note that this treatment only extends to plant and equipment actually hired by the subcontractor from a third party.

PLANT & MACHINERY OWNED BY THE SUBCONTRACTOR

If the subcontractor owns the plant employed in executing the work no 'notional' deduction for plant hire may be made.

If you are leasing and / or have Hirer Purchase arrangements and / or have purchased plant and machinery by way of loans then these costs shall not be deducted from any monies due when calculating CIS deductions.

CONSUMABLES FOR PLANT & MACHINERY OWNED BY THE SUBCONTRACTOR

Any consumables such as fuel, oil and hydraulic fluids may be treated as a deduction before the calculation of CIS tax.

Where the amounts seem excessive we may ask for proof. If proof is not forthcoming we shall estimate the cost.

SCAFFOLDING

The erection of scaffold where the men are provided with the scaffold falls within CIS.

However please note the following –

i	a deduction for the scaffold costs shall be allowed where the scaffold has been hired by the sub-contractor specifically for this job and these costs are proven;

ii	If you are leasing and / or have Hirer Purchase arrangements and / or have purchased scaffolding by way of loans then these costs shall not be deducted from any monies due when calculating CIS deductions.

TRAVEL EXPENSES

Travel expenses incurred by the sub-contractor when getting to and from site or from site to different site cannot be excluded from the CIS tax calculation. If they are paid, then they must be taxed in the normal way. It will be for the sub-contractor to claim relief for these costs in his personal tax return.

IN SUMMARY

It will be up to the individual sub-contractor to resolve any issues regarding Construction Industry Scheme deductions made directly with H M Revenue & Customs at the point of self-assessment.

We will calculate your tax deduction from the information which you are to provide or by our own estimate. The provision of all required information will assist this process.

List of Appendices

…………………………………………………………………………………………………………………………………...