# Expression of interest

# Title: Education Technology (EdTech) Survey 2020

Project reference: DFE/RPPU/2019/030

Deadline for expressions of interest: 23.59 Thursday 23 July 2020

## Summary

Expressions of interest are sought to conduct an Education Technology (EdTech) Survey, which will collect robust evidence on the current state of technology in schools in England to help inform policy development and delivery of initiatives announced in the EdTech Strategy, Realising the potential for technology in education, as well as COVID-19 response activity and next steps.

The expression of interest was posted Friday 10 July 2020.

## Background

The recently published EdTech Strategy, Realising the potential of technology in education, highlights DfE’s commitment to tackle the barriers to effective technology adoption and use, whilst also supporting the growth of the EdTech sector in ways that help ensure the EdTech industry meet the needs of education leaders and teachers. The commitments in the strategy are currently backed by £10million over the 2019/2020 and 2020/2021 financial years, and many have been accelerated to support the Government COVID-19 response.

This includes funding to support:

- A series of demonstrator schools and colleges to showcase best practice and provide peer-to-peer support for schools that want help implementing and using technology, including to support remote teaching strategies.

- Testbed activity designed to build evidence on the impact of technology on schools and colleges, including the impact ithas on different remote teaching strategies.

- An EdTech Innovation Fund programme enabling companies to align their product development to teacher, leader and pupil needs.

To support the success of these commitments, we are also taking several actions to enable schools and colleges to use technology effectively, including:

- Helping schools to secure the broadband and networking infrastructure they need through accelerating the roll-out of full fibre internet connectivity to schools and providing guidance.

- Supporting initiatives for teachers and school leaders to improve their skills and knowledge about good use of technology through creating greater opportunities for peer-to-peer learning and through supporting free online CPD courses developed by the Chartered College

- Improving support for procurement of technology, including through pre-negotiated buying deals

- Helping education providers and the technology industry understand the privacy, security and data guidance and standards they should adhere to.

## Evaluation aims

The aims of the project are to:

- Understand the current landscape of technology in schools in England, including state, type, use and spread of technology;

- Explore attititudes and perceptions of technology in education among teachers and headteachers;

- Explore the demands and needs of teachers when it comes to technology in education;

- Explore barriers to effective technology adoption in schools;

- Measure and monitor the impact of the EdTech Strategy and COVID-19 response related activity

This will help DfE build on the EdTech Strategy by helping us:

- Understand what more can be done to support schools to reap the benefits of technology;

- Iterate the focus of peer to peer support and research programmes;

- Inform future initiaves and EdTech policy post-COVID-19

We have allocated a budget of up to £90k to complete this work.

Methodology

We require a random probability survey of maintained primary and secondary schools in England. The survey should enable us to detect statistically significant differences (95% confidence level)  –

- Between primary and secondary schools

- Between headteachers and teachers

- We anticipate that the survey will be stratified by region and school type. The design should enable us to detect statistically significant differences over time so that we can monitor progress on key indicators.

- The survey will require completion by teachers, headteachers and business managers at each institution so we anticipate an online mode of collection. The multi-respondent approach has been tested with a survey of colleges undertaken in 2019; the learning from this will inform the final design for the school survey. A draft questionnaire – largely replicating questions that will have been tested (with colleges) in the field - will be available, but will require cognitive testing and piloting with schools. We expect to appoint the successful contractor in early September, with fieldwork taking place between October and December 2020.

- We will require a draft report of headline/key findings in January 2021 and a final report by March 2021. We will also require interim findings on a small number of key variables mid-way through the fieldwork period to inform policy.

## Timing

- Deadline for EOIs – 23.59 Thursday 23 July 2020

- Review EOIs – 27-31 July 2020

- Invitations to Tender (ITT) issued  –  Friday 1 August 2020 (provisional)

- Deadline for ITT – 23.59 Thursday 28 August 2020 (provisional)

The research project is expected to run from September 2020 to March 2021.

## Assessment criteria

Expressions of interest will be assessed against the following criteria:

- An understanding of the Department’s requirements, and demonstration of knowledge of the issues surrounding technology in schools

- Evidence of experience and technical ability in designing, conducting, analysing and reporting a large-scale probability survey

- Evidence of organisational capacity and project management skills to deliver the project in the specified timescales

Scoring

- No evidence/very poor

- Poor evidence

- Some evidence

- Good evidence

- Excellent evidence

Expressions of interests submitted must be no more than 1500 words overall; this includes any website links. Anything longer will be disregarded.

Closing date for EOIs: 23.59 Thursday 23 July 2020 Send your EOI form to: edtech.team@education.gov.uk and cc: helen.connolly@education.gov.uk

## How to submit an expressions of interest

You must submit an expression of interest (EOI) in order to be considered to be invited to tender. To do so, please complete the ‘EOI Form 2018’ which can be found under attachments in the ContractsFinder listing. A submission of an EOI does not guarantee an invitation to tender and the Department does not routinely advise organisations that they have not been successful in being invited to tender. Feedback is however available on request.

All contracts are let on the basis of the Depatrtment’s Terms & Conditions, a copy is available attached to the ContractsFinder listing. You are encouraged to check these before submitting your expression of interest, as these form part of your contractual obligations.

© Crown copyright 2020