Order Schedule 20 (Order Specification)

This Schedule sets out the characteristics of the Deliverables that the Supplier Fill be required to make to the Buyers under this Order Contract.

As issued at tender

# PURPOSE

  - The UK Covid-19 Inquiry (the Inquiry) requires a systematic review to assess changes to the mental health and wellbeing of the general population between March 2020 and June 2022 across the UK. This will be considered, wherever possible, in comparison to levels and trends immediately prior to the pandemic. It will also include consideration of the impact on specific groups in society, and any risk and protective factors for changes in mental health and wellbeing during the pandemic.

  - The project will include reporting of this review, which the Inquiry expects to submit as evidence to its hearings. This requires involvement of an expert who, at a minimum, would act as a consultant for the review and who could interpret and speak to the findings in hearings.

# BACKGROUND TO THE BUYER

  - The Buyer for this requirement is the Cabinet Office, in its capacity as the sponsor department for the UK Covid-19 Inquiry.

  - The UK Covid-19 Inquiry is an independent public inquiry examining the UK’s preparedness and response to the Covid-19 pandemic, and to learn lessons for the future.

  - The Inquiry is independent of the government and Ministers as set out in the Inquiries Act 2005.

# BACKGROUND	TO	REQUIREMENT/OVERVIEW	OF REQUIREMENT

  - The terms of reference for the Inquiry require the examination of the impact of the pandemic on the UK. A key component of this requires the Inquiry to examine “the impact on the mental health and wellbeing of the population, including but not limited to those who were harmed significantly by the pandemic.” Given the complexity of this topic and the challenges in measuring these phenomena at the level of whole populations, a crucial source of evidence for the Inquiry comes from scientific research.

  - The Inquiry is aware that the topic of mental health and wellbeing in the pandemic has been a very substantial area of scientific enquiry, with a large number of studies published. The Inquiry will benefit from a systematic review of this literature to provide an authoritative account of particular questions of interest.

  - Although other systematic reviews have been conducted — such as those on mental health changes in Europe during the pandemic, review on cohort studies, and the prevalence of anxiety and depression during Spring 2020 – the Inquiry requires a more comprehensive evidence review of both mental health and wellbeing, for the period March 2020 to June 2022, which captures any differences seen across groups in society and the risk and protective factors associated with changes in mental health over this period.

# DEFINITIONS

| Expression or Acronym | Definition |
| --- | --- |
| Core Participants | means a person, institution or organisation that has a specific interest in the work of the Inquiry, and has a formal role defined by legislation. Core Participants have special rights in the Inquiry process. These include receiving documentation, being represented and making legal submissions, suggesting questions and receiving advance notice of the Inquiry’s report. |
| The Inquiry | means the UK Covid-19 Inquiry. |
| Supplier | means the supplier (or suppliers) of services for this contract |

# SCOPE OF REQUIREMENT

  - The Inquiry requires a supplier to provide all of the following services for a robust systematic review.

  - The systematic review needs to:

    - Design the protocol and search strategy to answer all research questions

    - Use a systematic approach to searching and assessing the literature that is to be used. This should be transparent and well documented.

    - Develop and apply a clear set of criteria for assessing robustness and quality appraisal. Studies should be weighted based on this.

    - Extract data, analyse and synthesise the available evidence appropriately.

    - Determine and apply a structure for the final report which is both true to the findings of the review and easily accessible to non-specialist users.

    - Identify and document any evidence gaps and/or limitations with the methodology employed.

    - Distil the findings and themes into headline findings, so as to be easily usable to inform the work of the Inquiry.

  - As a minimum, the outputs will be:

    - A final report, written and structured for publication and to be adduced in hearings. The Inquiry would expect to review and comment on at least two drafts of this prior to agreeing a final version.

    - A technical appendix providing a clear statement of the methodology used.

    - If required by the Inquiry legal team, a senior member of the research team to attend one day of hearings to answer questions about the work.

  - The Supplier will have an appropriate team who are able to complete the work within the specified timeframe(s) and who have some prior knowledge of the topic. We require the project team to include a subject matter expert who, at a minimum, would act as a consultant for the review and who could interpret and speak to the findings in hearings.

  - The Inquiry will own the Intellectual Property Rights on all reports and outputs it has commissioned from any contract awarded via this tendering exercise, The Contracting Authority will have free and unencumbered usage of all such reports and outputs.

# THE REQUIREMENT

  - The Supplier is required to conduct a systematic review of evidence on changes to mental health and wellbeing during the pandemic (March 2020 to June 2022) in the UK. The Supplier will be expected to address the following research questions:

    - How did the general adult population's mental health and wellbeing change during the pandemic, if at all, compared to pre-pandemic trends?

    - What were the risk and protective factors for changes in mental health and wellbeing during the pandemic, relative to pre-pandemic trajectories? This is to include where available:

        - Behaviours/activities that have adaptive function to mental health such as physical activity levels, participation in cultural activities and participation in religious worship

        - Differences between occupations (including key workers)

        - Differences by equality characteristics, including clinical vulnerability and socioeconomic status

        - Differences by housing and residential status, incl. for individuals living alone or experiencing overcrowding

        - Specific vulnerable populations: people experiencing homelessness, people in prisons, and immigration detention centres, or people with severe mental illness

## Research Design

The supplier must develop detailed research plans covering all stages of the 	project, agreeing with the Inquiry a timetable and risk register.

### Methodology

    - The research design will be a systematic evidence review. The supplier will design all stages of the systematic review including: protocol and scope, search criteria, quality assessment, synthesis strategy and analysis.

    - The supplier will be responsible for following the Preferred Reporting Items for Systematic reviews and Meta-Analyses (PRISMA) guidelines and registering the protocol accordingly.

    - Clear inclusion/exclusion criteria should also be used and documented at the outset of the review, to appraise studies, and should be included in the final report, along with highlighted quality criteria. The Inquiry will have sight of these proposed criteria at an early stage for approval.

    - The review will examine differences in mental health trends by equality characteristics and for key workers, where relevant evidence is available. The review should focus, where possible, on key workers other than health and social care workers, as the mental health impact on these workers is being covered in earlier parts of the Inquiry.

    - Unless stated otherwise, the relationship between the following characteristics and changes in mental health and wellbeing is to be examined where possible.

        - Age - differences across the full adult age spectrum are to be assessed. (Note: This review will not include studies that only look at young people’s mental health, as this is a topic of investigation for another element of the Inquiry.)

        - Disability - where possible, differences between types or severity of disability are to be examined.

        - Sex

        - Race - differences between specific ethnicities are to be examined where possible.

        - Pregnancy and maternity

        - Gender reassignment

        - Religion or belief

        - Sexual orientation

        - Socioeconomic status - including household earnings and area-based deprivation.

        - Geographical differences - for instance, by nation, by region, by rurality.

        - Clinically vulnerable and clinically extremely vulnerable - both for the respondent and whether someone who met such criteria lived in the same home.

        - Occupation - key workers and employment-related factors. These could include factors such as seasonal working, employment status (zero-hours, self-employed, gig economy, part time vs full time, in-person, remote working) if information is available.

        - Immigration status

        - Carer for a dependent person (child, person with a disability or elderly person for example)

    - This is a broad topic and wellbeing and mental health can be characterised in different ways. The review will focus on self-reported survey data capturing validated measures of general mental health and common mental health disorders. For wellbeing, the Supplier should use measures which have been tested for comprehension and reliability. By common mental health disorders, the Inquiry means depression and anxiety in the first instance. The Supplier will consider broader measures, including a wider range of disorders, according to what is feasible.

    - The following criteria should be applied to include only those studies which:

      - Use validated measures for general mental health or individual common mental health disorders (depression and anxiety in the first instance), or which use validated wellbeing measures.

      - Changes over time and between groups are subjected to statistical tests, allowing inference as to whether patterns observed are likely to have arisen by chance or whether they likely represent a pattern at the population level.

      - The study uses data collected consistently and contemporaneously, thereby allowing comparison over time and without risk of recall bias.

    - In the event there is ample evidence on a particular research question(s) the following should be prioritised:

      - Pre-pandemic trends and seasonality are accounted for.

      - Surveys that employ probability-based sampling and/or other characteristics which increase the confidence that findings can be generalised to the population of interest.

      - Surveys that were conducted nationally and are intended to capture the general population as a whole. Surveys of specific groups (e.g. occupation/sector specific) may be considered, but we suggest these findings are reported separately.

      - Studies that capture a broad range of ages are to be prioritised in analysis, unless there are convincing reasons to include age-specific studies.

    - The Supplier should exclude studies that focus exclusively on mental health or wellbeing for the following groups, as they are being considered by other modules of the Inquiry:

        - those under the age of 25

        - those with dementia

        - those with intellectual disabilities

        - health and social care workers

    - The Buyer will need to review and approve the protocol and scope, search criteria, quality assessment, and synthesis strategy before the Supplier begins subsequent activity.

    - Notwithstanding the Inquiry’s interest in the scope set out above, given the relevance of some existing published systematic reviews the Inquiry encourages bidders to consider any approaches that may build on existing work to maximise efficiencies and value for money. For instance updating aspects of previous searches using pre-existing search terms and inclusion/exclusion criteria. (Example existing review: Ahmed et al 2023.)

### Project management

    - The Supplier needs to provide overall project management including management of any subcontractors. The lead Supplier is accountable for the quality and timeliness of deliverables for this contract.

    - The Supplier will provide a detailed and comprehensive timetable that sets out milestones, deadlines and what activities are due to take place and by who. The Supplier will also produce a detailed and tailored risk register at the outset of the contract. Both the timetable and risk register will be updated at least monthly and discussed at monthly contract performance calls (see section 8).

### Reporting

    - The Supplier will extract data, analyse and synthesise the available evidence appropriately, presenting it in an engaging manner.

    - The Supplier will produce two written outputs:

      - A detailed written report that presents the findings of the review, structured in accordance with the research questions of interest. Study quality criteria/grading will be explained with implications set out for a general audience. The report will include a bibliography of studies used. The report will contain an executive summary that is highly accessible to the general public.

      - A technical appendix containing information on the search strategy, quality criteria, analytical methods, limitations, and a full list of included and excluded studies.

    - The Inquiry considers that the full report and executive summary of the Royal Society’s systematic review into the effectiveness of non-pharmaceutical interventions represent good examples of the style required. Visual aids or graphs should be easily understood by a non-specialist audience and appropriately labelled.

    - The Supplier will submit a final report after two reviews by the Inquiry.

    - The project team must include a subject matter expert who will act as a consultant for the review and present the report and give evidence during hearings.

# KEY MILESTONES AND DELIVERABLES

  - The following Contract milestones/deliverables shall apply:

| Milestone / Deliverable | Description | Timeframe or Delivery Date |
| --- | --- | --- |
| 1 Research plan (inc. timetable) | Supplier must provide the Inquiry with a high-level plan for the whole research project, including protocol, searches, quality appraisal, data extraction, analysis and output delivery. | Within week 2 of Contract Award |
| 2 Protocol finalised | Supplier must finalise the protocol after review from the Inquiry | March 2025 |
| 3 Searches and quality assessment | Searches, screening, quality appraisal of studies completed by the Supplier | May 2025 |
| 4 First draft of report | Supplier to complete data extraction, analysis and provide the Inquiry with a draft version of the final report | June 2025 |
| 5 Final, signed off report | Supplier to provide the Inquiry with final, publishable draft after two rounds of comments from the Inquiry team. | August 2025 |

# MANAGEMENT INFORMATION/REPORTING

  - The Inquiry will provide the Supplier with a governance structure of meetings, escalation routes, and processes.

  - The types and frequency of monitoring should include:

Weekly tracking of:

      - Search design and quality criteria (until fixed)

      - Short-term timetable

      - Emerging themes (once available)

Monthly performance meetings between Supplier and Inquiry, which will require the supplier to provide reporting and monitoring of:

      - Full project timetable

      - Risk register

# VOLUMES

  - REDACTED TEXT under FOIA Section 43 Commercial Interests

  - The review should be conducted in line with PRISMA guidelines.

# CONTINUOUS IMPROVEMENT

  - The Supplier will be expected to continually improve the way in which the required Services are to be delivered throughout the Contract duration.

  - The Supplier should present new ways of working to the Authority during monthly Contract review meetings.

  - Changes to the way in which the Services are to be delivered must be brought to the Authority’s attention and agreed prior to any changes being implemented.

# SOCIAL VALUE AND SUSTAINABILITY

  - Social value will not be evaluated.

# QUALITY

  - The overall quality of outputs will be assessed by a committee with attendance from the Inquiry’s research team and module legal team.

  - PRISMA guidelines must be followed as per section 6.3.2 and the protocol must be registered accordingly e.g. on PROSPERO.

  - Specific additional metrics that we will judge quality by are outlined in section 7 ’key performance indicators’.

# PRICE

  - The pricing of the contract will contain fixed and variable cost elements for research design, analysis, report writing, and progress reporting to the Inquiry team. See attachment 4 – ‘Price Schedule’ for further details.

  - Prices are to be submitted via the e-Sourcing Suite Attachment 4 – Price Schedule excluding VAT and including all other expenses relating to Contract delivery.

  - Please provide full costs in the Price Schedule for all elements of the research included in your bid.

  - Failure to do so will mean you will need to deliver your proposed research approach within the costs outlined in your Pricing Model and be evaluated as part of the commercial envelope.

# STAFF AND CUSTOMER SERVICE

  - The Supplier shall provide a sufficient level of resource throughout the duration of the Contract in order to consistently deliver a quality service.

  - The project team must include a subject matter expert who will, at a minimum, act as a consultant for the review and interpret findings during hearings. This expert should have adequate knowledge of the topic and research design to address questions and interpret results for a non-specialist audience. The expert must not have participated in the government’s pandemic response (e.g., by advising the government) and must not have a public 'party political' profile, including publicly supporting or criticising any political party issues.

  - The Supplier’s staff assigned to the Contract shall have the relevant qualifications and experience to deliver the Contract to the required standard.

  - The Supplier shall ensure that staff understand the Authority’s vision and objectives and will provide excellent customer service to the Authority throughout the duration of the Contract.

# SERVICE LEVELS AND PERFORMANCE

  - The Inquiry will measure the quality of the Supplier’s delivery by responsiveness to urgent and non-urgent email requests. See the below table for details.

| KPI/ SLA | Service Area | KPI/SLA description | Target |
| --- | --- | --- | --- |
| 1 | Responsiveness | Supplier must respond to email requests from the Inquiry Key Staff* marked URGENT within 1 working day. *The list of those defined as key staff can be found in the Order Form | 95% |
| 2 | Responsiveness | Supplier must respond to other, non-urgent email requests from Inquiry Key Staff* within 2 working days. *The list of those defined as key staff can be found in the Order Form | 95% |
| 3 | Deadlines | The Supplier to achieve the table of milestones at 7.1. Failure to comply with the KPI will result in the deduction of 5% of the deliverables for each day over the target or agreed deadline where it is the fault of the Supplier. | 95% |

  - Please note that exceptions can be made for setbacks which the Supplier could not reasonably have foreseen, mitigated against or resolved effectively.

  - The supplier shall monitor its performance against each of the above Performance Indicators and update the Inquiry every fortnight as part of rolling updates

# SECURITY AND CONFIDENTIALITY REQUIREMENTS

  - All activity undertaken by the supplier must comply with Data Protection Legislation.

  - The Supplier will be required to ensure complete confidentiality at all times, both within their organisation and in external communications.

  - The Supplier must satisfy the Inquiry that their data destruction/deletion practices comply with UK Data Protection Legislation and follows all relevant National Cyber Security Centre guidance.

  - The Supplier must maintain an asset register of all Inquiry supplied information, data and equipment to ensure the Inquiry’s assets are returned and/or deleted

  - The Supplier will agree all data and deliverables included within this contract will be solely owned by the Inquiry and when the contract terminates all data and deliverables including but not limited to reports, data templates will be transferred to the Inquiry by an agreed method. The Inquiry reserves Intellectual Property Rights for all work during this contract.

# PAYMENT AND INVOICING

  - Payment can only be made following satisfactory delivery of pre-agreed certified products and deliverables.

  - Before payment can be considered, each invoice must include a detailed elemental breakdown of work completed and the associated costs.

  - Payments will be made within 30 days from receipt of invoice in arrears

# CONTRACT MANAGEMENT

  - The supplier will be expected to attend meetings virtually.

  - Both Parties shall pro-actively manage risks attributed to them under the terms of this Contract.

  - The Supplier shall develop, operate, maintain, amend and produce regular slide packs, with input and as agreed with the Inquiry, processes for:

- Identification and management of risks, issues and dependencies with agreed owners;

- Monitoring and controlling project plans for planning, delivery and execution.

- Key Performance Indicator outputs;

- Other requirements as defined in the contract including but not limited to contingency planning.

  - The Supplier will need to evidence the effectiveness of their business continuity plan, to ensure that there is a strategy in place to deal with any unforeseen disruptions to the delivery of service, should they arise during the term of the Contract.

  - Communication will be maintained with the supplier through weekly status meetings and email correspondence, to be agreed upon contract commencement.

  - Attendance at Contract Review meetings shall be at the supplier’s own expense.

  - Conflict of Interest

  - The Supplier must have appropriate processes in place to mitigate the effect of any potential or actual conflict of interests, including those of a financial, personal or professional nature. These processes must include:

  - Setting up appropriate ethical walls to ensure that any of  the supplier’s staff who may have been involved in decision making relating to the Government’s response to the Covid-19 pandemic does not work directly on this Contract account.

  - Ensuring visibility of all Supplier staff who worked on the Government’s response to the Covid-19 pandemic and that there are appropriate controls in place to restrict access to the Inquiry's client file.

  - Ensuring visibility of existing clients who are Core Participants in the Inquiry.

  - Ensuring that consideration of the potential or actual conflicts of interest is given when appointing subcontractors to work on this Contract account. These considerations must be shared with the Inquiry before any subcontractors are appointed.

  - Ensuring visibility of any affiliated companies which may have the potential or actual conflict of interest and ensuring that there are appropriate mitigations in place.

  - Measures to address the potential for conflicts of interests to occur over the course of the contract but which may not be present at the time of the contract award, for example:

    - a new staff member with experience of supporting the Government’s response to the Covid-19 pandemic; or,

    - taking on new work for an individual or organisation who is a Core Participant in the Inquiry or an existing client becoming a Core Participant in the Inquiry.

# LOCATION

  - The location of the Services will be carried out at the supplier’s offices or working from home. Meetings with the Inquiry will be remote. Attendance of one member of the research team to present findings at a hearing must take place in person, and is expected to be at the Inquiry’s hearing centre at Dorland House, London.

  - Recruitment sub-contractors or professional societies should be based throughout the UK, and face-to-face meetings may be required to develop working relationships.

Page MJ, McKenzie JE, Bossuyt PM, et al. The PRISMA 2020 statement: an updated guideline for reporting systematic reviews. BMJ 2021;372:n71.