## Q&A
Tender Name: | Extension to Leybourne Village Hall, Little Market Row, Leybourne
Questions that have been raised from the tender Document with answers
| Date | Question | Answer
1 | 2019-02-22 | Appendix 3 of the ITT document gives the Form of Contract as the JCT Intermediate Building Contract with Contractor's Design. We assume it is intended to use the 2016 editition with any current official amendments. | Yes that is correct
2 | 2019-02-22 | We assume that the Contractors Design Portion refers to the Electrical, Plumbing and Heating trades only. Please let us know if other trades should be included. | That is all the trades that are needed.
3 | 2019-02-22 | Appendix 3 of the ITT says that there will be retention up to 10%. Most projects of this size are at 5% during the construction work and reduce to 2 ½ % on practical completion. | We will keep the retention at 10% until Practical Completion and then reduce it to 5% for 12 months after PC
4 | 2019-02-22 | Is the Defects Liability period 6 or 12 months. | 12 months
5 | 2019-02-22 | Are Liquidated Damages likely to be applied for non completion of all or part of the works. | Yes
6 | 2019-02-22 | Do we arrange site visits with the Clerk to the Council | yes
7 | 2019-02-22 | We have noted that this will be a JCT Intermediate Building Contract with Contractor’s Design. Could you please confirm the Contractor’s Design Portion? | The design portion will be the heating and plumbing section.
8 | 2019-02-21 | Appendix 4 is titled “Supplier Technical Questions and Answer Sheet”, however there appear not to be questions, but categories instead. Please provide instruction as to how answers should be designed. | This is for potential tenderers to provide experience in these areas. Please provide all experiences
9 | 2019-02-21 | The ten declaration includes a clause committing the tenderer to completion of works on or before 17 March 2019. Assuming this is erroneous, please advise of what date should replace this? | This date should be October 2019
10 | 2019-02-21 | Please clarify how the Council deals with contingency sums | Contingencies are amounts that are held in reserve to deal with unforeseen circumstances
11 | 2019-02-21 | . Please confirm standard payment terms and whether progress payments will be considered | Payment terms will be 30 days or as otherwise agreed with the Parish Council.
12 | 2019-02-27 | I’ve been looking at the PPQ quality questions, I’m wondering if you can give us any indication of the information you are looking for under these questions, I’m currently questioning what information you would like to see, but not sure if I’m on the right track | We are looking for answers to the revelant questions of past experience of projects like this with references, We would like to see a brief POWs for the works.
13 | 2019-02-27 | The architects drawings and spec show a timber frame building with roof trusses but the structural engineer has specified a steel frame and roof. Can you please specify which spec we are to tender to? | Please price from the Structural Engineer specification.
14 | 2019-02-27 | There is currently no reference to the existing AC units or proposed solution? The current units are mounted on the ground and will need to be relocated for the new extension to be built. There was talks this morning of the AC being roof mounted but there is no reference to this option. Is there any information regarding this? | The contingency sum is in the tender document to cover this. There was a discussion of possibly relocating the Ac units into the roof space for the new extension.
15 | 2019-02-27