| CHANGE CONTROL NOTICE (001) |  |  |  |
| --- | --- | --- | --- |
| Contract Title: | Contract for the Provision of Vulnerable Persons and Vulnerable Children’s resettlement Schemes Evaluation (The Contract) |  |  |
| Contract Reference: | CCSN17A09 | Contract Change Number: | 001 |
| Date CCN issued: | 30th August 2018 | Date Change Effective from: | 3rd September 2018 |
| Between: The Home Office (The Authority) and IPSOS MORI (The Supplier) - The Contract is varied as follows: - 1.1 Reason for change: The addition of 2 longitudinal mini case studies per annum; with two different Community Sponsors. Therefore there will be 5 Local Authority and 2 Community Sponsor case studies conducted over the three years of the evaluation. Total additional cost per Year: - Year 1 £9,965.00 exclusive of VAT - Year 2 £12,703.00 exclusive of VAT - Year 3 £12,703.00 exclusive of VAT - Therefore increasing the value of the contract from £416,917.00 to 452,288.00 exclusive of VAT. - Words and expressions in this Change Control Notice shall have the meanings given to them in the Contract. - The Contract, exncluding any previous Contract changes, authorised in writing by both Parties, shall remain effective and unaltered except as amended by this Change Control Notice. |  |  |  |
| Redacted Change authorised to proceed by: (Authority’s representative): 5th September 2018 Redacted Signature Print Name and Job Title Date |  |  |  |
| Authorised for and on behalf of the Supplier: 6th September 2018 Redacted Redacted Signature Print Name and Job Title Date |  |  |  |
| Authorised for and on behalf of the Authority: Redacted Signature Print Name and Job Title Date 06th September 2018 Redacted |  |  |  |