SCHEDULE 6

CONTRACT CHANGE PROCESS

# CONTRACT  CHANGE PROCESS

- Authority Changes

  - Subject always to Condition 33 (Changes to the Contract) the Authority shall be entitled, acting reasonably, to require changes to this Contract (a "Change") in accordance with this Schedule 6 and DEFCONs 503 and 620. Where there is conflict between the terms in DEFCON 620 and this Schedule this Schedule shall take precedence.

- Notice of Change

  - If the Authority requires a Change, it shall serve an Authority Notice of Change (a "Contract Change Control Request") on the Contractor as per Annex B Part A.

  - The Authority Change Control Request shall set out the change required to the Contract in sufficient detail to enable the Contractor to provide a written proposal (a "Contractor Change Proposal") in accordance with condition 3 below and Part B of Annex A.

- Contractor Change Proposal

  - As soon as practicable, and in any event within fifteen (15) Business Days (or such other period as the Parties may agree) after having received the Authority’s Contract Change Control Request, the Contractor shall deliver to the Authority a Contractor Change Proposal, see Annex A Part B.

- Acceptance of Contract Change Proposal

  - The Authority will indicate its acceptance of the Contractor Change Proposal by issuing a sequential serially numbered Amendment letter and/or the form at Annex B, Change Control Notice.

    - The Contractor Change Proposal shall include:

      - the effect of the Change on the Contractor’s obligations under the Contract;

      - a detailed breakdown of any costs which result from the Change;

      - the programme for implementing the Change;

      - any amendment required to this Contract as a result of the Change, including, where appropriate, to the Contract Price(s); and

      - such other information as the Authority may reasonably require.

    - The price for any Change shall be based on the prices (including all rates) already agreed for the Contract in Schedule 1 and shall include, without double recovery, only such charges that are fairly and properly attributable to the Change.

- Contractor Change Proposal – Process and Implementation

  - As soon as practicable after the Authority receives a Contractor Change Proposal, the Authority shall:

    - evaluate the Contractor Change Proposal;

    - where necessary, discuss with the Contractor any issues arising and, following such discussions, the Authority may modify the Authority Change Control Notice and the Contractor shall, as soon as practicable, and in any event not more than ten (10) Business Days (or such other period as the Parties may agree) after receipt of such modification, submit an amended Contractor Change Proposal.

  - As soon as practicable after the Authority has evaluated the Contractor Change Proposal (amended as necessary) the Authority shall:

    - indicate its acceptance of the Change Proposal by issuing an amendment to the Contract in accordance with condition 32 (Changes to the Contract) and Annex B to this Schedule; or

    - serve a Notice on the Contractor rejecting the Contractor Change Proposal and withdrawing (where issued) the Authority Change Control Notice.

  - If the Authority rejects the Change Proposal it shall not be obliged to give its reasons for such rejection.

  - The Authority shall not be liable to the Contractor for any additional work undertaken or expense incurred unless a Contractor Change Proposal has been accepted in accordance with clause 4.b.(1).

- Contractor Changes

  - If the Contractor wishes to propose a Change, it shall serve a Contractor Change Proposal on the Authority, which shall include all of the information required by clause 3.b, and the process at condition 4 shall apply.

- Record of Changes

  - A record of all Contract changes will be detailed in Annex C which will be maintained on an on-going basis and any necessary changes included in Schedules 1 and 2 as appropriate.

CONTRACT CHANGE CONTROL REQUEST

| Proposed Change Control Number: |  | Priority/Routine: |  |
| --- | --- | --- | --- |
| Date Issued: |  |  |  |
| Contractor: |  |  |  |

PART A – Change Request (MOD) The Contractor is requested to provide a response to this Contract Change Control Request (CCCR) Part A in Part B below with a return date of XX/XX/XX

Task Title:

Request Description:

Deliverables:

Acceptance Criteria:

Government Furnished Information and Documents:

Government Furnished Assets:

Required Completion Date: (an assumed start date should also be stated)

Additional Terms and Conditions relating to this Task: (including Security)

Signature: …................................ Name (Block Capitals): …..................................... Post: …................................. Date: …................................................

PART B – CONTRACTOR CHANGE PROPOSAL Contractor confirms they do/do not understand the requirements, deliverables and Acceptance Critera and the Authority’s requested completion dates. The response below is to provide the Contractor’s Response to the above request (including impact to terms and Conditions, Scope, time, deliverables and price) to undertake the work above and to clarify any matters worthy of consideration by the Authority.

Price Impact (based on rates detailed at Annex A to Schedule 1 (Schedule of Requirement):

Impact to timescales: (confirm agreement to above or start an assumed start and committed end date)

Impact to Statement of Technical Requirement:

Impact to Deliverables:

Impact to Commercial Terms:

Signature: ….................................. Name (Block Capitals): …................................... Post: ….................................... Date: …................................................

Please Note:	No work shall commence until the Change Control Note has been fully approved.

Classification (if any)

CONTRACT CHANGE CONTROL NOTE NUMBER xxx/xxxx

TO CONTRACT SHIPACQ138

TITLE: xxxxxxxx

DETAILS OF CONTRACT CHANGE

This Contract Number SHIPACQ138 for Independent Commercial Ship Design and Support – Customer Friend is hereby amended by this Change Control Note Number XX as detailed below which is incorporated into the Contract in accordance with the terms and Conditions of Contract Number SHIPACQ138. The Contractor is to confirm acceptance of this change by countersigning and sending back a fully signed copy by return, to the Authority's Commercial Officer. This Contract Change Control Note takes immediate effect from the date of the Contractor’s countersignature.

- Change to Terms and Conditions

- Change to Schedule 1

- Change to Schedule 2

- Change to other Schedules

For the Authority

Name: ______________________________

Signature: ___________________________

Date:_________________

For the Contractor

Name: ______________________________

Signature: ___________________________

Date:_________________

INDEX OF CONTRACT CHANGES

| Amendment Number | Title | Paragraphs and Schedules affected | Date of Change | Value (£) Ex VAT | Price |
| --- | --- | --- | --- | --- | --- |

Note; this will be maintained as a live document.