|  | Form of Agreement incorporating the NEC4 Engineering and Construction Contract Option A: Priced Contract with activity schedule June 2017 |  |
| --- | --- | --- |
|  | For works comprising Stratford Upon-Avon JCP Refurbishment Crown Commercial Service, Department for Work and Pensions Framework dated 28th June 2018. Schedule 2 - Part 2 (Lot 2/3 Call-Off Contract Option A) Between |  |
|  | - The Secretary of State for Work and Pensions - and - Speller Metcalfe Malvern Limited |  |
|  | Dated: TBC |  |

Contents

In this contract the core clauses are the ECC core clauses and the clauses set out in the ECC as main Option clauses; Option A.

| Form of Agreement |  |  |  |
| --- | --- | --- | --- |
| Date |  |  | 1 |
| Parties |  |  | 1 |
| Recitals | 1 - 5 | Background | 1 |
| Operative clauses | 1 | Contract for the works | 2 |
|  | 2 | Priority of documents | 2 |
|  | 3 | Entire Agreement | 2 |
| Execution page |  |  | 2 |
| Schedule A |  | Contract Data Part One – Data provided by the Client | 4 |
| Schedule B |  | Option Z: Additional Conditions of Contract | 13 |
| Schedule C |  | Contract Data Part Two – Data provided by the Contractor |  |
| Schedule D |  | Scope | 79 |
| Schedule E |  | Activity Schedule | 80 |
| Schedule F |  | Site Programme | 81 |
| Schedule G |  | Collateral Warranties | 82 |
| Schedule H |  | Security Schedule | 83 |
| Schedule I |  | Management Information | 84 |
| Schedule J |  | Key Performance Indicators | 85 |
| Schedule K |  | TUPE – Not Used | 86 |
| Schedule L |  | Governance | 87 |
| Schedule M |  | Equality | 88 |
| Schedule N |  | Forms of Ultimate Holding Company Guarantee and Performance Bond – Not Used | 89 |
| Schedule O |  | Third Party Agreements – Not Used | 90 |
| Schedule P Schedule Q |  | Data Protection Financial Distress – Not Used | 91 |

This agreement is made the	   TBC       2020

Between:

- The Secretary of State for Work and Pensions of Caxton House, Tothill Street, London, SW1H 9NA acting as part of the Crown (the Client); and

- Speller Metcalfe Malvern Limited (Company no. 06740881) of / whose registered office is at Maple Road, Enigma Business Park, Malvern, Worcestershire, WR14 1GQ (the Contractor).

Background

- The Client established a national and regional framework divided into lots for projects Contracts of varying values for the benefit of public sector bodies.

- The Contractor was appointed to Lot [2]/[3] of the framework and has executed the framework agreement which is dated 28th June 2018 (the Framework Agreement).

- The Client acting as part of the Crown, by direct call off instructed the Contractor for the Stratford Upon-Avon JCP Refurbishment,

- and has completed the Contract Data Part 1.

- The Contractor has provided the data for the Contract Data Part 2.

- The Contractor has agreed to Provide the Works in accordance with this contract and the Framework Agreement.

    - It is agreed as follows:

- Contract for the works

  - The contract for the works comprises the terms and conditions of the NEC4 Engineering and Construction Contract Option A: Priced contract with activity schedule June 2017 which is supplemented and amended in accordance with such information and supplementary provisions as are provided in the Schedules.

  - The Schedules means any one or all of the schedules appended to this contract.

- Priority of documents

  - If there is any ambiguity or inconsistency in or between the documents comprising this contract, the priority of the documents is in accordance with the following sequence:

    - this Agreement;

    - the completed Contract Data;

    - the additional conditions of contract;

    - the other conditions of contract;

    - the Scope; and

    - any other document forming part of the contract.

- Entire Agreement

  - This contract is the entire agreement between the parties in relation to the works and supersedes and extinguishes all prior arrangements, understandings, agreements, statements, representations or warranties (whether written or oral) relating thereto.

  - Neither party has been given, nor entered into this contract in reliance on any arrangements, understandings, agreements, statements, representations or warranties other than those expressly set out in this contract.

  - Nothing in this clause 3 shall exclude any liability in respect of misrepresentations made fraudulently.

- In witness whereof the parties have caused this contract to be executed as a deed by their duly authorised representatives and delivered on the date first above written

- Signature page to the Agreement between the Client and the Contractor

| Executed as a Deed for and on behalf of The Secretary of State for Work and Pensions by affixing hereto its common seal in the presence of: Signature:..................................................... Name: ..................................................... Title: Authorised signatory Date: ..................................................... | ) ) ) ) |  |
| --- | --- | --- |
| Executed as a deed by Speller Metcalfe Malvern Limited acting by: Signature:..................................................... Name: ................................. Title: Managing Director Date: ..................................................... | ) ) ) ) | Signature:..................................................... Name: …............................... Title: Group Commercial Director Date: ..................................................... |

Schedule A

Contract Data Part One – Data provided by the Client

|  |  | General |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | The conditions of contract are the core clauses of the NEC4 Engineering and Construction Contract June 2017 Option A, the following Option for resolving and avoiding disputes and secondary Options of the NEC4 Engineering and Construction Contract June 2017: |  |  |  |  |  |  |
|  |  |  |  |  | Option for resolving and avoiding disputes: |  |  | W2 |  |  |
|  |  |  |  |  | Secondary Options: |  |  |  |  |  |
|  |  |  |  |  | - X2 |  |  | Changes in the Law |  |  |
|  |  |  |  |  | - X4 |  |  | Ultimate holding company guarantee |  |  |
|  |  |  |  |  | - X5 |  |  | Sectional Completion |  |  |
|  |  |  |  |  | - X7 |  |  | Delay Damages |  |  |
|  |  |  |  |  | - X8 |  |  | Undertakings to the Client or Others |  |  |
|  |  |  |  |  | - X10 |  |  | Information Modelling |  |  |
|  |  |  |  |  | - X11 |  |  | Termination by the Client |  |  |
|  |  |  |  |  | - X13 |  |  | Performance Bond |  |  |
|  |  |  |  |  | - X15 |  |  | Limitation of the Contractor's liability for his design to reasonable skill and care |  |  |
|  |  |  |  |  | - X16 |  |  | Retention |  |  |
|  |  |  |  |  | - X18 |  |  | Limitation of liability |  |  |
|  |  |  |  |  | - X20 |  |  | Key Performance Indicators |  |  |
|  |  |  |  |  | - X21 |  |  | Whole Life Cost |  |  |
|  |  |  |  |  | - Y(UK)2 |  |  | The Housing, Grants, Construction and Regeneration Act 1996 |  |  |
|  |  |  |  |  | Option Z: Additional conditions of contract |  |  |  |  |  |
|  |  |  |  |  | - Z1 – Z55 |  |  |  |  |  |
|  |  |  |  | - The works are |  |  |  | Stratford Upon-Avon JCP Refurbishment |  |  |
|  |  |  |  | - The Client is |  |  |  | defined in the form of agreement to which this Schedule is annexed |  |  |
|  |  |  |  |  |  |  |  | Address for communications: Department for Work and Pensions Caxton House Tothill Street London SW1H 9NA |  |  |
|  |  |  |  |  |  |  |  | Address for electronic communications: REDACTED |  |  |
|  |  |  |  | - The Project Manager is |  |  |  | Name: REDACTED Address for communications: Department for Work and Pensions Caxton House Tothill Street London SW1H 9NA Address for electronic communications: REDACTED |  |  |
|  |  |  |  | - The Supervisor is |  |  |  | Name: REDACTED |  |  |
|  |  |  |  |  |  |  |  | Address for communications: Department for Work and Pensions Caxton House Tothill Street London SW1H 9NA |  |  |
|  |  |  |  |  |  |  |  | Address for electronic communications: REDACTED Lead/ Architect: REDACTED - REDACTED Mechanical: REDACTED - REDACTED Electrical: REDACTED - REDACTED Public Health: REDACTED - REDACTED |  |  |
|  |  |  |  | - The Scope is in |  |  |  | Schedule D |  |  |
|  |  |  |  | - The Site Information is in |  |  |  | Schedule F as may be amended from time to time |  |  |
|  |  |  |  | - The boundaries of the site are |  |  |  | 38 Wood Street, Stratford Upon Avon, CV37 6JG |  |  |
|  |  |  |  | - The language of the contract is |  |  |  | English |  |  |
|  |  |  |  | - The law of the contract is the law of |  |  |  | The law of England and Wales, and includes all statute, primary and secondary legislation, and other regulations, orders and by-laws having the force of law. |  |  |
| - E |  |  |  | - The period for reply is |  |  |  | One weeks |  |  |
|  |  |  |  | - The following matters will be included in the Early Warning Register |  |  |  | Template required |  |  |
|  |  |  |  | - Early warning meetings are to be held at intervals no longer than: |  |  |  | Two weeks |  |  |
|  |  | The Contractor's main responsibilities |  |  |  |  |  |  |  |  |
|  |  |  |  | The key dates and conditions to be met are: |  |  |  |  |  |  |
|  |  |  |  | condition to be met |  |  |  | key date |  |  |
|  |  |  |  | - Completion |  |  |  | 11 December 2020 |  |  |
|  |  |  |  | - Not applicable |  |  |  |  |  |  |
|  |  |  |  | - Not applicable |  |  |  |  |  |  |
|  |  | Time |  |  |  |  |  |  |  |  |
|  |  |  |  | - The starting date is |  |  |  | 24 August 2020 |  |  |
|  |  |  |  | - The access dates are: |  |  |  | As above |  |  |
|  |  |  |  | Part of the Site - Not applicable - Not applicable - Not applicable |  |  |  |  |  |  |
|  |  |  |  | The Contractor submits revised programmes at intervals no longer than |  |  |  | Two Weeks |  |  |
|  |  |  |  | - The completion date for the whole of the works is |  |  |  | 11 December 2020 |  |  |
|  |  |  |  | - The period after the Contract Date within which the Contractor is to submit a first programme for acceptance is: |  |  |  | One Week |  |  |
| - O |  | Quality Management |  |  |  |  |  |  |  |  |
|  |  |  |  | - The period after the Contract Date within which the Contractor is to submit a quality policy statement and quality plan is: One Week |  |  |  |  |  |  |
|  |  |  |  | - The period between Completion of the whole of the works and the defects date is: One Year Urgent: Within 48 hours Not urgent: One week |  |  |  |  |  |  |
|  |  |  |  | - The defect correction period is |  |  |  |  |  |  |
|  |  |  |  | - The defect correction period for Urgent Repairs/ Replacement |  |  |  |  |  |  |
|  |  |  |  | Is |  |  |  | 48 Hours |  |  |
|  |  |  |  | - The defect correction period for Routine Repairs/ Replacements |  |  |  |  |  |  |
|  |  |  |  | Is |  |  |  | One Week |  |  |
|  |  | Payment |  |  |  |  |  |  |  |  |
|  |  |  |  | - The currency of this contract is the |  |  |  | GB pounds sterling |  |  |
|  |  |  |  | - The assessment interval is |  |  |  | Monthly |  |  |
|  |  |  |  | - The interest rate is |  |  |  | three per cent (3%) per annum (not less than 2) above the base rate of the Bank of England |  |  |
|  |  |  |  | - The period within which payments are to be made is: 10 Working Days |  |  |  |  |  |  |
|  |  | Compensation events |  |  |  |  |  |  |  |  |
|  |  |  |  | - The place where weather is to be recorded is |  |  |  | Wellesbourne Met Office Weather Station. |  |  |
|  |  |  |  | - The weather measurements to be recorded for each calendar month are: |  |  |  |  |  |  |
|  |  |  |  | - the cumulative rainfall (mm) |  |  |  |  |  |  |
|  |  |  |  | - the number of days with rainfall more than 5mm |  |  |  |  |  |  |
|  |  |  |  | - the number of days with minimum air temperature less than 0 degrees Celsius |  |  |  |  |  |  |
|  |  |  |  | - the number of days with snow lying at |  |  |  | Wellesbourne Met Office Weather Station. |  |  |
|  |  |  |  | - and these measurements |  |  |  |  |  |  |
|  |  |  |  | - The weather measurements are supplied by |  |  |  | Speller Metcalfe Malvern Limited |  |  |
|  |  |  |  | - The weather data are the records of past weather measurements for each calendar month which were recorded at |  |  |  | Wellesbourne Met Office Weather Station. |  |  |
|  |  |  |  | and which are available from |  |  |  | Met Office. |  |  |
|  |  |  |  | Where no recorded data are available |  |  |  |  |  |  |
|  |  |  |  | - Assumed values for the ten year return weather data for each weather measurement for each calendar month are |  |  |  | Not applicable |  |  |
|  |  |  |  | - The value engineering percentage is 50%, unless another percentage is stated here, in which case it is: |  |  |  | Not applicable 0% and not incentivised |  |  |
|  |  |  |  | - 60. 1 (21) These are additional compensation events: Any change to the minimum hourly rate of pay set by Government which applies to workers. Any change to the rate of Client’s National Insurance contribution. Any introduction of a compulsory Living Wage or London Living Wage or any change thereto which applies to workers. A change to the pension Client contribution rate for Transferring Former Contractor Employees or Transferring Client Employees. A change to the pension auto-enrolment costs for Transferring Former Contractor Employees or Transferring Client Employees |  |  |  |  |  |  |
| - 8 |  | Liabilities and Insurance |  |  |  |  |  |  |  |  |
|  |  |  |  | These are additional Client's liabilities: |  |  |  |  |  |  |
|  |  |  |  | (1) Loss or damage to any existing structure (other than property owned or occupied by the Client and the works) within which the works or part of the works are to be executed or to which they are to form an extension, unless the loss or damage arises from or in connection with the Contractor Providing the Works, in which case the Client is only liable for such loss or damage in excess of [Lot 2 – ten million pounds (£10,000,000)] in respect of any one claim. |  |  |  |  |  |  |
|  |  |  |  | (2) A difference between the rates of pay of Transferring Former Contractor Employees and/or Transferring Employer Employees and the equivalent rates of pay used by the Contractor and/or a Notified Contractor at to calculate the Prices under the Framework. Such difference, if any, shall be calculated and accounted for in accordance with Contract Schedule K, Part 2. |  |  |  |  |  |  |
|  |  |  |  | (3) A Transferring Former Contractor Employee and/or any Transferring Employer Employee is made redundant by the Contractor as a result of an economic technical organisational reason entailing changes to the workforce and the Contractor has followed a fair dismissal procedure and complied with all contractual and legislative requirements. Any resultant redundancy costs shall be calculated and accounted for in accordance with paragraph 1.6 of Contract Schedule K, Part 2. |  |  |  |  |  |  |
|  |  |  |  | The minimum amount of cover for insurance against loss of or damage to property (except the works, Plant and Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor Providing the Works for any one event is: |  |  |  |  |  |  |
|  |  |  |  | [Lot 2 - ten million pounds (£10,000,000)]any one occurrence the number of occurrences being unlimited in any annual policy period but [ten million pounds (£10,000,000)][twenty five million (£25,000,000)] any one occurrence and in the annual aggregate in respect of products liability and pollution/contamination liability (to the extent insured by the policy) |  |  |  |  |  |  |
|  |  |  |  | The minimum amount of cover for insurance against death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with the contract for any one event is |  |  |  |  |  |  |
|  |  |  |  | the amount required by law |  |  |  |  |  |  |
|  |  |  |  | If the Client is to provide Plant and Materials |  |  |  |  |  |  |
|  |  |  |  | - The insurance against loss of or damage to the works, Plant and Materials is to include cover for Plant and Materials provided by the Client for an amount of: |  |  |  | £[ ] |  |  |
|  |  |  |  | If the Client is to provide any of the insurances stated in the Insurance Table |  |  |  |  |  |  |
|  |  |  |  | - The Client provides these insurances from the Insurance Table |  |  |  |  |  |  |
|  |  |  |  | - Insurance against |  |  |  |  |  |  |
|  |  |  |  | Cover / indemnity is |  |  |  |  |  |  |
|  |  |  |  | The deductibles are |  |  |  |  |  |  |
|  |  |  |  | - Insurance against |  |  |  |  |  |  |
|  |  |  |  | Cover / indemnity is |  |  |  |  |  |  |
|  |  |  |  | The deductibles are |  |  |  |  |  |  |
|  |  |  |  | - Insurance against |  |  |  |  |  |  |
|  |  |  |  | Cover / indemnity is |  |  |  |  |  |  |
|  |  |  |  | The deductibles are |  |  |  |  |  |  |
|  |  |  |  | If additional insurances are to be provided |  |  |  |  |  |  |
|  |  |  |  | - The Client provides these additional insurances |  |  |  |  |  |  |
|  |  |  |  | - Insurance against |  |  |  |  |  |  |
|  |  |  |  | Cover / indemnity is |  |  |  |  |  |  |
|  |  |  |  | The deductibles are |  |  |  |  |  |  |
|  |  |  |  | - Insurance against |  |  |  |  |  |  |
|  |  |  |  | Cover / indemnity is |  |  |  |  |  |  |
|  |  |  |  | The deductibles are |  |  |  |  |  |  |
|  |  |  |  | - The Contractor provides these additional insurances |  |  |  |  |  |  |
|  |  |  |  | - Insurance against |  |  |  |  |  |  |
|  |  |  |  | Cover / indemnity is |  |  |  |  |  |  |
|  |  |  |  | The deductibles are |  |  |  |  |  |  |
|  |  |  |  | - Insurance against |  |  |  |  |  |  |
|  |  |  |  | Cover / indemnity is |  |  |  |  |  |  |
|  |  |  |  | The deductibles are |  |  |  |  |  |  |
|  |  | Resolving and avoiding disputes |  |  |  |  |  |  |  |  |
|  |  |  |  | - The tribunal is |  |  |  | The Courts of England and Wales |  |  |
|  |  |  |  | - The place where the arbitration is to be held is |  |  |  | N/A |  |  |
|  |  |  |  | - The person or organisation who will choose an arbitrator if the Parties cannot agree a choice or if the arbitration procedure does not state who selects an arbitrator is: |  |  |  | The Client |  |  |
|  |  |  |  | If Option W1 or W2 is used |  |  |  |  |  |  |
|  |  |  |  | - The Senior Representatives of the Client are |  |  |  |  |  |  |
|  |  |  |  | Name (1): |  |  |  | REDACTED |  |  |
|  |  |  |  | Address for Communications: |  |  |  | Department for Work and Pensions Caxton House Tothill Street London SW1H 9NA |  |  |
|  |  |  |  | Address for electronic communications: |  |  |  | REDACTED |  |  |
|  |  |  |  | Name (2): |  |  |  | REDACTED |  |  |
|  |  |  |  | Address for Communications: |  |  |  | Department for Work and Pensions Caxton House Tothill Street London SW1H 9NA |  |  |
|  |  |  |  | Address for electronic communications: |  |  |  | REDACTED |  |  |
|  |  |  |  | - The Adjudicator is: |  |  |  | TBC |  |  |
|  |  |  |  | Address for Communications: |  |  |  | TBC |  |  |
|  |  |  |  | Address for electronic communications: |  |  |  | TBC |  |  |
|  |  |  |  | - The Adjudicator nominating body is: |  |  |  | The Royal Institution of Chartered Surveyors |  |  |
|  |  |  |  | Option X5 |  |  |  | [Not used] |  |  |
|  |  |  |  | - The completion date for each section of the works is |  |  |  |  |  |  |
|  |  |  |  |  | section | description |  |  |  | completion date |
|  |  |  |  |  | 1 |  |  |  |  |  |
|  |  |  |  |  | 2 |  |  |  |  |  |
|  |  |  |  |  | 3 |  |  |  |  |  |
|  |  |  |  |  | 4 5 |  |  |  |  |  |
|  |  |  |  | Option X7 |  |  |  | [is used] |  |  |
|  |  |  |  | - Delay damages for Completion of the whole of the works are |  |  |  | £0 per day |  |  |
|  |  |  |  | Clause X8 |  |  |  | [not used] |  |  |
|  |  |  |  | Clause X10 |  |  |  | [not used] |  |  |
|  |  |  |  | Clause X13 |  |  |  | [is used] |  |  |
|  |  |  |  | - The amount of the performance bond is |  |  |  | Nil |  |  |
|  |  |  |  | Clause X14 |  |  |  | [is not used] |  |  |
|  |  |  |  | - The amount of the advanced payment is |  |  |  | Nil |  |  |
|  |  |  |  | - The Contractor repays the instalments in assessments starting not less than |  |  |  | Not applicable weeks after the Contract Date |  |  |
|  |  |  |  | - The instalments are |  |  |  | Not applicable (either an amount or a percentage of the payment otherwise due) |  |  |
|  |  |  |  | - An advanced payment bond |  |  |  | is not required |  |  |
|  |  |  |  | Clause X15 |  |  |  | [is used] |  |  |
|  |  |  |  | - The period for retention following Completion of the whole of the works or earlier termination is: |  |  |  | 12 months and release of Defects Liability Certificate |  |  |
|  |  |  |  | - The minimum amount of insurance cover for claims made against the Contractor arising out of its failure to use the skill and care normally used by professionals designing works similar to the works is, in respect of each claim: |  |  |  | Not less than [Lot 2 – two million pounds (£2,000,000)] any one claim the number of claims being unlimited in any annual period of insurance but [Lot 2 – two million pounds (£2,000,000)] any one claim and in the annual aggregate in respect of pollution and contamination and one million pounds (£1,000,000) any one claim and in the annual aggregate in respect of asbestos. |  |  |
|  |  |  |  | - The period following Completion of the whole of the works or earlier termination for which the Contractor maintains insurance for claims made against it arising out of its failure to use the skill and care is: |  |  |  | 12 years |  |  |
|  |  |  |  | Clause X16 |  |  |  | [is used] |  |  |
|  |  |  |  | - The retention free amount is |  |  |  | 100% |  |  |
|  |  |  |  | - The retention percentage is |  |  |  | 0% |  |  |
|  |  |  |  | Clause X18 |  |  |  | [is used] |  |  |
|  |  |  |  | - The Contractor's liability to the Client for indirect or consequential loss is limited to |  |  |  | Five million pounds (£5,000,000) |  |  |
|  |  |  |  | - For any one event, the Contractor's liability to the Client for loss of or damage to the Client's property is limited to |  |  |  | [Lot 2 – ten million pounds (£10,000,000)] |  |  |
|  |  |  |  | - The Contractor's liability for Defects due to his design which are not listed on the Defects Certificate is limited to |  |  |  | [Lot 2 – two million pounds (£2,000,000)] |  |  |
|  |  |  |  | - The Contractor's total liability to the Client for all matters arising under or in connection with this contract, other than the excluded matters is limited to |  |  |  | [Lot 2 – ten million pounds (£10,000,000)] |  |  |
|  |  |  |  | - The end of liability date is |  |  |  | 12 years after the end of the whole of the works |  |  |
|  |  |  |  | Option X20 |  |  |  | is used |  |  |
|  |  |  |  | - A report of performance against each Key Performance Indicator is provided at intervals of |  |  |  | 4 weeks |  |  |
|  |  |  |  | - The value of a single Service Credit is |  |  |  |  |  |  |
|  |  |  |  | - The Service Credit Cap is |  |  |  | 1% of the total of the Prices. |  |  |
|  |  |  |  | Option Y(UK)2 |  |  |  |  |  |  |
|  |  |  |  | - The period for payment is 30 days after the date on which payment becomes due |  |  |  |  |  |  |
|  |  |  |  | Option Z is used |  |  |  |  |  |  |
|  |  |  |  | The additional conditions of contract are: |  |  |  | Identified above and in Schedule B |  |  |
|  |  |  |  | Option Z17 CDM Regulations |  |  |  |  |  |  |
|  |  |  | - The Principal Designer is |  |  |  | the Contractor |  |  |  |
|  |  |  | Option Z26 SMEs |  |  |  |  |  |  |  |
|  |  |  | - the SME Percentage is |  |  |  | 20% |  |  |  |
|  |  |  | Option Z27 Apprenticeships |  |  |  |  |  |  |  |
|  |  |  | - the Apprenticeship Percentage is |  |  |  |  |  | 5% |  |
|  |  |  | Option Z29 Collateral Warranties The following parties are to be beneficiaries of collateral warranties: |  |  |  |  |  |  |  |
|  |  |  | - Parties for whom collateral warranties are provided: for Contractor Design Portions such as Civil, Architectural, Mechanical, Electrical and Public Health. |  |  |  |  |  | - The Client (save in respect of collateral warranties from the Contractor) - (where not the Client) each owner of the Site or any property on the site or any part of it - (where not the Client) each landlord of the Site or any property on the Site or any part of it - any person who purchases a freehold or long leasehold interest in the Site or any part of it - any person who has entered into a lease or an agreement for the grant of a leasehold interest in the Site or any part of it |  |
|  |  |  | - Subcontractors from whom collateral warranties are required: As above |  |  |  |  |  | - Any Subcontractor with design responsibility |  |

Schedule B

Option Z: Additional Conditions of Contract

The following provisions supplement, modify or replace the published provisions of the NEC4 Engineering and Construction Contract Option A: Priced contract with activity schedule (June 2017)

| Actions |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Option Z1 |  |  |  | Governance |  |
|  |  |  |  | Insert new clause: |  |
| Additional clause 10.3 |  | 10.3 |  | The parties comply with the provisions of Schedule L in relation to the management and governance of this contract. |  |
| Option Z2 |  |  |  | Identified and defined terms |  |
| Supplement to clause 11 |  | 11.1 |  | At the end of clause 11.1 add: Terms defined in the form of agreement to which this Schedule is annexed apply to this contract. Terms with capital initials not defined in this contract (excluding the Framework Agreement) have the meaning given to them in the Framework Agreement. Terms for which no interpretation is provided in this contract shall have the meaning ordinarily given to them by the legal profession where appropriate but otherwise shall be interpreted in accordance with their dictionary meaning. |  |
| Amend clause 11.2 (5) |  | 11.2 (5) |  | Replace existing clause 11.2 (5) with the following: "A Corrupt Act means: .1 to directly or indirectly offer, promise or give any person working for or engaged by the Client or other Contracting Body or any other public body a financial or other advantage to: |  |
|  |  |  |  | - induce that person to perform improperly a relevant function or activity; or - reward that person for improper performance of a relevant function or activity; |  |
|  |  |  |  | .2 to directly or indirectly request, agree to receive or accept any financial or other advantage as an inducement or a reward for improper performance of a relevant function or activity in connection with this contract; |  |
|  |  |  |  | .3 committing any offence: - under the Bribery Act 2010 (or any legislation repealed or revoked by such Act) |  |
|  |  |  |  | - under legislation or common law concerning fraudulent acts; or - defrauding, attempting to defraud or conspiring to defraud the Client; or .4 any activity, practice or conduct which would constitute one of the offences listed above if such activity, practice or conduct had been carried out in the UK"; |  |
| Amend clause 11.2 (6) |  | 11.2(6) |  | In the first bullet point, before "Scope", insert "contract and/or the"; In the second bullet point, delete "which the Project Manager has accepted" and replace with "or the other requirements of this contract and/or the Scope"; |  |
| Amend clause 11.2 (12) |  | 11.2(12) |  | At the end of the clause, insert ", and include any parties identified in the Scope as related to, contracting with or as providing a service to or receiving a service from the Client or "; |  |
| Amend clause 11.2 (18) |  | 11.2(18) |  | In the first bullet point, after the words "describes the Site", insert: "including the physical and other conditions (including the sub-surface conditions) of or affecting the Site"; |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 11.2(33) |  | 11.2(33) |  | Affiliate is in relation to a body corporate, any other entity which directly or indirectly controls, is controlled by, or is under direct or indirect common control with, that body corporate from time to time; |  |
| Additional clause 11.2(34) |  | 11.2(34) |  | Authority Supply Chain is the Contractor and the principal suppliers to the Client of the following services: - landlord and lease management; - furniture fittings & equipment; - security; and - project works each an Authority Supply Chain Member; |  |
| Additional clause 11.2(35) |  | 11.2(35) |  | Baseline Security Requirements means the relevant Client's Policy as the Client may notify to the Contractor from time to time; |  |
| Additional clause 11.2(36) |  | 11.2(36) |  | CDM Regulations is the Construction (Design and Management) Regulations 2015 and any modification or replacement of the same, together with the guidance set out in the most recently published approved code of practice thereto; |  |
| Additional clause 11.2(37) |  | 11.2(37) |  | Client Confidential Information means all Personal Data and any information, however it is conveyed, that relates to the business, affairs, developments, trade secrets, know-how, personnel, and contractors of the Client, including all IPRs, together with all information derived from any of the above, and any other information clearly designated as being confidential (whether or not it is marked "confidential") or which ought reasonably be considered to be confidential; |  |
| Additional clause 11.2(38) |  | 11.2(38) |  | Client Data means - the data, text, drawings, diagrams, images or sounds (together with any database made up of any of these) which are embodied in any electronic, magnetic, optical or tangible media, and which are: - supplied to the Contractor by or on behalf of the Client; or - which the Contractor is required to generate, process, store or transmit pursuant to this Contract; or - any Personal Data for which the Client is the Data Controller; |  |
| Additional clause 11.2(39) |  | 11.2(39) |  | Client's Policies are the policies of the Client as published from time to time at the Client's tendering website https://dwp.bravosolution.co.uk current at the date of this contract and as may be amended from time to time; |  |
| Additional clause 11.2(40) |  | 11.2(40) |  | Client's System means the Client's computing environment (consisting of hardware, software and/or telecommunications networks or equipment) used by the Client or the Contractor in connection with this contract which is owned by the Client or licensed to it by a third party and which interfaces with the Contractor System or which is necessary for the Client to receive the works; |  |
| Additional clause 11.2(41) |  | 11.2(41) |  | Commercially Sensitive Information is the information agreed between the parties to be commercially sensitive (if any); |  |
| Additional clause 11.2(42) |  | 11.2(42) |  | Confidential Information means the Client Confidential Information and/or the Contractor Confidential Information; |  |
| Additional clause 11.2(43) |  | 11.2 (43) |  | Contracting Body means any Contracting Body as defined in Regulation 5(2) of the Public Contracts (Works, Service and Supply) (Amendment) Regulations 2000 other than the Client; |  |
| Additional clause 11.2(44) |  | 11.2(44) |  | Contractor Confidential Information means any information, however it is conveyed, that relates to the business, affairs, developments, trade secrets, know-how, personnel and contractors of the Contractor, including IPRs, together with all information derived from the above, and any other information clearly designated as being confidential (whether or not it is marked as "confidential") or which ought reasonably to be considered to be confidential, including the Commercially Sensitive Information; |  |
| Additional clause 11.2(45) |  | 11.2(45) |  | Contractor Personnel are persons employed or engaged by the Contractor together with the Contractor’s servants, agents, suppliers, consultants and Subcontractor's (and all persons employed by any Subcontractor together with the Subcontractor’s servants, consultants, agents, suppliers and sub-subcontractors); |  |
| Additional clause 11.2(46) |  | 11.2(46) |  | Contractor System means the information and communications technology system used by the Contractor in implementing and performing the works including software, the equipment, configuration and management utilities, calibration and testing tools and related cabling (but excluding the Client's System); |  |
| Additional clause 11.2(47) |  | 11.2(47) |  | Control means that a person possesses, directly or indirectly, the power to direct or cause the direction of the management and policies of the other person (whether through the ownership of voting shares, by contract or otherwise) and "Controls" and "Controlled" shall be interpreted accordingly; |  |
| Additional clause 11.2(48) |  | 11.2(48) |  | Critical Performance Failure is more than four (4) Serious or Severe KPI Failures in a three month period; |  |
| Additional clause 11.2(49) |  | 11.2(49) |  | Crown Body means any department, office or agency of the Crown; |  |
| Additional clause 11.2(50) |  | 11.2(50) |  | Defects Protocol is the protocol set out in the Scope setting out timeframes within which the Contractor is to respond to specific categories of Defect; |  |
| Additional clause 11.2(51) |  | 11.2(51) |  | Data Controller has the meaning given in the Data Protection Legislation; |  |
| Additional clause 11.2(52) |  | 11.2(52) |  | Data Processor has the meaning given in the Data Protection Legislation; |  |
| Additional clause 11.2(53) |  | 11.2(53) |  | Data Protection Legislation means the Data Protection Act 1998 and any replacement legislation coming into effect from time to time including (without limitation) the GDPR together with any codes of practice or other guidance issued by any competent Regulatory Body; |  |
| Additional clause 11.2(54) |  | 11.2(54) |  | Data Subject has the meaning given in the Data Protection Legislation; |  |
| Additional clause 11.2(55) |  | 11.2(55) |  | DOTAS is the Disclosure of Tax avoidance Schemes rules which require a promoter of tax schemes to tell HM Revenue & Customs of any specified notable arrangements or proposals and to provide prescribed information on those arrangements or proposals within set time limits as contained in Part 7 of the Finance Act 2004 and in secondary legislation made under vires contained in Part 7 of the Finance Act 2004 and as extended to National Insurance Contributions by the National Insurance Contributions (Application of Part 7 of the Finance Act 2004) Regulations 2012, SI 2012/1868 made under s.132A Social Security Administration Act 1992; |  |
| Additional clause 11.2(56) |  | 11.2(56) |  | DWP Enterprise Security Risk Management Strategy means the relevant Client's Policy; |  |
| Additional clause 11.2(57) |  | 11.2(57) |  | DWP Information Security Policy means the relevant Client's Policy; |  |
| Additional clause 11.2(58) |  | 11.2(58) |  | DWP Offshoring Policy means the relevant Client's Policy; |  |
| Additional clause 11.2(59) |  | 11.2(59) |  | Environmental Information Regulations is the Environmental Information Regulations 2004 and any guidance and/or codes of practice issued by the Information Commissioner in relation to such regulations; |  |
| Additional clause 11.2(60) |  | 11.2(60) |  | FOIA is the Freedom of Information Act 2000 and any subordinate legislation made under this Act from time to time together with any guidance and/or codes of practice issued by the Information Commissioner in relation to such legislation; |  |
| Additional clause 11.2(61) |  | 11.2(61) |  | Former Contractor is the contractor supplying works to the Client before the Relevant Transfer Date that are the same as or substantially similar to the works (or any part of the works) and shall include any subcontractor of such supplier (or any sub-contractor of any such subcontractor); |  |
| Additional clause 11.2(62) |  | 11.2(62) |  | GDPR means the General Data Protection Regulation (EU) 2016/679 of the European Parliament and of the Council on the protection of natural persons with regard to the processing of personal data and on the free movement of such data; |  |
| Additional clause 11.2(63) |  | 11.2(63) |  | General Anti-Abuse Rule is: - the legislation in Part 5 of the Finance Act 2013; and - any future legislation introduced into parliament to counteract tax advantages arising from abusive arrangements and to avoid national insurance contributions; |  |
| Additional clause 11.2(64) |  | 11.2(64) |  | Good Industry Practice means the exercise of that degree of skill, care, prudence, efficiency, foresight and timeliness as would be expected from a leading company within the relevant industry or business sector; |  |
| Additional clause 11.2(65) |  | 11.2(65) |  | Government Digital Service Open Standards means the relevant Client's Policy; |  |
| Additional clause 11.2(66) |  | 11.2(66) |  | Halifax Abuse Principle is the principle explained in the CJEU Case C-255/02 Halifax and others; |  |
| Additional clause 11.2(67) |  | 11.2(67) |  | HMG Cyber Essentials Scheme means the relevant Client's Policy; |  |
| Additional clause 11.2(68) |  | 11.2(68) |  | HMG Security Policy Framework means the relevant Client's Policy; |  |
| Additional clause 11.2(69) |  | 11.2(69) |  | ICT Environment has the meaning given it in Schedule H; |  |
| Additional clause 11.2(70) |  | 11.2(70) |  | Improvement Notice has the meaning given in clause 67.2; |  |
| Additional clause 11.2(71) |  | 11.2(71) |  | Improvement Plan the plan to address the impact of and prevent the reoccurrence of a Notifiable Event; |  |
| Additional clause 11.2(72) |  | 11.2(72) |  | Improvement Plan Failure has the meaning given in clause 67.9; |  |
| Additional clause 11.2(73) |  | 11.2(73) |  | Information has the meaning given under section 84 of FOIA; |  |
| Additional clause 11.2(74) |  | 11.2(74) |  | Integrator means the Supplier named in the Integrator Agreement; |  |
| Additional clause 11.2(75) |  | 11.2(75) |  | Integrator Agreement means the agreement entered into by the Client and the Integrator dated 13 June 2017; |  |
| Additional clause 11.2(76) |  | 11.2(76) |  | Intellectual Property Rights or "IPRs" are: (a) copyright, rights related to or affording protection similar to copyright, rights in databases, patents and rights in inventions, semi-conductor topography rights, trade marks, rights in internet domain names and website addresses and other rights in trade names, designs, Know-How, trade secrets and other rights in Confidential Information; (b) applications for registration, and the right to apply for registration, for any of the rights listed at (a) that are capable of being registered in any country or jurisdiction; and (c) all other rights having equivalent or similar effect in any country or jurisdiction; |  |
| Additional clause 11.2(77) |  | 11.2(77) |  | Intervention Period has the meaning given to it at clause 68.5; |  |
| Additional clause 11.2(78) |  | 11.2(78) |  | Intervention Trigger Event is more than three (3) Serious KPI Failures or Severe KPI Failures in a three month period; |  |
| Additional clause 11.2(79) |  | 11.2(79) |  | Key Performance Indicator is a Performance Indicator stated to be "Key" in column [6] of Schedule J; |  |
| Additional clause 11.2(80) |  | 11.2(80) |  | KPI Failure is a failure to meet the Target Performance Level stated in Schedule J in respect of a Key Performance Indicator; |  |
| Additional clause 11.2(81) |  | 11.2(81) |  | Law means the law of the Contract and any revision, re-enactment of such law from time to time; |  |
| Additional clause 11.2(82) |  | 11.2(82) |  | Licence is any permit, consent, approval, authorisation, agreement, order, permission, certificate, waiver or licence which must be obtained from any person (including both private persons and public sector entities) in order to lawfully Provide the Works and for any goods to be transported, imported or exported; |  |
| Additional clause 11.2(83) |  | 11.2(83) |  | Malicious Software has the meaning given it in Schedule H; |  |
| Additional clause 11.2(84) |  | 11.2(84) |  | - Material KPI Failure - a Serious KPI Failure; or - a Severe KPI Failure; |  |
| Additional clause 11.2(85) |  | 11.2(85) |  | Material SPI Failure - a Serious SPI Failure; or - a Severe SPI Failure; |  |
| Additional clause 11.2(86) |  | 11.2(86) |  | Notifiable Event means: - a default by the Contractor which is material and is capable of remedy; or - any KPI Failure which relates to the same Key Performance Indicator and which occurs more than three (3) times in a three month period; - more than two (2) KPI Failures in any month - more than one (1) Material SPI Failure in successive months; |  |
| Additional clause 11.2(87) |  | 11.2(87) |  | Occasion of Tax Non-Compliance is: - where any tax return of the Contractor submitted to a Relevant Tax Authority on or after 1 October 2012 is found on or after 1 June 2017 to be incorrect as a result of: - A Relevant Tax Authority successfully challenging the Contractor under the General Anti-Abuse Rule or the Halifax Abuse Principle or under any tax rules or legislation that have an effect equivalent or similar to the General Anti-Abuse Rule or the Halifax Abuse Principle; - The failure of an avoidance scheme which the Contractor was involved in, and which was, or should have been, notified to a Relevant Tax Authority under DOTAS or any equivalent or similar regime; and/or - where any tax return of the Contractor submitted to a Relevant Tax Authority on or after 1 October 2012 gives rise, on or after 1 June 2017, to a criminal conviction in any jurisdiction for tax related offences which is not spent at the Contract Date or to a civil penalty for fraud or evasion; |  |
| Additional clause 11.2(88) |  | 11.2(88) |  | Performance Failure a KPI Failure or a SPI Failure; |  |
| Additional clause 11.2(89) |  | 11.2(89) |  | Performance Indicators the Key Performance Indicators and the Subsidiary Performance Indicators; |  |
| Additional clause 11.2(90) |  | 11.2(90) |  | Personal Data (as defined in the Data Protection Legislation) is data which is: - processed by the Contractor or any Subcontractor on behalf of the Client; or - for which one or both of the parties is Data Controller; pursuant to or in connection with this contract; |  |
| Additional clause 11.2(91) |  | 11.2(91) |  | Personal Data Breach means a breach of security leading to the accidental or unlawful destruction, loss, alteration, damage, unauthorised disclosure of, or access to, Personal Data; |  |
| Additional clause 11.2(92) |  | 11.2(92) |  | Process has the meaning given to it under the Data Protection Legislation and "Processed" and "Processing" shall be construed accordingly; |  |
| Additional clause 11.2(93) |  | 11.2(93) |  | Regulatory Bodies are those government departments and regulatory, statutory and other entities, committees and bodies which, whether under statute, rules, regulations, codes of practice or otherwise, are entitled to regulate, investigate, or influence the matters dealt with in this contract or any other affairs of the Client and "Regulatory Body" shall be construed accordingly; |  |
| Additional clause 11.2(94) |  | 11.2(94) |  | Proscribed Conduct is: - agreeing, permitting or entering into any arrangement (whether by contract, joint venture or otherwise) other than by this contract to carry out the works provided to the Client under the Integrator Agreement, either as Integrator or as any part of the Integrator's supply chain; - receiving or being entitled to receive any benefit. financial, commercial or otherwise which is derived expressly or impliedly from the Integrator save as expressly permitted by this contract; - being connected by a shareholding (controlling or otherwise) or by any arrangement (whether written or oral, by contract (other than this contract), joint venture or otherwise) in the Integrator or its Affiliates or its Subcontractors; - allowing the Integrator, its Affiliates or Subcontractors to exercise any control or influence over the Contractor or a Subcontractor save as required in the performance of the Integrator's duties under the Integrator Agreement; - exercising any control or influence over or permitting any Subcontractor to exercise and control or influence over the Integrator or its supply chain; or - appointing the Integrator or any Affiliate of the Integrator as a Subcontractor; |  |
| Additional clause 11.2(95) |  | 11.2(95) |  | Relevant Requirements are all applicable laws relating to bribery, corruption and fraud, including the Bribery Act 2010 and any guidance issued by the Secretary of State for Justice pursuant to section 9 of the Bribery Act 2010; |  |
| Additional clause 11.2(96) |  | 11.2(96) |  | Relevant Tax Authority is HM Revenue & Customs, or, if applicable, a tax authority in the jurisdiction in which the Contractor is established; |  |
| Additional clause 11.2(97) |  | 11.2(97) |  | Relevant Transfer is a transfer of employment to which the Employment Regulations (as defined in Schedule K) applies; |  |
| Additional clause 11.2(98) |  | 11.2(98) |  | Relevant Transfer Date is, in relation to a Relevant Transfer, the date upon which the Relevant Transfer takes place; |  |
| Additional clause 11.2(99) |  | 11.2(99) |  | Remedial Adviser the person appointed pursuant to clause 68; |  |
| Additional clause 11.2(100) |  | 11.2(100) |  | Remedial Adviser Failure has the meaning given to it in clause 68.9; |  |
| Additional clause 11.2(101) |  | 11.2(101) |  | Request for Information is a request for information or an apparent request under the FOIA or the Environmental Information Regulations; |  |
| Additional clause 11.2(102) |  | 11.2(102) |  | Required Action has the meaning given to it at clause 69.1; |  |
| Additional clause 11.2(103) |  | 11.2(103) |  | Serious KPI Failure means a SPI Failure which is indicated as a Serious Performance Failure against the relevant Performance Level in Schedule J; |  |
| Additional clause 11.2(104) |  | 11.2(104) |  | Serious SPI Failure means a SPI Failure which is indicated as a Serious Performance Failure against the relevant Performance Level in Schedule J; |  |
| Additional clause 11.2(105) |  | 11.2(105) |  | Service Credit means the amounts that may be payable by the Contractor as a consequence of the occurrence of one or more KPI Failures, and calculated by reference to the value of a single Service Credit stated in the Contract Data multiplied by the number of Service Failure Points accrued for such KPI Failure stated in Schedule J; |  |
| Additional clause 11.2(106) |  | 11.2(106) |  | Service Credit Cap is the service credit cap stated in the Contract Data part one; |  |
| Additional clause 11.2(107) |  | 11.2(107) |  | Service Failure Points means in relation to a: - KPI Failure; or - SPI Failure, the number of points that are set out against the relevant Key Performance Indicator and/or Subsidiary Performance Indicator (as the case may be) in Schedule J; |  |
| Additional clause 11.2(108) |  | 11.2(108) |  | Severe KPI Failure means a SPI Failure which is indicated as a Serious Performance Failure against the relevant Performance Level in Schedule J; |  |
| Additional clause 11.2(109) |  | 11.2(109) |  | Severe SPI Failure means a SPI Failure which is indicated as a Serious Performance Failure against the relevant Performance Level in Schedule J; |  |
| Additional clause 11.2(110) |  | 11.2(110) |  | Software has the meaning given to it in Schedule H; |  |
| Additional clause 11.2(111) |  | 11.2(111) |  | SPI Failure means a failure to meet the Target Performance Level in respect of a Subsidiary Performance Indicator; |  |
| Additional clause 11.2(112) |  | 11.2(112) |  | Specific Change in Law means a change in Law relating specifically to the business of the Client and which would not affect a supply of works or services to another customer of the Contractor that is the same or similar to the works; |  |
| Additional clause 11.2(113) |  | 11.2(113) |  | Step-In Notice has the meaning given to in clause 69.1; |  |
| Additional clause 11.2(114) |  | 11.2(114) |  | Step-In Trigger Event is - any event giving rise to a right to terminate this Contract; - a default by the Contractor which is materially preventing or delaying the performance of the works or a material part of them; - circumstances which the Client consider to amount to an emergency notwithstanding there is no breach of the contract by the Contractor; - the Client being advised by a Regulatory Body that the exercise of its step-in rights is necessary; - the need for the Client to exercise its step-in rights to discharge a statutory duty; - fire, leaks, act of god, storm damage, floods or similar events of force majeure; |  |
| Additional clause 11.2(115) |  | 11.2(115) |  | Step-Out Date has the meaning given to it in clause 69.5; |  |
| Additional clause 11.2(116) |  | 11.2(116) |  | Step-Out Notice has the meaning given to it in clause 69.5; |  |
| Additional clause 11.2(117) |  | 11.2(117) |  | Step-Out Plan has the meaning given to it in clause 69.6; |  |
| Additional clause 11.2(118) |  | 11.2(118) |  | Subsidiary Performance Indicator is a Performance Indicators which is identified as a Subsidiary Performance Indicator in Schedule J; |  |
| Additional clause 11.2(119) |  | 11.2(119) |  | Target Performance Level the minimum level of performance for a Performance Indicator which is required as set out against the relevant Performance Indicator in the column headed 'Target Performance' in the tables in Schedule J); |  |
| Additional clause 11.2(120) |  | 11.2(120) |  | Third Party Agreements are the third party agreements entered into by the Client, copies or relevant extracts of which are annexed at Schedule O; |  |
| Additional clause 11.2(121) |  | 11.2(121) |  | Third Party Software has the meaning given it in Schedule H; |  |
| Additional clause 11.2(122) |  | 11.2(122) |  | Transferring Client Employees are those employees of the Client to whom the Employment Regulations (as defined in Schedule K) will apply on the Relevant Transfer Date; |  |
| Additional clause 11.2(123) |  | 11.2(123) |  | Transferring Former Contractor Employees are, in relation to a Former Contractor, those employees of the Former Contractor to whom the Employment Regulations (as defined in Schedule K) will apply on the Relevant Transfer Date; |  |
| Additional clause 11.2(124) |  | 11.2(124) |  | TUPE Surcharge has the meaning given in Schedule K; |  |
| Additional clause 11.2(125) |  | 11.2(125) |  | Working Day is any day other than a Saturday or Sunday or public holiday in England and Wales; |  |
| Additional clause 11.2(126) |  | 11.2(126) |  | Works Exclusion Notice has the meaning given to it in clause 94.1; |  |
| Additional clause 11.2(127) |  | 11.2(127) |  | Works Exclusion Cause has the meaning given to it in clause 94.1. |  |
| Option Z3 |  |  |  | Communications |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 13.9 |  | 13.9 |  | The Contractor does not: - make any press announcements or publicise this Contract or its contents in any way; or - use the Client's name or brand in any promotion or marketing or announcement of orders; without the prior written consent of the Client. |  |
| Additional clause 13.10 |  | 13.10 |  | Each party acknowledges to the other that nothing in this contract either expressly or by implication constitutes an endorsement of any products or works of the other party (including the works) and each party agrees not to conduct itself in such a way as to imply or express any such approval or endorsement. |  |
| Additional clause 13.11 |  | 13.11 |  | Each party takes reasonable steps to ensure that its employees, agents, subcontractor's, suppliers, professional advisers and consultants comply with clauses 13.9 and 13.10. |  |
| Option Z4 |  |  |  | Integrator |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 14.6 |  | 14.6 |  | The Contractor provides to the Integrator copies of all documents and/or information required by this Contract to be provided: - to the Client, instead of the Client; and - to the Service Manager, as well as the Service Manager, unless in either case instructed otherwise by the Client. |  |
| Option Z5 |  |  |  | Early warning |  |
|  |  |  |  | Insert new clause: |  |
| Additional clause 15.5 |  | 15.5 |  | The Contractor complies, and procures compliance by its Subcontractors and other suppliers, with the risk management process described in the Scope as updated from time to time by the Client or (with the Client's approval) the Contractor. Reasons for updating the risk management process include reflecting the requirements of insurers. Any update of the risk management process by the Client shall be deemed to be an instruction from the Project Manager changing the Scope. Any update to the risk management process by the Contractor shall not be treated as a compensation event under this Contract. |  |
| Option Z6 |  |  |  | Ambiguities and Inconsistencies |  |
| Supplement to clause 17 |  | 17.1 |  | At the beginning of the second sentence, replace "The" with: "Subject to clause 2.1 of the Form of Agreement, the". |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 17.3 |  | 17.3 |  | Where an ambiguity or inconsistency in the Contractor's design accepted by the Project Manager or between the Contractor's design and the Scope, the Contractor provides the Project Manager with proposals to remove the same which are acceptable to the Project Manager acting reasonably. Such acceptance shall not be treated as an instruction changing the Scope. Where this clause 17.3 applies, in the event of any discrepancies being discovered in the documents, the Contractor shall at once notify the Project Manager in writing. If amendments to the design or methods of work are required as a result of discrepancies in the documents, such amendments shall not be regarded as a compensation event. The Contractor shall pay all fees and costs in connection therewith. The Contractor accepts entire responsibility for the design contained within the Scope for the Contractor’s design and for any mistake, inaccuracy, discrepancy or omission contained in the same. Nothing contained in the Scope for the Contractor’s design shall affect in any way the obligations of the Contractor under the Contract. |  |
| Additional clause 17.4 |  | 17.4 |  | If any term, condition or provision contained in this Contract is held to be invalid, unlawful or unenforceable to any extent, such term, condition or provision will not affect the validity, legality or enforceability of the remaining parts of this Contract |  |
| Option Z7 |  |  |  | Corrupt Acts |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 18.4 |  | 18.4 |  | The Contractor represents and warrants that neither it, nor to the best of its knowledge any of its employees, have at any time prior to the Contract Date: - committed a Corrupt Act or been formally notified that it is subject to an investigation or prosecution which relates to an alleged Corrupt Act; and/or - been listed by any government department or agency as being debarred, suspended, proposed for suspension or debarment, or otherwise ineligible for participation in government procurement programmes or Contracts on the grounds of a Corrupt Act. |  |
| Additional clause 18.5 |  | 18.5 |  | During the carrying out of the works the Contractor does not do or suffer anything to be done which would cause the Client or any of the Client’s employees, consultants, contractors, subcontractors or agents to contravene any of the Relevant Requirements or otherwise incur any liability in relation to the Relevant Requirements. |  |
| Additional clause 18.6 |  | 18.6 |  | During the carrying out of the works the Contractor: - establishes, maintains and enforces, and requires that its Subcontractors establish, maintain and enforce, policies and procedures which are adequate to ensure compliance with the Relevant Requirements and prevent the occurrence of a Corrupt Act; - keeps appropriate records of its compliance with this contract and make such records available to the Client on request; - provides and maintains and where appropriate enforces an anti-bribery policy (which shall be disclosed to the Client on request) to prevent it and any Contractor’s employees or any person acting on the Contractor's behalf from committing a Corrupt Act. |  |
| Additional clause 18.7 |  | 18.7 |  | The Contractor immediately notifies the Client in writing if it becomes aware of any breach of clause 18.1 or 18.5, or has reason to believe that it has or any of the its employees or Subcontractors have: - been subject to an investigation or prosecution which relates to an alleged Corrupt Act; - been listed by any government department or agency as being debarred, suspended, proposed for suspension or debarment, or otherwise ineligible for participation in government procurement programmes or contracts on the grounds of a Corrupt Act; and/or - received a request or demand for any undue financial or other advantage of any kind in connection with the performance of this contractor otherwise suspects that any person or Party directly or indirectly connected with this contract has committed or attempted to commit a Corrupt Act. |  |
| Additional clause 18.8 |  | 18.8 |  | If the Contractor makes a notification to the Client pursuant to clause 18.7, the Contractor responds promptly to the Client's enquiries, co-operates with any investigation, and allows the Client to audit any books, records and/or any other relevant documentation in accordance with this Contract. |  |
| Additional clause 18.9 |  | 18.9 |  | If the Contractor breaches clause 18.1 or 18.5, the Client may by notice require the Contractor to remove from Providing the Works any Contractor employee whose acts or omissions have caused the Contractor’s breach. |  |
| Additional clause 18.10 |  | 18.10 |  | The Contractor shall, as soon as reasonably practicable after becoming aware of the same, notify the Client in writing if: - any investigations are instituted into the affairs of the Contractor or any Subcontractors, other approved sub-contractors or suppliers of any of its or their directors or key managers, under the Companies, Financial Services or Banking Acts; - any police or Serious Fraud Office enquiries into possible fraud, or any involvement in Department of Trade and Industry investigations, and enquiries into the affairs of others which might result in public criticism of, or action against the Contractor or any Subcontractors or any other subcontractors or suppliers. |  |
| Additional clause 18.11 |  | 18.11 |  | The Contractor shall supply the Client with a copy of any notice, order or proposal for a notice or order affecting the Site served on the Contractor by any competent authority (or received by the Contractor from any of its Subcontractors or suppliers or other person) as soon as reasonably practicable after it is received by the Contractor and shall without delay take all steps necessary to comply with any such notice or order. |  |
| Option Z8 |  |  |  | Providing the Works |  |
| Replace clause 20.1 |  | 20.1 |  | Delete and replace with: "The Contractor provides the works in a proper and workmanlike manner and in accordance with this Contract, the Scope, the Licences, and all applicable Law." |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 20.2 |  | 20.2 |  | The Contractor undertakes to the Client that: |  |
|  |  |  |  | .1 in the carrying out of the works the Contractor shall procure that only materials and goods of sound and satisfactory quality and which have been manufactured or prepared in compliance with the specifications and quality plans; |  |
|  |  |  |  | .2 the Contractor shall (and shall procure that it Subcontractors and suppliers shall) at all times comply with the lawful requirements of the Relevant Authorities and comply with any Statutory Requirement either in carrying out the works or where design, development, workmanship, methods of construction, materials, plant, commissioning, testing or maintenance are to be reviewed by the Project Manager or any Relevant Authorities; |  |
|  |  |  |  | .3 it shall use its reasonable endeavours to ensure that all sub-contracts, equipment rental or lease agreements and all other (non-employment) contracts which are necessary to the performance of the works, are assignable to the Client or its nominee (without any transfer or charge); |  |
|  |  |  |  | .4 the Client shall acquire such title as the encumbrances created by or against the Contractor and the Client shall have the right of quiet possession thereof. |  |
| Additional clause 20.3 |  | 20.3 |  | The Contractor performs its obligations under this Contract (including those in relation to the works) in accordance with: - all applicable equality Law (whether in relation to race, sex, gender reassignment, age, disability, sexual orientation, religion or belief, pregnancy, maternity or otherwise); - the Client's Policies; - any other requirements and instructions which the Client reasonably imposes in connection with any equality obligations imposed on the Client at any time under applicable equality Law; and - the provisions of Schedule M. |  |
| Additional clause 20.4 |  | 20.4 |  | The Official Secrets Act 1989 and, where appropriate, the provisions of section 11 of the Atomic Energy Act 1946 apply to this contract from the starting date until Completion of the works or until a termination certificate has been issued. The Contractor notifies his employees and his Subcontractors of their duties under these Acts. |  |
| Additional clause 20.5 |  | 20.5 |  | The Contractor: - carries out and completes the works in conformity with the Client's obligations under the Third Party Agreements, and without infringing any right, reservation, covenant, restriction, stipulation or other encumbrance that is binding upon or affects the Site and which is notified by the Client to the Contractor. - undertakes to the Client that he has performed and will perform his obligations under this contracting such a manner and at such times that no act, omission or default by the Contractor or any of the Subcontractors or their respective employees or agents causes or contributes to any breach by the Client of any of his obligations under the Third Party Agreements and, to the extent that the Contractor causes or contributes to any breach by the Client of any of his obligations under the Third Party Agreements, the Contractor indemnifies the Client against any liability, claims, damages, costs, and losses that the Client may incur as a result of or arising out of a breach by the Contractor of his obligations under this clause 20.7. |  |
| Option Z9 |  |  |  | Tax Compliance |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 20.6 |  | 20.6 |  | The Contractor represents and warrants that as at the Contract Date, it has notified the Client in writing of any Occasions of Tax Non-Compliance or any litigation that it is involved in that is in connection with any Occasions of Tax Non-Compliance. |  |
| Additional clause 20.7 |  | 20.7 |  | If, at any point during the Provision of the Works, an Occasion of Tax Non-Compliance occurs, the Contractor shall: - notify the Client in writing of such fact within 5 days of its occurrence; and - promptly provide to the Client: - details of the steps which the Contractor is taking to address the Occasions of Tax Non-Compliance and to prevent the same from recurring, together with any mitigating factors that it considers relevant; and - such other information in relation to the Occasion of Tax Non-Compliance as the Client may reasonably require. |  |
| Option Z10 |  |  |  | Change of Control and conflicts |  |
|  |  |  |  | Insert a new clause: |  |
| Additional clause 20.8 |  | 20.8 |  | The Contractor promptly notifies the Project Manager in writing on each occasion of the occurrence of any change of control as defined by section 416 of the Income and Corporation taxes Act 1988 (any such case being a “Change of Control”). The Client is permitted to exercise its rights pursuant to this clause for only six months after service of each and any notice by the Contractor pursuant to this clause and is not permitted to exercise such rights where the Client has agreed in advance in writing to the particular Change of Control provided such Change of Control takes place as agreed. |  |
| Additional clause 20.9 |  | 20.9 |  | The Contractor discloses to the Project Manager any actual or potential conflict of interest arising from the Contractor’s provision of the works as soon as practicable after becoming aware of such actual or potential conflict. |  |
| Additional clause 20.10 |  | 20.10 |  | The Contractor immediately notifies the Project Manager of any circumstances giving rise to or potentially giving rise to conflicts of interest relating to the Contractor and/or the Client (including without limitation its reputation and standing) of which it is aware or anticipates may justify the Client taking action to protect its interests. |  |
| Additional clause 20.11 |  | 20.11 |  | The Contractor carries out (and procures that the Contractor Personnel carry out) the works in the Client's best interests. |  |
| Additional clause 20.12 |  | 20.12 |  | Without prejudice to the Contractor's obligations under clauses 20.8 to 20.11 (inclusive), the Contractor does not and procures that Subcontractors and any Contractor Personnel do not engage in Proscribed Conduct and notifies the Client immediately on any breach of this requirement. |  |
| Additional clause 20.13 |  | 20.13 |  | Without Prejudice to the Client's rights under clauses 91 and 92 where the Contractor is in breach of any of clauses 20.8 – 20.12 (inclusive) the Contractor within five (5) day of any breach becoming apparent to it, provides proposals to the Client for remedying and/or mitigating such breach. Upon any breach of clauses 20.8 – 20.12 (inclusive) becoming apparent to the Client (whether or not notified by the Contractor), the Client may at the Contractor's cost: - remove any or all of the works from the scope of this Contract and carry out such works itself and/or employ a third party to carry out such works; - require the Contractor to put such measures in place (including but not limited to information barriers) as required by the Client in its absolute discretion to rectify and/or mitigate the effect of any breach of clauses 20.8 – 20.12 (inclusive); and/or - instruct or commence increased monitoring. |  |
| Additional clause 20.14 |  | 20.14 |  | Save in the event of removal of the relevant element of the works or termination of all or part of the works, where as a result of the matters leading or contributing to a breach of clauses 20.8 – 20.12 (inclusive) the Contractor or a Contractor Personnel realises a profit or other financial benefit: - the Contractor accounts to the Client in respect of each assessment period; and - the Client is entitled to set off an amount equivalent to that financial benefit (as accounted for by the Contractor or otherwise as the Client may determine) from any amount due to the Contractor under this contract or under any other agreement between the Contractor and the Client. |  |
| Option Z11 |  |  |  | The Contractor's Design |  |
| Supplement to clause 21 |  | 21.1 |  | Insert a new second sentence as follows: "In the design and construction of the works, the Contractor takes all proper account of: - the considerations of health and safety contained in the CDM Regulations (and his design will include adequate health and safety information); and - the geological, geo-technical and sub-surface conditions affecting the Site." |  |
|  |  | 21.2 |  | Delete "the Scope" in the first line and replace with "any requirement of this Contract". Delete the second sentence and replace with "Reasons for not accepting the Contractor's design include: - that it does not comply with either the Scope or the applicable Law; and - that it has an impact on the Prices which is not necessary in order to comply with this Contract. |  |
| Option Z12 |  |  |  | - People |  |
| Additional clause 24.3 – 24.6 |  |  |  | Insert new clauses 24.3 to 24.6: |  |
|  |  | 24.3 |  | The Contractor ensures that the key persons named in the Contract Data fulfil the relevant jobs specified in the Contract Data at all times during the Provision of the Works. The Contractor appoints the key people to fill those jobs at the starting date. |  |
|  |  | 24.4 |  | The Client identifies any further jobs and, following agreement to the same by the Contractor the list of key people in the Contract Data includes the relevant person selected to fill those jobs. |  |
|  |  | 24.5 |  | - The Contractor does not remove or replace any key person unless: - the Client requests that the Contractor does so; - the key person concerned resigns, retires or dies or is on maternity or long-term sick leave; - the key person’s employment or Contractual arrangement with the Contractor or a Subcontractor is terminated for material breach of contract by the employee; or - the Contractor obtains the Client's prior written consent (such consent not to be unreasonably withheld or delayed). |  |
|  |  | 24.6 |  | - The Contractor: - notify the Client promptly of the absence of any key person(s) (other than for short-term sickness or holidays of 2 weeks or less, in which case the Contractor shall ensure appropriate temporary cover for that key person); - ensures that any key person's job is not vacant for any longer than ten (10) Working Days; - gives as much notice as is reasonably practicable of its intention to remove or replace any key person and, except in the cases of death, unexpected ill health or a material breach of the key person's employment contract, this will mean at least sixty (60) Working Days’ notice; - ensures that all arrangements for planned change of a key person or key people provide adequate periods during which incoming and outgoing key people work together to transfer responsibilities and ensures that such change does not have an adverse impact on the performance of the Services; and - ensures that any replacement for a key person: - has a level of qualifications and experience appropriate to the relevant key person; and - is fully competent to carry out the tasks assigned to the key person whom he or she has replaced. |  |
| Option Z13 |  |  |  | Contractor Personnel |  |
| Additional clause 24.4 |  | 24.7 |  | If the Client reasonably believes that any of the Contractor Personnel are unsuitable to undertake work in respect of this Contract, it may: - refuse admission to the relevant person(s) to the Site; and/or - direct the Contractor to end the involvement in the Provision of the Works of the relevant person(s). |  |
| Additional clause 24.8 | 24.8 |  | Where: - the commencement of the provision of the works or any part thereof results in one or more Relevant Transfers, Contract Schedule K, Part 1 shall apply as follows: - where the Relevant Transfer involves the transfer of Transferring Client Employees, Section A of Contract Schedule K, Part 1 shall apply; - where the Relevant Transfer involves the transfer of Transferring Former Contractor Employees, Section B of the Contract Schedule K, Part 1 shall apply; - where the Relevant Transfer involves the transfer of Transferring Client Employees and Transferring Former Contractor Employees, Sections A and B of Contract Schedule K, Part 1 shall apply; and - Section C of Contract Schedule K, Part 1 shall not apply; - commencement of the provision of the works or a part of thereof does not result in a Relevant Transfer, Section C of Contract Schedule K, Part 1 shall apply and Sections A and B of Contract Schedule K, Part 1 shall not apply; and - expiry or termination of the works or any part of thereof occurs Section D of Contract Schedule K, Part 1 shall apply. |  |  |
| Option Z14 |  |  |  | Working with the Client and Others |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 25.4 |  | 25.4 |  | .1 Compliance by the Contractor with this clause 25.4 is without additional cost to the Client. The Contractor shall not be entitled to a Compensation Event or otherwise to additional time or cost as a consequence of failure by it to observe this clause nor by the failure of Others to observe similar provisions in their contracts with the Client. |  |
|  |  |  |  | .2 The Contractor: a. provides access and co-operation to Others as required by the Project Manager; |  |
|  |  |  |  | b. co-ordinates and integrates the execution of the works with works of Others including those engaged by the Client under any contract which the Client may enter into in relation to the Site; |  |
|  |  |  |  | c. complies with such instructions as issued by the Project Manager to co-ordinate the Contractor's execution of the works with the work of Others; |  |
|  |  |  |  | d. plans and coordinates the works in accordance with the requirements of the Project Manager, taking into account the presence of Others and acknowledging in particular the need to communicate and cooperate with Others so that the works and the works provided by Others are delivered in a coordinated and efficient manner without delay or disruption to the works and avoiding unnecessary disruption or inconvenience to the users of the Site through lack observance of the requirements of this clause; |  |
|  |  |  |  | e. affords reasonable facilities for Others who are properly authorised or who are statutory bodies employed in the execution on or near the Site of any works not in the contract or which is required under any contract which the Client may enter into in relation to the Site; |  |
|  |  |  |  | f. provides or assists in provision of all information, data, know-how and calculations necessary for the Client and/or any person appointed by the Client to carry out any works or services in a timely, economic and efficient manner without delay and disruption and keeps the Client informed at all times of all relevant matters pertaining to the Site; |  |
|  |  |  |  | g. is fully responsible for identifying and obtaining all information, data, know-how, calculations, drawings, documents, reports, investigations and surveys used for or in connection with the Site the provision of which is undertaken by Others in order that the works are executed in a timely, economic and efficient manner without delay and disruption to the business of the Client; |  |
|  |  |  |  | h. jointly and severally with Others engaged by the Client co-operates and manages the interface of the works with the works of such Others and provides all management services, labour, materials, goods, plants and works necessary for the Contractor's cooperation and management; and i. updates the latest programme as appropriate to reflect any matter set out in this clause. |  |
| Additional clause 25.5 |  | 25.5 |  | It is agreed and declared that the Contractor could reasonably foresee the activities of Others engaged by the Client and statutory undertakers referred to in the Scope on or near the Site. |  |
| Additional clause 25.6 |  | 25.6 |  | The Contractor provides attendance for Others as may be directed by the Client. For this purpose attendance shall be deemed to cover all expenses incurred by the Contractor in: - planning, programming and co-ordinating the works with that of Others; and - accepting delivery, unloading and storing material for Others as required. |  |
| Additional clause 25.7 |  | 25.7 |  | The Contractor shall ensure that the Client's business is not interrupted, hindered or prevented due to the act, neglect or omission of the Contractor or any person for whom it is responsible or as a result of any industrial action or interruption in utilities supplies, provided that this clause 25.7 shall not apply in relation to interruption in utilities supplies caused directly by the Client. |  |
| Option Z15 |  |  |  | Subcontracting |  |
| Amendment to clause 26 |  | 26.2 |  | Delete clauses 26.2 and 26.3 and replace with the following: |  |
|  |  | 26.2 |  | The Contractor exercises due skill and care in the selection and appointment of any Subcontractor to ensure that the Contractor is able to: - manage any Subcontractors in accordance with Good Industry Practice; - comply with its obligations under the contract in the delivery of the works; and - assign, novate or otherwise transfer to the Client any of its rights and/or obligations under each sub-contract that relates to this Contract. |  |
|  |  | 26.3 |  | Prior to sub-contracting any of its obligations under this Contract, the Contractor notifies the Client in writing of: - the proposed Subcontractor's name, registered office and company registration number; - the scope of any works to be provided by the proposed Subcontractor; and - where the proposed Subcontractor is an Affiliate of the Contractor, evidence that demonstrates to the reasonable satisfaction of the Client that the proposed Sub-contract has been agreed on an arms-length basis, and provides the Client with a copy of the proposed sub-contract and any other information reasonably required by the Client. |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 26.4 |  | 26.4 |  | The Client may within ten (10) days of receipt of the Contractor's notice issued pursuant to clause 26.3 (or if later receipt of any further information requested pursuant to clause 26.3) object to the appointment of the relevant proposed Subcontractor if it considers that: - the appointment of a proposed Subcontractor may prejudice the provision of the works and/or may be contrary to the interests of the Client; - the proposed Subcontractor is unreliable and/or has not provided reasonable services to its other customers; - the proposed Subcontractor employs unfit persons; and/or - the proposed Subcontractor should be excluded in accordance with clause 26.5. |  |
| Additional clause 26.5 |  | 26.5 |  | Where the Client considers whether there are grounds for the exclusion of a Subcontractor under Regulation 57 of the Public Contracts Regulations 2015, then: - if the Client finds there are compulsory grounds for exclusion, the Contractor replaces or does not appoint the proposed Subcontractor; - if the Client finds there are non-compulsory grounds for exclusion, the Client may require the Contractor to replace or not to appoint the Subcontractor and the Contractor complies with such a requirement. |  |
| Additional clause 26.6 |  | 26.6 |  | The Contractor shall not and shall procure that any Subcontractor, other approved sub-contractors and suppliers shall not place or cause to be placed any orders with suppliers, or otherwise incur liabilities in the name of the Client or any representative of the Client. |  |
| Option Z16 |  |  |  | Other responsibilities |  |
| Supplement to clause 27 |  | 27.1 |  | Re-number 27.1 as 27.1.1 and insert, at the end of this clause: .2 The Client obtains the Licences required to Provide the Works which the Scope states are to be provided by the Client. The Contractor obtains all other Licences required to Provide the Works. |  |
|  |  |  |  | .3 The Contractor obtains the Licences required for use of the completed works which the Scope states are to be obtained by the Contractor. The Client obtains any other Licences required for use of the completed works. |  |
|  |  |  |  | .4 In relation to Licences which it is the Client's responsibility to obtain, the Contractor (without taking the risk that such Licences are not obtained, save to the extent that this is caused by the Contractor's failure to provide the support required by this Contract): - provides such support as the Scope states the Contractor is to provide to the Client in applying for and obtaining such Licences; and - provides such other support as the Client reasonably requires, not entailing excessive cost to the Contractor (or if entailing such cost, provided the same is reimbursed by the Client). |  |
|  |  |  |  | .5 The Contractor ensures that the works comply with all Licences and Laws. The Contractor's duty to Provide the Works includes providing all work necessary to satisfy the requirements of any agreement entered into by the Client and/or the Contractor with Others pursuant to the requirements of a Licence, unless (in relation only to work which is not situated on or adjacent to the Site) the Client, acting reasonably, agrees otherwise in writing. |  |
| Option Z17 |  |  |  | CDM Regulations |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 27.5 |  | 27.5 |  | Where stated in the Contract Data, the Contractor is the Principal Designer, Principal Contractor, and a designer for the works for the purposes of the CDM Regulations. |  |
| Additional clause 27.6 |  | 27.6 |  | The Contractor takes full responsibility for the adequacy, stability and safety of all site operations (so far as the Site is under his control) and methods of construction in relation to the works and obeys the requirements of the CDM Regulations. |  |
| Option Z18 |  |  |  | Freedom of Information and Transparency |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 27.7 |  | 27.7 |  | The Contractor acknowledges that unless the Project Manager has notified the Contractor that the Client is exempt from the provisions of the FOIA, the Client is subject to the requirements of the FOIA and the Environmental Information Regulations. The Contractor cooperates with and assists the Client so as to enable the Client to comply with its information disclosure obligations. |  |
| Additional clause 27.8 |  | 27.8 |  | The Contractor: - transfers to the Project Manager all Requests for Information that it receives as soon as practicable and in any event within two Working Days of receiving a Request for Information; - provides the Project Manager with a copy of all Information in its possession, or power in the form that the Project Manager requires within five (5) Working Days (or such other period as the Project Manager may specify) of the Project Manager’s request; - provides all necessary assistance as reasonably requested by the Project Manager to enable the Client to respond to the Request for Information within the time for compliance set out in section 10 of the FOIA or regulation 5 of the Environmental Information Regulations; and - procures that its Subcontractors do likewise. |  |
| Additional clause 27.9 |  | 27.9 |  | The Client is responsible for determining in its absolute discretion whether any information is exempt from disclosure in accordance with the provisions of the FOIA or the Environmental Information Regulations. |  |
| Additional clause 27.10 |  | 27.10 |  | The Contractor does not respond directly to a Request for Information unless authorised to do so by the Project Manager. |  |
| Additional clause 27.11 |  | 27.11 |  | The Contractor acknowledges that the Client may, acting in accordance with the Department of Constitutional Affairs’ Code of Practice on the Discharge of the Functions of Public Authorities under Part 1 of FOIA, be obliged to disclose Information without consulting or obtaining consent from the Contractor or despite the Contractor having expressed negative views when consulted. |  |
| Additional clause 27.12 |  | 27.12 |  | The Contractor ensures that all Information is retained for disclosure throughout the period for retention and permits the Project Manager to inspect such records as and when reasonably requested from time to time. |  |
| Additional clause 27.13 |  | 27.13 |  | The parties acknowledge that: - reports generated by the Contractor pursuant to the terms of this contract; and - the content of this contract, including any changes to this contract agreed from time to time, except for: - any information which is exempt from disclosure in accordance with the provisions of the FOIA, which shall be determined by the Client; and - commercially sensitive information; (together the Transparency Information) are not Confidential Information. |  |
| Additional clause 27.14 |  | 27.14 |  | Notwithstanding any other provision of this contract, the Contractor hereby gives its consent for the Client to publish to the general public the Transparency Information in its entirety (but with any information which is exempt from disclosure in accordance with the provisions of the FOIA redacted). The Client shall, prior to publication, consult with the Contractor on the manner and format of publication and to inform its decision regarding any redactions but shall have the final decision in its absolute discretion. |  |
| Additional clause 27.15 |  | 27.15 |  | The Contractor shall assist and co-operate with the Client to enable the Client to publish the Transparency Information. |  |
| Additional clause 27.16 |  | 27.16 |  | If the Client believes that publication of any element of the Transparency Information would be contrary to the public interest, the Client shall be entitled to exclude such information from publication. The Client acknowledges that it would expect the public interest by default to be best served by publication of the Transparency Information in its entirety. Accordingly, the Client acknowledges that it will only exclude Transparency Information from publication in exceptional circumstances and agrees that where it decides to exclude information from publication it will provide a clear explanation to the Contractor. |  |
| Additional clause 27.17 |  | 27.17 |  | The Client shall publish the Transparency Information in a format that assists the general public in understanding the relevance and completeness of the information being published to ensure the public obtain a fair view on how this contract is being performed, having regard to the context of the wider commercial relationship with the Contractor. |  |
| Option Z19 |  |  |  | Records and reports |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 27.18 |  | 27.18 |  | All records created pursuant to this contract including without limitation financial records, sub-contract agreements, supply agreements, progress reports, quality monitoring and health and safety documents shall be retained and maintained for a period of 6 years by the Contractor in sufficient detail, an organised manner and generally in such manner to enable the Contractor to comply with its obligations under the contract and shall be made available for inspection to the Client upon request. |  |
| Additional clause 27.19 |  | 27.19 |  | Where records are maintained as provided in clause 27.18 and the period for their retention has expired, the Contractor shall notify the Client with regards to its retention in relation to such records and if it intends to dispose of them or subsequently decides to dispose of them it shall notify the Client and if the Client, within sixty (60) business days of such notice elects to receive certain of those records, the Contractor shall deliver such records to the Client in the manner and at the location as the Client shall reasonably specify. |  |
| Additional clause 27.20 |  | 27.20 |  | The Contractor shall on request afford the Client all such rights of access to those records required to be kept by the Contractor under clause 27.18 as may be required for the purpose of examination and certification of the Client's accounts or any examination pursuant to Section 6(1) of the National Audit Act 1983 of the economy, efficiency and effectiveness with which the Client has used its resources. The Comptroller and Auditor General (both as defined by the National Audit Act 1983) may examine documents evidencing expenditure and income by the Client which are owned, held or otherwise within the control of the Contractor and may require the Contractor to produce such oral or written explanations as the Client considers necessary. |  |
| Option Z20 |  |  |  | Malicious Software |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 27.21 |  | 27.21 |  | The Contractor shall, as an enduring obligation throughout the Provision of the Works, use the latest versions of anti-virus definitions and software available from an industry accepted anti-virus software vendor to check for, contain the spread of, and minimise the impact of Malicious Software in the ICT Environment (or as otherwise agreed by the parties). |  |
| Additional clause 27.22 |  | 27.22 |  | Notwithstanding the above clause, if Malicious Software is found, the parties shall co-operate to reduce the effect of the Malicious Software and, particularly if Malicious Software causes loss of operational efficiency or loss or corruption of Client Data, assist each other to mitigate any losses and to restore the service to their desired operating efficiency. |  |
| Additional clause 27.23 |  | 27.23 |  | Any cost arising out of the actions of the parties taken in compliance with the provisions of the above clause shall be borne by the parties as follows: - by the Contractor where the Malicious Software originates from the Contractor's own software, the Third Party Software supplied by the Contractor (except where the Client has waived the obligation) or the Client Data (whilst the Client Data was under the control of the Contractor) unless the Contractor can demonstrate that such Malicious Software was present and not quarantined or otherwise identified by the Client when provided to the Contractor; and - by the Client if the Malicious Software originates from the Client's Software (in respect of which the Client has waived its obligation) or the Client Data (whilst the Client Data was under the control of the Client). |  |
| Option Z21 |  |  |  | Public and private nuisance |  |
|  |  |  |  | Insert new clause: |  |
| Additional clause 27.24 |  | 27.24 |  | The Contractor, at all times, prevents any public or private nuisance (including, without limitation, any such nuisance caused by noxious fumes, noisy working operations or the deposit of any material or debris on the public highway) or other interference with the rights of any adjoining or neighbouring landowner, tenant or occupier or any statutory undertaker arising out of Providing the Works or the performance of any obligation pursuant to clause 44 and assists the Client in defending any action or proceedings which may be instituted in relation thereto. |  |
| Additional clause 27.25 |  | 27.25 |  | The Contractor ensures that there is no trespass on or over any adjoining or neighbouring property arising out of or in the course of Providing the Works or the performance of any obligation pursuant to clause 44. If Providing the Works or the performance of any obligation pursuant to clause 44 is likely to necessitate any interference (including, without limitation, the over-sailing of tower crane jibs) with the rights of adjoining or neighbouring owners or occupiers, then the Contractor, at no cost to the Client, is to obtain the prior written agreement of such owners and/or occupiers thereto, and such agreement is subject to the approval of the Client before execution. The Contractor is to comply in every respect with any conditions contained in any such agreement. |  |
| Option Z22 |  |  |  | Client Data |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 27.26 |  | 27.26 |  | The Contractor shall not delete or remove any proprietary notices contained within or relating to the Client Data. |  |
| Additional clause 27.27 |  | 27.27 |  | The Contractor shall not store, copy, disclose, or use the Client Data except as necessary to Provide the Works or as otherwise expressly authorised in writing by the Client. |  |
| Additional clause 27.28 |  | 27.28 |  | To the extent that Client Data is held and/or processed by the Contractor, the Contractor shall supply that Client Data to the Client as requested by the Client and in the format specified in this contract (if any) and in any event as specified by the Client from time to time in writing. |  |
| Additional clause 27.29 |  | 27.29 |  | The Contractor shall take responsibility for preserving the integrity of Client Data and preventing the corruption or loss of Client Data. |  |
| Additional clause 27.30 |  | 27.30 |  | The Contractor shall perform secure back-ups of all Client Data and shall ensure that up-to-date back-ups are stored off-site in accordance with: - any business continuity and/or disaster recovery plan created as part of the contract (if any); - the Client’s requirements set out in this contract (if any); - Good Industry Practice; and - such reasonable instructions in relation to business continuity and disaster recovery as the Client may notify to the Contractor from time to time. (together the "BCDR Requirements") |  |
| Additional clause 27.31 |  | 27.31 |  | The Contractor ensures that such back-ups are available to the Client at all times upon request and delivers to the Client at regular intervals prescribed by the Client from time to time acting reasonably. The Contractor delivers all existing Client Data not previously provided to the Client within 10 days of termination of this Contract. |  |
| Additional clause 27.32 |  | 27.32 |  | The Contractor shall ensure that any system on which the Contractor holds any Client Data, including back-up data, is a secure system that: - complies with the DWP Information Security Policy; - complies with the Baseline Security Requirements; - is capable of implementing and enforcing appropriate security standards as specified by DWP from time to time including but not limited to the result of any information risk assessment undertaken pursuant to the DWP Enterprise Security Risk Management Strategy; - as part of HMG Security Policy Framework, complies with and shall have certificated the HMG Cyber Essentials Scheme or approved equivalent as defined under the HMG Cyber Essentials Scheme (further details available at: www.cyber-essentials-scheme.co.uk); - complies with all relevant aspects of the Government Digital Service Open Standards. |  |
| Additional clause 27.33 |  | 27.33 |  | If the Client Data is corrupted, lost or sufficiently degraded as a result of an action, error, breach or default of the Contractor so as to be unusable, the Client may: - require the Contractor (at the Contractor's expense) to restore or procure the restoration of Client Data to the extent and in accordance with the BCDR Requirements and the Contractor shall do so as soon as practicable but in any event not later than such date as is notified to the Contractor by the Client acting reasonably; and/or - itself restore or procure the restoration of Client Data, and shall be repaid by the Contractor any reasonable expenses incurred in doing so to the extent and in accordance with the requirements specified the by BCDR Requirements. |  |
| Additional clause 27.34 |  | 27.34 |  | If at any time the Contractor suspects or has reason to believe that Client Data has or may become corrupted, lost or sufficiently degraded in any way for any reason, then the Contractor shall notify the Client immediately and inform the Client of the remedial action the Contractor proposes to take. |  |
| Additional clause 27.35 |  | 27.35 |  | The Contractor complies with the requirements of Schedule H. |  |
| Additional clause 27.36 |  | 27.36 |  | The Contractor and its Subcontractors comply with the DWP Offshoring Policy. |  |
| Additional clause 27.37 |  | 27.37 |  | In accordance with the DWP Offshoring Policy and without limiting any other provision of this contract, the Contractor and any of its Subcontractors, do not offshore Client Data outside the United Kingdom without the prior written consent of the Client. Where the Client gives consent, the Contractor complies with any reasonable instructions notified to it by the Client in relation to the Client Data in question. |  |
| Additional clause 27.38 |  | 27.38 |  | Where the Client has given its prior written consent to the Contractor to process, host or access Client Data from premises outside the United Kingdom (in accordance with clause 27.37): - the Contractor notifies the Client (in so far as they are not prohibited by Law) where any Regulatory Bodies seek to gain or have gained access to such Client Data; and - the Contractor takes all necessary steps in order to prevent any access to, or disclosure of, any Client Data to any regulatory bodies outside the United Kingdom unless required by Law without any applicable exception or exemption |  |
| Additional clause 27.39 |  | 27.39 |  | The Client notifies the Contractor of any changes or proposed changes to the Baseline Security Requirements. The Contractor complies with any such changes required by the Client. |  |
| Additional clause 27.40 |  | 27.40 |  | The Contractor retains throughout the period for retention: - copies of drawings, specifications, reports, calculations and other documents which record the works; - documents and information obtained or prepared by the Contractor or any Subcontractor in connection with this Contract. |  |
| Additional clause 27.41 |  | 27.41 |  | The copies are retained in the form stated in the Scope and - in accordance with the requirements of the National Archives and Good Industry Practice; - in chronological order; - in a form capable of audit; and - at its own expense. |  |
| Additional clause 27.42 |  | 27.42 |  | The Contractor permits the Project Manager and/or the Client to examine documents held or controlled by the Contractor or any Subcontractor. |  |
| Additional clause 27.43 |  | 27.43 |  | The Contractor provides such oral or written explanations as the Project Manager and/or the Client considers necessary. |  |
| Additional clause 27.44 |  | 27.44 |  | This clause does not constitute a requirement or agreement for the purposes of section 6(3) (d) of the National Audit Act 1983 for the examination, certification or inspection of the accounts of the Contractor. |  |
| Additional clause 27.45 |  | 27.45 |  | The Contractor acknowledges that all Client Data is owned by the Client. The Project Manager and/or the Client may request the Contractor to deliver up to the Client and/or Project Manager (in a format notified by the Client and/or Project Manager and at no cost) any and all Client Data and the Contractor delivers up such Client Data within 7 days following a request. |  |
| Additional clause 27.46 |  | 27.46 |  | The Contractor ensures that (at no additional cost to the Client) the Contractor System on which the Contractor holds any Client Data fully integrates and interoperates with any system of the Client and Project Manager (including but not limited to the Client's System) such that the Client Data is available to the Client, the Integrator and the Project Manager via the systems of the Client and the Integrator (including but not limited to the Clients System). The Contractor does not store or process any Client Data on its own systems alone without such Client Data being also available to the Client and the Project Manager through the interface with the system of the Client and Project Manager (including but not limited to the Client's System). The Contractor and the Project Manager work together to ensure that their respective systems on which Client Data is stored and processed interface and interoperate appropriately. |  |
| Option Z23 |  |  |  | Protection of Personal Data |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 27.42 |  | 27.47 |  | The parties acknowledge that during the Provision of the Works the Contractor will Process Personal Data on behalf of the Client in connection with the Provision of the Works and may also, from time to time, Process Personal Data for its own purposes as a Data Controller in connection the Provision of the Works. |  |
| Additional clause 27.48 |  | 27.48 |  | In all cases when the Contractor is Processing Personal Data in connection with this contract as a Data Controller the Contractor shall (and shall procure that all Subcontractors shall): - take such steps identified by the Client to assist the Client to comply with the Data Protection Legislation; - comply with the Data Protection Legislation; - not: - do anything to cause the Client to contravene any provisions of the Data Protection Legislation; - carry out any Processing of Client's Data, or any Personal Data obtained in the course of this contract at or from a location outside of the United Kingdom without the Client's prior consent; or - allow Authority Data to be accessed from outside of the United Kingdom without the Client's prior consent; - ensure that at all times it has in place appropriate technical and organisational measures to guard against unauthorised or unlawful processing of the Personal Data and/or accidental loss, destruction or damage to the Personal Data, including the measures as are set out in clause 27.26-27.46 and Schedules H and P); - provide all reasonable co-operation and assistance as may be requested by the Client from time to time to enable the Client to comply with the Data Protection Legislation, including providing input into and carrying out data protection impact assessments and assisting with consultations with the Information Commissioner's Office; - notify the Client promptly if a data security breach occurs, if any complaints are made or if a regulatory investigation is commenced (in each case in connection with the Personal Data) and provide all such information as may be requested by the Client in relation to such breach, complaint or notification (as applicable); and - provide the Client with such information as the Client may from time to time require to satisfy itself that the Contractor and its Subcontractors have complied with the obligations of clauses 27.47-27.50 (inclusive). |  |
| Additional clause 27.49 |  | 27.49 |  | Without limiting clause 27.48 or any applicable standards, policies, procedures and regulations specified in the Client's Policies, the parties shall comply with their respective obligations as set out in Schedule P. |  |
|  |  | 27.50 |  | The Contractor, via the Contractor System or otherwise, has systems and processes in place to receive and process requests from the helpdesk operated by the Integrator in accordance with and within the timescales stipulated in the Scope. |  |
| Option Z24 |  |  |  | Income Tax and National Insurance Contributions |  |
|  |  |  |  | Insert new clause |  |
|  |  | 27.51 |  | - Where the Contractor or any Contractor Personnel are liable to be taxed in the UK or to pay national insurance contributions in respect of consideration received under this contract, the Contractor: |  |
|  |  |  |  | - .1 at all times complies with the Income Tax (Earnings and Pensions) Act 2003 and all other statutes and regulations relating to income tax, and the Social Security Contributions and Benefits Act 1992 and all other statutes and regulations relating to national insurance contributions, in respect of that consideration; and |  |
|  |  |  |  | - .2 indemnifies the Client against any income tax, national insurance and social security contributions and any other liability, deduction, contribution, assessment or claim arising from or made in connection with the Provision of the Works by the Contractor or any Contractor Personnel. |  |
| Option Z25 |  |  |  | Assignment |  |
|  |  |  |  | Delete clause 28.1 and replace with the following new clauses 28.1 – 28.5: |  |
| Amendment to clause 28.1 |  | 28.1 |  | The Client is entitled to assign or otherwise dispose of its rights under this contract or any part thereof to: - any Contracting Body; - any other body (including any private sector body) which substantially performs any of the functions that previously had been performed by the Client; or - to a devolved government or assembly (or agency thereof) which performs any of the functions that previously had been performed by the Client. |  |
| Additional clause 28.2 |  | 28.2 |  | The Contractor does not, without the written consent of the Project Manager, assign or transfer this contract, or any part of, share of or interest in it. In the absence of the Project Manager’s written consent no sum of money becoming due under this contract is payable to any person other than the Contractor. |  |
| Additional clause 28.3 |  | 28.3 |  | The Client is entitled to, and the Contractor gives consent and agrees to give effect to, the novation of this contract or any part thereof to: - any Contracting Body; or - any other body (including any private sector body) which substantially performs any of the functions that previously had been performed by the Client; upon such terms as the Client proposes, provided that where such novation increases the burden on the Contractor pursuant to this contract, the novation shall be a compensation event. The Contractor shall do all things required to give effect to such novation including executing a deed of novation at the request of the Client. |  |
| Additional clause 28.4 |  | 28.4 |  | Any change in the legal status of the Client such that it ceases to be a Contracting Body does not affect the validity of this contract. In such circumstances, this contract binds and inures to the benefit of any successor body to the Client. |  |
| Additional clause 28.5 |  | 28.5 |  | If this contract is novated to a body which is not a Contracting Body or if a successor body which is not a Contracting Body becomes the Client (both such bodies being referred to in the remainder of this clause as the “transferee”) the transferee is only able to assign, novate or otherwise dispose of its rights and obligations under this contract or any part thereof with the written consent of the Contractor. |  |
| Option Z26 |  |  |  | Small and Medium Sized Enterprises (SMEs) |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 29.3 |  | 29.3 |  | The Contractor is required to take all reasonable steps to engage SMEs as Subcontractors and to seek to ensure that no fewer than the percentage of the Subcontractors stated in the Contract Data (the “SME Percentage”) are SMEs or that a similar proportion of the Defined Cost of the works is undertaken by SMEs. |  |
| Additional clause 29.4 |  | 29.4 |  | The Contractor is required to report to the Client in its regular contract management monthly reporting cycle the numbers of SMEs engaged as Subcontractors and the value of the Defined Cost of the works that has been undertaken by SMEs. |  |
| Additional clause 29.5 |  | 29.5 |  | Where available and if required by the Client, the Contractor is required to tender its sub-contracts using the same online electronic portal as was provided by the Client for the purposes of tendering this Contract. |  |
| Additional clause 29.6 |  | 29.6 |  | The Contractor is to ensure that the terms and conditions used to engage Subcontractors are no less favourable than those of this contract. A reason for the Project Manager not accepting Sub-Contract conditions proposed by the Contractor is that they are unduly disadvantageous to the Subcontractor. |  |
| Option Z27 |  |  |  | Apprenticeships |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 29.7 |  | 29.7 |  | The Contractor is required to take all reasonable steps to employ apprentices, and report to the Client the numbers of apprentices employed and the wider skills training provided, during the delivery of the works. |  |
| Additional clause 29.8 |  | 29.8 |  | The Contractor is required to take all reasonable steps to ensure that no fewer than the percentage of its employees stated in the Contract Data (the “Apprenticeship Percentage”) are on formal apprenticeship programmes or that a similar proportion of hours worked in delivering the works, (which may include support staff and Subcontractors) are provided by employees on formal apprenticeship programmes. |  |
| Additional clause 29.9 |  | 29.9 |  | The Contractor is required to make available to its employees and Subcontractors working on the contract, information about the Government’s Apprenticeship programme and wider skills opportunities. |  |
| Additional clause 29.10 |  | 29.10 |  | The Contractor is to provide any further skills training opportunities that are appropriate for its employees engaged in Providing the Works. |  |
| Additional clause 29.11 |  | 29.11 |  | The Contractor is to provide a written report detailing the following measures in its regular contract management monthly reporting cycle and be prepared to discuss apprenticeships at its regular meetings with the Project Manager: - the number of people during the reporting period employed on the contract, including support staff and Subcontractors; - the number of apprentices and number of new starts on apprenticeships directly initiated through the procurement process; - the percentage of all employees taking part in an apprenticeship programme; - if applicable, an explanation from the Contractor as to why it is not managing to meet the specified percentage target; - actions being taken to improve the take up of apprenticeships; - other training/skills development being undertaken by employees in relation to this contract, including: - work experience placements for 14 to 16 year olds; - work experience /work trial placements for other ages; - student sandwich/gap year placements; - graduate placements; - vocational training; - basic skills training; and - on site training provision/ facilities. |  |
| Option Z28 |  |  |  | IPR and Confidentiality |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 29.12 |  | 29.12 |  | In clause 29.13 – 29.19 only: “Document” means all designs, drawings, specifications, software, electronic data, photographs, plans, surveys, reports, and all other documents and/or information prepared by or on behalf of the Contractor in relation to this Contract. |  |
| Additional clause 29.13 |  | 29.13 |  | The Intellectual Property Rights in all Documents prepared by or on behalf of the Contractor in relation to this Contract and the works executed from them remains the property of the Contractor. The Contractor hereby grants to the Client an irrevocable, royalty free, non-exclusive licence to use and reproduce the Documents for any and all purposes connected with the Site. Such licence entitles the Client to grant sub-licences to third parties in the same terms as this licence provided always that the Contractor shall not be liable to any licensee for any use of the Documents or the Intellectual Property Rights in the Documents for purposes other than those for which the same were originally prepared by or on behalf of the Contractor. |  |
| Additional clause 29.14 |  | 29.14 |  | In the event that the Contractor does not own the copyright or any Intellectual Property Rights in any Document the Contractor uses all reasonable endeavours to procure the right to grant such rights to the Client to use any such copyright or Intellectual Property Rights from any third party owner of the copyright or Intellectual Property Rights. In the event that the Contractor is unable to procure the right to grant to the Client in accordance with the foregoing the Contractor procures that the third party grants a direct licence to the Client on industry acceptable terms. |  |
| Additional clause 29.15 |  | 29.15 |  | The Contractor waives any moral right to be identified as author of the Documents in accordance with section 77, Copyright Designs and Patents Acts 1988 and any right not to have the Documents subjected to derogatory treatment in accordance with section 8 of that Act as against the Client or any licensee or assignee of the Client. |  |
| Additional clause 29.16 |  | 29.16 |  | In the event that any act unauthorised by the Client infringes a moral right of the Contractor in relation to the Documents the Contractor undertakes, if the Client so requests and at the Client’s expense, to institute proceedings for infringement of the moral rights. |  |
| Additional clause 29.17 |  | 29.17 |  | The Contractor warrants to the Client that he has not granted and shall not (unless authorised by the Client) grant any rights to any third party to use or otherwise exploit the Documents. |  |
| Additional clause 29.18 |  | 29.18 |  | The Contractor supplies copies of the Documents to the Project Manager and to the Client’s other Contractors and consultants for no additional fee to the extent necessary to enable them to discharge their respective functions in relation to this contract or the works. |  |
| Additional clause 29.19 |  | 29.19 |  | After the termination or conclusion of the Contractor’s employment hereunder, the Contractor supplies the Project Manager with copies and/or computer discs of such of the Documents as the Project Manager may from time to time request and the Client pays the Contractor’s reasonable costs for producing such copies or discs. |  |
| Additional clause 29.20 |  | 29.20 |  | In Providing the Works the Contractor does not infringe any Intellectual Property Rights of any third party. The Contractor indemnifies the Client against claims, proceedings, compensation and costs arising from an infringement or alleged infringement of the Intellectual Property Rights of any third party. |  |
| Additional clause 29.21 |  | 29.21 |  | The Client grants to the Contractor a limited, non-exclusive, non-transferable, non-sub licensable licence during the Provision of the Works to use the Client's systems, and software solely for the purpose of providing the works to the Client under this contract and for no other use. The licence granted by the Client terminates on termination of this contract howsoever arising. The Contractor indemnifies and keeps indemnified the Client on demand from and against all and any losses, cost or expenses (including management costs and professional fees) whatsoever arising out of or in connection with any liability arising in respect of the Contractor's use of the Project Manager's systems and software licenced to the Contractor by the Client under this clause 29.21. |  |
| Additional clause 29.22 |  | 29.22 |  | The Contractor grants to the Client, the Integrator, and the Project Manager a perpetual, royalty free, sub-licensable and non-exclusive licence to use (including but not limited to the right to load, execute, store, transmit, display and copy (for the purposes of archiving, backing-up, loading, execution, storage, transmission or display) the Contractor System for the purpose of receiving the benefit of the works or otherwise in connection with this contract. The Contractor provides all support and maintenance services in respect of the use of the Contractor System by the Client and the Project Manager. |  |
| Additional clause 29.23 |  | 29.23 |  | Except to the extent set out in this clause or where disclosure is expressly permitted elsewhere in this contract, each party shall: - treat the other party's Confidential Information as confidential and safeguard it accordingly; and - not disclose the other party's Confidential Information to any other person without the owner's prior written consent. |  |
| Additional clause 29.24 |  | 29.24 |  | The clause above shall not apply to the extent that: - such disclosure is a requirement of the Law placed upon the party making the disclosure, including any requirements for disclosure under the FOIA or the Environmental Information Regulations; - such information was in the possession of the party making the disclosure without obligation of confidentiality prior to its disclosure by the information owner; - such information was obtained from a third party without obligation of confidentiality; - such information was already in the public domain at the time of disclosure otherwise than by a breach of this contract; or - it is independently developed without access to the other party's Confidential Information. |  |
| Additional clause 29.25 |  | 29.25 |  | The Contractor may only disclose the Client Confidential Information to the Contractor Personnel who are directly involved in the provision of the works and who need to know the information, and shall ensure that such Contractor Personnel are aware of and shall comply with these obligations as to confidentiality. The Contractor shall not, and shall procure that the Contractor Personnel do not, use any of the Client Confidential Information received otherwise than for the purposes of this Contract. |  |
| Additional clause 29.26 |  | 29.26 |  | In the event that any default, act or omission of any Contractor Personnel causes or contributes (or could cause or contribute) to the Contractor breaching its obligations as to confidentiality under or in connection with this contract, the Contractor shall take such action as may be appropriate in the circumstances, including the use of disciplinary procedures in serious cases. To the fullest extent permitted by its own obligations of confidentiality to any Contractor Personnel, the Contractor shall provide such evidence to the Client as the Client may reasonably require (though not so as to risk compromising or prejudicing the case) to demonstrate that the Contractor is taking appropriate steps to comply with this clause, including copies of any written communications to and/or from Contractor Personnel, and any minutes of meetings and any other records which provide an audit trail of any discussions or exchanges with Contractor Personnel in connection with obligations as to confidentiality. |  |
| Additional clause 29.27 |  | 29.27 |  | At the written request of the Client, the Contractor shall procure that those members of the Contractor Personnel identified in the Client's notice signs a confidentiality undertaking prior to commencing any work in accordance with this Contract. |  |
| Additional clause 29.28 |  | 29.28 |  | Nothing in this Contract shall prevent the Client from disclosing and the Client may disclose the Contractor Confidential Information: - on a confidential basis to any Crown Body or any other Contracting Bodies. All Crown Bodies or Contracting Bodies receiving such Confidential Information shall be entitled to further disclose the Confidential Information to other Crown Bodies or other Contracting Bodies on the basis that the information is confidential and is not to be disclosed to a third party which is not part of any Crown Body or any Contracting Body; - to Parliament and Parliamentary Committees or if required by any Parliamentary reporting requirement; - to any consultant, contractor or other person engaged by the Client; - for the purpose of the exercise of its rights under this Contract; - for the purpose of the examination and certification of the Client's accounts; or - on a confidential basis to a proposed successor body of the Client in connection with any assignment, novation or disposal of any of its rights, obligations or liabilities under this Contract; - for any examination pursuant to Section 6(1) of the National Audit Act 1983 of the economy, efficiency and effectiveness with which the Client has used its resources. and for the purposes of the foregoing, disclosure of the Contractor Confidential Information shall be on a confidential basis and subject to a confidentiality agreement or arrangement containing terms no less stringent than those placed on the Client under this clause 29.28. |  |
| Additional clause 29.29 |  | 29.29 |  | The Client shall use all reasonable endeavours to ensure that any government department, Contracting Body, employee, third party or Subcontractor to whom the Contractor Confidential Information is disclosed pursuant to the above clause is made aware of the Client's obligations of confidentiality. |  |
| Additional clause 29.30 |  | 29.30 |  | Nothing in this clause shall prevent either party from using any techniques, ideas or know-how gained during the performance of the contract in the course of its normal business to the extent that this use does not result in a disclosure of the other party's Confidential Information or an infringement of IPR |  |
| Additional clause 29.31 |  | 29.31 |  | The Contractor warrants to the Client that: - to the best of the Contractor's knowledge, all information, representation and other matters of fact communicated in writing to the Client or its agents or employees in connection with the Contractor's response to the invitation to tender in respect of the works or in the course of the subsequent negotiations in respect of this contract are true, complete and accurate in all material respects at the time communicated to the Client or its agents or employees; - it is a limited liability company, duly incorporated and validly existing under the laws of the jurisdiction of its incorporation; - it has full power and authority to enter into this contract and to carry out the works and this contract is executed by duly authorised representatives; - the entry into and performance by it of this contract does not and will not: - conflict with its constitutional documents; and - conflict with any document which is binding upon it, or any of its assets to the extent that such conflict would be reasonably likely to have a material adverse effect on the ability of the Contractor to perform its obligations under this Contract. |  |
| Option Z29 |  |  |  | Collateral warranty agreements |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 29.32 |  | 29.32 |  | The Contractor enters into the collateral warranty agreements in the relevant formats appended in Schedule G in favour of the parties identified in the Contract Data and delivers executed copies in duplicate to the Project Manager no later than ten (10) Working Days after the Project Manager has provided the Contractor with appropriate collateral warranty agreements suitable for execution. |  |
| Additional clause 29.33 |  | 29.33 |  | The Contractor procures from the Subcontractors identified in the Contract Data collateral warranty agreements in the relevant formats appended in Schedule G in favour of the parties identified in the Contract Data and delivers executed copies in duplicate to the Project Manager no later than fifteen (15) Working Days after the Project Manager has provided the Contractor with appropriate collateral warranty agreements suitable for execution. |  |
| Additional clause 29.34 |  | 29.34 |  | If the Contractor fails to deliver the required collateral warranty agreements in the manner and within the time stipulated by this contract, one quarter (1/4) of the Price for Works Provided to Date is retained in assessments of the amount due until the Contractor has remedied the failure. |  |
| Option Z30 |  |  |  | Starting, Completion and Key Dates |  |
|  |  |  |  | Insert new clause: |  |
| Additional clause 30.4. |  | 30.4 |  | Before Completion, the Contractor supplies to the Client, without additional charge, such documents, deliverables and other related information as may be specified in the Scope or as the Client may request, showing or describing the works as constructed and concerning the maintenance and operation of the works including any Plant. Notwithstanding any provision to the contrary in this contract, the Contractor is not entitled to any payment of any amount retained pursuant to clause X16 that would (but for this provision) become due and payable until the provisions of this clause 30.4 have been complied with. If, prior to the issue of the Defects Certificate, errors are discovered in the documents, drawings and information supplied by the Contractor in accordance with this clause 30.4 or, if as a result of any revision or remedial work carried out prior to the issue of the Defects Certificate, the said documents, drawings and information no longer show or describe the works as required by this clause 30.4, then the Contractor is to amend the said documents, drawings and information so that they comply with the requirements of this clause 30.4. |  |
| Option Z31 |  |  |  | Revising the programme |  |
| Additional clause 32.3 |  | 32.3. |  | "The Contractor: .1 provides at least seven (7) days' in advance of any admission to the Site a list of the names of all Contractor Personnel requiring such admission, specifying the capacity in which they require admission and giving such other particulars as the Client reasonably requires; |  |
|  |  |  |  | .2 ensures that all Contractor Personnel: |  |
|  |  |  |  | - are appropriately qualified, trained and experienced to Provide the Works with all reasonable skill, care and diligence; |  |
|  |  |  |  | - are vetted in accordance with Good Industry Practice and, where applicable, the security requirements set out in the Scope and Schedule H; and |  |
|  |  |  |  | - comply with such rules, regulations and requirements (including those relating to security arrangements) as are in force from time to time for the conduct of personnel and all reasonable requirements of the Site conduct at or outside of the Site, including the security requirements as set out in Schedule H; |  |
|  |  |  |  | .3 subject to Schedule I, retains overall control of the Contractor Personnel at all times so that the Contractor Personnel are not deemed to be employees, agents or Contractors of the Client; |  |
|  |  |  |  | .4 is liable at all times for all acts or omissions of Contractor Personnel, so that any act or omission of a member of any Contractor Personnel which results in a default under this contract is a default by the Contractor; |  |
|  |  |  |  | .5 uses all reasonable endeavours to minimise the number of changes in Contractor Personnel; |  |
|  |  |  |  | .6 replaces (temporarily or permanently, as appropriate) any Contractor Personnel as soon as practicable if any Contractor Personnel have been removed or are unavailable for any reason whatsoever; |  |
|  |  |  |  | .7 bears the programme familiarisation and other costs associated with any replacement of any Contractor Personnel; and |  |
|  |  |  |  | .8 procures that the Contractor Personnel vacate the Site immediately upon the termination or expiry of this Contract." |  |
| Option Z32 |  |  |  | Access to and use of the Site |  |
| Supplement to clause 33 |  | 33.1 |  | After the words "each part of the Site to the Contractor", insert "in accordance with the Scope". Before the words "Access and use", insert: "The Contractor acknowledges that access to and use of the Site may be shared with Others in accordance with the Scope." |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 33.2 |  | 33.2 |  | The Contractor submits to the Project Manager details of people who are to be employed by him and his Subcontractors in connection with the works. The details include a list of names and addresses, the capabilities in which they are employed, and other information required by the Project Manager. |  |
| Additional clause 33.3 |  | 33.3 |  | The Project Manager may instruct the Contractor to take measures to prevent unauthorised persons being admitted to the Site. The instruction is a compensation event if the measures are additional to those required by the Scope. |  |
| Additional clause 33.4 |  | 33.4 |  | Employees of the Contractor and his Subcontractors are to carry a Client’s pass whilst they are on the parts of the Site identified in the Scope. |  |
| Additional clause 33.5 |  | 33.5 |  | The Contractor submits to the Project Manager for acceptance a list of the names of the people for whom passes are required. The Project Manager issues the passes to the Contractor. Each pass is returned to the Project Manager when the employee no longer requires access to that part of the Site or after the Project Manager has given notice that the employee is not to be admitted to the Site. |  |
| Option Z33 |  |  |  | Acceleration |  |
| Supplement to clause 36 |  | 36.1 |  | After the words "A quotation for an acceleration comprises proposed changes to the Prices" insert "(unless the acceleration is required to recover delay beyond the Completion Date not resulting from a compensation event, in which case the Prices are not adjusted)." |  |
| Option Z34 |  |  |  | Correcting Defects |  |
| Supplement to clause 43 |  | 43.2 |  | After the words "the Contractor corrects a notified Defect" insert "in accordance with any applicable timeframes set out in the Defects Protocol, and in any event". |  |
| Option Z35 |  |  |  | Uncorrected Defects |  |
| Amendment to clause 46 |  | 46.1 |  | Delete clauses 46.1 and 46.2 and replace with the following: "If the Contractor fails to correct any Defect within the defect correction period, the Client may employ or pay others to correct such Defect and the Contractor pays to the Client the following: - the reasonable and proper costs incurred by the Client in employing and paying others to correct such Defect; and - any other losses incurred by the Client as a consequence of the Contractor's failure to correct such Defect within the defect correction period." |  |
| Option Z36 |  |  |  | Assessing the amount due |  |
| Supplement to clause 50 |  | 50.1 |  | Change the first word from "The" to "the" and insert at the beginning: "Provided the Project Manager has received all substantiation necessary or reasonably required by the Project Manager and the Contractor has complied with its obligations under clause 26, clause X4 and clause X13". |  |
| Option Z37 |  |  |  | Payment certificates |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 56.1 |  | 56.1 |  | The issue of any payment certificate or the payment of any amount by the Client to the Contractor does not constitute or imply or be evidence of the Project Manager's, the Supervisor's, or the Client's approval or acceptance of any design, work, Plant and Materials forming part of the works or relieve the Contractor of any of his obligations under this Contract. |  |
| Additional clause 56.2 |  | 56.2 |  | The Contractor assesses the amount due to a Subcontractor without taking into account the amount certified by the Project Manager. |  |
| Additional clause 56.3 |  | 56.3 |  | The Contractor includes in the contract with each Subcontractor - a period for payment of the amount due to the Subcontractor not greater than 5 days after the final date for payment in this contract. The amount due includes, but is not limited to, payment for work which the Subcontractor has completed from the previous assessment date up to the current assessment date in this Contract, - a provision requiring the Subcontractor to include in each subsubcontract the same requirement, except that the period for payment is to be not greater than 9 days after the final date for payment in this contract and - a provision requiring the Subcontractor to assess the amount due to a subsubcontractor without taking into account the amount paid by the Contractor. |  |
| Additional clause 56.4 |  | 56.4 |  | The Client may set off any liability of the Contractor to: - the Client; - any Contracting Body; or - any Crown Body against any liability of the Client, any Contracting Body or any Crown Body, whether such liability is present or future, liquidated or unliquidated and whether or not such liability arises under this Contract. |  |
| Option Z38 |  |  |  | Compensation Events |  |
| Supplement to clause 60 |  | 60.1(2) |  | In the first line, after "Site", insert "within the time periods stated in the Scope as being the time periods during which access to the Site will be available to the Contractor." |  |
|  |  | 60.1(10) |  | At the end of the sentence, insert "or where, although the search fails to disclose non-compliance with this contract and/or the Scope, such search was instigated as a result of problems or failures having been discovered in similar items of Plant, Materials or the works, and the Project Manager or the Supervisor had reasonable grounds to believe that such a problem or fault existed in the items of Plant, Materials or the works on which the search was carried out." |  |
| Additional clause 63.17 |  |  |  | Insert new clause: |  |
|  | 63.17 |  | A compensation event which - arises from a difference between the rates of pay of Transferring Former Contractor Employees and/or Transferring Client Employees and the equivalent rates of pay used by the Contractor and/or Notified Sub-contractor to calculate the Prices under the Framework Agreement, the change to the Prices is the TUPE Surcharge assessed in accordance with Schedule K, Part 2 - arises where a Transferring Former Contractor Employee and/or any Transferring Client Employee is made redundant by the Contractor and/or any Notified Sub-Contractor as a result of an economic technical organisational reason entailing changes to the workforce and the Contractor and/or the Notified Sub-Contractor has followed a fair dismissal procedure and complied with all contractual and legislative requirements, the change to the Prices is the Redundancy Surcharge assessed in accordance with Schedule K, Part 2. |  |  |
| Option Z39 |  |  |  | Improvement Plan Process |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 67.1 |  | 67.1 |  | The Contractor notifies the Client of a Notifiable Event within 3 days of becoming aware of the same and in such notice sets out details of the actual or anticipated effect of the Notifiable Event. |  |
| Additional clause 67.2 |  | 67.2 |  | If the Client considers that a Notifiable Event has occurred or the Client receives a notice from the Contractor under clause 67.1, the Client may serve notice (an Improvement Notice) on the Contractor setting out sufficient detail to make it clear what the Contractor has to rectify. |  |
| Additional clause 67.3 |  | 67.3 |  | Where an Improvement Notice is served under clause 67.2 the Contractor submits to the Client a draft Improvement Plan and the Client reviews it as soon as possible and in any event within 10 days (or such other period as the parties agree) of the original notification under clause 67.1 or 67.2. The Contractor submits a draft Improvement Plan even if it disputes that it is responsible for the Notifiable Event. |  |
| Additional clause 67.4 |  | 67.4 |  | The draft Improvement Plan sets out: - full details of the Notifiable Event; - the steps the Contractor proposes to take to rectify the Notifiable Event (if applicable) and to prevent such Notifiable Event from recurring, including timescales for such steps. |  |
| Additional clause 67.5 |  | 67.5 |  | The Contractor provides the Client with such additional information or documentation as the Client reasonably requires. |  |
| Additional clause 67.6 |  | 67.6 |  | The Client notifies the Contractor that: - it agrees the draft Improvement Plan; or - it rejects the draft Improvement Plan because it is inadequate for example because it is not detailed enough to evaluate, will take too long to complete, will not prevent reoccurrence of the Notifiable Event or is otherwise unacceptable to the Client. Where the Client does so it shall set out its reasons for doing so. |  |
| Additional clause 67.7 |  | 67.7 |  | Where the Client accepts the Improvement Plan the Contractor immediately implements the actions in the Improvement Plan. |  |
| Additional clause 67.8 |  | 67.8 |  | Where the Client rejects the Improvement Plan the Contractor resubmits its draft Improvement Plan taking into account the Client's comments within 5 day of notice that the Client rejects the preceding Improvement Plan. |  |
| Additional clause 67.9 |  | 67.9 |  | In relation to a KPI Failure, the Client may terminate this contract because the Contractor fails: - to submit a draft Improvement Plan to the Client in accordance with clause 67.4 or 67.8; - to submit a draft Improvement Plan which the Client acting reasonably does not approve; - to rectify a Notifiable Event capable of remedy within the later of: - 30 day of notification pursuant to clause 67.1; or - Where the parties agree an Improvement Plan and the Contractor is implementing the same, the date for rectification stipulated in the Improvement Plan. - Following successful implementation of a Improvement Plan the same event occurs within a period of 6 months for the same (or substantially the same) root cause as that original Notifiable Event, (each an Improvement Plan Failure). |  |
| Additional Clause 66.10 |  | 67.10 |  | Where the Client accepts the Improvement Plan, the Contractor immediately implements the actions in the Improvement Plan. |  |
| Option Z40 |  |  |  | Increased Monitoring |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 68.1 |  | 68.1 |  | At any time the Client may notify the Contractor that it is increasing its level of monitoring of the Contractor and/or (at the Client's option) of the Contractor's monitoring of its own performance under this Contract until such time as the Contractor demonstrates to the reasonable satisfaction of the Client that is performing its obligations under this Contract. |  |
| Additional clause 68.2 |  | 68.2 |  | Where the Client issues a notice under clause 68.1 as a result of any failure by the Contractor to perform its obligations under this contract, the Contractor bears its own costs and indemnifies and keeps indemnified the Client at all times from and against all reasonable costs and expenses incurred by or on behalf of the Client (including management costs and professional fees) in relation to such increased monitoring. |  |
| Additional clause 68.3 |  | 68.3 |  | Where the Client issues a notice under 68.1 other than as a result of any failure by the Contractor to perform its obligations under this contract, the Client bears its own costs and indemnifies and keeps indemnified the Contractor at all times from and against all reasonable costs and expenses incurred by or on behalf of the Contractor in relation to such increased monitoring. |  |
| Option Z41 |  |  |  | Remedial Adviser |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 68.4 |  | 68.4 |  | Without prejudice to any right to terminate this contract the Client may have, if an Intervention Trigger Event occurs or, in the Client's reasonable opinion, is likely to occur the Client gives notice to the Contractor with reasonable details in the Intervention Trigger Event and requiring: - a meeting between the Client and the Contractor to discuss the Intervention Trigger Event; and/or - the appointment as soon as practicable of a Remedial Adviser. |  |
| Additional clause 68.5 |  | 68.5 |  | If the Client notifies the Contractor that it requires a Remedial Adviser to the appointed: - the Contractor shall select and the Client shall approve within 10 day a person to be appointed as Remedial Adviser or if no such person is approved the Client shall identify the person to be appointed as Remedial Adviser; - the terms of engagement and start date agreed with the Remedial Adviser are approved by the Client; - any right of the Client to terminate this contract in respect of the relevant Intervention Trigger Event is suspended for 60 days from the date of the notice issued pursuant to this clause 68.5 (the Intervention Period). |  |
| Additional clause 68.6 |  | 68.6 |  | The Remedial Adviser's overall objective is to mitigate the effects of, and (to the extent possible) remedy the relevant Intervention Trigger Event and avoid the recurrence of the same. In order to achieve that objective the parties agree that the Remedial Adviser may: - observe the conduct of and work alongside the Contractor Personnel to the extent that the Remedial Adviser considers reasonable and proportionate having regard to the relevant Intervention Trigger Event; - gather any information the Remedial Adviser considers relevant in the furtherance of its objective; - write reports and provide information to the Client in connection with the steps being taken by the Contractor to remedy the relevant Intervention Trigger Event; - make recommendations to the Client and/or the Contractor as to how the relevant Intervention Trigger Event might be mitigated or avoided in the future; and/or - take any other steps that the Client and/or the Remedial Adviser reasonably considers necessary or expedient in order to mitigate or rectify the relevant Intervention Trigger Event. |  |
| Additional clause 68.7 |  | 68.7 |  | The Contractor: - works alongside, provide information to, co-operate in good faith with and adopt any reasonable methodology in providing the works recommended by the Remedial Adviser. - ensures that the Remedial Adviser has all the access it may require in order to carry out its objective, including access to the Site; - submits to such monitoring as the Client and/or the Remedial Adviser considers reasonable and proportionate in respect of the relevant Intervention Trigger Event; - implements all reasonable recommendations made by the Remedial Adviser and approved by the Client within the timescales stipulated; and - shall not terminate the appointment of the Remedial Adviser prior to the end of the Intervention Period without the Client's consent, not to be unreasonably withheld. |  |
| Additional clause 68.8 |  | 68.8 |  | The Contractor is responsible for the costs of appointing, and the fees charged by, the Remedial Adviser. The Contractor bears its own costs in connection with any action required by the Client and/or Remedial Adviser pursuant to this clause 68. |  |
| Additional clause 68.9 |  | 68.9 |  | If the Contractor fails to comply with the instructions given in any notice issued pursuant to clause 68.4 or defaults on its obligations under clause 68.7 or if the relevant Intervention Trigger Event is not rectified by the end of the Intervention Period (each a Remedial Adviser Failure) the Client is entitled to terminate this Contract. |  |
| Option Z42 |  |  |  | Step in rights |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 69.1 |  | 69.1 |  | On the occurrence of a Step-In Trigger Event the Client serves notice on the Contractor (a Step-In Notice) that it will take action under this clause 69 either itself or via a third party specifying: - the action that the Client wishes to take and in particular the works that it wishes to control (the Required Action); - the Step-In Trigger Event that has occurred and whether the Client believes that the Required Action is due to a default by the Contractor; - the date on which it wishes to commence the Required Action; - the time period which it believes will be necessary for the Required Action; and - to the extent practicable, the impact that the Client anticipates the Required Action will have on the Contractor's obligations to Provide the Works during the period that the Required Action is being taken |  |
| Additional clause 69.2 |  | 69.2 |  | Following service of a Step-In Notice the Client: - takes the Required Action(s) and any consequential additional actions as it reasonably believes is necessary to achieve the Required Action; - keeps records of the Required Action(s) taken and provide information about the same to the Contractor; - co-operates wherever reasonable with the Contractor in order to enable the Contractor to continue to Provide the Works in relation to which the Client is not assuming control; - acts reasonably in mitigating the cost that the Contractor will incur as a result of the exercise of the Client's rights under this clause 69. |  |
| Additional clause 69.3 |  | 69.3 |  | For so long as and to the extent that the Required Action is continuing, then: - the Contractor shall not be obliged to Provide the Works to the extent that they are the subject of the Required Action; - no deductions shall be applicable in relation to amounts due under this contract in respect of works that are the subject of the Required Action; and - the Client shall deduct its additional costs of providing the Required Action(s) from amounts otherwise due under this contract. |  |
| Additional clause 69.4 |  | 69.4 |  | If the Contractor demonstrates to the reasonable satisfaction of the Client that the Required Action is resulting in the degradation of any works not subject to the Required Action beyond that which would be the case if the Client was not taking the Required Action, then the Contractor shall be entitled to an agreed adjustment of the Price. |  |
| Additional clause 69.5 |  | 69.5 |  | Before ceasing to exercise its right to step-in, the Client delivers a written notice to the Contractor (a Step-Out Notice), specifying: - the Required Action it has actually taken; and - the date on which the Client plans to end the Required Action (the Step-Out Date) subject to the Client being satisfied with the Contractor's ability to resume the provision of the works and the Contractor providing a satisfactory Step-Out Plan. |  |
| Additional clause 69.6 |  | 69.6 |  | The Contractor, following receipt of a Step-Out Notice and not less than twenty (20) day prior to the Step-Out Date, develops for approval a draft plan (a Step-Out Plan) relating to the resumption by the Contractor of the works, including any action the Contractor proposes to take to ensure that the affected works satisfy the requirements of this Contract. |  |
| Additional clause 69.7 |  | 69.7 |  | If the Client does not approve the draft Step-Out Plan, the Client informs the Contractor of its reasons for not doing so. The Contractor shall then revise the draft Step-Out Plan taking those reasons into account and shall re-submit the revised plan to the Client for approval. The Client shall not withhold or delay approval of the draft Step-Out Plan unnecessarily. |  |
| Additional clause 69.8 |  | 69.8 |  | The Contractor shall bear its own costs in connection with any step-in by the Client under this clause 69, provided that the Client shall reimburse the Contractor's reasonable additional expenses incurred directly as a result of any step-in action taken by the Client other than as a result of a default of threat of default by the Contractor. |  |
| Option Z43 |  |  |  | Liabilities and insurance |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 83.4 |  | 83.4 |  | The Contractor does not without the prior written approval of the Project Manager settle or compromise with the insurers any claim which the Contractor may have against the insurers and which relates to a claim by the Client against the Contractor, nor by any act or omission lose or prejudice the Contractor’s right to make or proceed with such a claim against the insurers. |  |
| Additional clause 83.5 |  | 83.5 |  | The Contractor shall discharge in full all duties and obligations in respect of the Insurance Act 2015 when procuring, maintaining or amending any insurance(s) required by this Contract, including in circumstances where the Contractor is required to name the Client on any such insurance policies to protect the Client’s separate interests. |  |
| Additional clause 83.6 |  | 83.6 |  | Where the minimum limit of indemnity required in relation to any of the Insurances is specified as being "in the aggregate": - if a claim or claims which do not relate to this contract are notified to the insurers which, given the nature of the allegations and/or the quantum claimed by the third party(ies), is likely to result in a claim or claims being paid by the insurers which could reduce the level of cover available below that minimum, the Contractor shall immediately submit to the Client: - details of the policy concerned; and - its proposed solution for maintaining the minimum limit of indemnity specified; and - if and to the extent that the level of insurance cover available falls below that minimum because a claim or claims which do not relate to this contract are paid by insurers, the Contractor shall: - ensure that the insurance cover is reinstated to maintain at all times the minimum limit of indemnity specified for claims relating to this contract; or - if the Contractor is or has reason to believe that it will be unable to ensure that insurance cover is reinstated to maintain at all times the minimum limit of indemnity specified, immediately submit to the Client full details of the policy concerned and its proposed solution for maintaining the minimum limit of indemnity specified.. |  |
| Additional clause 83.7 |  | 83.7 |  | Except where the Client is the claimant party, the Contractor gives the Client notice within twenty (20) working days after any insurance claim in excess of fifty thousand pounds (£50,000) relating to this contract on any of the insurances required by this contract or which, but for the application of the applicable policy excess, would be made on any of the insurances required by this contract and (if required by the Client) provides full details of the incident giving rise to the claim. The Contractor co-operates with the Client and assist it in dealing with such claims including without limitation providing information and documentation in a timely manner. |  |
| Additional clause 83.8 |  | 83.8 |  | The public liability insurance required by this contract is in the joint names of the Client and such other person as the Project Manager may reasonably require including, without limitation, the Client’s consultants and contractors, the Contractor and all Subcontractors. |  |
| Additional clause 83.9 |  | 83.9 |  | All insurances required to be effected and maintained under this contract are placed with reputable insurers, to whom the other party has no reasonable objection, lawfully carrying on such insurance business in the United Kingdom, and upon customary and usual terms prevailing for the time being in the European insurance market. The said terms and conditions do not include any term or condition to the effect that any insured must discharge any liability before being entitled to recover from the insurers. |  |
| Additional clause 83.10 |  | 83.10 |  | Nothing in this clause 83 relieves the Contractor from any of its obligations and liabilities under this Contract |  |
| Option Z44 |  |  |  | Termination |  |
| Supplement to clause 90 |  | 90.2 |  | Delete the Termination Table and replace with: TERMINATION TABLE. Terminating Party; Reason; Procedure; Amount due. The Client; A reason other than R1-R32; P1, P2 and P4; A1, A2 and A4. R1-R15, R18 or R22-R38; P1, P2, P3 and P4; A1, A2 and A3. R17 or R20; P1 and P4; A1 and A2. R21; P1, P3 and P4; A1 and A2. The Contractor; R1-R10, R16 or R19; P1, P2 and P4; A1, A2 and A4. R17 or R20; P1, P2 and P4; A1 and A2. R23; P1, P2, P3 and P4; A1, A2 and A3. |
|  |  |  |  | Replace clause 91.8 with the following: |  |
| Additional clause 91.8 |  | 91.8 |  | The Client may terminate if: .1 the Contractor - does a Corrupt Act, unless it was done by a Subcontractor or supplier and the Contractor: - was not and should not have been aware of the Corrupt Act, or - informed the Project Manager of the Corrupt Act and took action to stop it as soon as the Contractor became aware of it, or breaches clause 18.7, 18.8 or 18.9 (R22); |  |
|  |  |  |  | .2 the Parties are unable to either remove a conflict of interest and/or to reduce its damaging effect to a reasonably acceptable level (R23); or |  |
|  |  |  |  | .3 the warranty given by the Contractor in relation to Occasions of Tax Non-Compliance is materially untrue (R24); or |  |
|  |  |  |  | .4 the Contractor commits a material breach of its obligation to notify the Client of any Occasion of Tax Non-Compliance (R25); or |  |
|  |  |  |  | .5 the Contractor fails to provide details of proposed mitigating factors in accordance with this contract in relation to any Occasion of Tax Non-Compliance which in the reasonable opinion of the Client, are acceptable (R26). |  |
|  |  |  |  | .6 the Contractor: - is convicted or has been convicted of a criminal offence relating to the conduct of its business or profession (R27); or - commits or is found to have committed an act of grave misconduct in the course of its business or profession (R28); or - fails or has failed to comply with any obligations relating to the payment of any taxes or social security contributions (R29); or - has made any serious misrepresentations in the tendering process for any project or matter in which the public sector has or had a significant participation (R30); or - fails to obtain any necessary licences or to obtain or maintain membership of any relevant body (R31); or - demerges into two or more firms, merges with another firm, incorporates or otherwise changes its legal form or there is a change of control as defined by section 416 of the Income and Corporation taxes Act 1988 (any such case being a “Change of Control”) and, in any such Change of Control, there are reasonable grounds for the Client to withhold its consent relating to the financial standing of the new entity through which it is proposed that the works will be delivered or there are security concerns arising from the provision of the works by the new entity (R32); or - breaches clauses 20.11 or 20.12 (R33); |  |
|  |  |  |  | .7 on the occurrence of a: - Remedial Adviser Failure; - Improvement Plan Failure; or - Critical Performance Failure (R34). |  |
|  |  |  |  | .8 the Contractor fails to notify the Client of an event of the kind contemplated by Paragraph 2.1 to Contract Schedule Q (R35); |  |
|  |  |  |  | .9 the Client and the Contractor fail to agree a Financial Distress Recovery Plan (or any updated Financial Distress Recovery Plan) in accordance with Paragraphs 3.3.2 (a) and 3.5 to 3.9 of Contract Schedule Q (Financial Distress) (R36); |  |
|  |  |  |  | .10 the Contractor fails to comply with the terms (in whole or in part) of the Financial Distress Recovery Plan (or any updated Financial Distress Recovery Plan) in accordance with Contract Schedule Q (Financial Distress) (R37); and/or |  |
|  |  |  |  | .11 the Contractor fails to comply with or defaults on its obligations under Paragraph 3.9 to Contract Schedule Q (Financial Distress) (R38). |  |
| Option Z45 |  |  |  | Termination of Subcontracts |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 91A |  | 92.3 |  | The Contractor terminates a contract with a Subcontractor where the Client requires the Contractor to do so for a reason (1) to (4) below: - the acts or omissions of the relevant Subcontractor have caused or materially contributed to the Client's right of termination pursuant to clause 90 (Termination); - the relevant Subcontractor or any of its Affiliates have embarrassed the Client or otherwise brought the Client into disrepute by engaging in any act or omission which is reasonably likely to diminish the trust that the public places in the Client, regardless of whether or not such act or omission is related to the Subcontractor's obligations in relation to the works or otherwise; - the relevant Subcontractor has failed to comply in the performance of its sub-contract with legal obligations in the fields of environmental, social or labour Law; and/or - there is a breach of clauses 20.8 – 20.10 (inclusive) and/or 20.12 by the Subcontractor or by the Contractor as a result of the Subcontractors involvement in the delivery of the works. |  |
| Option Z46 |  |  |  | Works exclusion |  |
|  |  |  |  | Insert new clauses: |  |
| Additional clause 94.1 |  | 94.1 |  | Where the Contractor: - breaches clauses 20.8 – 20.10 (inclusive) and/or 20.12 or the Client reasonably believes that a breach of clauses 20.8 – 20.10 (inclusive) and/or 20.12 has or is likely to occur; and/or - a material breach in relation to part of the works; (each a Works Exclusion Cause) the Client may give notice to the Contractor (a Works Exclusion Notice) giving reasonable details of the Works Exclusion Cause. |  |
| Additional clause 94.2 |  | 94.2 |  | Following service of a Works Exclusion Notice: - the Client takes and/or procure that a third party takes the action set out in the Works Exclusion Notice and any consequential additional action as it reasonably believes is necessary to ensure that the works (or relevant part thereof) are delivered to the standard required pursuant to the terms of this contract and so that the Client is not in breach of any applicable Law, the Client's Policies and/or its statutory duties; - without double counting the Contractor is responsible for the Client's reasonable and properly incurred costs and expenses (including any internal management time and/or procurement cost associated with appointing a third party) relating to the exercise of the Client's rights under this clause 94; and - the Price is adjusted to reflect the removal of the relevant part of the works identified in the Works Exclusion Notice. |  |
| Option Z47 |  |  |  | Changes in Law |  |
| Supplement to clause X2 |  | X2.1 |  | Delete X2.1 and replace with: |  |
|  |  | X2.1 |  | The Contractor is not relieved of its obligations pursuant to this Contract and is not entitled to claim that a compensation event has occurred as the result of: - a change in Law which is of a general legislative nature including taxation or duties of any sort affecting the Contractor; or - any other change in Law which an experienced Contractor ought to have foreseen as at the Contract Date. |  |
|  |  |  |  | Insert new clause: |  |
| Additional clause X2.2 |  | X2.2 |  | Subject to clause X2.1 A change in the Law in the country in which the Site is located is a compensation event if it is a Specific Change in Law which: - occurs after the Contract Date; - impacts on the performance of the works in a material way; and - it is not one of the other compensation events stated in this Contract, |  |
| Additional clause X2.3 |  | X2.3 |  | The Project Manager may notify the Contractor of a compensation event for a change in the Law and instruct him to submit quotations. If the effect of a compensation event which is a change in the Law is to reduce the total Defined Cost, the Prices are reduced. |  |
| Option Z48 |  |  |  | Ultimate holding company guarantee |  |
| Supplement to clause X4 |  | X4.1 |  | Delete the words "the Scope" and replace with "Schedule N". At the end of the clause, insert the following: "Until the Contractor discharges its obligations under this clause, the Project Manager when certifying payment deducts from the Price for Work Done to Date a sum being 10% of the Price for Work Done to Date." |  |
| Option Z49 |  |  |  | Option X7: Delay damages |  |
| Supplement to clause X7.1 |  | X7.1 |  | After the second bullet point, add a new sentence as follows: “The Contractor hereby acknowledges that such delay damages are not the Client’s sole remedy.” |  |
| Option Z50 |  |  |  | Performance bond |  |
| Supplement to clause X13 |  | X13.1 |  | Insert at the beginning of the clause the following sentence "The Contractor complies with this clause where an ultimate holding company does not own the Contractor." Replace the words "the Scope" with the words "Schedule N". At the end of the clause, insert the following: "Until the Contractor discharges its obligations under this clause, the Project Manager when certifying payment deducts from the Price for Work Done to Date a sum being 10% of the Price for Work Done to Date." |  |
| Option Z51 |  |  |  | The Contractor's design |  |
| Supplement to clause X15 |  | X15.1 |  | Delete "reasonable skill and care" and replace with "all the reasonable skill care and diligence of a competent design consultant experienced in work of a similar size, scale and complexity as the works." |  |
| Supplement to clause X15.5 |  |  |  | At the end of the clause, insert "The Contractor obtains and maintains the professional indemnity insurance upon customary and usual terms and conditions prevailing for the time being in the insurance market, and with reputable insurers lawfully carrying on such insurance business in the United Kingdom on the basis and in an amount not less than that stated in the Contract Data, provided always that such insurance is available at commercially reasonable rates. The said terms and conditions do not include any term or condition to the effect that the Contractor must discharge any liability before being entitled to recover from the insurers." |  |
| Option Z52 |  |  |  | Retention |  |
|  |  |  |  | Insert new clause: |  |
| Additional clause X16.3 |  | X16.3 |  | The Client's interest in the amount retained shall not be fiduciary, either as trustee for the Contractor or any other person. The relationship of the Client and the Contractor with regard to the amount retained shall be solely that of debtor and unsecured creditor and subject to the terms of this contract. The Client shall have no obligation to invest the amount retained or any part thereof. The Client shall have no obligation to place the amount retained or any part thereof in a separate banking account nor shall the Client be required to identify any amount retained as being held by the Client on trust and the Client shall be entitled to the full beneficial interest in any interest accruing on such amount retained and shall be under no duty to account for any such interest to the Contractor. |  |
| Option Z53 |  |  |  | Limitation of liability |  |
| Supplement to clause X18.4 |  | X18.4 |  | Delete the text of the third bullet point and replace with "any amounts payable by the contract pursuant to clause X20." |  |
| Option Z54 |  |  |  | Performance Indicators (not used with Option X12) |  |
| Supplement to clause X20 |  |  |  | Delete X20 and replace with: |  |
|  |  | X20.1 |  | From the starting date until the date of the issue of the Defects Certificate, the Contractor reports to the Project Manager: .1 the management and performance information required by Schedule I and J respectively; .2 his performance against each of the Key Performance Indicators and the Subsidiary Performance Indicators. Reports are provided at monthly intervals. |  |
|  |  | X20.2 |  | Subject to clause X20.3, if: |  |
|  |  |  |  | .1 a KPI Failure occurs, Service Credits accrue in respect of such KPI Failure and may be deducted from an amount due to the Contractor or are paid by the Contractor in accordance with clause X20.4; |  |
|  |  |  |  | .2 a Material KPI Failure occurs, the Contractor complies with the Improvement Plan process if the failure is a Notifiable Event and Service Credits accrue in accordance with clause X20.4; |  |
|  |  |  |  | .3 a SPI Failure occurs, the Contractor notifies the Project Manager of the action (if any) it proposes to take to rectify the SPI Failure and/or to prevent the SPI Failure from recurring; and/or |  |
|  |  |  |  | .4 a Material SPI Failure occurs: - the Contractor complies with the Improvement Plan Process if the failure if a Notifiable Event; and - the Project Manager withholds a proportionate sum (calculated on the same basis as Service Credits are calculated by reference to the Service Failure Points for the relevant SPI Failure) from the amount due until the relevant Material SPI Failure is rectified to the reasonable satisfaction of the Project Manager, at which point the Project Manager shall pay the amount withheld. |  |
|  |  | X20.3 |  | Without prejudice to the Contractor's obligation to report in accordance with clause X20.1, no Service Credits accrue, are paid or withheld and no right to terminate in respect of a KPI Failure or a SPI Failure to the extent that the same arises as a consequence of or is caused by: - a compensation event; or - any matter which is outside the reasonable control of the Contractor. |  |
|  |  | X20.4 |  | Service Credits are calculated on the following basis: - the amount of any applicable Service Credit is calculated by: - multiplying the number of Service Failure Points stated in Schedule J in relation to the category of KPI Failure (Minor, Serious or Severe) for the relevant KPI Failure by the value of a single Service Credit stated in the Contract Data; and - multiplying the product of the calculation in X20.4 (a) by the higher of one and number of consecutive months over which the KPI Failure has occurred (the Ratchet). |  |
|  |  |  |  | - The Project Manager sets off and/or withholds the value of Service Credits calculated under this clause X20.4 as a proportionate sum from the amount due under clause 50.2 or a sum equal to the value of the Service Credits may be recovered by the Client as a debt due from the Contractor provided always that the maximum sum in respect of Service Credits relating to any month that may be withheld or recovered by the Client shall not exceed the Service Credit Cap. |  |
|  |  | X20.5 |  | - Critical Performance Failure Subject to clause 67.9, if, a Critical Performance Failure occurs, the Client may exercise its rights to terminate this contract in whole or in part. |  |
| Option Z55 |  |  |  | Financial Distress |  |
|  |  |  |  | - Insert new clause 10.4 as follows: |  |
|  |  | 10.4 |  | - The Client and the Contractor comply with Contract Schedule Q. |  |

Schedule C

Contract Data Part Two – Data provided by the Contractor

| - Statements given in all Contracts |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | The Contractor is Speller Metcalfe Malvern Ltd |  |  | [defined in the form of agreement to which this Schedule is annexed] |  |  |
|  |  | The fee percentage is |  |  | 7% |  |  |
|  |  | The subcontracted fee percentage is |  |  | 7% |  |  |
|  |  | The working areas are the Site and Speller Metcalfe Malvern Ltd, Maple Road, Enigma Business Park, Malvern, Worcestershire, WR14 1GQ |  |  |  |  |  |
|  |  | The Framework Manager is REDACTED |  |  |  |  |  |
|  |  | The key people are |  |  |  |  |  |
|  |  |  | Name – REDACTED |  |  |  |  |
|  |  |  | Job - Contracts Manager |  |  |  |  |
|  |  |  | Responsibilities - Control of the contract including Programme Planning, Health and Safety, Environmental, Quality and Client/Design team liaison |  |  |  |  |
|  |  |  | Qualifications – See CV issued with submission |  |  |  |  |
|  |  |  | Experience - REDACTED |  |  |  |  |
|  |  |  | Name – REDACTED |  |  |  |  |
|  |  |  | Job – Senior Quantity Surveyor |  |  |  |  |
|  |  |  | Responsibilities – Contract commercial management |  |  |  |  |
|  |  |  | Qualifications- Bsc (hons) Commercial Management & Quantity surveying |  |  |  |  |
|  |  |  | Experience- REDACTED |  |  |  |  |
|  |  | The following matters will be included in the Early Warning Register – See risk register issued at submission |  |  |  |  |  |
| - The Contractor's main responsibilities |  |  |  |  |  |  |  |
|  | If the Contractor is to provide Scope for his design |  |  |  |  |  |  |
|  |  | The Scope for the Contractor's design is in Speller Metcalfe Contractors Proposals |  |  |  |  |  |
|  | - Time |  |  |  |  |  |  |
|  | If a programme is identified in the Contract Data |  |  |  |  |  |  |
|  |  | The programme identified in the Contract Data is – SW469 DWP Stratford Rev. Construction |  |  |  |  |  |
|  | If the Contractor is to decide the completion date for the whole of the works |  |  |  |  |  |  |
|  |  | The completion date for the whole of the works is 11/12/20 |  |  |  |  |  |
|  | - Payment |  |  |  |  |  |  |
|  |  | The activity schedule is SW469 Stratford Activity Schedule |  |  |  |  |  |
|  |  | The tendered total of the Prices is |  |  | £593,962.99 |  |  |
| 2 and avoiding disputes |  |  |  |  |  |  |  |
| If Option W1 or W1 is used |  |  |  |  |  |  |  |
| Data for the Shorter Schedule of Cost Components |  |  |  |  |  |  |  |
|  |  | The people rates are: |  |  |  |  |  |
|  |  | category of person 1. See schedule F Cost components issued with framework submission 2. 3. |  |  | unit | rate |  |
|  |  | The published list of Equipment is the last edition of the list published by – Laxtons 2020 |  |  |  |  |  |
|  |  | The percentage for adjustment for Equipment in the published list is |  |  | +10% (state plus or minus) |  |  |
|  |  | The rates for other Equipment are |  |  |  |  |  |
|  |  | Equipment 1. See schedule F Cost components issued with framework submission 2. 3. |  | size or capacity |  |  | rate |
|  |  | The rates for Defined Cost of manufacture and fabrication outside the Working Areas by the Contractor are: |  |  |  |  |  |
|  |  | category of person rate 1. See schedule F Cost components issued with framework submission 2. 3. |  |  |  |  |  |
| - R |  | The rates for Defined Cost of design outside the Working Areas are |  |  |  |  |  |
|  |  | category of employee 1. See schedule F Cost components issued with framework submission 2. 3. |  |  | hourly rate |  |  |
|  |  | The categories of design employees whose travelling expenses to and from the Working Areas are included in Defined Cost are: |  |  |  |  |  |

Schedule D

Scope

The Contractor shall Design & Build this project Fit for the Purposes meeting obligations as follows:

- Statutory Requirements, Codes and Practice

- Regulatory Requirements

- DWP Design Guide

- Design the works not to exceed to the Agreed Contract Price with provisions for samples and detailed specification to be supplied for Client Approval prior to procurement. Confirming material, colour, texture, finishes or product information, equipment performance specifications.

Specification for i.e wash ware for WCs, new suspended ceiling, LED lighting, mechanical and electrical technical specifications.

Samples for i.e. vinyl flooring

The above is not exhaustive.

- Provide an approved method statement to undertake the design, build and handover with coordination of the Client’s Supplier’ including FM Operator.

- Agree with the Client site arrangements including Out of normal hours working

- Provide an approved quality management plan

- Provide an approved handover, testing and inspection plan.

- Provide an approved O&M and H&S file

The works shall comprise of:

- Designs ready and fit for construction.

- Prelims, management, site welfare and CDM, Principle Designer and H&S obligations

- Liaise with planning and building control to obtain necessary approvals

- Fit out in accordance with concept design, developed by the contractor.

The Scope of this work is to be read in-conjunction with the drawings, the price schedule and technical advisor comments.

Schedule E

Activity Schedule

The Contractor is to supply a detailed task based activity schedule within 5 working days from the date of this agreement as follows:

- Fully detail all activities which can be measured in the design and physical work tasks for managing performance and expenditure.

- To be linked to the Agreed contract Programme.

- To be linked to the Agreed pricing Schedule for managing payments.

- To be linked to the planned monthly spend profile to completion and end of defects liability period.

- Include provisions for any Advance Payments sought.*

*Please note Advance Payments will only be paid against a valid and approved Advance Payment Bond / Vesting Certificate as agreed with the Client.

Schedule F

Site Programme

Schedule G

Collateral Warranties

The Contractor shall provide Collateral Warranties for all Contractor Design Portions such as Civil, Architectural, Mechanical, Electrical and Public Health.

- Template as agreed between DWP and the Contractor

Schedule H

Security Provisions

(Appended)

Schedule I

Management Information

The Contractor MI Reports are to include the following information

- Programme

- Summary of works in progress

- Key Dates completed in the month

- Progress Reports

- Programme Forecasts including critical path

- Current or anticipated delays and mitigation measures

- Risk & Compliance

- Early Warning Register

- Early Warning Register at a Programme level (where applicable)

- Notices and Licences applied for and obtained in Providing the Works

- Outstanding approvals

- BIM reports

- Proportion of SME’s supporting delivery of projects

- Apprenticeship schemes supporting delivery of projects

- H&S / Incident reporting

- Incidents including near misses

- Tool box talks undertaken in the period

- Commercial

- Variations status report

- Payment Applications status report

- Quality

- Snagging status report

- Defects status reports

- Performance

- Performance reports via the Integrator Performance Management System

Schedule J

Key Performance Indicators – as agreed with the Framework Contract

Schedule K

TUPE surcharge - No Requirement

Schedule L

Governance

(Appended)

Schedule M

Equality

(Appended)

Schedule N

Form of Ultimate Holding Company Guarantee and Performance Bond – Not Used

Schedule O

- Third Party Agreements – Not Used

Schedule P

Data Protection

All as per the details contained within the Contractor's policies, procedures and other measures

Schedule Q

Financial Distress

- 1	DEFINITIONS

  - In this Schedule, the following definitions shall apply:

| Additional Security | either: - an on-demand payment and performance bond in favour of the Client in a form and substance and for a value and from a provider in each case satisfactory to the Client; and/or - an enforceable deed of guarantee from a New Guarantor to be approved by the Client in substantially the form of the Guarantee (if any) or in such other form as the Client may, in its absolute discretion, agree; and/or - any other alternative security as may be acceptable to the Client in its absolute discretion; |
| --- | --- |
| Contract Year | the period of 12 calendar months ending at each anniversary of the Contract Date; |
| Financial Distress Events | has the meaning given to it in Paragraph 3.1 and references to Financial Distress Event shall be construed accordingly; |
| Financial Distress Recovery Plan | the plan to be submitted by the Contractor pursuant to Paragraph 3.3.2 (a); |
| Financial Statements | the audited consolidated accounts for the relevant Major Contractor Party; |
| Major Contractor Party | means each of the Contractor, the Guarantor, a New Guarantor (if an Affiliate of the Contractor) and references to Major Contractor Parties shall be construed accordingly; |
| Rating Agency | a credit rating agency generally recognised in the United Kingdom business sector as publishing ratings of the ability of a debtor to pay interest and the likelihood of debt default; and |
| New Guarantor | means in the event of a Financial Distress Event relating to the Guarantor, the provider of a new, additional or replacement enforceable deed of guarantee. |

- DUTY TO NOTIFY

  - The Contractor shall:

    - deliver to the Client:

      - when required all financial information (including covenant certificates) that it is required to deliver to its lenders within the time period allowed by those lenders for doing so; and

      - the annual accounts of each Major Contractor Party as soon as they are available and in any event within 10 working days from publication;

    - promptly and in any event within five (5) Working Days notify the Client (or procure that its auditors notify the Client within five (5) Working Days) in respect of a Major Contractor Party of any:

      - material adverse change to such party's financial standing, including but not limited to any:

        - profit warning to a stock exchange or the making of any other public announcement concerning a material deterioration of its financial position or prospects;

        - public investigation into improper financial accounting or reporting, suspected fraud or any other impropriety;

        - material adverse change to the organisation that might impact on its on-going financial viability;

        - material breach of covenant to lenders;

        - commencement of any dispute resolution procedure against with respect to such party's financial indebtedness of more than five million pounds (£5,000,000);

        - non-payment of any financial indebtedness;

        - any financial indebtedness becoming due as a result of an event of default;

        - the cancellation or suspension of any financial indebtedness;

        - downgrade or material adverse change in the credit rating issued by a Rating Agency

      - proposed changes to the organisational control or group structure, proposed mergers or acquisitions or proposed changes which may impact on the relevant Major Contract Party's financial viability; and/or

      - adverse change in the assets, business or financial condition of a Major Contractor Party since the date of the most recent accounts,

- provided that compliance with this paragraph 2.1 shall not require a Major Contractor Party to breach restrictions on its performance reporting prescribed by legislation.

    - promptly and in any event within five (5) Working Days of it becoming aware notify the Client of any material adverse change to the financial standing of a bond provider or of a New Guarantor who is not also a Major Contracting Party.

  - If there is any downgrade of a credit rating issued by any Rating Agency for any Major Contractor Party, the Contractor shall ensure that the relevant Major Contractor Party's auditors thereafter provide the Client within ten (10) Working Days of the end of each Contract Year and within ten (10) Working Days of written request by the Client with written calculations of the quick ratio for the relevant Major Contractor Party as at the end of each Contract Year or such other date as may be requested by the Client. For these purposes the “quick ratio” on any date means:

A + B + C

D

where

A 	is the value at the relevant date of all cash in hand and at the bank of the relevant Major Contractor Party;

B 	is the value of all marketable securities held by the relevant Major Contractor Party determined using closing prices on the Working Day preceding the relevant date;

C 	is the value at the relevant date of all account receivables of the relevant Major Contractor Party; and

D 	is the value at the relevant date of the current liabilities of the relevant Major Contractor Party.

- FINANCIAL DISTRESS EVENT

  - Upon:

    - notification of an event under Paragraph 2.1.2 or 2.1.3; and/or

    - notice from a Notified Sub-contractor to the Client that the Contractor has not satisfied any material sums properly due under a specified invoice which is not subject to a genuine dispute; or

    - the Client becoming aware of an event under Paragraph 2.1.2 or 2.1.3 without notification and brings the event to the attention of the Contractor,

        - the Client may in its discretion inform the Contractor that it considers a Financial Distress Event has occurred in which case the Contractor shall have the obligations and the Client shall have the rights and remedies set out in Paragraphs 3.3 to 3.9.

  - In the event of a late or non-payment of a Notified Subcontractor pursuant to Paragraph 3.1.2, the Client shall not exercise any of its rights or remedies under Paragraph 3.3 without first giving the Contractor ten (10) Working Days to:

    - rectify such late or non-payment; or

    - demonstrate to the Client's reasonable satisfaction that there is a valid reason for late or non-payment.

  - The Contractor shall (and shall procure that other Major Contractor Parties shall):

    - at the request of the Client, meet the Client as soon as reasonably practicable (and in any event within three (3) Working Days of the initial notification (or awareness) of the Financial Distress Event or such other period as the Client may permit and notify to the Contractor) to review the effect of the Financial Distress Event on the continued performance and delivery of the works in accordance with this Contract; and

    - where the Client reasonably believes (taking into account the discussions and any representations made under Paragraph 3.3.1) that the Financial Distress Event could impact on the continued performance and delivery of the Services in accordance with this Contract:

      - submit to the Client for its approval, a draft Financial Distress Recovery Plan as soon as reasonably practicable (and in any event, within ten (10) Working Days of the initial notification (or awareness) of the Financial Distress Event or such other period as the Client may permit and notify to the Contractor in writing); and

      - provide such financial information relating to the relevant Major Contractor Party as the Client may reasonably require including, without limitation, details of the revenue replacement strategy and impact awareness on the organisation's profitability and stability where significant contracts are due to end.

  - Where a Financial Distress Event relates to the Guarantor and the Guarantor's credit rating issued by a Rating Agency is lower than the credit rating issued by a Rating Agency as at the date of this Contract the Financial Distress Recovery Plan shall as a minimum set out details of the Additional Security.

  - Following receipt of the Financial Distress Recovery Plan pursuant to Paragraph 3.3.2 (a) the Client may, in addition to any other rights under this Contract Schedule Q notify the Contractor that it is increasing its monitoring pursuant to Clause 68.1 of the Contract and the Client and Contractor acknowledge and agree that the provisions of clause 68.2 shall apply accordingly.

  - The Client shall inform the Contractor whether or not the draft Financial Distress Recovery Plan is approved.  The Client shall not withhold its approval of a draft Financial Distress Recovery Plan unreasonably. If the Client does not approve the draft Financial Distress Recovery Plan, it shall inform the Contractor of its reasons and the Contractor shall take those reasons into account in the preparation of a further draft Financial Distress Recovery Plan, which shall be resubmitted to the Client within five (5) Working Days of the rejection of the first draft.

  - If following resubmission of the draft Financial Distress Recovery Plan the Client considers that:

    - the draft Financial Distress Recovery Plan is insufficiently detailed to be properly evaluated;

    - the draft Financial Distress Recovery Plan will take too long to complete or will not ensure the continued performance of the Contractor’s obligations in accordance with the Contract, or

    - in relation to:

      - the Additional Security, the Client does not believe that the proposed Additional Security meets the requirements set out in limbs (a) – (c) of the definition of Additional Security; or

      - the New Guarantor, the Client does not believe that the proposed New Guarantor is of at least the same financial standing and has at least the same credit rating from a Rating Agency as the Guarantor had as at the date of this Contract,

        - then the Client may either agree a further time period for the development and agreement of the Financial Distress Recovery Plan or escalate any issues with the draft Financial Distress Recovery Plan by referring the draft Financial Distress Recovery Plan to the Governance Board for a recommendation under Contract Schedule L.

  - This process in Paragraphs 3.6 and 3.7 (excluding referral to the Governance Board) shall be repeated until;

    - the Financial Distress Recovery Plan is approved by the Client; or

    - the Client determines that its approval will not be given provided that the Client shall only so determine if it has escalated the matter to the Governance Board under Contract Schedule L and the Governance Board has given a recommendation or the Governance Board has failed to meet within ten working days of the referral.

  - Following approval of the Financial Distress Recovery Plan by the Client, the Contractor shall:

    - on a regular basis (which shall not be less than monthly), review the Financial Distress Recovery Plan and assess whether it remains adequate and up to date to ensure the continued performance and delivery of the Services in accordance with this Contract;

    - where the Financial Distress Recovery Plan is not adequate or up to date in accordance with Paragraph 3.9.1, submit an updated Financial Distress Recovery Plan to the Client for its approval, and the provisions of Paragraphs 3.5 to 3.8 shall apply to the review and approval process for the updated Financial Distress Recovery Plan; and

    - comply with the Financial Distress Recovery Plan (including any updated Financial Distress Recovery Plan).

  - Where the Contractor reasonably believes that the relevant Financial Distress Event under Paragraph 3.1 (or the circumstance or matter which has caused or otherwise led to it) no longer exists, it shall notify the Client and the Parties may agree that the Contractor shall be relieved of its obligations under Paragraph 3.9.