## Sheet1
RISK REGISTER
| Project: The Passmore Edwards Building | Project Code: P200654 | Severity | L | M | H
| Client: Camborne Town Library | Date: 09.02.21 |  | 3 | 6 | 9 | H | Likelihood | Severity | RISK RATING | Severity - Where applied to non-H&S risks, ratings to be considered as severe, medium and low risk (eg financial).
| Principal Designer: RTP Surveyors | Version: 01 |  | 2 | 4 | 6 | M | H – Certain, or near certain | H – Fatality, major injury causing long term disability | 6-9 – High risk – Action required
|  |  |  | 1 | 2 | 3 | L | M – Reasonably likely | M – Injury or illness causing short term disability | 3-4 – Medium risk – Action required unless good reason
| C = Construction/M = Maintenance/U = Use of Building |  |  | Likelihood |  |  |  | L – Very seldom or never | L – Other injury or illness | 1-2 – Low risk – No action
Ref: | Description of risk and hazard: | Phase (C/M/U): | L | S | R | Mitigation (Actions proposed by Designer/Project Planner): |  |  | Residual Risk: | Additional actions: |  | By whom: | Ongoing/Complete:
1 | Working at height - access up to the roof level during construction works, unguarded parapet edges, where risk of falls exists. | C | 3 | 3 | 9 | Risk remains as working at height is essential for repair works. Certified scaffolding required for contractors' access. Scaffolding to be installed in accordance with good practice. Netting to scaffolding and brick guards, to protect occupants in and around the building. |  |  | 3 | Method Statement from contractors and toolbox talks. Temporary guarding needed for working above ground level. Crane hire for the removal of the chimney construction. |  | Designers for investigation works/Principal Contractor for main project | Ongoing
2 | Working at height and - dismantling / assembly of heavy components - works involved in the dismantling of the Bathstone chimney | C | 3 | 3 | 9 | Structural Engineer's reports and advice to be followed for stability and support of structures and for the removal of the Bath-stone chimney. |  |  | 3 | Further support and working platforms will be needed prior removal of materials and reinstatement (follow Structural Engineer's requirements as well). |  | Principal Contractor and specialist scaffold designer for main project | Ongoing
3 | Working at height - for the pointing of the external masonry elevation and associated works | C | 3 | 3 | 9 | Risk remains as working at height is essential for repair works. Certified scaffolding required for contractors' access. Scaffolding to be installed in accordance with good practice. Netting to scaffolding and brick guards, to protect occupants in and around the building. |  |  | 3 | Method Statement from contractors and toolbox talks. Temporary guarding needed for working above ground level. Crane hire for the removal of the chimney construction. |  | Designers for investigation works/Principal Contractor for main project | Ongoing
4 | Working at height - cleaning and maintenance operations for gutters and upper level windows. Potential for operatives/objects falling from height. | M/U | 2 | 3 | 6 | Window configuration has not changed, therefore existing risks remain. All decisions regarding alterations or temporary works to be agreed with Structural Engineer. |  |  | 3 | Instructions to be included in H&S File. Consider window and gutter cleaning from ground level using pole systems. |  | Principal Designer/ Occupier | When works complete
5 | Working at height - for the internal repairs and redecoration works | C | 2 | 3 | 6 | Risk remains as working at height is essential for the works. Contractors to provide suitable access. Tower scaffolding to be installed in accordance with good practice. |  |  | 3 | Method Statement from contractors and toolbox talks. Temporary guarding needed for working above ground level. |  | Principal Contractor | Ongoing
6 | Working with Lead - for the works associated with the capping and dressing of the parapets and lining of the tapered and parapet gutters |  | 1 | 3 | 3 | Minimise lead sizes and fabricate where possible at ground level. |  |  | 3 | Method Statement from contractors and toolbox talks. Additional means fo lifting to roof levels. |  | Principal Contractor /Sub-contractor | Ongoing
7 | Working with chemicals/solvents/rot treatment - Operatives and occupiers at risk from fumes and exposure to toxic substances. | C | 2 | 2 | 4 | Contractors to undertake COSHH assessment and ensure Designers agree products. Neighbours and operatives to be advised, if residual risks. Operatives to wear PPE if required by MSDS. Do not allow products to enter watercourse. |  |  | 2 | Method Statement/CPP from contractor to address. Storage of any hazardous materials on site to be limited and secured. PC to provide own spill kit. |  | Principal Contractor | Ongoing
8 | Working with chemicals/solvents - Operatives and occupiers at risk from fumes and exposure to toxic substances. | M | 1 | 2 | 2 | Building Manual and H&S File to contain records of residual risks (such as for timber treatments or other chemicals used), to enable SSOW to be planned by others for future maintenance. |  |  | 2 | MSDS will be provided by PC for completion of works. |  | Principal Contractor and Principal Designer | For handover documents
9 | Contact with biological hazards; Legionella/bacteria/Weil’s disease | C | 1 | 3 | 3 | Work with materials/in areas potentially exposed to rodents is necessary as part of works, therefore contractor informed of Weil’s disease risks. Risks increased by rural environment and proximity to water course. Potential exposure risks to disease from waste deposits seen from bats/birds/vermin in confined spaces. Black mould with inhalation risks. Cleaning required during construction project. Bat surveys completed and licence issued in January 2021. Legionella risks from water supplies in tanks – testing of treated water required – M&E consultant to advise. Welfare facilities provided on site for all operatives/visitors. COVID-19 RA applied. |  |  | 3 | Ecological report/bat licence requirements to be adhered to. Contractor to undertake risk assessment and inform operatives of all precautions necessary, including PPE and good hygiene. Method Statement Required. |  | Principal Contractor | Ongoing
10 | Operatives at risk from electrocution during the construction project, including opening-up/demolition and scaffolding erection. | C | 2 | 3 | 6 | Mains electrical supply appears underground on site. Overhead cables to the rear of the property. 'Scan before you dig' policy to be employed. Qualified operatives with suitable skills, knowledge and experience to be undertaking the works. Works to be carried out in accordance with WPD requirements and SSOW. Scaffolding to be installed and maintained using SSOW and avoidance of overhead cabling. Similarly deliveries and waste removal to be undertaken safely, with consideration of overhead cable on site and any on approach roads/lanes. |  |  | 3 | Method Statement/CPP from contractor to address. As-built records to show locations and isolations. All cabling locations to be noted in H&S File. Certification required for isolations prior to works and before final use, following improvements. |  | Principal Contractor | Ongoing
11 | Manual Handling and use of Mechanical devices – Installation/removal of heavy/prefabricated structures. | C | 2 | 3 | 6 | Implement safe method of removing/installing heavy items (such as granite fire surrounds or large timber beams) within property, using appropriate lifting equipment wherever necessary. Repetitive works, such as large quantities of slates and stone to be removed/replaced with SSOW. LOLER requirements to be applied. |  |  | 3 | Method Statement/CPP from contractor to address. SSOW for operation and checking (hoists/lifting gear/props and scaffolding platforms, including weights). |  | Principal Contractor | Ongoing
12 | Pedestrian/Vehicle Conflict throughout the contract. Operatives, neighbours and public at risk. | C | 2 | 3 | 6 | Location of building fixed - cannot remove hazard. Risk reduced by method of work – to always include banksman and separation of pedestrians, plus designated route (to be confirmed). Manage deliveries with barriers or personnel where crossing roads/pavements. Consider neighbour's requirements in accessing areas safely. Gates to be shut where required. (narrow and not suitable for heavy goods/large construction vehicles). Off-site storage of items and small vehicle delivery onto site suggested. |  |  | 3 | Access to site for parking contractors' vans/cars/storage limited to public parking adjacent to Railway Station. Local on street parking must not obstruct neighbouring properties' entrances. |  | Principal Contractor | Ongoing
13 | Exclusion of unauthorised persons from the work area. Members of the public at risk during construction. Location of premises means this property is vulnerable to unauthorised entry during non-working times. | C | 3 | 3 | 9 | Entrances/fencing to be fixed securely/locked when not in use. Scaffolding to be fully surrounded with netting or fencing and all construction site gateways to be kept closed when not in use. Apply signage to warn of dangers. Lowest ladders to be removed from scaffolding at the end of each working day or anti-climb devices installed for added security. |  |  | 6 | Method Statement/CPP from contractor to include measures advised. Review ongoing security of site and consider installation of CCTV cameras to scaffolding if intrusions suspected. |  | Principal Contractor | Ongoing
14 | Risk of fire from works, compounded by large premises with complexity of escape routes from scaffolding and within the property. | C | 2 | 3 | 6 | Mains gas on site, contractors to be aware of method for isolation and emergency proceedures. PCIP made clear to contractors the requirement to retain M.O.E. access at all times. Hot Works will require permits. Fire Plan required for construction phase, with several fire points needed due to the extent of the premises/areas covered. |  |  | 3 | Method Statement/CPP from contractor to address fire risk and control. Fire Plans to be amended following receipt of RAMS. Site management to be carefully monitored. |  | Principal Contractor | Ongoing
15 | Risk of fire from occupied premises or adjacent buildings. | M/U | 2 | 3 | 6 | Design to address fire protection to structural elements and any Regulatory need for changes to means of escape. Improvements to smoke detection and fire controls to be considered, particularly in the light of the complex layout and roof voids. |  |  | 3 | H&S File to record as-built solutions, with plans for fire safety measures. |  | Designers /Principal Designer | When works complete
16 | Risk of finding hazardous materials during the course of the works. Risk of exposure of operatives to asbestos/lead/lime. | C | 2 | 3 | 6 | Refurbishment Asbestos Survey of the 1st floor and roof void only carried out in June2017 and report issued to project team in February 2021. The property was constructed early in the 20th century and could contain other hazardous substances, such as lead content in paintwork. This can be analysed or presumed and risks managed accordingly. Lead flashings and details are also present. Lime and cement based materials are present. Unforeseen hazardous materials may still be uncovered in voids. Site induction to cover such risks. Vigilance required by trained operatives. |  |  | 3 | Contractor to implement procedure for halting works upon discovery of possible ACM/other hazardous materials and advise CA. SSOW required from contractors for working with lime mortar and lead. H&S File to record remaining ACM. Asbestos survey conducted in roof voids/bat occupied areas following licence. NOTE suspected ACM to doors on the ground floor. Further survey to be undertaken before internal refurbishment works. |  | Principal Contractor and Principal Designer | Ongoing
17 | Exposure to noise and vibration during the works (operatives). | C | 2 | 2 | 4 | Contractors to perform tasks in accordance with good practice. Monitoring to be undertaken by Contractors and additional protection measures provided if required. |  |  | 2 | Method Statement/CPP from contractor to address. To inform neighbours/gardener/others accessing site, prior to prolonged noisy works. |  | Principal Contractor | Ongoing
18 | Removal of materials from existing building/during alteration works. Risk of injury from sharp edges, broken glass, falling roofing and falling masonry etc | C | 2 | 3 | 6 | Method Statement/CPP from contractor to address. Implement exclusion zones for specific tasks. PPE to be worn at all times. Structural Engineer's advice to be followed. Detailed SSOW to be agreed prior to removal works and construction activities. Additional working platforms and protection for support of building elements needed where removal of walls/chimneys are to occur. |  |  | 3 | Method Statement/CPP from contractor to address and be monitored. Weather conditions to be reviewed and condition of building to be monitored, with SSOW adjusted when necessary. |  | Principal Contractor | Ongoing
17 | Weather conditions cause delay to the delivery of the works. | C | 2 | 2 | 4 | Ecology and financial risks, as well as impact on programming of areas to be considered. All parties to be kept informed via Project Manager/Contract Administrator. |  |  | 2 | Works to be stopped when necessary. |  | Principal Contractor | Ongoing
18 | Failure of sub-contractors to perform with due diligence. | C | 1 | 2 | 2 | Principal Contractor to manage sub-contractors closely and ensure all adhere to Site Rules and perform tasks in accordance with specifications and good practice. |  |  | 2 | RAMS from sub-contractors to address expectations. Induction from contractor to all operatives to reinforce suitable working attitudes and actions. |  | Principal Contractor | Ongoing
19 | Water penetration during the works, leading to damage of building fabric, finishes and contents. | C | 2 | 2 | 4 | Temporary roofing provided for scantle roof works. Contractors to plan works according to weather conditions and ensure openings (such as windows) not left exposed. |  |  | 2 | Insurance cover to be reviewed for occupiers and contractors. |  | Principal Contractor and Owner | Ongoing
20 | COVID-19 Risks from operatives to each other/visitors to site | C | 2 | 3 | 6 | Designers aware of situation and reviewing own risk for visits to site. Principal Contractor was informed of risks and prepared their own COVID-RA. Enhanced welfare facilities and arrangements for social distancing on site to deal with the management of risks. |  |  | 3 | Contractor to inform operatives and visitors to site of all precautions necessary, including social distancing, PPE and good hygiene. Further provisions of sanitising stations and signage have been introduced to site following 5th January 2021 review by PC. |  | Principal Contractor | Ongoing