## OUTLINE SOW
PROJECT: | MusicAbility Phase 2
REF: | OUTLINE SCHEDULE OF WORKS
251/5.02
DATE: | 16.1.25 REV C
AMENDMENTS
SoW. REF. | ITEM | ADDITIONAL INFORMATION | COST | KOHA / EMPLOYER COMMENTS | CONTRACTOR COMMENT
GENERAL
i | Description of the Works:
Internal Alterations and refurbishment and upgrades for Change of Use compliance. New External accessible ramp and steps.
ii | Employer:
MusicAbility Foundation 10 Parade Street, Penzance, Cornwall, TR
iii | Architect:
Koha Archtiects, Tremough Innovation Centre, TR10 9TA T:01326 567224 derekjackson@kohaarchitects.com
iV | Structural Engineer & Below Ground Drainage:
Ian Harban : Harban Redwood - Tel : 01736 317877 - email : Ian@harbanredwood.com
V | Timescale:
Start on site 24th March 2025 (TBC). Programme length between 12 to 24 weeks
TENDER
X | Documentation:
The documentation includes the following information. - Koha Architects drawings as highlighted on the attached Koha Drawing Issue Sheet. - Douglas Geomatics' Topographical and Measured Survey Drawings - Douglas Cawley & Associates ‘Schedule of Conditions‘ dated 7th April 2021. - Structural information by Harban Redwood. - CEC’s Ecology Report, ref:4303 dated 13.06.2024. - Alliums’ Refurbishment Survey ref: L-27741 dated 26.6.2023. - Conditional Planning & Listed Building Approval PA22/11075 & PA22/11076 - This document, Schedule of Works dated January 2025. - Photograph Schedule by Koha Architects. - Daniel Ratcliff's Statement Heritage, Ref: SH MUSIC0723 - Fire Safety Report
Xi | Preamble
Include for any costs associated with specification items as stated in this document, Specification of Works.
Xii | Tender Price:
Allow for all works to complete the works described and for all making good where necessary.
A priced copy of the Schedule of Work showing a detailed breakdown of the pricing (including all divisions) is to be submitted with the tender
PRELIMINARIES
Refer to separate Preliminaries document. Include allowances below.
XX | Allowances to meet CDM 2015 Regulations including those listed below.
XXi | Provide proper management and co-ordination of the works including close supervision of the contractors own employees, sub-contractors, named sub-contractors, direct contractors and others.
XXii | For tendering purposes assume the working hours are 8.00am to 5.30pm. Monday to Friday.
Xxiii | The contractor’s representative is to be available for regular site meetings with the employer and other consultants as necessary every week to discuss on going works, up coming works, programme, costs, queries etc.
XXiV | Allow for protection of the Existing Building and Site and make good where necessary.
XXV | Ensure that adjoining areas, pavements, roadways etc. around the property are kept clean and tidy at all times and dust and debris are swept and cleared away at the end of each working day to minimise disturbance to the neighbours.
XXVi | Interim valuations are to be prepared for submission to the Employer for checking, agreeing and payement.
XXVii | The property is to be scaffolded as appropriate, to enable the alterations and decorations to be undertaken. Refer to clause K below.
XXViii | Do not store materials beyond curtilage of the property without prior permits from the Local Authority
Allow for full Health and Safety procedures under current legislation. It will be the Contractor’s responsibility to ensure that Health and Safety requirements are fully implemented on site and that the construction of the works are undertaken in a safe manner.
XXiX | A Health and Safety file must be kept on site.
XXX | Allow for all works as illustrated on the accompanying drawings prepared by both Architect and Structural Engineer.
XXXi | It will be the Contractor’s responsibility to thoroughly check through the drawing package, the schedule of works and specification to ensure that all building works have been accounted for in pricing the project. The Contractor is also to check with the client and take direct instruction from the Contract Administrator with regards to items noted as ‘to be confirmed by the client’.
XXXii | Although the schedule of works document presents a breakdown of the works, any items not included in this schedule but highlighted / indicated on the drawings will be deemed to be included in the Contractor’s pricing.
XXXiii | Access – Main access to the site is via St Mary’s Terrace. Banksmen to control traffic during deliveries. There is a small offroad parking area.
XXXiv | Contractors area – The Parking Area along St.Mary’s Terrace is to be used for the contractors area. Note some of this area will be required for storage of clients items (shipping container).
XXXv | Power and water check metered and paid for by the Contractor and included in the Preliminaries for pricing.
XXXvi | Contractor to make every effort to minimise dust and noise or other disturbance to neighbours and to avoid any sediment / chemical discharge into drains.
HEALTH & SAFETY CDM Notes (CDM Regs 2015)
A | Contractor to be aware of speed limits and restricted widths to surrounding roads. Caution with vehicular access. Ensure banksman is present during all material deliveries
B | Contractor to provide all necessary protections to boundary walls as required and to make good where needed.
C | No fires are permitted on site
D | If asbestos is found on site ALL WORK MUST STOP until it has been removed by an approved specialist sub-contractor - See Allium Report.
E | Contractor and client to discuss sequence of works.
F | Due care and attention to be given during all demolitions.
G | PPE to be worn at all times on site during construction. Contractor to be maintained throughout construction phase. A first aid trained person to be on site at all times
H | Care to be taken when working at height. Allow for guardings and all gangways to be clear to avoid tripping. Care to be taken when walking under somebody working. Refer to drawings regarding hazards. Contractor to provide method statements where requested.
I | Caution with manual handling of dense concrete blocks and steel beams.
J | Contractor to identify and isolate existing services and disconnect in accordance with work programme as works proceed.
K | All scaffolding to comply with BS5867-2008 and BS EN 12811-1:2003
L | The Contractor is to provide as installed record drawings and photos of all works described for incorporation into the Health and Safety File and the Operation and Maintenance Manuals.
M | The Contractor is to liaise and advise the local neighbours regarding delieveries and group deliveries to site.
SITE SURVEY / INVESTIGATION
XL | Services survey:
XLi | Locate all existing underground and overhead services, survey and submit a report showing the position of these and their function and type before starting excavations and/or demolition works.
XLii | Foundation excavations:
XLiii | Refer to Koha Archtiects Below Ground Plan for draft foundation layout (for budget pricing purposes only). To be superceded by structural engineer's design when this is issued.
XLiV | Damp survey:
Immediately after strip out a survey for damp is to be undertaken. Refer to Damp Survey by David Reynolds (to follow)
XLV | Allow for all necessary protection to existing footpaths, buildings as necessary
3.0 | DEMOLITION / STRIP OUT – Refer to drawings of existing building & demolitions
3.1 | Locate and mark the positions of all services affected by the work and disconnect the services in those areas where demolition work is to take place.
3.2 | Protect the drains and fittings still in use and keep free of debris at all time and make good any damage arising from the demolition work leaving clean and in working order on completion.
3.3 | Identify those items that are to be retained and provide adequate protection.
3.4 | Demolish structures in accordance with BS6187 and the HSC guidance notes GS29/1, 3 & 4 and ensure that all site staff responsible for the control of the work are experienced in the assessment of the risks involved and the methods of demolition to be used. Refer to any specific notes that may be set out on the Structural Engineers drawings regarding demolitions / work sequencing.
3.5 | Report immediately any suspected asbestos base materials discovered and avoid disturbing such materials and agree methods for safe removal. Refer to Alliums’ Refurbishment Survey for existing ACMs already identified.
3.6 | Strip out all fixtures and fittings which will become redundant as part of the refurbishment works. Some strip out of electrical fittings has already been completed. Refer to photograph schedule. Refer to the drawings that identify the key areas for Demolitions and strip out. Client to confirm items that are to be set aside for specific re-use. - Existing internal doors that are to be removed are to be stored in the basement.
3.7 | Allow for a strip back of mechanical and electrical services in preparation for new works.
3.8 | Remove internal walls as noted on drawings. Notably to be demolished / removed; -WC arrangement at Basement Level, -WC arrangement at Ground Floor Level (G10/G11) -Cupboard in room G04, wall between G04a and G06. -Door and Window Screen DG3
3.9 | Remove existing suspended ceilings and associated fixings.
3.10 | Allow for protection of retained features such as the main staircase, any architraves, covings and existing joinery, general finishes throughout on all floors. Lay temporary protection as required.
3.11 | Contractor to make good any damage done caused by the execution of the works.
4.0 | FUNGUS / BEETLE ERADICATION / ROT
4.1 | A Timber Rot and Infestation Survey will be provided by others. Once available, refer to this for notes and any provisional sum allowances recommended for specialist treatment of any fungus / beetle attack / Rot to the existing fabric of the building and for any damp-proofing requirements. Minimum 10 year guarantee required. Allow for profit and attendance.
5.0 | PROTECTION
5.1 | Allow for all necessary protection to existing footpaths, buildings as necessary
6.0 | NOTICE
6.1 | Give due notice to the Contract Administrator of any unknown items / services / artefacts as soon as they are made known and prior to continuing any further works.
6.2 | The Client’s team will be carrying out Schedule of Condition of adjoining properties as necessary in advance of starting works on site.
6.3 | The Contractor is to give notice to adjoining neighbours/ occupants of noisy or disruptive works starting on site and the likely timescales and provide a contact for the Contractor for neighbours to report to if they have any issues with on-going works.
7.0 | EXCAVATING AND FILLING
7.1 | Excavate as per areas illustrated on Koha Architects drawings and in accordance with the Structural Engineers information to form foundations for new ramp walls and steps.
7.2 | Allow for excavation of trenches and service runs for general services and drainage as required.
7.3 | Allow for buried conduit to provide power supply to external lighting & CCTV areas.
7.4 | Allow for excavation of trenches and service runs for general services and drainage as required and as per drawings / information.
7.5 | Ducts and Cables to be buried to the following minimum depths:
| Electric Cables (LV) | 800mm
| LPG | 750mm
| Mains Cold Water Supply, MCWS | 900mm
| Soakaway/ Surface Water | 900mm
| Telecom, Data, Fibre, Spare or Audio | 600mm
8.0 | INSITU & PRE CAST CONCRETE
8.1 | Refer to SE details for New strip foundations for Access Ramp and Steps.
8.2 | Refer to S.E. details and information for pre-cast concrete padstones for new beams / lintels as necessary.
8.3 | Mass concrete steps and associated low level wall to courtyard to S.E. details and Koha General Arrangement Drawings.
9.0 | MASONRY WALLING
9.1 | Dense Concrete Blocks are to be used for the new side wall for the proposed ramp and steps.
9.2 | Allowance making holes in the stonework walls to allow for new MVHR ductwork / Ventilation Grilles.
9.3 | Allowance for making holes in the stonework walls for all other services.
10.0 | STRUCTURAL STEEL WORK / METAL WORK
10.1 | Steel Beam to Structural Engineer’s Design above removed wall between G04a and G06 to allow for future folding partition.
10.2 | Allow for 2 no. layers 12.5mm gypsum plasterboard to in-case steel beam. (repeated in linings)
11.0 | CARPENTRY / TIMBER FRAMINGS, FIRST FIXING
11.1 | Allow for timber stud walling generally for new partition walls as illustrated on drawings to include boxings. Nom. CLS 89 x 38 mm treated s.w. studs @ 600 mm centres fixed between 89 x 38 treated s.w. head and sole plates. Studs to be at @400mm centres for any areas of wall tiling.
11.1.1 | Insert horizontal intermediate rails @ 1200 mm c/c with additional 50 x 50 treated s.w. noggins where required to locate electrical fittings, radiators, sanitary equipment etc. Ensure all edges of plasterboard cladding are secured back to timber framework.
11.1.2 | Allow for noggins, plywood backing where bathroom fittings are fixed to walls, or where radiator positions are indicated, built in shower valves, taps etc.
11.1.2 | Allow for plywood backing where kitchen units, sanitaryware, shelving or other fixings are to be hung. Refer to section 16.0 for acoustic specification of wall partitions.
11.2 | New timber walls to WCs in G09/G10/G11 which are part of the protected escape route need to be FEI 30 minute fire rated. The walls are to be clad with 1 No. Layer of 12.5mm Moisture resistant plasterboard on the WC side and on the Lobby Side 1 No. Layer of 12.5mm Gypsum Plasterboard and 1 No. Layer of 12.5mm Soundbloc Plasterboard.
11.3 | New timber walls to Hallway in G05 which are part of the protected escape route need to be FEI 30 minute fire rated. The walls are to be clad with 1 No. Layer of 12.5mm Gypsum Plasterboard on the Hall Side(G05) and 2 No. Layers of 12.5mm Soundbloc Plasterboard with a sound deadening mat sandwiched between on the Groups Room/Educational Room(G04a/G06) side.
11.4 | Provide min. 50mm Rockwool sound insulation quilt between studs.
11.5 | Allow for general framings throughout the building to boxings for soil stacks, stub stacks etc. where run internally.
11.6 | Include for general bathroom pipe boxings and heating pipe and cable riser ducts etc.
11.7 | Allow to encase any structural beams with 2 No. Layers of 12.5mm gypsum plasterboard or fire-rated linings to achieve fire ratings confirmed by Structural Engineer.
11.8 | Allow for alteration, trimming and internal cheek walls to new Smoke vent above Staircase/Landing F01.
11.9 | Allow for double timber joists where indicated on S.E. drawings and also beneath all new partitions above suspended timber floors.
11.10 | Allow for any timber lintels as per Structural Engineers information.
11.11 | New Floor Battens/joists to raise floor level in Lobby/WCs (G09/G10/G11) and Battens to form ramp (R2) over existing steps.
11.12 | New Timber Structure and Marine Grade Plywood Deck to External Ramp. Structure to be bolted to existing / proposed masonry walls to S.E Design. See Detail Sheets.
11.13 | Suspended Ceilings in G04 / G03 / G05 / G02 ;
12.0 | ROOFING / FINISHES
12.1 | Allow for alteration of roof slates, underlay and battens for installation of new Velux type Smoke Vent above Landing F01. Allow for New leadwork associated with installation of Smoke Vent.
13.0 | DAMP PROOF & WATERPROOFING MEMBRANES
13.1 | Minimum 1200 Gauge DPM above existing ground-bearing floor slab in Lobby and WCs. Allow for strips of DPC between new studwork where they meet existing external walls.
14.0 | RIGID SHEET FLOORING, SHEAVING, SARKINGS, LININGS, CASINGS
14.1 | Allow for plywood sheeting applied to stud walling as previously itemised for the fixing of radiators, bathroom appliances, kitchen units etc.
14.2 | 25mm T&G Chipboard/Weyroc Floor Deck to raised floor in and ramp in Lobby/WC area.
14.3 | See 11.10 for Plywood to External Ramp.
15.0 | INSULATION
15.1 | Install min 50mm Acoustic insulation within new studwork walls generally.
15.2 | Install min 100mm acoustic insulation above new suspended ceilings in Hall G03, Hall G05 and Group Space G04.
15.3 | Install Min 50mm Acoustic insulation around all MVHR ductwork within boxings and above suspended ceilings.
16.0 | LININGS
16.1 | Existing primary lath and plaster ceilings are to be repaired locally where existing suspended ceilings are to be removed.
16.2 | REI 60 Linings to Basement Ceiling
16.2.1 | All areas of the Basement ceiling including the staircase up to ground floor require a 60 minute lining consisting of 2 layers of 12.5mm Gypsum plasterboard with staggered joints.
16.2.2 | Some areas of the ceiling appear to have an adequate lining as existing. All areas are to be checked on site and results shared with Architect, Client and Building Control Officer.
16.2.3 | The following areas need the existing lining removed and replaced as detailed above;
16.2.4 | -Access Corridor to B03
16.2.5 | -Basement Access B01 (Internal Walls and ceiling)
16.3 | REI 30 Lining to Protected Corridor. Repeated in Section 22 (Decoration)
16.4 | An REI 30 minute Lining to walls and ceilings are required. This will consisting of a single layer of 12.5mm gypsum plasterboard and skimcoat plaster or an intumescent paint in areas of existing lath and plaster. Unless otherwise notified, areas of plastered masonry wall are not required to be upgraded. See note 48 on plans for locations.
16.5 | Install 60 minute Fire resistant lining Around New Steel Beam. Consisting of 2 No. Layers of 12.5mm thk Gypsum Plasterboard with staggered joints. Finish with skimcoat plaster.
17.0 | WINDOWS & ROOFLIGHTS
17.1 | Window WG7 has rot and is to be repaired locally and re-decorated as per section 22. See photo226 in photo schedule.
17.2 | Shutters to Window Refs WG1, WG6, WG7, WG8: Re-instate shutters to fully operational, replace handles with flush inset type (half moon brass type) to avoid clash with glazing/secondary glazing. Inspect, make good and re-decorate all woodwork associated with shutters as per Decoration (Section 22).
17.3 | Secondary Glazing Site Measure prior to order. Secondary glazing must fit in conjunction with re-furbished shutters, handles, hinges and existing fittings. Install Secondary Glazing to Window Refs WG1, WG6, WG7, WG8, WF2, WF3, WF4, WF5, WF6. Install New Secondary glazing; White painted Metal, Vertical Sash (or Casement), Single glazed with Acoustic Trickle Vents (45dB). -Example Secondary Glazing is based on Selectaglaze, Slimline 20(VS), 6.8mm low E glazing. -WG2 Secondary Glazing is based on Selectaglaze Slimline 46(FL), 4mm glazing, showing 2 fixed lights to align with existing sashes. -WG2 Secondary Glazing lower pane to be laminated safety glass. Inspect, make good and re-decorate all woodwork associated with installation of secondary glazing.
17.4 | Windows WG1, WG6, WG7, WG8, WF2, WF3, WF4, WF5, WF6. To be re-furbished in-situe, remove excessive existing paint, sand back to key all surfaces, fill damage with wood suitable putty, sand and re-paint with white eggshell paint 2 no’ coats.
17.4.1 | Replace existing sash pulls with 'Croft' Ring Sash Lift 1765 (Brass Finish) – 2 no’ per window.
17.5 | New Smoke Vent SV.01 above Landing F01 with 1m2 clear opening. Velux type. Allow for all roofwork involved with the installation aswell as making good and re-decorating.
18.0 | EXTERNAL DOORS
18.1 | The External Door DG1, which is an historic timber door is to be handed and refurbished. This is to include; -Strengthening of joinery -Installing a new lock of a modern yale type. -All woodwork associated with handing the door -Re-furbishing, including oiling or greasing hinges and transferring any ironmongery relevant to the handing of the door. -New weather brush strips to base of door -Re-decoration as per Section 22 (Decoration)
18.2 | The External Door DG9 is a new door to replace DG19. This new door will be a timber door with a glazed panel as shown in the door schedule. The U-Value of new door is to achieve a minimum of 1.2 W/m2K using sealed glazing units with argon filled cavity gap and low emissivity glass. It is proposed to use the existing frame, allow for all joinery associated with the installation of the new door. Please note the internal floor level is being altered (increased). The door is to be decorated as per Section 22 (Decoration)
19.0 | INTERNAL DOORS
19.1 | GENERALLY: Hardwood flush-panel solid core timber doors, contemporary styling with safety glazing as required for vision panels. Door schedule to be produced by Koha Architects. Doors to be painted as per woodwork in section 22.
19.2 | Allow to install FD30s fire doors with self-closers to doors as shown in the door schedule to doors which form part of the protected escape route.
19.3 | At DG4 and DG6 The existing doors will be retained aswell as new FD30s fire doors installed. This will be a twin door scenario, see plans. The existing doors will be re-swung to be outward opening and the new doors will be inward opening. This is for improved sound proofing.
19.4 | DG17 and DG18 will also be a twin door scenario for sound proofing.
21.0 | PLASTER / RENDER
21.1 | Allow for internal plaster skim to all new plasterboard walls
21.2 | Allow for provisional sum for repair of existing defective plaster with a Lime-based plaster system to be confirmed following discussions with Cornish Lime.
22.0 | DECORATING / FINISHES
22.1 | All Lath and plaster (non-solid) walls which form part of the protected escape route (G05 / G03 / F01) are to be painted with fire resistant paint suitable for lath and plaster, such as Envirograf product 105 or similar approved in accordance with manufacturer's recommendations including all preparation.
22.2 | At Ground Floor thoroughly prepare all ceilings, timber and wall surfaces where decorations are required following lining replacement or alterations. Burn off and remove any loose and flaky paint work with particular reference to any heavy build-up of paint finishes to woodwork.
22.3 | Repair locally any existing areas of plaster or woodwork using suitable a filler and sand back to match existing.
22.4 | To ceilings and cornices, allow for one mist coat and two coats of emulsion water based paint throughout the house. Allow for 2 no colours.
22.5 | To all new internal woodwork, allow primer coat, 2 no. undercoat and 2 no. egg shell top coat. For the purpose of costing, typical specification for paintwork will be Dulux. Allow for 2 no colours.
22.6 | REI 30 Lining to Protected Corridor. Repeated in Section 16 (Linings) An REI 30 minute Lining to walls and ceilings are required. This will consisting of a single layer of 12.5mm gypsum plasterboard and skimcoat plaster or an intumescent paint in areas of existing lath and plaster. Areas of plastered masonry wall are not required to be upgraded. See note 48 on plans for locations.
22.7 | External Doors
22.7.1 | New External Door DG9 will require decorating. Allow for either a factory finish of external gloss (colour tbc) or 1 No. Coat of external undercoat and 2 no. coats of external gloss.
22.8 | Existing Front Door DG1 to be handed, strengthened and re-decorated. Sand back existing paint to base coat, removing areas of paint build-up. Repair with wood suitable putty locally and finish with 1 No. Coat of external undercoat and 2 no. coats of external gloss.
22.9 | Upon completion ensure all hinges and other moving parts move freely and remove all masking tape and temporary covering.
22.10 | Provide new Forbo Marmoleum as splashbacks to Wash Basins to in WCs in G10 and G11. Install to manufacturers guidelines.
22.10.1 | Seal Edges of Marmoleum Splashback to wall with compatible Silicone based sealant to ensure no water ingress behind. Sealant colour to match wall if possible.
22.10.2 | Provide new Forbo Marmoleum flooring to new Lobby, WCs and Ramp R2. Install to manufacturers guidelines.
22.10.3 | Install the Marmoleum flooring using adhesives recommended by the manufacturers, including all edgings, cover strips and nosings required as part of the installation.
22.10.4 | Retain any spare sections of covering materials suitable for patching and hand over to the client upon completion.
22.11 | An aluminium single piece floor transition strip is to be installed at both the base and top of the ramp R2 and is to be a contrasting colour to finished floor surfaces.
22.12 | Floor finishes in other areas to be retained as existing generally. Best effort is to be made to cover and protect existing carpets and floor finishes during building works.
22.13 | External Ramp to be finished with waterproof and slip resistant resin based surface to such as Watco Safety Grip Flex or Similar Approved.
22.13.1 | Ramp Surface to include 150mm upstand with corner fillet to existing outside face of Lobby/WC wall. See details Sheet. Include flashing cut into existing masonry wall and covering 150mm surface upstand.
23.0 | SKIRTINGS / LININGS / TRIMS / ARCHITRAVES
23.1 | New Skirting boards to match existing along new internal walls between Hall 2(G05) and Rooms G04a and G06. For purposes of pricing allow for 200mm softwood moulded skirtings.
23.2 | For the purpose of pricing, allow for ex 75mm ogee architrave to all new internal door sets.
23.3 | Allow for 32mm softwood lining door sets throughout where new doors are incorporated.
23.4 | Allow for Decoration to all woodwork as per Section 22 (Decoration).
24.0 | HOLES / CHASES / SUPPORTS FOR SERVICES
24.1 | Allow for holes, chases, cut outs, supports etc. for general construction, mechanical and electrical services for the building.
24.2 | All new or replacement sockets / switches and fittings are to be recessed and all wiring to be routed within walls/floors or chased into walls where internal routing not possible. Allow for all making good of wall chasing.
24.3 | Allow for making holes in masonry walls to pass ducting and cabling as mentioned in section 9.
25.0 | EXTERNAL SLAB PAVING
25.1 | Allow for making good of brick/paving in areas surrounding new Accessible ramp and steps.
26.0 | RAINWATER / PIPEWORK / GUTTERS
26.1 | Cleanout of existing gutters and downpipes to ensure fully functional. TBC
27.0 | FOUL DRAINAGE ABOVE GROUND
27.1 | Refer to drawings GENERALLY: The above ground foul drainage shall be in accordance with BS5572. Pipes, fittings and accessories shall comply with the following British Standards: UPVC pipes BS4514:1983 ABS pipes BS5255: 1976 Polypropylene BS5255: 1976 Overflow pipes BS5255: 1976
27.2 | SANITARY DRAINAGE INSTALLATION
27.2.1 | Traps to all appliances shall have a 75mm water seal. Waste pipes and trap sizes shall be sized as set out below. Overflow pipes 19mm diameter Wash hand basins 32mm diameter Urinals 40mm diameter Wc’s 100mm diameter
27.3 | All waste pipes shall connect into straight vertical UPVC 100mm diameter stub stack with an air admittance valve positioned above highest flood level appliance.
27.4 | Provide Floplast air admittance valves to traps to basins.
27.5 | Soil and vent pipes shall be taken to the ground floor slab and connect with a watertight seal to the underground drainage using a suitable connector.
27.6 | Overflow pipes shall be taken from all cisterns to discharge through the external walling at a visible location.
27.7 | The whole drainage installation shall be airtight and able to withstand a pressure equal to 38mm on the manometer scale for a period of not less than three minutes after temperature stabilisation.
28.0 | FOUL DRAINAGE BELOW GROUND
28.1 | GENERALLY: New Foul drainage to connect to existing Inspection Chambers in the rear parking area which discharge to mains drains.
28.2 | DRAINAGE INSTALLATION GENERALLY:
28.2.1 | a) Pipes and fittings – Plain end clay pipes, bends and junctions to BS 65 with flexible push fit joints as manufactured by Hepworth Iron Company Limited, or equivalent, reference Super Strength (Supersleeve). Channels to be vitrified clay, three quarter section channels and branch channel bends to BS65.
28.2.2 | b) Installation – Drains from the building shall commence with a slow rest bend having a radius not less than 450mm. All drains shall be not less that 600mm. Drains having a cover less than 600mm below vehicular areas to be surround in concrete.
28.2.3 | c) Backfilling – All drains to receive 150mm surround of suitable granular material with trenches below vehicular areas backfilled with hardcore of sub base material used in subsequent construction compacted in 150mm layers. Trenches otherwise to be backfilled with as dug material compacted in150mm layers. All backfilling material limited to 40mm maximum aggregate size until at least 300mm above crown of pipe.
28.2.4 | d) Sundry Requirements – Any pipe passing through structural walls of foundations below ground shall be passed through a prepared opening having a minimum of 50mm clearance to barrel of pipe. Head of opening to be fully supported by pre stressed concrete lintels. Couplings to be provided within 150mm each side of any wall penetration or concrete surround.
28.2.5 | e) Preformed inspection chambers – Inspection chambers (IC) shown on the drawings shall be as manufactured by Osma, complete with frames and covers. CONTRACTOR TO CONFIRM PREFERENCE FOR OPTION E OR F.
28.2.6 | f) Manholes and chambers – internal sizes as detailed on drawings. Bases to be 150mm 25N/mm2 concrete. Walls shall generally be precast concrete rings to BS5911: Part 2 1982 or be 225mm brickwork of Class B engineering brick set in 1:3 (cement:sand) mortar. Cover slabs to be 225mm thick of 25Nmm2 concrete reinforced with 12mm diameter high yield mild steel bars at 100mm sections in both directions, 40mm (minimum) cover from slab soffit. Benching to manholes to rise vertically from edge of channel and radius to a slope of 1:12.Step irons to be provided in all manholes and chambers at 300mm centres, vertically staggered and commencing 450mm from the cover level. Manhole or chamber covers and frames to be double seal type having appropriate load capacity. CONTRACTOR TO CONFIRM PREFERENCE FOR OPTION E OR F.
29.0 | STORM WATER DRAINAGE ABOVE GROUND
Refer to section 28.0
30.0 | STORM WATER DRAINAGE BELOW GROUND
30.1 | DRAINAGE INSTALLATION: The installation shall be as described in 28.02 and in accordance with the notes set out below:
30.2 | Where possible existing RW gullies below downpipes are to be retained.
31 | SEALANTS
31.1 | Allow for running mastic pointing to all new junctions of construction between dissimilar materials.
31.2 | Allow for silicone sealant undertaken by a specialist company to all bathrooms and kitchen area. Sealant required between sanitary ware, walling, tops, internal wall junctions.
31.2.1 | Colour to be agreed.
32 | MECHANICAL AND PLUMBING SERVICES
32.1 | Contractor to allow for design for all mechanical services and provide collateral warranties to cover all of the design for the building owners benefit.
32.2 | Allow for the supply and fix of heating as per the drawings above slab level drainage, mechanical extraction etc. to be undertaken by a specialist contractor. Allow for profit and attendance, chasing, lifting of floor boards, formation of holes etc. associated with these works.
32.3 | Supply and install new Rio Electric Ceramic Core Radiators (https://www.rioheating.com/rio-eco/) in locations shown on proposed drawings. New Sockets are required adjacent to each radiator. Each Radiator is to be 2kw.
32.4 | Confirm the supply details of the radiators with the Architect / client before placing orders.
32.5 | Provide mechanical extract ventilation to existing and proposed WCs capable of operating at 6 litres per second switched back to the PIR light switch on a 2 minute overrun.
32.6 | Install, test and commission the sanitaryware to the supply specification agreed with the client including all necessary fixtures and fittings altering as necessary the existing plumbing arrangements to accord with the requirements of the Building Regulations.
32.7 | Allow for the builders work associated with mechanical installation.
32.8 | Ensure that all testing and commissioning certificates are issued to the client upon completion
32.9 | Contractor to allow for design for all mechanical and plumbing services and provide collateral warranties to cover all of the design for the building owners benefit.
33.0 | ELECTRICAL WORKS
33.1 | Allow for the installation of electrical services throughout by a specialist sub-contractor. See Provided M&E Plans for amounts, type and locations.
33.2 | Note that the 3 No. Video Coms outside G01, G04 and F01 are either as existing or to be supplied and installed by the client and not part of this works package.
33.3 | To include running of cables, new distribution boards, lighting, power and data etc.
33.4 | Allow for profit and attendance, chasing, lifting of floor boards, formation of holes etc. associated with these works.
33.5 | Electrical work associated with installation must be complete in accordance with BS7671 (the IEE wiring regulations) and comply with requirements of the Structural Engineer in respect of cutting holes/chases/notches through structural steelwork or walls.
33.6 | Liase with the Electrical Supply company as necessary to ensure the suitability of the supply and earthing arrangements and install, test and commission the electrical work in accordance with BS 7671 to provide a safe, well insulated, earth protected system capable of supplying the anticipated maximum demand.
33.7 | Ensure that installation work is carried out by qualified electricians fully conversant with BS 7671
33.8 | In locations where moisture is present or may occur, use corrosion resisting fastenings and avoid contact between dissimilar metals.
33.9 | Comply with restrictions on cutting of holes, chases, notches etc. specified under the mechanical services installation section.
33.10 | All cabling is to be BASEC certified, concealed where possible and positioned a minimum of 150mm clear of other services. Sleeve cables passing through masonry walls and do not run cables in spaces where they will be surrounded or covered by insulation. Protect cables in plaster with galvanised steel channel.
33.11 | Smoke alarms to be in accordance with BS5436:Part 1: Kite mark certified & BS5839, self-contained on a mains operated separately fused circuit. Electrical subcontractor to advise on the requirements for additional smoke detectors following new extensions and alterations
33.12 | Light switch locations and new Double switch socket outlet locations to new or extended rooms as per M+E Plans.
33.13 | To all recessed downlight positions in the new refurbishment, allow for the supply and fix of firehoods over recessed lights.
33.14 | Exterior Lighting – Allow for 2 PIR exterior light fittings adjacent to tp new ramp in accordance with drawings. Ensure that all fittings are IP65 rated as a minimum.
34.0 | SIGNAGE
34.1 | Escape signage to be installed above doors which lead to an escape route. Signage to be on a brass (or brass effect) backplate with black text such as product shown here; https://www.jafgraphics.co.uk/classic-brushed-brass-fire-exit-sign
34.2 | Signage to be fixed to wall with screws using appropriate wall fixing plugs for the wall type. Brass screw caps are to be installed over screw heads.
34.3 | Use a similar Brass backed style for any other informative signage required such as for The Fire Control Panel, WCs, FD30/FD60 signage, Electrical and Warning signage, cleaners cupboard, Refuge Point, Call Point.
35.0 | BUILDERS CLEAN
35.1 | On completion of the works, arrange for a professional domestic cleaning specialist to thoroughly clean the entire building. This must include the cleaning of windows inside and out, the wiping of all surfaces, shelving, ledges etc. dusting and cleaning of floors throughout, washing down and polishing all sanitary ware, mirrors, removal of labels etc. on completion.
36.0 | OPERATING MANUALS
36.1 | On completion of the works, ensure that a complete set of operating manuals are presented to the client illustrating full operation of the building with particular reference to mechanical and electrical services.
36.2 | The main contractor is to coordinate the mechanical and electrical sub-contractors information and incorporate this in a single pack of information. Include all maintenance information for floor / wall finishes as recommended by manufacturers.
37.0 | CONTINGENCY
37.1 | Allow a contingency of 20% on pricing for all unknown items
38.0 | PRELIMINARIES
38.1 | Allow for contractors preliminaries, overheads and profit
39 | STANDARDS
39.1 | All work is to comply with the latest British and European (BS-EN) standards, Building Regulations and relevant codes of practice for the various trades.
40.0 | EXCLUSIONS
40.1 | Soft Furnishings, fixtures, fittings and equipment where not already described in the schedule.
41.0 | PROVISIONAL SUMS
41.1 | 4.1 Remedial Works to any timber rot or beetle infestation found in survey (by others – not yet available) |  | 3000
41.2 | Lintels to ramp blockwork walling over existing insepction chamber. |  | 2000
END
END