Kick the Dust Programme Evaluation

Organisation	Heritage Lottery Fund

Department	Strategy & Business Development

Title of procurement	Kick the Dust programme evaluation

Brief description of supply	Evaluation services

Estimated value of tender		Up to £30,000 including expenses and VAT, up to £150,000 over the programme duration if extended annually

Estimated duration	September 2017 to February 2019 (to cover development phase and year one of projects’ life, with the possibility of extending it annually for the whole programme duration, potentially up to 2023)

Name of HLF contact	John McMahon
Strategy & Business Development
020 7591 6161
john.mcmahon@hlf.org.uk

Timetable	Tender response deadline:
11am on 29 August 2017

Clarification, Negotiations & Interviews may be held with shortlisted consultants and would take place in w/c 4 September 2017

Outcome notification:
w/c 11 September 2017

HLF CONTRACT NUMBER	HLF207

# Overview

The Heritage Lottery Fund (HLF) was set up in 1994 under the National Lottery Act and distributes money raised by the National Lottery to support projects involving the national, regional and local heritage of the United Kingdom. We operate under the auspices of the National Heritage Memorial Fund (NHMF). Since April 2013 we have been operating under our fourth Strategic Framework: ‘A lasting difference for heritage and people’ (see the HLF website for more details).

HLF invests in the full breadth of the UK’s heritage, and through our funding we aim to make a lasting difference for heritage and people. This is reflected in the outcomes for heritage, people and communities that underpin our grant-making.

Kick the Dust is a £10million pilot grants programme that aims to make heritage relevant to the lives of young people, aged 11-25, now and in to the future. Building on their needs and interests, we want to see a greater number and diversity of young people benefit from high quality engagement with heritage. This programme is also about developing the skills and confidence of heritage sites and services to sustain their work with young people over the long-term. Kick the Dust offers grants of between £500,000 and £1m to projects led by a consortium of heritage and youth partners. It was named by young people who wanted to ‘stir things up’.

Kick the Dust successful projects were announced in July 2017 and HLF will fund 12 between 2017 and 2023. From July/August they will start a development phase of approximately six months when they will further plan their projects ahead of a round two submission; there may be work with young people delivered in this development phase. HLF is looking for a service provider/services providers that will support individual project evaluation and will assess the impact of the programme as a whole, two distinct workstreams. We will expect you to involve young people as appropriate; HLF has recruited a group of Heritage Ambassadors - #DustKickers – some of whom may want to be involved with project design and we will expect the successful bidder to include youth input and engagement in the evaluation process.

HLF wants this evaluation to make a difference and as part of the overall pilot approach to the programme we are open doing things differently. We want to ensure that there is high-quality evaluation within projects, and develop an evidence base to inform our future approach and help build the ambition of the heritage sector. As part of Kick the Dust, we will expect the service provider(s) to work together with the grantees and other consortiums as a group. As part of the group the service provider(s) will:

- provide support for grantees to plan their own project evaluation and help them to decide what they need to measure and how;

- look at shared outcomes, and identify common measures across projects to contribute to a programme-level impact study.

The successful first-round grantees will meet together as a group during the development phase to build in evaluation from the beginning of their project and look at what can be measured across all projects. We expect that the group will meet twice a year during the delivery phase of their projects, as noted a period potentially up to 2023, though the projects vary in length.

At project level grantees are encouraged to set aside between 3% and 7% of their total project budget for evaluation and to pay for an independent evaluation of their project. They are expected to submit an evaluation report at the end of the project to release the last 10% of grant. They will also be expected to draw on their learning to test and refine practice as their project progresses. They will need to collect quantitative information (numbers) during their project, for example, recording the number and types of activities that take place, how many young people are engaged, and the staff or volunteers trained. On their own, these numbers will not tell the whole story of their project, and the evaluation report will need to go far ‘beyond the numbers’. This will include evidence of the outcomes that the project has achieved. The consultant will be expected to help projects develop a common measurement framework, which will feed into the programme level evaluation, and potentially how HLF and other funders evaluate work with young people going forward.

At programme-level the impact study led by the service provider will help HLF draw lessons about the impact of the funding as a whole. This will also enable HLF to create an evidence base to better understand the value of youth engagement with heritage. The quantitative information that HLF expects grantees to collect for the programme-level impact study will be confirmed during the group meeting at the development phase. Indicatively HLF may ask for numbers about the following:

- Co-production work with young people

- On-site workshops and sessions

- Outreach sessions

- Training courses and on the job training opportunities

- Digital outputs and reach

- Steering group and non-Executive opportunities

- Events

- Exhibitions and displays

- People taking part – engagement with young people before, during and after the project, volunteers and trainees

- New staff.

For people taking part, volunteers, trainees and staff, HLF will also ask for details by age, gender, ethnic group, sexuality, socio-economic group and disability in line with the Equality Act and our desire to see a diversity of young people engaged by Kick the Dust.

The programme-level impact study will also include collecting qualitative data (for example, data collected through observations, interviews, reflective diaries, vlogs), which will be discussed when the group meets. This may seek to gather reflections on youth practice and also document culture change within heritage organisations.

The primary audiences for the report(s) are youth and heritage practitioners and organisations, senior sector leaders, research institutions, statutory bodies and civil servants, and the wider youth and heritage sectors. The report will be made available on the HLF website and circulated amongst all participating grantees. The report will also inform HLF’s Board of Trustees and HLF’s strategy.

This contract covers the first 18 months of the evaluation work which will take place over the whole period of the programme. It is possible for HLF to extend the contract dependant on results from the appointed contractor(s).

# Purpose of the evaluation

The aims of the evaluation are to:

- Assess the impact of the programme;

- Improve project evaluation and encourage reflective practice, including giving young people a voice in evaluation;

- Contribute to a national debate about the value of youth engagement with heritage.

We want to contribute to the body of knowledge, policy and practice related to youth engagement with heritage. To this end, the process and outputs of this programme evaluation will be communicated both internally and externally.

# Overarching evaluation questions

To what extent has the programme meets its aims to:

- make heritage relevant to more and a greater diversity of young people, building on their needs and interests;

- increase the ambition, scale and quality of youth engagement with heritage;

- develop sustainable, ongoing work with young people within heritage organisations;

- show the value of youth engagement with heritage.

Linked to this fourth aim, to what extent has the project supported grantees to improve their project evaluation, by helping them to determine what to measure and which methods to use?

What have been the benefits of the programme for young people?

How has the programme contributed to organisations’ capacity building and long-term change through reflective practice? What difference has the programme made to how heritage organisations work with young people?

# Methodology

Kick the Dust programme evaluation has a dual purpose which comprises improving project evaluation and measuring the programme’s overall success. Each aspect of the programme evaluation could be undertaken by a different consultancy based on their capacity, expertise and experience. The consultancy/ies are expected to work with all projects as a group throughout the contract/programme (and with one another as applicable).

In the event that two consultancies are commissioned (one to support project evaluation and one to undertake programme evaluation) they will be expected to communicate and collaborate with each other so that evaluation processes are clear to the grantees and project and programme evaluation are complementing each other and do not duplicate grantees work and contributions.

The consultancy/ies will meet with projects at the development stage to provide training and advice on how to develop their project evaluation approach and decide their evaluation methods at the individual project level. At the same time (development phase) the consultancy will look at the projects as a whole and will identify common aspects to measure to develop an overarching framework that will be guided by HLF’s programme aims.

Each grantee will be responsible for their own project evaluation and all the grantees will be also expected to contribute to the programme-level evaluation.

Grantees will have complete ownership of their project evaluations. At the programme level grantees will co-decide with the consultancy the common data collections methods, which all grantees will use.

Grantees will have the option to contact the consultancy responsible for supporting the project evaluation for tailored advice/mentoring. The consultancy will support projects to conduct on-going evaluation and use the findings as part of continuous reflective practice. By the end of their project grantees will be expected to have developed their capacity to do project evaluation better.

Grantees may contact the consultancy responsible for the programme evaluation if they have any enquiries regarding the process, how they collect and feedback data for the programme-level impact study.

Grantees and the consultancy/ies will meet as a group with the programme team and possibly some grants officers up to twice a year to discuss and reflect on their project and programme evaluation findings, share best practice and co-create ideas of how to improve their practice based on evidence. In responding to this tender you may want to give consideration to how the cohort might communicate and share practice between meetings.

# Outputs

A project plan with specific deliverables* and timetable will be agreed with the successful consultant/ies. However, HLF expects the following deliverables in accordance with the following timetable as a minimum:

| Deliverable/Key Milestones* | Due date |
| --- | --- |
| Inception meeting to agree plans. | To be agreed |
| Make arrangements to contact all grantees. | Within 10 working days of contract start date |
| Provide support for grantees to plan their project evaluations, including advice on how and what to measure. | On going |
| Develop a common measurement framework for use by grantees, which will contribute to the programme-level evaluation. | To be agreed |
| Facilitate two grantee events to promote common data collection and share best practice. | Twice yearly |
| A report of maximum 10 pages including the programme evaluation plan, based on the grantees’ development phase meeting. | 15 February 2018 |
| A report of maximum 5 pages outlining the detailed plan for support of the projects’ self-evaluation. | 15 February 2018 |
| A report of maximum 30 pages which details the programme-level impact study. This should include a one page executive summary with narrative and a one page infographic presenting the main findings (covering the first year of programme delivery). The report should include a description of the evaluation framework, key findings and recommendations for improvement. | 21 January 2019 |
| A report of maximum 20 pages which details the projection level evaluation. This should include one page executive summary with narrative and a one page infographic presenting the main findings. The report should include an overview of grantees reflective practice based on their project evaluation findings. | 21 January 2019 |

# The above represents our minimum requirements. *HLF reserves the right to amend this timetable where required.

Reports and other documents produced under this contract MUST adhere to HLF’s accessibility and formatting requirements (appended).

- The evaluation data collected during the evaluation should be made available to HLF.

- All bidders are required to adhere to all appropriate regulations and guidelines on the collection, storage, transmission and destruction of personal data (MRS/SRA, Data Protection Act 1998: Guidelines for Social Research, April 2013).

- The results will be confidential to HLF. HLF may prepare or commission summary reports and other materials for subsequent wider distribution, based on the results.

- The successful bidder will be expected to discuss and present findings, at appropriate times, to internal and external audiences, including our Board, our Senior Management Team, Grantees, policy makers and other external stakeholders. The purpose of these presentations is to enable lessons to be learned and key policy and practice issues to be highlighted as the evaluation progresses.

- We expect all projects that we fund to adhere to the Social Research Association (SRA) ethical guidelines. If your proposal raises particular ethical issues, you must indicate what they are and what your strategy for addressing them is.

# Contract term and budget

- We expect this first phase of evaluation to begin in September 2017 and be completed by end of February 2018 (end of year one, development of the programme). The programme and project support evaluation plan report(s) shall be submitted to HLF by 15 February 2018. The first year of programme delivery phase reports (programme evaluation findings and project evaluation support) shall be submitted to HLF by 21 January 2019.

- The anticipated budget for this evaluation is £30,000 including all expenses and VAT. The contract will be let by the National Heritage Memorial Fund. Payments will be made in three equal instalments. The first payment will be upon signing of the contract and the inception meeting. The second one on receipt of the February 2018 report, and the final payment upon HLF’s receipt of an approved final copy of the report in January/February 2019.

- Please note that the contract will be based on the HLF standard terms and conditions.

# Evaluation management

The evaluation will be managed on a day-to-day basis for HLF by John McMahon, Policy Adviser, Young People.

# Procurement Process

The proposal for undertaking the work should be a maximum of 10 pages and include:

- A detailed methodology for undertaking the study

- Details of staff allocated to the project, together with experience of the contractor and staff members in carrying out similar projects

- The allocation of days between members of the team

- The daily charging rate of individual staff involved

- A timescale for carrying out the project

- An overall cost for the work.

You will need to indicate if your proposal will cover both programme and project support evaluation work.

We are inviting submissions from a single organisation or a consortium to deliver all areas of this evaluation work. We anticipate two possible scenarios:

- 1. HLF appoints a single organisation, who has the capacity and skillset to deliver all aspects of this evaluation work.

- 2. A consortium is appointed, who together bring the required skills and resources to deliver all aspects of this evaluation work.

- We are open to proposals from consortia of organisations or individual consultants, where there are appropriate measures in place to ensure clear lines of management and communication. Payment arrangements will be via a single organisation and these details should be included in the tender return.

- HLF reserves the right not to appoint and to achieve the outcomes of the evaluation through other methods.

Your bid will be scored out of 100%.  50% of the marks will be allocated to your response to the Quality Questions below. Each question will be scored using the methodology in the table below:

Quality Questions scoring methodology

| Criteria | Weighing % |
| --- | --- |
| Demonstrated a clear understanding of the aims, objectives and main concerns of the evaluation. | Weighing 25% |
| Demonstrated an awareness of the different policy contexts, evaluation and issues relating to youth engagement. | Weighting 20% |
| Demonstrated experience of similar work including working with voluntary and community sector organisations, young people and heritage. | Weighting 15% |
| Demonstrated the bidder has the capacity and resources to carry out the evaluation within the timescale, or if working in partnership, each organisation has the capacity to fulfil its role and roles of each partner is clear. | Weighting 10% |
| Demonstrated a clear and realistic project plan, showing phases of the evaluation, tasks for each phase and roles and responsibilities for each member of the team. | Weighting 15% |
| Demonstrated well considered plans for dissemination of evaluation findings. | Weighting 15% |

Scores will be given for each criteria in a range of 1 (low) to 5 (high), as per the descriptions in the quality questions scoring methodology table below.

## Quality Questions scoring methodology

| Score | Word descriptor | Description |
| --- | --- | --- |
| 0 | Poor | No response or partial response and poor evidence provided in support of it. Does not give the HLF confidence in the ability of the Bidder to deliver the Contract. |
| 1 | Weak | Response is supported by a weak standard of evidence in several areas giving rise to concern about the ability of the Bidder to deliver the Contract. |
| 2 | Satisfactory | Response is supported by a satisfactory standard of evidence in most areas but a few areas lacking detail/evidence giving rise to some concerns about the ability of the Bidder to deliver the Contract. |
| 3 | Good | Response is comprehensive and supported by good standard of evidence. Gives the HLF confidence in the ability of the Bidder to deliver the contract. Meets the HLF’s requirements. |
| 4 | Very good | Response is comprehensive and supported by a high standard of evidence. Gives the HLF a high level of confidence in the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in some respects. |
| 5 | Excellent | Response is very comprehensive and supported by a very high standard of evidence. Gives the HLF a very high level of confidence the ability of the Bidder to deliver the contract. May exceed the HLF’s requirements in most respects. |

50% of marks will be awarded for Price.

Price: The evaluation of price will be carried out on the Schedule of charges you provide in response to Table A.

# Price Criterion at 50%

- 50 marks will be awarded to the lowest priced bid and the remaining bidders will be allocated scores based on their deviation from this figure. Your fixed and total costs figure in your schedule of charges table will be used to score this question.

- For example, if the lowest price is £100 and the second lowest price is £108 then the lowest priced bidder gets 50% (full marks) for price and the second placed bidder gets 46% and so on. (8/100 x 50 = 4 marks; 50-4 = 46 marks)

- The scores for quality and price will be added together to obtain the overall score for each Bidder.

# Table A - Schedule of Charges

Please show in your tender submission, the number of staff and the amount of time that will be scheduled to work on the contract with the daily charging rate.

Please complete the table below providing a detailed breakdown of costs against each capitalised description, detailing a total and full ‘Firm Fixed Cost’ for each element of the service provision for the total contract period. Bidders may extend the tables to detail additional elements/costs if required.

VAT is chargeable on the services to be provided and this will be taken into account in the overall cost of this contract.

As part of our wider approach to corporate social responsibility the National Heritage Memorial Fund/Heritage Lottery Fund prefers our business partners to have similar values to our own. We pay all of our staff the living wage (in London and the rest of the UK) and we would like our suppliers and contractors to do likewise. Please highlight in you proposal/tender/bid whether you do pay your staff the living wage.

Bidders shall complete the schedule below, estimating the number of days, travel and subsistence costs associated with their tender submission.

TABLE A (firm and fixed costs)

| Cost | Post 1 @cost per day (No of days) e.g. Project Manager/ Director@ £2 | Post 2 @cost per day (No of days) e.g. Senior Consultant/manager/@£1.5 | Post 3 @cost per day (No of days) Junior Consultant/Researcher@£1 | Total days | Total fees |
| --- | --- | --- | --- | --- | --- |
| Inception meeting to agree plans and finalise requirements with the Fund | e.g. 0.5 | 1 | 1 | 2.5 | £3.5 |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |
| [Add as necessary] |  |  |  |  |  |

| Cost Type | Value (£) |
| --- | --- |
| Sub - Total |  |
| VAT |  |
| Total* |  |

*(This must include all expenses as well as work costs; this figure will be used for the purposes of allocating your score for the price criterion and must cover the cost of meeting all our requirements set out in the ITT).

Notes: 	HLF reserves the right to reject abnormally low tenders. HLF reserves the right to amend the timetable of work where required.

You should not submit additional assumptions with your pricing submission. If you submit assumptions you will be asked to withdraw them. Failure to withdraw them will lead to your exclusion from further participation in this competition.

The procurement timetable will be:

- Tender return deadline: completed proposal to be returned to HLF by 11am on 29 August 2017.

- Interviews may be held with shortlisted consultants and would take place in week commencing 4 September 2017.

- Notification about the outcomes of the procurement in week commencing 11 September 2017.

Your tender proposals must be sent electronically via e-mail before the tender return deadline of 11am on 29 August 2017 to the following contact:

# Diane La Rosa
Heritage Lottery Fund
7 Holbein Place

# London SW1W 8NR

Diane.La.Rosa@hlf.org.uk

Please visit the HLF website for further information about the organisation.

# Appendix: Accessibility and formatting guidance

HLF is committed to providing a website that is accessible to the widest possible audience. Our website is annually tested by accessibility auditors and we must meet the WCAG 2.0 AA compliance level. Our accessibility testing covers all of our content, including downloadable documents, as well as the design and functionality of the site.

Reports and other documents created for HLF (including the tender submissions) need to be clear, straightforward to use, and ready to circulate internally, externally and online, as well as suitable for use by screen reading software. Tips for creating accessible documents can be found below. However, we strongly recommend referring to the RNIB, Gov.uk and WebAIM for more detailed information.

## Readability

In the final report, and all other documents that may be published online including the tender application consultants should ensure that:

- The size of the font is at least 11pt;

- There is a strong contrast between the background colour and the colour of the text. Black text on a white background provides the best contrast. This also applies to any shading used in tables and/or diagrams;

- Italics are only used when quoting book titles for citations and items on the reference list should be arranged alphabetically by author

- Colour formatting and use of photos should be of a resolution size that is easily printable and does not compromise the printability of the document.

For further guidance on ensuring readability of printed materials, please refer to the RNIB Clear Print guidelines. These can be found on the RNIB website.

## Accessibility

Reports should adhere to the following guidelines:

- Formatting

Headings and content in your document should be clearly identified and consistently formatted, to allow easy navigation for users. Heading Styles should be used to convey both the structure of the document and the relationship between sections and sub-sections of the content.

- Spacing

Screen readers audibly represent spaces, tabs and paragraph breaks within copy, so it is best practice to avoid the repetitive use of manually inserted spaces. Instead, indenting and formatting should be used to create whitespace (e.g., use a page break to start a new page, as opposed to multiple paragraph breaks).

- Alternative text

Alt text is additional information for images and tables. This extra information is essential for both document accessibility (screen reading software reads the Alt text aloud) and for the web. Alt text should be concise and descriptive, and should not begin with ‘Image of’ or ‘Picture of’.

- Images

These should be formatted in-line with text, to support screen readers. Crediting pictures may be necessary, usually in response to a direct request from a third party.

- Tables

These should be for used for presenting data and not for layout or design. They should also be simple, and include a descriptive title.

- Additional documents

Any additional information, separate to the report, for example proformas and transcripts which may be used as standalone documents must be fully referenced to the piece of work being submitting and therefore dated, formatted and numbered appropriately.

- Acknowledgement

All reports should acknowledge HLF. Our logo can be found on the HLF website.

- Further resources

Please refer to the links below for further information:

- 'Microsoft Word: creating accessible documents' - webaim.org

- 'How to create an accessible PDF' - GOV.UK

We also recommend using an accessibility consultant to help you produce your reports. Agencies that HLF have worked with include Shaw Trust and The Accessible Digital Documents Company.

HLF retains the right to amend documents in order to create accessible versions for publishing.